## ExpenseReports
MFG.NO. | COM. | SO No. | WORK APPROVAL | CONTRACT TIME FRAME | CLOSED PROJECT | SITE INFORMATION | [6 empty] | PERSON IN CHARGE | [7 empty] | CONTRACT |  |  |  | EQ INFORMATION | [9 empty] | Prepare Stage | [36 empty] | Delivery Stage | [17 empty] | Install Stage | [83 empty] | Power Supply Stage | [5 empty] | Testing Stage | [13 empty] | QC Stage | [18 empty] | QC Hand Over Stage | [7 empty] | Submit to service Stage | [39 empty] | Close Project Stage | [11 empty] | TOTAL USAGE |  |  |  |  | REAINING USAGE |  |  |  |  | % COMPLTETE | PROGRESS INDICATOR | MANUFACTURING | PURCHASE ORDER INFORMATION | [5 empty] | D/O |  | QC RESULT
[35 empty] | Plan Start Date | 1. เช็คบ่อ Pit |  |  |  | 2. เช็คช่องลิฟท์ |  |  |  | 3. เช็คห้องเครื่อง |  |  |  | 4. ตรวจรับพื้นที่ช่องลิฟท์ |  |  |  | 5. เตรียมพื้นที่ในการวางอุปกรณ์ |  |  |  | 1. เช็คความลึกและความกว้างของบ่าบันไดเลื่อน |  |  |  | 2. เช็ค Center ระหว่างบ่อบันไดเลื่อนด้านบนและด้านล่าง |  |  |  | 3. เช็ค Floor to Floor และ Beam to Beam |  |  |  | 4. เตรียมพื้นที่ในการวางอุปกรณ์ |  |  |  | Plan Start Date | Plan Finish Date | 1. ฝ่ายจัดส่งอุปกรณ์คอนเฟิร์มกับทางโรงงานว่าอุปกรณ์พร้อมส่งเข้าโครงการแล้ว |  |  |  | 2. ตรวจเช็คพื้นที่ลงอุปกรณ์ในโครงการ |  |  |  | 3. ดำเนินการลงอุปกรณ์ในโครงการ |  |  |  | 4. ตรวจเช็คอุปกรณ์ในโครงการ |  |  |  | Plan Start Date | Plan Finish Date | 1. Preliminary Work and Plumb line |  |  |  | 2. Fixing Sill Support |  |  |  | 3. Install of Entrance |  |  |  | 4. Install of Hatch Door |  |  |  | 5. Fixing Bracket of Guide Rail |  |  |  | 6. Install of Guide Rail and Check Center |  |  |  | 7. Install of Machine Room Equipment |  |  |  | 8. Fixing Duct in Hoist way and Machine Room |  |  |  | 9. Install CWT and Roping |  |  |  | 10. Assembly of Cage |  |  |  | Progress(EL) | 1. Preliminary Work and Center Line |  |  |  | 2. Setting the Bearing |  |  |  | 3. Frame Assembling |  |  |  | 4. Fixing the Frame to the Building |  |  |  | 5. Confirming the Frame position to Building |  |  |  | 6. Installing the Outer deck |  |  |  | 7. Installing the Driving and Step Chain |  |  |  | 8. Installing Handrail Chain, Skirt guard and Inter desk |  |  |  | 9. Installing The Steps |  |  |  | 10. Assembling The Glass and Handrail |  |  |  | Progress(EL) | Plan Start Date | Plan Finish Date | Power Supply |  |  |  | Plan Start Date | 1. Slow |  |  |  | 2. Adjust |  |  |  | 3. High |  |  |  | Progress | Plan Start Date | Plan Finish Date | 1. Inprocess 1 |  |  |  | 2. Inprocess 2 |  |  |  | 3. QC Final |  |  |  | 4. Rectify Defect (QC Recheck) |  |  |  | Progress | 1. Prepare Handover Document |  |  |  | 2. Customer Signed |  |  |  | 1. FILE RVC. |  |  |  | 2. DO-BG |  |  |  | 3. DO-Forecast |  |  |  | 4. HO-BG |  |  |  | 5. HO-Forecast |  |  |  | 6. DO-ISSUED |  |  |  | 7. D/O Signed |  |  |  | 8. DO-BACK TO HO |  |  |  | 9. Hand Over Document |  |  |  | 10. Submit to Service |  |  |  | 1. Claim |  |  |  | 2. Clear Defects |  |  |  | 3. Final payment |  |  |  | I | T | QC-I | QC-F | TOTAL | I | T | QC-I | QC-F | TOTAL
[92 empty] | 5% |  |  |  | 5% |  |  |  | 10% |  |  |  | 5% |  |  |  | 20% |  |  |  | 20% |  |  |  | 10% |  |  |  | 5% |  |  |  | 10% |  |  |  | 10% |  |  |  | 100% | 5% |  |  |  | 5% |  |  |  | 15% |  |  |  | 15% |  |  |  | 15% |  |  |  | 5% |  |  |  | 15% |  |  |  | 5% |  |  |  | 10% |  |  |  | 10% |  |  |  | 100% | [7 empty] | 20% |  |  |  | 60% |  |  |  | 20% |  |  |  | 100% |  |  | 25% |  |  |  | 25% |  |  |  | 40% |  |  |  | 10% |  |  |  | 100%
[6 empty] | SITE No. | SITE NAME | EQ No. | EL | ES | MSW | EQ | DM PROJECT | LEADER | PE | INST MP | PO. NO SUBCONTACT | TEST MP | SM QC | SALESMAN | REV. | DELIVER | H/O | REVISED H/O | SPECIFICATION | TYPE | CAPACITY | SPEED | S | F | Rise(mm.) | PRICE | PROVINCE | LOCATION |  | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note |  |  | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note |  |  | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note |  | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note |  |  |  | Working Date | Result | Problem | Problem Note |  | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note |  |  |  | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note |  | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | Working Date | Result | Problem | Problem Note | [13 empty] | P/O. No. SUBCONTRACT | P/O. No. EQ | P/O. SHIPMENT DATE | CONFIRM DSCR DATE | PARTIAL DATE | PARTIAL ITEM | No. | DATE
THA0069-TH | SHE | 21000296 | HO | ส่งมอบแล้ว | - | TH150014 | Circle Sukhumvit 11 | P1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Atcha Wongrak | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2014-07-05 | 2015-02-20 | 2015-09-05 | 2020-06-27 | HVF-1000-2PCO180;34S/34F; | HVF | 1000 | 180 | 34 | 34 |  | 6473500 | Bangkok | แขวงคลองเตยเหนือ | 1900-01-01 | 2016-06-02 | Finished | [34 empty] | 2015-03-20 | 2015-04-28 | 2015-04-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2016-06-02 | 2016-10-02 | 2016-06-02 | Finished |  |  | 2016-06-12 | Finished |  |  | 2016-06-30 | Finished |  |  | 2016-07-10 | Finished |  |  | 2016-07-25 | Finished |  |  | 2016-08-15 | Finished |  |  | 2016-08-25 | Finished |  |  | 2016-09-05 | Finished |  |  | 2016-10-15 | Finished |  |  | 2016-10-02 | Finished |  |  | 100 | [41 empty] | 2016-10-02 | 2019-05-01 | 2019-05-01 | Finished |  |  | 2019-05-01 | 2019-05-01 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 100 | 2020-06-26 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-06-29 | Finished |  |  | 2014-12-11 | Finished | [10 empty] | 2020-06-29 | Finished | [6 empty] | 2015-04-27 | Finished |  |  | 2015-04-29 | Finished |  |  | 2015-04-29 | Finished |  |  | 2020-06-29 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished |  | pass |  |  |  |  | 2025 | 118 | 64 | 32 | 2239 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000112 | 2015-04-27 | QC Passed
THA0070-TH | SHE | 21000296 | HO | ส่งมอบแล้ว | - | TH150014 | Circle Sukhumvit 11 | P2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Atcha Wongrak | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2014-07-05 | 2015-02-20 | 2015-08-20 | 2020-06-27 | HVF-1000-2PCO180;34S/34F; | HVF | 1000 | 180 | 34 | 34 |  | 6473500 | Bangkok | แขวงคลองเตยเหนือ | 1900-01-01 | 2016-06-02 | Finished | [34 empty] | 2015-03-20 | 2015-04-29 | 2015-04-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2016-06-02 | 2016-10-02 | 2016-06-02 | Finished |  |  | 2016-06-12 | Finished |  |  | 2016-06-30 | Finished |  |  | 2016-07-10 | Finished |  |  | 2016-07-25 | Finished |  |  | 2016-08-15 | Finished |  |  | 2016-08-25 | Finished |  |  | 2016-09-05 | Finished |  |  | 2016-10-15 | Finished |  |  | 2016-10-02 | Finished |  |  | 100 | [41 empty] | 2016-10-02 | 2019-05-01 | 2019-05-01 | Finished |  |  | 2019-05-01 | 2019-05-01 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2021-05-13 | 2020-03-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-04 | Finished | [6 empty] | 90 | 2020-06-26 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-06-29 | Finished |  |  | 2014-12-11 | Finished | [18 empty] | 2015-04-27 | Finished |  |  | 2015-04-29 | Finished |  |  | 2015-04-29 | Finished |  |  | 2020-06-29 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished |  | pass |  |  |  |  | 2025 | 118 | 64 | 32 | 2239 | 0 | 0 | 0 | 3 | 3 | 99.87 | Blue | [7 empty] | DME000112 | 2015-04-27 | QC Passed
THA0071-TH | SHE | 21000296 | HO | ส่งมอบแล้ว | - | TH150014 | Circle Sukhumvit 11 | P3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2014-07-05 | 2015-02-20 | 2015-08-05 | 2020-06-27 | HVF-1000-2PCO180;30S/34F; | HVF | 1000 | 180 | 30 | 34 |  | 6473500 | Bangkok | แขวงคลองเตยเหนือ | 1900-01-01 | 2016-06-02 | Finished | [34 empty] | 2015-03-20 | 2015-04-29 | 2015-04-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2016-06-02 | 2016-10-02 | 2016-06-02 | Finished |  |  | 2016-06-12 | Finished |  |  | 2016-06-30 | Finished |  |  | 2016-07-10 | Finished |  |  | 2016-07-25 | Finished |  |  | 2016-08-15 | Finished |  |  | 2016-08-25 | Finished |  |  | 2016-09-05 | Finished |  |  | 2016-10-15 | Finished |  |  | 2016-10-02 | Finished |  |  | 100 | [41 empty] | 2016-10-02 | 2019-05-01 | 2019-05-01 | Finished |  |  | 2019-05-01 | 2019-05-01 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2021-05-13 | 2021-05-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-14 | Finished |  |  | 100 | 2020-06-26 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-06-29 | Finished |  |  | 2014-12-11 | Finished | [18 empty] | 2015-04-27 | Finished |  |  | 2015-04-29 | Finished |  |  | 2015-04-29 | Finished |  |  | 2020-06-29 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass |  |  |  |  | 2025 | 118 | 64 | 32 | 2239 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000112 | 2015-04-27 | QC Passed
TAC0313-TH | SHE | 21000296 | HO | ส่งมอบแล้ว | - | TH150014 | Circle Sukhumvit 11 | S1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2014-07-05 | 2015-02-20 | 2015-07-05 | 2020-06-27 | VFI-II-1600-2PCO150;36S/37F; | VFI-II | 1600 | 150 | 36 | 37 |  | 6259500 | Bangkok | แขวงคลองเตยเหนือ | 2016-06-02 | 2016-06-02 | Finished | [34 empty] | 2015-01-20 | 2015-04-28 | 2015-03-14 | Finished | CONSTRUCTION STOP | [13 empty] | 2016-06-02 | 2016-10-02 | 2016-06-02 | Finished |  |  | 2016-06-12 | Finished |  |  | 2016-06-30 | Finished |  |  | 2016-07-10 | Finished |  |  | 2016-07-25 | Finished |  |  | 2016-08-15 | Finished |  |  | 2016-08-25 | Finished |  |  | 2016-09-05 | Finished |  |  | 2016-10-15 | Finished |  |  | 2016-10-02 | Finished |  |  | 100 | [41 empty] | 2016-10-02 | 2016-12-24 | 2016-12-24 | Finished |  |  | 2016-12-24 | 2016-12-24 | Finished |  |  | 2017-01-25 | Finished |  |  | 2017-02-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-10-26 | Finished |  |  | 2020-06-29 | Finished |  |  | 2014-12-11 | Finished | [18 empty] | 2015-03-17 | Finished |  |  | 2015-03-25 | Finished |  |  | 2015-03-14 | Finished |  |  | 2020-06-29 | Finished | [13 empty] | no pass |  |  |  |  | 2295 | 127 | 72 | 40 | 2534 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000106 | 2015-03-17
TAC0316-TH | SHE | 21000301 | HO | ยังอยู่ในสัญญา HO | - | TH140164 | Krieng Sin Wattana Building | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | BANJONGSAK KWANGMUANG | 2014-07-31 | 2015-01-31 | 2015-03-31 | 2022-09-19 | VFI-II-600-2PCO60;5S/5F; | VFI-II | 600 | 60 | 5 | 5 |  | 1444500 | Bangkok | แขวงสะพานสูง | 2022-08-02 | [36 empty] | 2014-12-31 | 2016-02-12 | 2016-02-12 | Finished | STORE AREA | [13 empty] | 2022-08-03 | 2022-09-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-09-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-09-19 | Working | ADJUSTMENT DEFECT RECTIFICATION DELAY | [5 empty] | 2014-09-24 | Finished | [18 empty] | 2016-02-10 | Finished |  |  | 2016-02-12 | Finished |  |  | 2016-02-12 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Green | [7 empty] | DSE000506 | 2016-02-10
TAC0427-TH | SHE | 21000388 | HO | ยังอยู่ในสัญญา HO | - | TH150096 | สรรพสิทธิ์อพาร์ทเม้นท์ | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Yosvaris Limmethaphant | 2015-03-18 | 2015-08-18 | 2016-01-18 | 2021-10-18 | VFI-II-1000-2PCO60;5S/5F; | VFI-II | 1000 | 60 | 5 | 5 |  | 1420000 | Ubon Ratchathani | อำเภอเมืองอุบลรราชธานี | 2017-04-25 | 2016-03-01 | Finished | [34 empty] | 2015-08-03 | 2016-01-12 | 2016-01-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2016-03-10 | 2016-05-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-08-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2021-10-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2015-04-28 | Finished | [10 empty] | 2022-03-22 | Finished | [6 empty] | 2016-01-08 | Finished |  |  | 2016-01-13 | Finished |  |  | 2016-01-12 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 16 | 16 | 32 | 95.08 | Green | [7 empty] | DSE000488 | 2016-01-08
TAF0030-TH | SHE | 21000415 | HO | ยังอยู่ในสัญญา HO | - | TH150122 | Church of Blessed Sacrament | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2015-05-20 | 2015-10-20 | 2015-12-20 | 2021-11-20 | UAB-750-2S2P60;4S/4F; | UAB | 750 | 60 | 4 | 4 |  | 1650000 | Bangkok | ถนนสวนผัก แขวงตลิ่งชัน | 2016-06-02 | 2016-06-02 | Finished | [34 empty] | 2015-10-05 | 2015-12-09 | 2015-12-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2016-02-26 | 2016-03-22 | 2016-02-26 | Finished |  |  | 2016-02-28 | Finished |  |  | 2016-03-05 | Finished |  |  | 2016-03-08 | Finished |  |  | 2016-03-10 | Finished |  |  | 2016-03-12 | Finished |  |  | 2016-03-14 | Finished |  |  | 2016-03-16 | Finished |  |  | 2016-03-18 | Finished |  |  | 2016-03-22 | Finished |  |  | 100 | [41 empty] | 2016-03-22 | 2018-11-10 | 2018-11-10 | Finished |  |  | 2018-11-10 | 2018-11-10 | Finished |  |  | 2018-11-15 | Finished |  |  | 2018-11-20 | Finished |  |  | 100 | [18 empty] | 0 | 2021-11-18 | Working | POWER SUPPLY DELAY | [5 empty] | 2015-06-12 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2015-12-08 | Finished |  |  | 2015-12-09 | Finished |  |  | 2015-12-09 | Finished | [22 empty] | 455 | 81 | 16 | 16 | 568 | 0 | 0 | 16 | 16 | 32 | 94.37 | Green | [7 empty] | DSE000476 | 2015-12-08
TAC0488-TH | SHE | 21000423 | HO | ยังอยู่ในสัญญา HO | - | TH150130 | Resident Onnut 28 Building 1 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2015-06-08 | 2015-12-08 | 2016-02-08 | 2021-10-22 | VFI-II-550-2PCO60;8S/8F; | VFI-II | 550 | 60 | 8 | 8 |  | 1400000 | Bangkok | แขวงสวนหลวง | 2017-04-20 | 2017-04-20 | Finished | [34 empty] | 2015-11-08 | 2015-12-03 | 2015-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-04-21 | 2017-05-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2015-07-14 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2016-01-08 | Finished |  |  | 2016-01-09 | Finished |  |  | 2015-12-03 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Green | [7 empty] | DSE000487 | 2016-01-08
TAC0489-TH | SHE | 21000424 | HO | ยังอยู่ในสัญญา HO | - | TH150131 | Resident Onnut 28 Building 2 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2015-06-08 | 2015-12-08 | 2016-02-08 | 2021-10-22 | VFI-II-550-2PCO60;8S/8F; | VFI-II | 550 | 60 | 8 | 8 |  | 1400000 | Bangkok | แขวงสวนหลวง | 2017-10-05 | 2017-10-05 | Finished | [34 empty] | 2015-11-08 | 2015-12-03 | 2015-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-07 | 2020-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-31 | 2020-03-31 | Finished |  |  | 2020-03-31 | 2020-04-08 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-30 | Finished | [6 empty] | 90 | 2021-11-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2015-07-14 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2016-01-08 | Finished |  |  | 2016-01-09 | Finished |  |  | 2015-12-03 | Finished | [17 empty] | no pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Green | [7 empty] | DSE000486 | 2016-01-08
TAC0492-TH | SHE | 21000429 | HO | ส่งมอบแล้ว | - | TH150136 | Da De Blue Hotel | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2015-06-18 | 2015-11-18 | 2016-01-18 | 2020-11-18 | VFI-II-550-2PCO60;5S/5F; | VFI-II | 550 | 60 | 5 | 5 |  | 1220000 | Mukdahan |  | 2017-06-15 | 2016-07-25 | Finished | [34 empty] | 2015-10-18 | 2016-07-28 | 2016-07-28 | Finished | STORE AREA | [13 empty] | 2016-07-28 | 2016-08-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-23 | 2020-03-23 | Finished |  |  | 2020-04-30 | 2020-03-26 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-31 | Finished |  |  | 100 | 2021-05-13 | 2021-01-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-07 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2021-02-13 | Finished | POWER SUPPLY DELAY |  | 2020-11-18 | Finished |  |  | 2015-07-14 | Finished | [10 empty] | 2020-12-15 | Finished | [6 empty] | 2016-07-26 | Finished |  |  | 2016-07-28 | Finished |  |  | 2016-07-28 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000603 | 2016-07-26 | QC Passed
TAC0493-TH | SHE | 21000429 | HO | ส่งมอบแล้ว | - | TH150136 | Da De Blue Hotel | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2015-06-18 | 2015-11-18 | 2016-01-18 | 2020-11-18 | VFI-II-550-2PCO60;5S/5F; | VFI-II | 550 | 60 | 5 | 5 |  | 1220000 | Mukdahan |  | 2016-07-28 | 2016-07-25 | Finished | [34 empty] | 2015-10-18 | 2016-07-28 | 2016-07-28 | Finished | STORE AREA | [13 empty] | 2016-07-28 | 2016-08-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-23 | 2020-03-23 | Finished |  |  | 2020-04-30 | 2020-03-26 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-31 | Finished |  |  | 100 | 2021-05-13 | 2021-01-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-07 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2021-02-13 | Finished | POWER SUPPLY DELAY |  | 2020-11-18 | Finished |  |  | 2015-07-14 | Finished | [10 empty] | 2020-12-15 | Finished | [6 empty] | 2016-07-26 | Finished |  |  | 2016-07-28 | Finished |  |  | 2016-07-28 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000603 | 2016-07-26 | QC Passed
TAC0516-TH | SHE | 21000458 | HO | เลยสัญญา HO | - | TH160004 | Amphawa De View | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2015-08-06 | 2016-02-06 | 2016-04-06 | 2021-09-15 | VFI-II-700-2PCO60;4S/4F; | VFI-II | 700 | 60 | 4 | 4 |  | 1412400 | Samut Songkhram | ต.อัมพวา | 2016-05-20 | 2016-05-20 | Finished | [34 empty] | 2016-01-22 | 2016-05-18 | 2016-05-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2016-05-20 | 2017-03-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-06-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2015-08-25 | Finished | [18 empty] | 2016-05-16 | Finished |  |  | 2016-05-18 | Finished |  |  | 2016-05-18 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 0 | 90 | 16 | 16 | 122 | 79.46 | Red | [7 empty] | DSE000565 | 2016-05-16
TFA0456-TH | SHE | 21000534 | HO | เลยสัญญา HO | - | TH160079 | Bukis Phuket | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 |  | TEERASAK JUNTHAWEE | 2016-01-18 | 2016-06-02 | 2016-08-02 |  | 1200SX-EN;35;4250; | SX-EN |  |  |  |  | 4250 | 1391000 | Phuket | ต.วิชิต อ.เมืองภูเก็ต | 2017-10-01 | [20 empty] | 2017-10-01 | Finished | [14 empty] | 2016-05-18 | 2016-12-04 | 2016-12-04 | Finished | PAYMENT DELAY | [13 empty] | 2022-01-05 | 2022-03-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-04-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-04-30 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2016-01-29 | Finished | [18 empty] | 2016-12-02 | Finished |  |  | 2016-12-04 | Finished |  |  | 2016-12-04 | Finished | [22 empty] | 567 | 42 | 16 | 21 | 646 | 567 | 42 | 16 | 21 | 646 | 0 | Red | [7 empty] | DME000171 | 2016-12-02
TAC0576-TH | SHE | 21000534 | HO | เลยสัญญา HO | - | TH160079 | Bukis Phuket | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2016-01-18 | 2016-06-02 | 2016-08-02 |  | VFI-II-750-2PCO60;4S/4F; | VFI-II | 750 | 60 | 4 | 4 |  | 1198400 | Phuket | ต.วิชิต อ.เมืองภูเก็ต | 2017-10-15 | 2017-10-15 | Finished | [34 empty] | 2016-05-18 | 2016-12-04 | 2016-12-04 | Finished | PAYMENT DELAY | [13 empty] | 2022-01-05 | 2022-03-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-04-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-04-30 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2016-01-29 | Finished | [18 empty] | 2016-12-02 | Finished |  |  | 2016-12-04 | Finished |  |  | 2016-12-04 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Red | [7 empty] | DME000171 | 2016-12-02
TBK0038-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-EL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO240;30S/30F; | HVF-5 | 1600 | 240 | 30 | 30 |  | 7811000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-09-10 | 2019-09-21 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-16 | 2019-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-03 | 2019-11-03 | Finished |  |  | 2019-12-01 | 2019-11-03 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-28 | Finished |  |  | 100 | 2021-01-25 | 2000-01-01 | 2021-01-25 | Finished |  |  | 2020-07-03 | Finished |  |  | 2021-01-22 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | CUSTOMER PAYMENT DELAY |  | 2021-01-08 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 3 | 3 | 99.85 | Blue
TBK0029-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO180;16S/16F; | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-03-12 | 2019-03-13 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-13 | 2019-09-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-10-03 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-20 | Finished |  |  | 100 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Blue
TBK0030-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO180;16S/16F; | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-03-12 | 2019-03-13 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-13 | 2019-09-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-10-03 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-20 | Finished |  |  | 100 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Blue
TBK0031-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO180;16S/16F; | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-03-12 | 2019-03-13 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-13 | 2019-09-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-10-04 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-20 | Finished |  |  | 100 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Blue
TBK0032-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO180;16S/16F; | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-03-12 | 2019-03-13 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-13 | 2019-09-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-10-04 | Finished |  |  | 100 | 2021-05-13 | 2021-08-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-20 | Finished |  |  | 100 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TBK0033-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-05 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO240;18S/30F; | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-05-31 | 2019-08-15 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-02 | 2019-10-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-26 | 2019-10-26 | Finished |  |  | 2019-11-20 | 2019-10-26 | Finished |  |  | 2019-10-29 | Finished |  |  | 2019-11-03 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-28 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 3 | 3 | 99.85 | Blue
TBK0034-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-06 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO240;18S/30F; | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-05-31 | 2019-08-15 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-02 | 2019-10-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-27 | 2019-10-27 | Finished |  |  | 2019-11-20 | 2019-10-27 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-04 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-28 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 3 | 3 | 99.85 | Blue
TBK0035-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-07 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO240;18S/30F; | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-05-31 | 2019-08-15 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-02 | 2019-10-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-30 | 2019-10-30 | Finished |  |  | 2019-11-20 | 2019-10-30 | Finished |  |  | 2019-11-03 | Finished |  |  | 2019-11-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-28 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 3 | 3 | 99.85 | Blue
TBK0036-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-08 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO240;18S/30F; | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-05-31 | 2019-09-21 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-02 | 2019-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-07 | 2019-11-07 | Finished |  |  | 2019-12-01 | 2019-11-07 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-01-14 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 3 | 3 | 99.85 | Blue
TBK0037-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-PL-09 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2019-02-05 | 2020-05-30 | HVF-5-1600-2PCO240;18S/30F; | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-05-31 | 2019-09-21 | Finished | [34 empty] | 2016-12-01 | 2019-01-28 | 2019-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-02 | 2019-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-05 | 2019-11-05 | Finished |  |  | 2019-12-01 | 2019-11-05 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-28 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 3 | 3 | 99.85 | Blue
TAC0741-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2017-05-01 | 2020-05-30 | VFI-II-1600-2PCO150;16S/16F; | VFI-II | 1600 | 150 | 16 | 16 |  | 5564000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-03-12 | 2019-03-13 | Finished | [34 empty] | 2016-12-01 | 2019-01-22 | 2019-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-13 | 2019-09-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-09-19 | 2019-09-21 | Finished |  |  | 2020-01-26 | Finished |  |  | 2019-10-06 | Finished |  |  | 100 | 2020-04-08 | 2000-01-01 | 2020-04-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-25 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-01-21 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1135 | 109 | 40 | 20 | 1304 | 0 | 0 | 0 | 2 | 2 | 99.85 | Blue | [7 empty] | DME000233 | 2018-03-06
TAC0742-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 1-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2017-05-01 | 2020-05-30 | VFI-II-1600-2PCO150;31S/31F; | VFI-II | 1600 | 150 | 31 | 31 |  | 5992000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-05-31 | 2019-09-16 | Finished | [34 empty] | 2016-12-01 | 2019-01-22 | 2019-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-16 | 2019-11-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-12 | 2019-11-12 | Finished |  |  | 2019-11-12 | 2019-12-08 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-21 | Finished |  |  | 100 | 2021-01-25 | 2000-01-01 | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-22 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | CUSTOMER PAYMENT DELAY |  | 2021-01-08 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2019-01-21 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-01-30 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1964 | 122 | 64 | 32 | 2182 | 0 | 0 | 0 | 3 | 3 | 99.86 | Blue | [7 empty] | DME000233 | 2018-03-06
TAC0755-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 2-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2018-12-31 | 2020-05-30 | VFI-II-1000-2PCO105;7S/7F; | VFI-II | 1000 | 105 | 7 | 7 |  | 2675000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-03-11 | 2019-03-12 | Finished | [34 empty] | 2016-09-01 | 2018-09-26 | 2018-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-12 | 2019-04-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-03 | 2020-02-03 | Finished |  |  | 2019-11-20 | 2020-02-05 | Finished |  |  | 2020-02-06 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-05-11 | 2000-01-01 | 2020-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-06 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2018-09-25 | Finished |  |  | 2018-09-28 | Finished |  |  | 2018-09-28 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue | [7 empty] | DME000233 | 2018-03-06
TAC0756-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 2-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2018-12-31 | 2020-05-30 | VFI-II-1000-2PCO105;7S/7F; | VFI-II | 1000 | 105 | 7 | 7 |  | 2675000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-03-11 | 2019-03-12 | Finished | [34 empty] | 2016-09-01 | 2018-09-26 | 2018-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-12 | 2019-04-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-03 | 2020-02-03 | Finished |  |  | 2019-11-20 | 2020-02-15 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-22 | Finished |  |  | 100 | 2020-05-11 | 2021-05-21 | 2020-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-06 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2018-09-25 | Finished |  |  | 2018-09-28 | Finished |  |  | 2018-09-28 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000233 | 2018-03-06 | QC Passed
TAC0757-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 3-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2018-12-31 | 2020-05-30 | VFI-II-1000-2PCO60;5S/5F; | VFI-II | 1000 | 60 | 5 | 5 |  | 1765500 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2018-05-20 | 2018-12-02 | Finished | [34 empty] | 2016-09-01 | 2018-12-01 | 2018-12-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-02 | 2018-12-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-29 | 2020-01-29 | Finished |  |  | 2019-11-25 | 2020-01-29 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | 2020-03-09 | 2021-04-02 | 2020-03-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-27 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2018-12-03 | Finished |  |  | 2018-12-12 | Finished |  |  | 2018-12-14 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000233 | 2018-03-06 | QC Passed
TAC0758-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 3-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2018-12-31 | 2020-05-30 | VFI-II-1000-2PCO60;5S/5F; | VFI-II | 1000 | 60 | 5 | 5 |  | 1765500 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2018-05-20 | 2018-12-02 | Finished | [34 empty] | 2016-09-01 | 2018-12-01 | 2018-12-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-02 | 2018-12-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-29 | 2020-01-29 | Finished |  |  | 2019-11-25 | 2020-01-29 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | 2020-03-11 | 2021-04-02 | 2020-03-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-27 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2018-12-03 | Finished |  |  | 2018-12-12 | Finished |  |  | 2018-12-14 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000233 | 2018-03-06 | QC Passed
TAD0151-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 3-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2018-12-31 | 2020-05-30 | B-II(VFI-II)-1000-2S2P60;5S/5F; | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1819000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2018-05-20 | 2018-12-02 | Finished | [34 empty] | 2016-09-01 | 2018-12-01 | 2018-12-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-02 | 2018-12-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-30 | 2020-01-30 | Finished |  |  | 2019-11-25 | 2020-01-30 | Finished |  |  | 2020-02-03 | Finished |  |  | 2020-02-04 | Finished |  |  | 100 | 2021-05-13 | 2021-08-09 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-27 | Finished |  |  | 2021-08-09 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2018-12-03 | Finished |  |  | 2018-12-12 | Finished |  |  | 2018-12-14 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000233 | 2018-03-06 | QC Passed
TAC0743-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 5-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-07-19 | 2017-07-20 | Finished | [34 empty] | 2016-09-01 | 2017-07-08 | 2017-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-07-20 | 2017-12-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-18 | Finished |  |  | 2019-12-20 | Finished |  |  | 2020-01-08 | Finished |  |  | 100 | 2020-04-24 | 2000-01-01 | 2020-04-24 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished | [6 empty] | 90 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Blue | [7 empty] | DME000200 | 2017-07-07
TAC0744-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 5-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-07-19 | 2017-07-20 | Finished | [34 empty] | 2016-09-01 | 2017-07-08 | 2017-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-07-20 | 2017-12-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-18 | Finished |  |  | 2019-12-20 | Finished |  |  | 2020-01-08 | Finished |  |  | 100 | 2020-03-24 | 2021-05-21 | 2020-03-24 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0745-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 5-PL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-07-19 | 2017-07-20 | Finished | [34 empty] | 2016-09-01 | 2017-07-08 | 2017-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-07-20 | 2017-12-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-20 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-04-13 | 2021-05-21 | 2020-04-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-06-12 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0746-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 5-PL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-07-19 | 2017-07-20 | Finished | [34 empty] | 2016-09-01 | 2017-07-09 | 2017-07-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-07-20 | 2017-12-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-20 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-04-13 | 2021-08-09 | 2020-04-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-09 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-06-12 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0747-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 5-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO105;20S/20F; | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-07-19 | 2017-07-20 | Finished | [34 empty] | 2016-09-01 | 2017-07-10 | 2017-07-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-07-20 | 2017-12-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-18 | 2019-10-18 | Finished |  |  | 2019-10-18 | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2019-11-18 | Finished |  |  | 100 | 2020-03-30 | 2000-01-01 | 2020-03-30 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-11-15 | Finished | POWER SUPPLY DELAY |  | 2021-01-08 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07
TAC0748-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 5-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO105;20S/20F; | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-07-19 | 2017-07-20 | Finished | [34 empty] | 2016-09-01 | 2017-07-10 | 2017-07-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-07-20 | 2017-12-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-23 | Finished |  |  | 2019-12-24 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | 2020-03-27 | 2021-08-13 | 2020-03-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-06-12 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0749-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 6-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-11-06 | 2017-11-07 | Finished | [34 empty] | 2016-09-01 | 2017-07-10 | 2017-07-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-07 | 2017-12-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-24 | Finished |  |  | 2019-12-26 | Finished |  |  | 2020-01-11 | Finished |  |  | 100 | 2020-03-23 | 2021-05-21 | 2020-03-23 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0750-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 6-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-11-06 | 2017-11-07 | Finished | [34 empty] | 2016-09-01 | 2017-07-10 | 2017-07-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-07 | 2017-12-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-24 | Finished |  |  | 2019-12-26 | Finished |  |  | 2020-01-11 | Finished |  |  | 100 | 2020-04-08 | 2021-05-21 | 2020-04-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-05-27 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-05-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0751-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 6-PL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-11-06 | 2017-11-07 | Finished | [34 empty] | 2016-09-01 | 2017-07-12 | 2017-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-07 | 2017-12-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-26 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2021-03-25 | 2021-08-09 | 2021-03-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-09 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-06-12 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0752-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 6-PL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO150;20S/20F; | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-11-06 | 2017-11-07 | Finished | [34 empty] | 2016-09-01 | 2017-07-12 | 2017-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-07 | 2017-12-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-12-26 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2021-03-25 | 2021-08-09 | 2021-03-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-09 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-06-12 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07 | QC Passed
TAC0753-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 6-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO105;20S/20F; | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2017-11-06 | 2017-11-07 | Finished | [34 empty] | 2016-09-01 | 2017-07-12 | 2017-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-07 | 2017-12-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-18 | 2019-10-18 | Finished |  |  | 2019-10-18 | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-11-15 | Finished | POWER SUPPLY DELAY |  | 2021-01-08 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07
TAC0754-TH | SHE | 21000599 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | 6-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2016-09-15 | 2016-11-30 | 2020-05-30 | VFI-II-1000-2PCO105;20S/20F; | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2018-05-15 | 2018-05-15 | Finished | [34 empty] | 2016-09-01 | 2017-07-12 | 2017-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-04-16 | 2018-06-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 2019-01-10 | Finished |  |  | 2019-01-12 | Finished |  |  | 2020-02-24 | Finished |  |  | 100 | 2020-03-27 | 2000-01-01 | 2020-03-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-09 | Finished |  |  | 100 | 2020-04-10 | Finished | POWER SUPPLY DELAY |  | 2020-06-12 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2017-07-07 | Finished |  |  | 2017-07-13 | Finished |  |  | 2017-07-17 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000200 | 2017-07-07
TAE0896-TH | SHE | 21000617 | HO | ยังอยู่ในสัญญา HO | - | TH160152 | MB Court | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2016-05-18 | 2016-11-18 | 2017-01-18 | 2022-07-16 | UAG-550-2PCO60;6S/6F; | UAG | 550 | 60 | 6 | 6 |  | 1251900 | Bangkok | แขวงสวนหลวง | 2022-06-05 | [36 empty] | 2016-11-03 | 2017-05-24 | 2017-05-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-06-06 | 2022-06-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-07-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-07-16 | Working | CONSTRUCTION DELAY | [5 empty] | 2016-06-08 | Finished | [18 empty] | 2017-05-23 | Finished |  |  | 2017-05-24 | Finished |  |  | 2017-05-25 | Finished | [22 empty] | 566 | 82 | 24 | 16 | 688 | 566 | 82 | 24 | 16 | 688 | 0 | Green | [7 empty] | DSE000752 | 2017-05-23
TBG0055-TH | SHE | 21000621 | HO | ส่งมอบแล้ว | - | TH160157 | Asia Training Center | SE1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2016-05-16 | 2016-09-30 | 2016-11-16 |  | OUG-2000-2PCO60;7S/7F; | OUG | 2000 | 60 | 7 | 7 |  | 1883200 | Chon Buri | อำเภอพานทอง | 2016-10-20 | 2016-10-20 | Finished | [34 empty] | 2016-09-15 | 2016-11-09 | 2016-11-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2016-10-20 | 2016-11-20 | 2016-09-29 | Finished |  |  | 2016-09-30 | Finished |  |  | 2016-10-01 | Finished |  |  | 2016-10-05 | Finished |  |  | 2016-10-06 | Finished |  |  | 2016-10-07 | Finished |  |  | 2016-10-10 | Finished |  |  | 2016-10-15 | Finished |  |  | 2016-10-16 | Finished |  |  | 2016-10-20 | Finished |  |  | 100 | [41 empty] | 2016-10-20 | 2016-10-22 | 2016-10-22 | Finished |  |  | 2016-11-22 | 2016-10-21 | Finished |  |  | 2016-10-25 | Finished |  |  | 2016-10-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 100 | 2016-12-07 | Finished | PARTIAL DELIVERY |  | 2016-12-02 | Finished |  |  | 2016-06-22 | Finished | [18 empty] | 2016-11-03 | Finished |  |  | 2016-11-09 | Finished |  |  | 2016-11-09 | Finished |  |  | 2016-12-02 | Finished | [13 empty] | no pass |  |  |  |  | 619 | 87 | 24 | 16 | 746 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000657 | 2016-11-03
TEB0031-TH | SHE | 21000648 | HO | ส่งมอบแล้ว | - | TH160179 | Home K.Suphatana Phornprapha | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | -155786 | -155679 | -155649 |  | P3-200-2S20 (SED200S)--;2S/2F; | P3 |  |  | 2 | 2 |  | 900000 | Bangkok | เขตสวนหลวง | 2016-10-30 | 2016-10-19 | Finished | [34 empty] | 2016-09-15 | 2016-10-18 | 2016-10-18 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2016-10-19 | 2016-10-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2016-12-01 | 2016-12-01 | Finished |  |  | 2016-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-12-16 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-12-22 | Finished |  |  | 2016-08-10 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2016-10-18 | Finished |  |  | 2016-10-28 | Finished |  |  | 2016-10-18 | Finished |  |  | 2020-12-22 | Finished | [13 empty] | pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue | [9 empty] | QC Passed
TAC0810-TH | SHE | 21000657 | HO | ส่งมอบแล้ว | - | TH170017 | National Housing Authority | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Orawan Kwanpheng | 2016-07-01 | 2017-01-01 | 2017-03-01 |  | VFI-II-600-2PCO60;7S/7F; | VFI-II | 600 | 60 | 7 | 7 |  | 1391000 | Bangkok | แขวงคลองจั่น เขตบางกะปิ | 1900-01-01 | 2017-02-11 | Finished | [34 empty] | 2016-12-16 | 2017-02-08 | 2017-02-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-02-12 | 2017-03-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-11-15 | 2017-11-15 | Finished |  |  | 2017-11-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-04-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2019-06-06 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-06-06 | Finished |  |  | 2016-08-01 | Finished | [18 empty] | 2017-02-07 | Finished |  |  | 2017-02-08 | Finished |  |  | 2017-02-08 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-23 | Finished |  | pass | 2019-08-23 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000688 | 2017-02-07 | QC Passed
TAC0811-TH | SHE | 21000657 | HO | ส่งมอบแล้ว | - | TH170017 | National Housing Authority | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Orawan Kwanpheng | 2016-07-01 | 2017-01-01 | 2017-03-01 |  | VFI-II-600-2PCO60;7S/7F; | VFI-II | 600 | 60 | 7 | 7 |  | 1391000 | Bangkok | แขวงคลองจั่น เขตบางกะปิ | 1900-01-01 | 2017-01-11 | Finished | [34 empty] | 2016-12-16 | 2017-02-08 | 2017-02-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-02-12 | 2017-03-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-11-15 | 2017-11-15 | Finished |  |  | 2017-11-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-05 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | 2018-03-15 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2018-02-13 | Finished |  |  | 2016-08-01 | Finished | [18 empty] | 2017-02-07 | Finished |  |  | 2017-02-08 | Finished |  |  | 2017-02-08 | Finished |  |  | 2018-02-13 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-23 | Finished |  | pass | 2019-08-23 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000688 | 2017-02-07 | QC Passed
TAE1067-TH | SHE | 21000659 | HO | ยังอยู่ในสัญญา HO | - | TH160187 | Dobergo | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2016-07-11 | 2016-11-11 | 2016-12-26 | 2021-10-26 | UAG-11G-A-900-2PCO60;2S/2F; | UAG-11G-A | 900 | 60 | 2 | 2 |  | 1475000 | Bangkok | ตำบลบางพลับ | 2017-09-05 | 2017-10-02 | Finished | [34 empty] | 2016-10-27 | 2017-05-30 | 2017-05-30 | Finished | PAYMENT DELAY | [13 empty] | 2017-10-02 | 2017-10-17 | 2017-10-02 | Finished |  |  | 2017-10-03 | Finished |  |  | 2017-10-04 | Finished |  |  | 2017-10-07 | Finished |  |  | 2017-10-09 | Finished |  |  | 2017-10-11 | Finished |  |  | 2017-10-13 | Finished |  |  | 2017-10-14 | Finished |  |  | 2017-10-15 | Finished |  |  | 2017-10-17 | Finished |  |  | 100 | [41 empty] | 2017-10-17 | 2020-07-07 | 2020-07-07 | Finished |  |  | 2020-05-30 | 2020-07-08 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | [18 empty] | 0 | 2022-02-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2016-07-26 | Finished | [18 empty] | 2017-05-29 | Finished |  |  | 2017-05-30 | Finished |  |  | 2017-05-31 | Finished | [22 empty] | 345 | 79 | 16 | 16 | 456 | 0 | 0 | 16 | 16 | 32 | 92.98 | Green | [7 empty] | DSE000755 | 2017-05-29
TBG0056-TH | SHE | 21000673 | HO | ส่งมอบแล้ว | - | TH160197 | PT Galleria | L-03 (A) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2016-07-25 | 2016-11-09 | 2017-02-09 |  | OUG-2000-2PCO60;3S/3F; | OUG | 2000 | 60 | 3 | 3 |  | 3349100 | Bangkok | เขตลาดกระบัง | 2017-01-12 | 2017-01-12 | Finished | [34 empty] | 2016-11-09 | 2017-01-24 | 2017-01-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-01-12 | 2017-01-27 | 2017-01-14 | Finished |  |  | 2017-01-16 | Finished |  |  | 2017-01-17 | Finished |  |  | 2017-01-18 | Finished |  |  | 2017-01-19 | Finished |  |  | 2017-01-20 | Finished |  |  | 2017-01-22 | Finished |  |  | 2017-01-24 | Finished |  |  | 2017-01-26 | Finished |  |  | 2017-01-27 | Finished |  |  | 100 | [41 empty] | 2017-01-27 | 2017-02-05 | 2017-02-05 | Finished |  |  | 2017-02-05 | 2017-02-05 | Finished |  |  | 2017-02-10 | Finished |  |  | 2017-02-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-18 | Finished |  |  | 100 | 2018-02-20 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-05-14 | Finished |  |  | 2016-08-30 | Finished | [18 empty] | 2017-01-23 | Finished |  |  | 2017-02-17 | Finished |  |  | 2017-01-24 | Finished |  |  | 2019-05-14 | Finished | [13 empty] | no pass |  |  |  |  | 399 | 84 | 16 | 16 | 515 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000179 | 2017-01-23
TAD0181-TH | SHE | 21000680 | HO | ส่งมอบแล้ว | - | TH160203 | Bangyai Hospital (114 Bed) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2016-08-15 | 2016-11-15 | 2016-12-31 | 2020-05-03 | B-II(VFI-II)-1000-2S2P60;5S/5F; | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1498000 | Nonthaburi | อำเภอบางใหญ่ | 2017-12-15 | 2017-12-15 | Finished | [34 empty] | 2016-11-07 | 2017-01-23 | 2017-01-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-01-23 | 2017-03-04 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-06-16 | 2017-06-16 | Finished |  |  | 2017-06-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-10 | Finished | [6 empty] | 90 | 2017-07-07 | Finished | POWER SUPPLY DELAY |  | 2017-07-18 | Finished |  |  | 2016-09-06 | Finished | [18 empty] | 2017-01-17 | Finished |  |  | 2017-01-24 | Finished |  |  | 2017-01-23 | Finished |  |  | 2017-07-18 | Finished |  |  | 2017-08-18 | Finished |  |  | 2017-08-18 | Finished |  |  | 2017-08-18 | Finished |  | pass | 2017-08-18 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue | [7 empty] | DSE000680 | 2017-01-17 | QC Passed
TAD0182-TH | SHE | 21000680 | HO | ส่งมอบแล้ว | - | TH160203 | Bangyai Hospital (114 Bed) | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2016-08-15 | 2016-11-15 | 2016-12-31 | 2020-05-03 | B-II(VFI-II)-1000-2S2P60;5S/5F; | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1498000 | Nonthaburi | อำเภอบางใหญ่ | 2017-12-15 | 2017-12-15 | Finished | [34 empty] | 2016-11-07 | 2017-01-23 | 2017-01-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-01-23 | 2017-03-04 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-06-16 | 2017-06-16 | Finished |  |  | 2017-06-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-10 | Finished | [6 empty] | 90 | 2017-07-07 | Finished | POWER SUPPLY DELAY |  | 2017-07-18 | Finished |  |  | 2016-09-06 | Finished | [18 empty] | 2017-01-17 | Finished |  |  | 2017-01-24 | Finished |  |  | 2017-01-23 | Finished |  |  | 2017-07-18 | Finished |  |  | 2017-08-18 | Finished |  |  | 2017-08-18 | Finished |  |  | 2017-08-18 | Finished |  | pass | 2017-08-18 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue | [7 empty] | DSE000680 | 2017-01-17 | QC Passed
TAE1077-TH | SHE | 21000681 | HO | ส่งมอบแล้ว | - | TH170021 | Office (Chief Judge) | PL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2016-08-25 | 2017-02-09 | 2017-04-09 | 2020-05-03 | UAG-11G-A-900-2PCO60;4S/4F; | UAG-11G-A | 900 | 60 | 4 | 4 |  | 1500000 | Bangkok | เขตตลิ่งชัน | 2017-02-07 | 2017-02-07 | Finished | [34 empty] | 2017-01-25 | 2017-02-07 | 2017-02-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-02-08 | 2017-02-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-07-25 | 2017-07-25 | Finished |  |  | 2017-07-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2017-08-17 | Finished | POWER SUPPLY DELAY |  | 2017-09-28 | Finished |  |  | 2016-10-05 | Finished | [18 empty] | 2017-02-06 | Finished |  |  | 2017-02-07 | Finished |  |  | 2017-02-07 | Finished |  |  | 2017-09-28 | Finished | [13 empty] | no pass |  |  |  |  | 455 | 81 | 16 | 16 | 568 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue | [7 empty] | DSE000685 | 2017-02-06
TAC0834-TH | SHE | 21000696 | Install | เลยสัญญา HO | - | TH170035 | Government Center Phuket | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2016-09-30 | 2017-07-31 | 2017-10-31 |  | VFI-II-1000-2PCO60;5S/5F; | VFI-II | 1000 | 60 | 5 | 5 |  | 1605000 | Phuket | ตำบลตลาดเหนือ | 2017-10-29 | 2017-11-03 | Finished | [34 empty] | 2017-07-24 | 2017-10-03 | 2017-10-03 | Finished | CONSTRUCTION STOP | [13 empty] | 2017-11-13 | 2017-11-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-05 | 2020-01-05 | Finished |  |  | 2020-01-03 | 2021-06-16 | Finished |  |  | 2021-06-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-04-20 | Finished | [18 empty] | 2017-10-02 | Finished |  |  | 2017-10-04 | Finished |  |  | 2017-10-25 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 4 | 16 | 20 | 96.92 | Red | [7 empty] | DSE000839 | 2017-10-02
TAC0835-TH | SHE | 21000696 | Install | เลยสัญญา HO | - | TH170035 | Government Center Phuket | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2016-09-30 | 2017-07-31 | 2017-10-31 |  | VFI-II-1000-2PCO60;5S/5F; | VFI-II | 1000 | 60 | 5 | 5 |  | 1605000 | Phuket | ตำบลตลาดเหนือ | 2017-10-29 | 2017-11-03 | Finished | [34 empty] | 2017-07-24 | 2017-10-03 | 2017-10-03 | Finished | CONSTRUCTION STOP | [13 empty] | 2017-11-13 | 2017-11-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-05 | 2020-01-05 | Finished |  |  | 2020-01-03 | [12 empty] | 0 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-04-20 | Finished | [18 empty] | 2017-10-02 | Finished |  |  | 2017-10-04 | Finished |  |  | 2017-10-25 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Red | [7 empty] | DSE000839 | 2017-10-02
TAC0836-TH | SHE | 21000696 | Install | เลยสัญญา HO | - | TH170035 | Government Center Phuket | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2016-09-30 | 2017-07-31 | 2017-10-31 |  | VFI-II-1000-2PCO60;5S/5F; | VFI-II | 1000 | 60 | 5 | 5 |  | 1605000 | Phuket | ตำบลตลาดเหนือ | 2017-10-29 | 2017-11-03 | Finished | [34 empty] | 2017-07-24 | 2017-10-03 | 2017-10-03 | Finished | CONSTRUCTION STOP | [13 empty] | 2017-11-13 | 2017-11-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-05 | 2020-01-05 | Finished |  |  | 2020-01-03 | 2021-06-16 | Finished |  |  | 2021-06-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-04-20 | Finished | [18 empty] | 2017-10-02 | Finished |  |  | 2017-10-04 | Finished |  |  | 2017-10-25 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 4 | 16 | 20 | 96.92 | Red | [7 empty] | DSE000839 | 2017-10-02
TAC0837-TH | SHE | 21000696 | Install | เลยสัญญา HO | - | TH170035 | Government Center Phuket | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2016-09-30 | 2017-07-31 | 2017-10-31 |  | VFI-II-1000-2PCO60;5S/5F; | VFI-II | 1000 | 60 | 5 | 5 |  | 1605000 | Phuket | ตำบลตลาดเหนือ | 2017-10-29 | 2017-11-03 | Finished | [34 empty] | 2017-07-24 | 2017-10-03 | 2017-10-03 | Finished | CONSTRUCTION STOP | [13 empty] | 2017-11-13 | 2017-11-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-05 | 2020-01-05 | Finished |  |  | 2020-01-03 | [12 empty] | 0 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-04-20 | Finished | [18 empty] | 2017-10-02 | Finished |  |  | 2017-10-04 | Finished |  |  | 2017-10-25 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Red | [7 empty] | DSE000839 | 2017-10-02
TAC0866-TH | SHE | 21000729 | HO | ส่งมอบแล้ว | - | TH170051 | Pratunam Pavilion Hotel 2 (Soi Ratchaprarop 8) | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2016-09-22 | 2017-02-22 | 2017-04-22 | 2020-06-08 | VFI-II-550-2PCO60;6S/6F; | VFI-II | 550 | 60 | 6 | 6 |  | 1000000 | Bangkok | แขวงพญาไท | 2018-11-15 | 2018-11-11 | Finished | [34 empty] | 2017-02-15 | 2018-08-29 | 2018-08-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-11 | 2018-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-04 | 2019-10-04 | Finished |  |  | 2019-10-04 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-11 | Finished | [6 empty] | 90 | 2020-07-15 | Finished | POWER SUPPLY DELAY |  | 2020-07-20 | Finished |  |  | 2016-11-11 | Finished | [18 empty] | 2018-08-22 | Finished |  |  | 2018-11-16 | Finished |  |  | 2018-11-16 | Finished |  |  | 2020-07-20 | Finished | [13 empty] | pass (defect) |  |  |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 1 | 1 | 99.86 | Blue | [7 empty] | DSE000894 | 2018-08-22
TAC0867-TH | SHE | 21000729 | HO | ส่งมอบแล้ว | - | TH170051 | Pratunam Pavilion Hotel 2 (Soi Ratchaprarop 8) | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2016-09-22 | 2017-02-22 | 2017-04-22 | 2020-06-08 | VFI-II-750-2PCO60;6S/6F; | VFI-II | 750 | 60 | 6 | 6 |  | 1050000 | Bangkok | แขวงพญาไท | 2018-11-15 | 2018-11-11 | Finished | [34 empty] | 2017-02-15 | 2018-08-29 | 2018-08-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-11 | 2018-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-04 | 2019-10-04 | Finished |  |  | 2019-10-04 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-11 | Finished | [6 empty] | 90 | 2020-07-15 | Finished | POWER SUPPLY DELAY |  | 2020-07-20 | Finished |  |  | 2016-11-11 | Finished | [18 empty] | 2018-08-22 | Finished |  |  | 2018-11-16 | Finished |  |  | 2018-11-16 | Finished |  |  | 2020-07-20 | Finished | [13 empty] | pass (defect) |  |  |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 1 | 1 | 99.86 | Blue | [7 empty] | DSE000894 | 2018-08-22
TAE1120-TH | SHE | 21000745 | HO | ส่งมอบแล้ว | - | TH170075 | Akara Clinic | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | TEERASAK JUNTHAWEE | 2016-10-31 | 2017-01-31 | 2017-03-31 | 2020-06-08 | UAG-11G-A-750-2PCO60;4S/4F; | UAG-11G-A | 750 | 60 | 4 | 4 |  | 1320000 | Bangkok | แขวงบางจาก | 2018-04-30 | 2018-04-20 | Finished | [34 empty] | 2017-01-31 | 2017-05-03 | 2017-05-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-04-20 | 2018-05-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-05-17 | 2018-05-17 | Finished |  |  | 2018-05-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2019-09-30 | 2000-01-01 | 2019-09-30 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-09-30 | Finished |  |  | 2021-09-09 | Finished |  |  | 100 | 2021-07-26 | Finished | CUSTOMER DECORATION DELAY |  | 2021-03-31 | Finished |  |  | 2016-11-15 | Finished | [10 empty] | 2021-03-31 | Finished | [6 empty] | 2017-05-02 | Finished |  |  | 2017-05-12 | Finished |  |  | 2017-05-12 | Finished |  |  | 2021-03-31 | Finished | [13 empty] | no pass |  |  |  |  | 455 | 81 | 16 | 16 | 568 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000737 | 2017-05-02
TFA0686-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | 1200SX-EN;35;3900; | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงถนนพญาไท | 2019-10-30 | [20 empty] | 2019-10-28 | Finished | [14 empty] | 2018-08-15 | 2018-09-27 | 2018-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-28 | 2020-04-30 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-03-11 | 1900-01-01 | 2020-03-11 | Waiting | POWER SUPPLY DELAY |  | 2021-11-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-27 | Finished |  |  | 2018-09-28 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 16 | 14 | 62 | 90.14 | Green | [7 empty] | DME000248 | 2018-09-18
TFA0687-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | 1200SX-EN;35;3900; | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงถนนพญาไท | 2019-10-30 | [20 empty] | 2019-10-28 | Finished | [14 empty] | 2018-08-15 | 2018-09-27 | 2018-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-28 | 2020-04-30 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-03-11 | 1900-01-01 | 2020-03-11 | Waiting | POWER SUPPLY DELAY |  | 2021-11-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-27 | Finished |  |  | 2018-09-28 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 16 | 14 | 62 | 90.14 | Green | [7 empty] | DME000248 | 2018-09-18
TFA0688-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | 1200SX-EN;35;3900; | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงถนนพญาไท | 2019-10-30 | [20 empty] | 2019-10-28 | Finished | [14 empty] | 2018-08-15 | 2018-09-27 | 2018-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-28 | 2020-04-30 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-03-11 | 1900-01-01 | 2020-03-11 | Waiting | POWER SUPPLY DELAY |  | 2021-11-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-27 | Finished |  |  | 2018-09-28 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 16 | 14 | 62 | 90.14 | Green | [7 empty] | DME000248 | 2018-09-18
TFA0689-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | ES4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | 1200SX-EN;35;3900; | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงถนนพญาไท | 2019-10-30 | [20 empty] | 2019-10-28 | Finished | [14 empty] | 2018-08-15 | 2018-09-27 | 2018-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-28 | 2020-04-30 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-03-11 | 1900-01-01 | 2020-03-11 | Waiting | POWER SUPPLY DELAY |  | 2021-11-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-27 | Finished |  |  | 2018-09-28 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 16 | 14 | 62 | 90.14 | Green | [7 empty] | DME000248 | 2018-09-18
TFA0690-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | ES5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | 1200SX-EN;35;3900; | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงถนนพญาไท | 2019-10-30 | [20 empty] | 2019-10-28 | Finished | [14 empty] | 2018-08-15 | 2018-09-27 | 2018-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-28 | 2020-04-30 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-03-11 | 1900-01-01 | 2020-03-11 | Waiting | POWER SUPPLY DELAY |  | 2021-11-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-27 | Finished |  |  | 2018-09-28 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 16 | 14 | 62 | 90.14 | Green | [7 empty] | DME000248 | 2018-09-18
TFA0691-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | ES6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | 1200SX-EN;35;3900; | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงถนนพญาไท | 2022-01-15 | [36 empty] | 2018-08-15 | 2018-09-27 | 2018-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-01-15 | 2022-02-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-02 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | OTHERS | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-27 | Finished |  |  | 2018-09-28 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 567 | 32 | 16 | 14 | 629 | 0 | Green | [7 empty] | DME000248 | 2018-09-18
TEC0087-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | DW1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | DT-100-T/B30;14S/14F; | DT | 100 | 30 | 14 | 14 |  | 428000 | Bangkok | แขวงถนนพญาไท | 2020-11-30 | 2021-01-15 | Finished | [34 empty] | 2018-10-15 | 2019-01-23 | 2021-02-01 | Finished | PAYMENT DELAY | [13 empty] | 2021-02-01 | 2021-04-01 | 2021-02-02 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-03-20 | Finished |  |  | 100 | [41 empty] | 2021-03-20 | 1900-01-01 | 2021-03-20 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 504 | 0 | 32 | 0 | 536 | 0 | 0 | 32 | 0 | 32 | 94.03 | Green | [7 empty] | DME000264 | 2021-03-16
TEC0088-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | DW2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | DT-100-T/B30;10S/10F; | DT | 100 | 30 | 10 | 10 |  | 428000 | Bangkok | แขวงถนนพญาไท | 2020-11-30 | 2021-01-15 | Finished | [34 empty] | 2018-10-15 | 2018-08-18 | 2021-02-01 | Finished | PAYMENT DELAY | [13 empty] | 2021-02-01 | 2021-04-01 | 2021-02-02 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-03-20 | Finished |  |  | 100 | [41 empty] | 2021-03-20 | 1900-01-01 | 2021-03-20 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 393 | 0 | 24 | 0 | 417 | 0 | 0 | 24 | 0 | 24 | 94.24 | Green | [7 empty] | DME000264 | 2021-03-16
TEC0089-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | DW3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | DT-100-T/B30;7S/9F; | DT | 100 | 30 | 7 | 9 |  | 374500 | Bangkok | แขวงถนนพญาไท | 2020-11-30 | 2021-01-15 | Finished | [34 empty] | 2018-10-15 | 2018-08-18 | 2021-02-01 | Finished | PAYMENT DELAY | [13 empty] | 2021-02-01 | 2021-04-01 | 2021-02-02 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-03-20 | Finished |  |  | 100 | [41 empty] | 2021-03-20 | 1900-01-01 | 2021-03-20 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 366 | 0 | 24 | 0 | 390 | 0 | 0 | 24 | 0 | 24 | 93.85 | Green | [7 empty] | DME000264 | 2021-03-16
TAD0216-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | B-II(VFI-II)-1000-2S2P105;27S/27F; | B-II(VFI-II) | 1000 | 105 | 27 | 27 |  | 2889000 | Bangkok | แขวงถนนพญาไท | 2020-04-10 | 2020-04-10 | Finished | [34 empty] | 2018-08-15 | 2019-03-22 | 2019-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-01 | 2020-04-01 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-11 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | [41 empty] | 2020-05-20 | 1900-01-01 | 2020-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-03-15 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-26 | Finished | [22 empty] | 1743 | 119 | 56 | 24 | 1942 | 0 | 119 | 56 | 24 | 199 | 89.75 | Green | [7 empty] | DME000261 | 2019-03-15
TAD0217-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | B-II(VFI-II)-1000-2S2P105;27S/27F; | B-II(VFI-II) | 1000 | 105 | 27 | 27 |  | 2889000 | Bangkok | แขวงถนนพญาไท | 2020-04-10 | 2020-04-10 | Finished | [34 empty] | 2018-10-15 | 2019-03-22 | 2019-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-01 | 2020-04-01 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | [41 empty] | 2020-06-27 | 1900-01-01 | 2020-06-27 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-03-15 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-26 | Finished | [22 empty] | 1743 | 119 | 56 | 24 | 1942 | 0 | 119 | 56 | 24 | 199 | 89.75 | Green | [7 empty] | DME000261 | 2019-03-15
TAC0908-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | VFI-II-1000-2PCO150;27S/27F; | VFI-II | 1000 | 150 | 27 | 27 |  | 3210000 | Bangkok | แขวงถนนพญาไท | 2020-04-10 | 2020-04-01 | Finished | [34 empty] | 2018-10-15 | 2019-03-22 | 2019-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-01 | 2020-04-01 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | [41 empty] | 2020-06-27 | 1900-01-01 | 2020-06-27 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-03-15 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-26 | Finished | [22 empty] | 1743 | 119 | 56 | 24 | 1942 | 0 | 119 | 56 | 24 | 199 | 89.75 | Green | [7 empty] | DME000261 | 2019-03-15
TAC0909-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | VFI-II-1000-2PCO150;27S/27F; | VFI-II | 1000 | 150 | 27 | 27 |  | 3210000 | Bangkok | แขวงถนนพญาไท | 2020-04-10 | 2020-04-20 | Finished | [34 empty] | 2018-10-15 | 2019-03-22 | 2019-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-01 | 2020-04-20 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-02 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-08-10 | Finished |  |  | 100 | [41 empty] | 2020-08-10 | 1900-01-01 | 2020-08-10 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-03-15 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-26 | Finished | [22 empty] | 1743 | 119 | 56 | 24 | 1942 | 0 | 119 | 56 | 24 | 199 | 89.75 | Green | [7 empty] | DME000261 | 2019-03-15
TAC0910-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | VFI-II-1000-2PCO150;27S/27F; | VFI-II | 1000 | 150 | 27 | 27 |  | 3210000 | Bangkok | แขวงถนนพญาไท | 2020-04-10 | 2020-04-20 | Finished | [34 empty] | 2018-10-15 | 2019-03-22 | 2019-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-01 | 2020-04-20 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-02 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-08-10 | Finished |  |  | 100 | [41 empty] | 2020-08-10 | 1900-01-01 | 2020-08-10 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-03-15 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-26 | Finished | [22 empty] | 1743 | 119 | 56 | 24 | 1942 | 0 | 119 | 56 | 24 | 199 | 89.75 | Green | [7 empty] | DME000261 | 2019-03-15
TAC0911-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | VFI-II-1000-2PCO150;18S/20F; | VFI-II | 1000 | 150 | 18 | 20 |  | 2808750 | Bangkok | แขวงถนนพญาไท | 2020-01-15 | 2020-01-10 | Finished | [34 empty] | 2018-09-15 | 2019-06-22 | 2019-06-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-10 | 2020-03-20 | 2020-01-04 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-21 | Finished |  |  | 100 | [41 empty] | 2020-03-21 | 1900-01-01 | 2020-03-21 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-06-15 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-26 | Finished | [22 empty] | 1356 | 113 | 40 | 24 | 1533 | 0 | 113 | 40 | 24 | 177 | 88.45 | Green | [7 empty] | DME000263 | 2019-06-15
TAC0912-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | VFI-II-1000-2PCO150;18S/20F; | VFI-II | 1000 | 150 | 18 | 20 |  | 2808750 | Bangkok | แขวงถนนพญาไท | 2020-01-15 | 2020-01-10 | Finished | [34 empty] | 2018-09-15 | 2019-06-22 | 2019-06-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-10 | 2020-03-20 | 2020-01-04 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-21 | Finished |  |  | 100 | [41 empty] | 2020-03-21 | 1900-01-01 | 2020-03-21 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-22 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-06-15 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-26 | Finished | [22 empty] | 1356 | 113 | 40 | 24 | 1533 | 0 | 113 | 40 | 24 | 177 | 88.45 | Green | [7 empty] | DME000263 | 2019-06-15
TAD0218-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | B-II(VFI-II)-1000-2S2P105;18S/20F; | B-II(VFI-II) | 1000 | 105 | 18 | 20 |  | 2300500 | Bangkok | แขวงถนนพญาไท | 2021-09-20 | [36 empty] | 2018-09-15 | 2019-06-22 | 2019-06-22 | Finished | PAYMENT DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-06-15 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-26 | Finished | [22 empty] | 1356 | 113 | 40 | 24 | 1533 | 1356 | 113 | 40 | 24 | 1533 | 0 | Green | [7 empty] | DME000263 | 2019-06-15
TAD0219-TH | SHE | 21000792 | Test | ยังอยู่ในสัญญา HO | - | TH180001 | Academy of Dermatology | L9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-09-30 | 2018-09-01 | 2019-02-01 | 2021-12-30 | B-II(VFI-II)-1000-2S2P105;18S/20F; | B-II(VFI-II) | 1000 | 105 | 18 | 20 |  | 2300500 | Bangkok | แขวงถนนพญาไท | 2021-09-20 | [36 empty] | 2018-09-15 | 2019-06-22 | 2019-06-22 | Finished | PAYMENT DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-11-03 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2019-06-15 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-26 | Finished | [22 empty] | 1356 | 113 | 40 | 24 | 1533 | 1356 | 113 | 40 | 24 | 1533 | 0 | Green | [7 empty] | DME000263 | 2019-06-15
TBJ0011-TH | SHE | 21000803 | HO | ส่งมอบแล้ว | - | TH170052 | Thai Flour Mill Industry Phase II | FL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2016-10-12 | 2017-05-12 | 2017-09-12 |  | F(H)-EL-4000-3S3P30;6S/6F; | F(H)-EL | 4000 | 30 | 6 | 6 |  | 7704000 | Samut Prakan | ต.สำโรงใต้ | 2017-05-13 | 2017-10-25 | Finished | [34 empty] | 2017-04-27 | 2018-08-29 | 2017-08-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-01 | 2018-01-31 | 2017-11-05 | Finished |  |  | 2017-11-09 | Finished |  |  | 2017-12-15 | Finished |  |  | 2017-12-15 | Finished |  |  | 2017-11-20 | Finished |  |  | 2017-11-20 | Finished |  |  | 2017-11-25 | Finished |  |  | 2018-01-25 | Finished |  |  | 2017-12-25 | Finished |  |  | 2018-01-10 | Finished |  |  | 100 | [41 empty] | 2018-01-10 | 2019-03-04 | 2019-03-04 | Finished |  |  | 2019-03-04 | 2019-03-04 | Finished |  |  | 2019-03-06 | Finished |  |  | 2019-03-08 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-02-21 | Finished | POWER SUPPLY DELAY |  | 2019-06-06 | Finished |  |  | 2016-11-10 | Finished | [18 empty] | 2017-08-18 | Finished |  |  | 2017-08-21 | Finished |  |  | 2017-08-28 | Finished |  |  | 2019-06-06 | Finished | [13 empty] | no pass |  |  |  |  | 719 | 111 | 72 | 20 | 922 | 0 | 0 | 0 | 2 | 2 | 99.78 | Blue | [7 empty] | DSE000817 | 2017-08-18
TAC0864-TH | SHE | 21000803 | HO | ส่งมอบแล้ว | - | TH170052 | Thai Flour Mill Industry Phase II | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2016-10-12 | 2017-05-12 | 2017-09-12 | 2021-10-21 | VFI-II-1000-2PCO60;6S/6F; | VFI-II | 1000 | 60 | 6 | 6 |  | 1658500 | Samut Prakan | ต.สำโรงใต้ | 2017-05-13 | 2017-10-25 | Finished | [34 empty] | 2017-04-27 | 2018-08-29 | 2017-08-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-01 | 2018-01-31 | 2017-11-05 | Finished |  |  | 2017-11-09 | Finished |  |  | 2017-12-15 | Finished |  |  | 2017-12-15 | Finished |  |  | 2017-11-20 | Finished |  |  | 2017-11-20 | Finished |  |  | 2017-11-25 | Finished |  |  | 2018-01-25 | Finished |  |  | 2017-12-25 | Finished |  |  | 2018-01-10 | Finished |  |  | 100 | [41 empty] | 2018-01-10 | 2019-07-22 | 2019-07-22 | Finished |  |  | 2019-07-22 | 2019-07-25 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-08-16 | Finished |  |  | 2021-02-01 | Finished |  |  | 100 | 2021-09-06 | Finished | POWER SUPPLY DELAY |  | 2021-09-08 | Finished |  |  | 2016-11-10 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2017-08-16 | Finished |  |  | 2017-08-21 | Finished |  |  | 2017-08-28 | Finished |  |  | 2021-09-08 | Finished | [13 empty] | pass (defect) |  |  |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000815 | 2017-08-16
TAC0865-TH | SHE | 21000803 | HO | ส่งมอบแล้ว | - | TH170052 | Thai Flour Mill Industry Phase II | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2016-10-12 | 2017-05-12 | 2017-09-12 | 2021-10-21 | VFI-II-1000-2PCO60;6S/6F; | VFI-II | 1000 | 60 | 6 | 6 |  | 1658500 | Samut Prakan | ต.สำโรงใต้ | 2017-05-13 | 2017-10-25 | Finished | [34 empty] | 2017-04-27 | 2017-05-03 | 2017-08-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-11-01 | 2018-01-31 | 2017-11-05 | Finished |  |  | 2017-11-09 | Finished |  |  | 2017-12-15 | Finished |  |  | 2017-12-15 | Finished |  |  | 2017-11-20 | Finished |  |  | 2017-11-20 | Finished |  |  | 2017-11-25 | Finished |  |  | 2018-01-25 | Finished |  |  | 2017-12-25 | Finished |  |  | 2018-01-10 | Finished |  |  | 100 | [41 empty] | 2018-01-10 | 2019-07-22 | 2019-07-22 | Finished |  |  | 2019-07-22 | 2019-07-25 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-08-16 | Finished |  |  | 2021-02-01 | Finished |  |  | 100 | 2021-09-06 | Finished | POWER SUPPLY DELAY |  | 2021-09-08 | Finished |  |  | 2016-11-10 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2017-08-16 | Finished |  |  | 2017-08-21 | Finished |  |  | 2017-08-28 | Finished |  |  | 2021-09-08 | Finished | [13 empty] | pass (defect) |  |  |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000815 | 2017-08-16
TFA0733-TH | SHE | 21000807 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | ES11 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Naris Janjaroenkit | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2017-09-15 |  | 1200SX-EN;30;6000; | SX-EN |  |  |  |  | 6000 | 1300000 | Bangkok | เขตพระโขนง | 1900-01-01 | [20 empty] | 2017-07-25 | Finished | [14 empty] | 2017-04-01 | 2017-05-21 | 2017-05-21 | Finished | PAYMENT DELAY | [13 empty] | 2017-07-25 | 2017-09-30 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-08-01 | 2019-08-01 | Finished |  |  | 2019-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2019-12-12 | Finished | POWER SUPPLY DELAY |  | 2019-12-17 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-05-22 | Finished |  |  | 2017-05-22 | Finished |  |  | 2017-05-23 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-23 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 24 | 21 | 45 | 94.23 | Blue | [7 empty] | DME000192 | 2017-05-22
TFA0735-TH | SHE | 21000807 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | ES13 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Naris Janjaroenkit | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2017-09-15 |  | 1200SX-EN;30;6000; | SX-EN |  |  |  |  | 6000 | 1300000 | Bangkok | เขตพระโขนง | 1900-01-01 | [20 empty] | 2017-07-22 | Finished | [14 empty] | 2017-04-01 | 2017-05-21 | 2017-05-21 | Finished | PAYMENT DELAY | [13 empty] | 2017-07-25 | 2017-09-30 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-08-01 | 2019-08-01 | Finished |  |  | 2019-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2019-12-12 | Finished | POWER SUPPLY DELAY |  | 2019-12-17 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-05-22 | Finished |  |  | 2017-05-22 | Finished |  |  | 2017-05-23 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-23 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 24 | 21 | 45 | 94.23 | Blue | [7 empty] | DME000192 | 2017-05-22
TAC0932-TH | SHE | 21000807 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | FL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2017-09-15 |  | VFI-II-1000-2PCO90;11S/11F; | VFI-II | 1000 | 90 | 11 | 11 |  | 1550000 | Bangkok | เขตพระโขนง | 2017-09-01 | 2017-09-01 | Finished | [34 empty] | 2017-04-01 | 2017-06-18 | 2017-06-18 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2017-09-05 | 2017-09-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-10-12 | 2017-10-12 | Finished |  |  | 2017-10-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2017-11-16 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2017-12-13 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-06-15 | Finished |  |  | 2017-06-18 | Finished |  |  | 2017-06-20 | Finished |  |  | 2017-12-13 | Finished | [13 empty] | pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000197 | 2017-06-15 | QC Passed
TAC0930-TH | SHE | 21000807 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | L5 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Naris Janjaroenkit | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2017-09-15 |  | VFI-II-1000-2PCO105;8S/8F; | VFI-II | 1000 | 105 | 8 | 8 |  | 1600000 | Bangkok | เขตพระโขนง | 1900-01-01 | 2017-08-15 | Finished | [34 empty] | 2017-04-01 | 2017-06-18 | 2017-06-18 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2017-09-01 | 2017-09-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-10-16 | 2017-10-16 | Finished |  |  | 2017-10-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2017-11-16 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2017-12-13 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-06-15 | Finished |  |  | 2017-06-18 | Finished |  |  | 2017-06-20 | Finished |  |  | 2017-12-13 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-24 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000197 | 2017-06-15 | QC Passed
TAC0931-TH | SHE | 21000807 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2017-09-15 |  | VFI-II-1000-2PCO105;8S/8F; | VFI-II | 1000 | 105 | 8 | 8 |  | 1600000 | Bangkok | เขตพระโขนง | 2017-08-15 | 2017-08-15 | Finished | [34 empty] | 2017-04-01 | 2017-06-18 | 2017-06-18 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2017-09-01 | 2017-09-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-10-16 | 2017-10-16 | Finished |  |  | 2017-10-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-30 | Finished |  |  | 100 | 2017-11-16 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2017-12-13 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-06-15 | Finished |  |  | 2017-06-18 | Finished |  |  | 2017-06-20 | Finished |  |  | 2017-12-13 | Finished | [13 empty] | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000197 | 2017-06-15 | QC Passed
TBK0062-TH | SHE | 210008071 | HO | ยังอยู่ในสัญญา HO | - | TH170067 | Century The Movie Plaza 2 | FL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2018-03-31 | 2021-11-17 | HVF-5-1150-2PCO180;37S/37F; | HVF-5 | 1150 | 180 | 37 | 37 |  | 5350000 | Bangkok | เขตพระโขนง | 2018-05-20 | 2018-05-20 | Finished | [34 empty] | 2017-08-01 | 2017-10-08 | 2017-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-06-01 | 2018-11-13 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-11-19 | 2018-11-19 | Finished |  |  | 2018-11-19 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 50 | 2021-11-15 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2017-03-25 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2017-11-29 | Finished |  |  | 2017-12-06 | Finished |  |  | 2017-12-07 | Finished | [22 empty] | 2172 | 120 | 72 | 40 | 2404 | 0 | 0 | 18 | 40 | 58 | 97.59 | Green
TBK0058-TH | SHE | 210008071 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2018-03-31 |  | HVF-5-1350-2PCO180;33S/36F; | HVF-5 | 1350 | 180 | 33 | 33 |  | 5500000 | Bangkok | เขตพระโขนง | 2018-06-15 | 2018-06-15 | Finished | [34 empty] | 2017-08-01 | 2017-10-08 | 2017-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-06-16 | 2019-02-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-02-11 | 2019-02-11 | Finished |  |  | 2019-02-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-08 | 2021-07-21 | 2021-01-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 200 | 2020-10-12 | Finished | POWER SUPPLY DELAY |  | 2019-12-17 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-11-29 | Finished |  |  | 2017-12-06 | Finished |  |  | 2017-12-07 | Finished |  |  | 2019-12-17 | Finished | [13 empty] | pass |  |  |  |  | 1976 | 117 | 64 | 32 | 2189 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TBK0059-TH | SHE | 210008071 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2018-03-31 |  | HVF-5-1350-2PCO180;33S/36F; | HVF-5 | 1350 | 180 | 33 | 33 |  | 5500000 | Bangkok | เขตพระโขนง | 2018-06-15 | 2018-06-15 | Finished | [34 empty] | 2017-08-01 | 2017-10-08 | 2017-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-06-16 | 2019-02-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-02-12 | 2019-02-12 | Finished |  |  | 2019-02-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 200 | 2020-10-12 | Finished | POWER SUPPLY DELAY |  | 2019-12-17 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-11-29 | Finished |  |  | 2017-12-06 | Finished |  |  | 2017-12-07 | Finished |  |  | 2019-12-17 | Finished | [13 empty] | pass |  |  |  |  | 1976 | 117 | 64 | 32 | 2189 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TBK0060-TH | SHE | 210008071 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2018-03-31 |  | HVF-5-1350-2PCO180;33S/36F; | HVF-5 | 1350 | 180 | 33 | 33 |  | 5500000 | Bangkok | เขตพระโขนง | 2018-06-15 | 2018-06-15 | Finished | [34 empty] | 2017-08-01 | 2017-10-08 | 2017-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-16 | 2019-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-01 | 2019-11-01 | Finished |  |  | 2019-11-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 200 | 2020-10-22 | Finished | CUSTOMER DECORATION DELAY |  | 2020-02-21 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-11-29 | Finished |  |  | 2017-12-06 | Finished |  |  | 2017-12-07 | Finished |  |  | 2020-02-21 | Finished | [13 empty] | pass |  |  |  |  | 1976 | 117 | 64 | 32 | 2189 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TBK0061-TH | SHE | 210008071 | HO | ส่งมอบแล้ว | - | TH170067 | Century The Movie Plaza 2 | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2016-10-10 | 2017-04-15 | 2018-03-31 |  | HVF-5-1350-2PCO180;33S/36F; | HVF-5 | 1350 | 180 | 33 | 33 |  | 5500000 | Bangkok | เขตพระโขนง | 2018-06-15 | 2018-06-15 | Finished | [34 empty] | 2017-08-01 | 2017-10-08 | 2017-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-16 | 2019-08-05 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-01 | 2019-09-01 | Finished |  |  | 2019-09-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 200 | 2020-10-22 | Finished | CUSTOMER DECORATION DELAY |  | 2020-02-21 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-11-29 | Finished |  |  | 2017-12-06 | Finished |  |  | 2017-12-07 | Finished |  |  | 2020-02-21 | Finished | [13 empty] | pass |  |  |  |  | 1976 | 117 | 64 | 32 | 2189 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TBK0050-TH | SHE | 21000809 | HO | ส่งมอบแล้ว | - | TH170031 | The Saint Residences | FL/SL (A) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Naris Janjaroenkit | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2016-10-06 | 2017-07-01 | 2018-03-03 | 2018-02-21 | HVF-5-1000-2S2P180;41S/41F; | HVF-5 | 1000 | 180 | 41 | 41 |  | 5831500 | Bangkok | เขตจตุจักร | 1900-01-01 | 2017-11-05 | Finished | [34 empty] | 2017-06-15 | 2017-07-28 | 2017-07-28 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-11-06 | 2018-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-01-11 | 2018-01-11 | Finished |  |  | 2018-01-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-06-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-23 | Finished |  |  | 100 | 2020-08-05 | Finished | OTHERS |  | 2020-08-11 | Finished |  |  | 2017-01-13 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2017-09-13 | Finished |  |  | 2018-02-07 | Finished |  |  | 2018-02-08 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass |  |  |  |  | 2368 | 123 | 80 | 48 | 2619 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000824 | 2017-09-13 | QC Passed
TBK0051-TH | SHE | 21000809 | HO | ส่งมอบแล้ว | - | TH170031 | The Saint Residences | FL/SL (B) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Naris Janjaroenkit | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2016-10-06 | 2017-07-01 | 2018-03-03 | 2018-02-21 | HVF-5-1000-2PCO180;41S/41F; | HVF-5 | 1000 | 180 | 41 | 41 |  | 5831500 | Bangkok | เขตจตุจักร | 1900-01-01 | 2017-11-10 | Finished | [34 empty] | 2017-06-15 | 2017-07-28 | 2017-07-28 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-11-11 | 2018-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-01-16 | 2018-01-16 | Finished |  |  | 2018-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 100 | 2020-08-05 | Finished | OTHERS |  | 2020-08-11 | Finished |  |  | 2017-01-13 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2017-09-13 | Finished |  |  | 2018-02-07 | Finished |  |  | 2018-02-08 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass |  |  |  |  | 2368 | 123 | 80 | 48 | 2619 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000824 | 2017-09-13 | QC Passed
TBK0052-TH | SHE | 21000809 | HO | ส่งมอบแล้ว | - | TH170031 | The Saint Residences | FL/SL (C) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Naris Janjaroenkit | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2016-10-06 | 2017-07-01 | 2018-03-03 | 2018-02-21 | HVF-5-1000-2PCO180;41S/41F; | HVF-5 | 1000 | 180 | 41 | 41 |  | 5831500 | Bangkok | เขตจตุจักร | 1900-01-01 | 2017-10-19 | Finished | [34 empty] | 2017-09-15 | 2017-07-28 | 2017-07-28 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-10-20 | 2017-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2017-12-26 | 2017-12-26 | Finished |  |  | 2017-12-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-01-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | 2020-08-25 | Finished | OTHERS |  | 2020-09-03 | Finished |  |  | 2017-01-13 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2017-09-13 | Finished |  |  | 2018-02-07 | Finished |  |  | 2018-02-08 | Finished |  |  | 2020-09-03 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass |  |  |  |  | 2368 | 123 | 80 | 48 | 2619 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000824 | 2017-09-13 | QC Passed
TAE1153-TH | SHE | 21000846 | HO | ส่งมอบแล้ว | - | TH170159 | Home Praditpong | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2017-02-21 | 2017-09-21 | 2017-11-21 | 2020-10-24 | UAG-11G-A-600-2PCO60;5S/5F; | UAG-11G-A | 600 | 60 | 5 | 5 |  | 1400000 | Surat Thani | ตำบลตลาด | 2017-10-03 | 2017-10-03 | Finished | [34 empty] | 2017-09-14 | 2018-02-05 | 2018-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-12-25 | 2018-01-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-31 | 2020-01-31 | Finished |  |  | 2020-01-31 | 2020-01-02 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-06 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | 2020-06-19 | Finished | POWER SUPPLY DELAY |  | 2020-06-19 | Finished |  |  | 2017-03-25 | Finished | [18 empty] | 2017-11-14 | Finished |  |  | 2018-02-07 | Finished |  |  | 2018-02-09 | Finished |  |  | 2020-06-19 | Finished | [13 empty] | pass (defect) |  |  |  |  | 510 | 82 | 16 | 16 | 624 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000863 | 2017-11-14
TFB0008-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1MW1 |  |  | 1 | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-12-30 |  | 1200EXS-N;12;3800; | EXS-N |  |  |  |  | 3800 | 2017592 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | [20 empty] | 2018-01-08 | Finished | [14 empty] | 2017-07-01 | 2018-01-05 | 2018-01-05 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2018-01-08 | 2018-02-15 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2018-02-21 | 2018-02-21 | Finished |  |  | 2018-02-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-08 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-08 | Finished |  |  | 100 | 2019-01-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-02-13 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2018-01-08 | Finished |  |  | 2018-01-16 | Finished |  |  | 2018-01-17 | Finished |  |  | 2019-02-13 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-15 | Finished |  | pass |  |  |  |  | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000224 | 2018-01-08 | QC Passed
TFA0748-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | 1200SX-EN;35;3750; | SX-EN |  |  |  |  | 3750 | 957650 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | [20 empty] | 2017-09-01 | Finished | [14 empty] | 2017-07-01 | 2017-08-05 | 2017-08-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-09-01 | 2017-10-31 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2018-01-08 | 2018-01-08 | Finished |  |  | 2018-01-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-08 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-08 | Finished |  |  | 100 | 2020-01-27 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-08-16 | Finished |  |  | 2017-09-16 | Finished |  |  | 2017-09-19 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000204 | 2017-08-16 | QC Passed
TAJ0046-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;6S/6F; | UAG-SN1 | 1600 | 60 | 6 | 6 |  | 1498000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2017-11-20 | Finished | [34 empty] | 2017-06-01 | 2017-08-18 | 2017-08-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-11-20 | 2018-01-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-20 | 2018-02-20 | Finished |  |  | 2018-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2019-05-30 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-05-18 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-05-18 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  | pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0047-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;6S/6F; | UAG-SN1 | 1600 | 60 | 6 | 6 |  | 1498000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2017-11-20 | Finished | [34 empty] | 2017-06-01 | 2017-08-18 | 2017-08-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-11-20 | 2018-01-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-20 | 2018-02-20 | Finished |  |  | 2018-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2019-05-30 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-05-18 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-05-18 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  | pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0048-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;6S/6F; | UAG-SN1 | 1600 | 60 | 6 | 6 |  | 1498000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2017-11-01 | Finished | [34 empty] | 2017-06-01 | 2017-08-18 | 2017-08-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-11-01 | 2018-01-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-20 | 2018-02-20 | Finished |  |  | 2018-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2019-05-30 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-05-18 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-05-18 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  | pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0065-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;6S/6F; | UAG-SN1 | 1600 | 60 | 6 | 6 |  | 1498000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2017-11-01 | Finished | [34 empty] | 2017-07-07 | 2017-08-18 | 2017-08-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-11-01 | 2018-01-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-20 | 2018-02-20 | Finished |  |  | 2018-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-01-27 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  | pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0049-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;5S/5F; | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1444500 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-02-01 | Finished | [34 empty] | 2017-06-01 | 2017-08-18 | 2017-08-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-02-01 | 2018-03-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-03-01 | 2018-03-01 | Finished |  |  | 2018-03-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-17 | 2021-07-12 | 2020-07-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-01-27 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0050-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;5S/5F; | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1444500 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-02-01 | Finished | [34 empty] | 2017-06-01 | 2017-08-18 | 2017-08-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-02-01 | 2018-03-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-01 | 2019-09-01 | Finished |  |  | 2019-09-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-17 | 2021-07-12 | 2020-07-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-01-27 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TBG0058-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | OUG-2000-2S2P60;5S/5F; | OUG | 2000 | 60 | 5 | 5 |  | 2247000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2017-11-20 | Finished | [34 empty] | 2017-06-01 | 2017-12-15 | 2017-12-15 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2017-11-20 | 2018-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-20 | 2018-02-20 | Finished |  |  | 2018-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-17 | 2021-07-12 | 2020-07-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-01-27 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-12-20 | Finished |  |  | 2017-12-26 | Finished |  |  | 2017-12-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 509 | 86 | 16 | 16 | 627 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000223 | 2017-12-20 | QC Passed
TBG0059-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 1P8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | OUG-2000-2S2P60;5S/5F; | OUG | 2000 | 60 | 5 | 5 |  | 2247000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2017-11-20 | Finished | [34 empty] | 2017-06-01 | 2017-12-15 | 2017-12-15 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2017-11-20 | 2018-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-20 | 2018-02-20 | Finished |  |  | 2018-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-17 | 2021-05-28 | 2020-07-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-28 | Finished |  |  | 100 | 2020-01-27 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-12-20 | Finished |  |  | 2017-12-26 | Finished |  |  | 2017-12-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 509 | 86 | 16 | 16 | 627 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000223 | 2017-12-20 | QC Passed
TAJ0051-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 2P3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;4S/4F; | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1391000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-01-15 | Finished | [34 empty] | 2017-07-07 | 2017-09-09 | 2017-09-09 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-01-15 | 2018-03-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-06-01 | 2018-06-01 | Finished |  |  | 2018-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2019-05-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-05-18 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-05-18 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0052-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 2P4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;4S/4F; | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1391000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-01-15 | Finished | [34 empty] | 2017-07-07 | 2017-09-09 | 2017-09-09 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-01-15 | 2018-03-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-06-01 | 2018-06-01 | Finished |  |  | 2018-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2019-05-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-05-18 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-05-18 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0053-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 2P5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;4S/4F; | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1391000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-01-15 | Finished | [34 empty] | 2017-07-07 | 2017-09-09 | 2017-09-09 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-01-15 | 2018-03-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-06-01 | 2018-06-01 | Finished |  |  | 2018-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2019-05-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-05-18 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-05-18 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-14 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0055-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 2P7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;4S/4F; | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1391000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-02-15 | Finished | [34 empty] | 2017-07-07 | 2017-09-16 | 2017-09-16 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-02-15 | 2018-03-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-06-01 | 2018-06-01 | Finished |  |  | 2018-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-01-27 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0056-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 2P8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;4S/4F; | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1391000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-02-15 | Finished | [34 empty] | 2017-07-07 | 2017-09-16 | 2017-09-16 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-02-15 | 2018-03-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-06-01 | 2018-06-01 | Finished |  |  | 2018-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-01-27 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0057-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 2P9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;4S/4F; | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1391000 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-02-15 | Finished | [34 empty] | 2017-07-07 | 2017-09-16 | 2017-09-16 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-02-15 | 2018-03-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-06-01 | 2018-06-01 | Finished |  |  | 2018-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-08-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | 2020-01-27 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-11-29 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0059-TH | SHE | 21000849 | HO | ส่งมอบแล้ว | - | TH170156 | AEC Market | 3P5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-02-03 | 2017-06-01 | 2017-11-30 |  | UAG-SN1-1600-2PCO60;3S/3F; | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1337500 | Phra Nakhon Si Ayutthaya | ต.เชียงรากน้อย อ.บางปะอิน | 1900-01-01 | 2018-01-10 | Finished | [34 empty] | 2017-07-07 | 2017-09-16 | 2017-09-16 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-01-10 | 2018-02-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-04-18 | 2018-04-18 | Finished |  |  | 2018-04-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2019-07-30 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-08-02 | Finished |  |  | 2017-06-24 | Finished | [18 empty] | 2017-09-21 | Finished |  |  | 2017-09-27 | Finished |  |  | 2017-09-27 | Finished |  |  | 2019-08-02 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass |  |  |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000210 | 2017-09-21 | QC Passed
TAJ0083-TH | SHE | 21000876 | HO | เลยสัญญา HO | - | TH170170 | Prasat Thong Garnsura Office | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-04-04 | 2017-11-04 | 2018-01-04 | 2021-09-26 | UAG-SN1-1000-2PCO60;4S/4F; | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1498000 | Phra Nakhon Si Ayutthaya | ตำบลคลองจิก | 2019-02-02 | 2019-02-02 | Finished | [34 empty] | 2017-10-28 | 2018-03-26 | 2018-03-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-02 | 2019-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-02-25 | 2019-02-25 | Finished |  |  | 2021-08-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2021-12-25 | Working | INSTALLATION DEFECT RECTIFICATION DELAY | [5 empty] | 2017-05-11 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2018-03-26 | Finished |  |  | 2018-03-27 | Finished |  |  | 2018-03-28 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 16 | 16 | 32 | 93.29 | Red | [7 empty] | DSE000889 | 2018-03-26
TFA0884-TH | SHE | 21000887 | Install | ยังอยู่ในสัญญา HO | - | TH170209 | Central World (Major Renovation 2016)(Phase 4)(New Zone | ESC13 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-02-06 | 2017-10-01 | 2017-12-01 | 2021-12-15 | 1200SX-EN;35;4500; | SX-EN |  |  |  |  | 4500 | 1064650 | Bangkok | เขตปทุมวัน | 2020-06-12 | [36 empty] | 2017-09-15 | 2017-10-18 | 2017-10-18 | Finished | STORE AREA | [13 empty] | 2020-06-13 | 2020-06-21 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2020-12-01 | [12 empty] | 0 | 2021-02-12 | 2000-01-01 | 2021-02-12 | Finished | [14 empty] | 25 | 2021-12-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-08-26 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2017-10-16 | Finished |  |  | 2017-10-20 | Finished |  |  | 2017-10-24 | Finished | [22 empty] | 567 | 42 | 16 | 21 | 646 | 0 | 42 | 4 | 21 | 67 | 89.63 | Green | [7 empty] | DBE000014 | 2017-10-16
TFA0885-TH | SHE | 21000887 | Install | ยังอยู่ในสัญญา HO | - | TH170209 | Central World (Major Renovation 2016)(Phase 4)(New Zone | ESC14 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-02-06 | 2017-10-01 | 2017-12-01 | 2021-12-15 | 1200SX-EN;35;4500; | SX-EN |  |  |  |  | 4500 | 1064650 | Bangkok | เขตปทุมวัน | 2020-06-12 | [36 empty] | 2017-09-15 | 2017-10-18 | 2017-10-18 | Finished | STORE AREA | [13 empty] | 2020-06-13 | 2020-06-21 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2020-12-01 | [12 empty] | 0 | 2021-02-12 | 2000-01-01 | 2021-02-12 | Finished | [14 empty] | 25 | 2021-12-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-08-26 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2017-10-16 | Finished |  |  | 2017-10-20 | Finished |  |  | 2017-10-24 | Finished | [22 empty] | 567 | 42 | 16 | 21 | 646 | 0 | 42 | 4 | 21 | 67 | 89.63 | Green | [7 empty] | DBE000014 | 2017-10-16
TFA0892-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-01 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-06 | 2019-01-22 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-02-18 | 2020-02-18 | Finished |  |  | 2020-02-18 | 2020-02-25 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-10 | Finished |  |  | 100 | 2020-05-20 | 2021-04-02 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0893-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-02 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-06 | 2019-01-22 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-02-18 | 2020-02-18 | Finished |  |  | 2020-02-18 | 2020-02-25 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-10 | Finished |  |  | 100 | 2020-05-20 | 2021-04-02 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0894-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-03 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-16 | 2018-12-20 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2018-12-22 | 2018-12-22 | Finished |  |  | 2018-12-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-20 | 2021-04-02 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0895-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-04 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-16 | 2018-12-20 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2018-12-22 | 2018-12-22 | Finished |  |  | 2018-12-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-20 | 2021-04-02 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0912-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-05 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;7900; | SX-EN |  |  |  |  | 7900 | 2140000 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-09-04 | 2018-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-06 | 2019-01-22 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-02-18 | 2020-02-18 | Finished |  |  | 2020-02-18 | 2020-02-25 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-10 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-08-07 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0913-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-06 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;7900; | SX-EN |  |  |  |  | 7900 | 2140000 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-09-04 | 2018-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-06 | 2019-01-22 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-02-18 | 2020-02-18 | Finished |  |  | 2020-02-18 | 2020-02-25 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-10 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-08-07 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0914-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-07 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;7900; | SX-EN |  |  |  |  | 7900 | 2140000 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-09-04 | 2018-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-16 | 2018-12-31 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-01-07 | 2019-01-07 | Finished |  |  | 2019-01-07 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-08-07 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0915-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CA-ES-08 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;7900; | SX-EN |  |  |  |  | 7900 | 2140000 | Bangkok | เขตดุสิต | 2018-11-01 | [20 empty] | 2018-07-30 | Finished | [14 empty] | 2018-03-01 | 2018-09-04 | 2018-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-16 | 2018-12-31 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-01-07 | 2019-01-07 | Finished |  |  | 2019-01-07 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-08-07 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0904-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-01 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-03-05 | Finished | [14 empty] | 2018-02-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-23 | 2019-08-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-02-25 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0905-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-02 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-03-05 | Finished | [14 empty] | 2018-02-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-23 | 2019-08-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-02-25 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0906-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-03 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-03-05 | Finished | [14 empty] | 2018-02-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-23 | 2019-08-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-02-25 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0907-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-04 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-03-05 | Finished | [14 empty] | 2018-02-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-23 | 2019-08-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-02-25 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2021-02-16 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0908-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-05 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-03-05 | Finished | [14 empty] | 2018-02-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-23 | 2019-08-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-02-25 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2000-01-01 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Working |  |  | 2021-06-22 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 2 | 2 | 99.72 | Blue
TFA0909-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-06 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-03-05 | Finished | [14 empty] | 2018-02-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-23 | 2019-08-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-02-25 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2021-04-02 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0910-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-07 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-04-16 | Finished | [14 empty] | 2018-02-15 | 2018-03-07 | 2018-03-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-04-18 | 2019-09-19 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-04 | 2020-03-04 | Finished |  |  | 2020-03-09 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2021-03-01 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-02-14 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 2 | 2 | 99.72 | Blue | [9 empty] | QC Passed
TFA0911-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | CB-ES-08 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 |  | 1200SX-EN;30;5000; | SX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | เขตดุสิต | 2018-11-10 | [20 empty] | 2019-04-16 | Finished | [14 empty] | 2018-03-01 | 2018-03-07 | 2018-03-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-04-18 | 2019-09-19 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-03-04 | 2020-03-04 | Finished |  |  | 2020-03-09 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2020-05-20 | 2021-04-02 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-02-14 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0916-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | LA-ES-01 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2021-04-19 | 1200SX-N;30;4700; | SX-N |  |  |  |  | 4700 | 1786900 | Bangkok | เขตดุสิต | 2020-05-05 | [20 empty] | 2020-04-06 | Finished | [14 empty] | 2018-03-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-05 | 2020-06-10 | [41 empty] | 2020-04-08 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-20 | Finished |  |  | 100 | 2020-04-20 | 2020-06-29 | 2020-06-29 | Finished |  |  | 2020-05-05 | 2020-06-30 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | 2020-07-02 | 2020-11-29 | 2020-07-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-29 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 2 | 2 | 99.69 | Blue | [9 empty] | QC Passed
TFA0890-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-01 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-02 | 2019-11-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-08-04 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0891-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-02 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-02 | 2019-11-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-15 | 2019-11-15 | Finished |  |  | 2019-11-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-08-04 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0920-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-03/1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;3900; | SX-EN |  |  |  |  | 3900 | 1177000 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-26 | 2019-11-20 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-10 | 2019-11-10 | Finished |  |  | 2019-11-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-08-04 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0898-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-03/2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;4000; | SX-EN |  |  |  |  | 4000 | 1177000 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-10 | 2019-11-15 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-08 | 2019-11-08 | Finished |  |  | 2019-11-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-08-04 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0921-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-04/1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;3900; | SX-EN |  |  |  |  | 3900 | 1177000 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-26 | 2019-11-20 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-10 | 2019-11-10 | Finished |  |  | 2019-11-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-08-04 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0899-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-04/2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;4000; | SX-EN |  |  |  |  | 4000 | 1177000 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-10 | 2019-11-15 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-08 | 2019-11-08 | Finished |  |  | 2019-11-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-04 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0902-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-05 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;7000; | SX-EN |  |  |  |  | 7000 | 1872500 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-08-23 | 2018-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-18 | 2019-11-10 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-06 | 2019-11-06 | Finished |  |  | 2019-11-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-08-22 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 2 | 2 | 99.76 | Blue | [9 empty] | QC Passed
TFA0903-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-06 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-EN;30;7000; | SX-EN |  |  |  |  | 7000 | 1872500 | Bangkok | เขตดุสิต | 2018-09-15 | [20 empty] | 2018-10-30 | Finished | [14 empty] | 2018-02-01 | 2018-08-23 | 2018-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-18 | 2019-11-10 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-11-06 | 2019-11-06 | Finished |  |  | 2019-11-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-08-22 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 2 | 2 | 99.76 | Blue | [9 empty] | QC Passed
TFA0917-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | N-ES-07 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-04 | 1200SX-N;30;4000; | SX-N |  |  |  |  | 4000 | 1712000 | Bangkok | เขตดุสิต | 2019-01-05 | [20 empty] | 2019-01-21 | Finished | [14 empty] | 2018-02-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-23 | 2019-02-26 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-12-21 | 2019-12-21 | Finished |  |  | 2019-12-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 2 | 2 | 99.69 | Blue | [9 empty] | QC Passed
TFA0888-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-01 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-25 | 2019-07-21 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-23 | 2019-07-23 | Finished |  |  | 2019-07-23 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 100 | 2019-08-09 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0889-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-02 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;5500; | SX-EN |  |  |  |  | 5500 | 1337500 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-25 | 2019-07-21 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-23 | 2019-07-23 | Finished |  |  | 2019-07-23 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-02-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 100 | 2019-08-09 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0918-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-03/1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;3900; | SX-EN |  |  |  |  | 3900 | 1177000 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-03 | 2019-07-19 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-23 | 2019-07-23 | Finished |  |  | 2019-07-23 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2019-08-09 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0896-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-03/2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;4000; | SX-EN |  |  |  |  | 4000 | 1177000 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-30 | 2019-07-18 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-20 | 2019-07-20 | Finished |  |  | 2019-07-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2019-08-09 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0919-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-04/1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;3900; | SX-EN |  |  |  |  | 3900 | 1177000 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-03 | 2019-07-19 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-23 | 2019-07-23 | Finished |  |  | 2019-07-23 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2019-08-09 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0897-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-04/2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;4000; | SX-EN |  |  |  |  | 4000 | 1177000 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-05 | 2018-07-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-30 | 2019-07-18 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-20 | 2019-07-20 | Finished |  |  | 2019-07-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2020-07-15 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-09 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0900-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-05 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;7000; | SX-EN |  |  |  |  | 7000 | 1872500 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-19 | 2018-07-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-06 | 2019-07-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-20 | 2019-07-20 | Finished |  |  | 2019-07-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2019-08-09 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-19 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA0901-TH | SHE | 21000889 | HO | ส่งมอบแล้ว | - | TH150105 | New Parliament | S-ES-06 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2013-11-09 | 2017-10-01 | 2019-06-30 | 2019-12-25 | 1200SX-EN;30;7000; | SX-EN |  |  |  |  | 7000 | 1872500 | Bangkok | เขตดุสิต | 2018-08-15 | [20 empty] | 2018-10-22 | Finished | [14 empty] | 2018-01-15 | 2018-07-19 | 2018-07-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-06 | 2019-07-16 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2019-07-20 | 2019-07-20 | Finished |  |  | 2019-07-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2019-08-09 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-07-19 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TBL0056-TH | SHE | 21000903 | Install | เลยสัญญา HO | - | TH180052 | Faculty of Medicine Vajira Hospital | BL4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-03-27 | 2018-07-05 | 2019-03-01 | 2021-08-31 | OUG-ON1-1600-2S2P105;5S/5F; | OUG-ON1 | 1600 | 105 | 5 | 5 |  | 2193500 | Bangkok | เขตดุสิต | 2021-09-01 | 2021-09-01 | Finished | [34 empty] | 2021-03-26 | 2021-03-26 | 2021-06-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-02 | 2021-09-30 | 2021-09-02 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-05-05 | Finished |  |  | 2022-08-12 | Finished | [6 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-26 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished | [22 empty] | 490 | 86 | 16 | 16 | 608 | 465 | 86 | 16 | 16 | 583 | 4.11 | Red | [7 empty] | DME000265 | 2021-03-26
TAE1178-TH | SHE | 21000903 | HO | ส่งมอบแล้ว | - | TH180052 | Faculty of Medicine Vajira Hospital | SL3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-03-27 | 2018-07-05 | 2019-03-01 | 2021-10-30 | UAG-11G-A-1000-2PCO105;10S/10F; | UAG-11G-A | 1000 | 105 | 10 | 10 |  | 1926000 | Bangkok | เขตดุสิต | 1900-01-01 | 2019-05-03 | Finished | [34 empty] | 2018-06-20 | 2018-09-17 | 2018-09-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-15 | 2019-04-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-06-18 | 2019-06-18 | Finished |  |  | 2019-06-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-25 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2019-10-01 | Finished | CUSTOMER DECORATION DELAY |  | 2019-09-24 | Finished |  |  | 2018-05-05 | Finished | [18 empty] | 2018-09-12 | Finished |  |  | 2018-09-19 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 787 | 85 | 24 | 16 | 912 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TAE1179-TH | SHE | 21000903 | HO | ส่งมอบแล้ว | - | TH180052 | Faculty of Medicine Vajira Hospital | SL4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-03-27 | 2018-07-05 | 2019-03-01 |  | UAG-11G-A-1000-2PCO105;10S/10F; | UAG-11G-A | 1000 | 105 | 10 | 10 |  | 1926000 | Bangkok | เขตดุสิต | 2018-12-23 | 2018-12-23 | Finished | [34 empty] | 2018-06-20 | 2018-09-17 | 2018-09-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-15 | 2019-04-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-06-18 | 2019-06-18 | Finished |  |  | 2019-06-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2019-10-01 | Finished | CUSTOMER DECORATION DELAY |  | 2019-09-24 | Finished |  |  | 2019-11-15 | Finished | [18 empty] | 2018-09-12 | Finished |  |  | 2018-09-19 | Finished |  |  | 2018-09-19 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-15 | Working |  | no pass |  |  |  |  | 787 | 85 | 24 | 16 | 912 | 0 | 0 | 24 | 16 | 40 | 95.61 | Blue |  |  | 98000830 | 2018-06-20
TAD0309-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | B-II(VFI-II)-1000-2S2P90;8S/8F; | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1915300 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-22 | 2020-02-02 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-01-31 | Finished |  |  | 2020-01-31 | Finished |  |  | 2020-02-02 | Finished |  |  | 100 | 2021-05-13 | 2020-05-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-18 | Finished | [6 empty] | 90 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue | [7 empty] | DSE000907 | 2019-05-21 | QC Passed
TAD0310-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | B-II(VFI-II)-1000-2S2P90;8S/8F; | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1915300 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-22 | 2020-02-02 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-01-31 | Finished |  |  | 2020-01-31 | Finished |  |  | 2020-02-02 | Finished |  |  | 100 | 2021-05-13 | 2020-05-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-18 | Finished | [6 empty] | 90 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue | [7 empty] | DSE000907 | 2019-05-21 | QC Passed
TAD0311-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | B-II(VFI-II)-1000-2S2P90;8S/8F; | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1915300 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-22 | 2020-02-02 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-01-31 | Finished |  |  | 2020-01-31 | Finished |  |  | 2020-02-02 | Finished |  |  | 100 | 2021-05-13 | 2020-05-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-18 | Finished | [6 empty] | 90 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue | [7 empty] | DSE000907 | 2019-05-21 | QC Passed
TAD0313-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | B-II(VFI-II)-1000-2S2P90;12S/12F; | B-II(VFI-II) | 1000 | 90 | 12 | 12 |  | 2236300 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2020-01-22 | 2020-02-29 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-02-16 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 100 | 2021-05-13 | 2020-10-26 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000907 | 2019-05-21 | QC Passed
TAD0314-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | B-II(VFI-II)-1000-2S2P90;12S/12F; | B-II(VFI-II) | 1000 | 90 | 12 | 12 |  | 2236300 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2020-01-22 | 2020-02-29 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-02-16 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 100 | 2021-05-13 | 2020-10-26 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000907 | 2019-05-21 | QC Passed
TAD0312-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | B-II(VFI-II)-1000-2S2P90;8S/8F; | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1872500 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2020-01-22 | 2020-02-29 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-02-16 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished | [6 empty] | 90 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished | [13 empty] | no pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue | [7 empty] | DSE000907 | 2019-05-21
TAK0201-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | UAG-SN1-1000-2S2P90;9S/9F; | UAG-SN1 | 1000 | 90 | 9 | 9 |  | 2247000 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2020-01-22 | 2020-02-29 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-02-16 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished | [13 empty] | no pass |  |  |  |  | 585 | 84 | 24 | 16 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000907 | 2019-05-21
TAC1294-TH | SHE | 21000906 | HO | ส่งมอบแล้ว | - | TH190001 | รพ.มหาราช นครศรีธรรมราช [อ.วินิจฉัยและรักษา] | L8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | TEERASAK JUNTHAWEE | 2017-12-22 | 2019-05-22 | 2019-09-22 | 2020-05-08 | VFI-II-900-2PCO90;8S/8F; | VFI-II | 900 | 90 | 8 | 8 |  | 1690600 | Nakhon Si Thammarat | อำเภอเมืองนครศรีธรรมราช | 2019-05-22 | 2019-05-22 | Finished | [34 empty] | 2019-05-07 | 2019-05-22 | 2019-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-22 | 2020-02-29 | 2019-07-06 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-07-29 | Finished |  |  | 100 | [41 empty] | 2019-07-29 | 2020-01-22 | 2020-01-22 | Finished |  |  | 2020-01-22 | 2020-02-16 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-07 | Finished |  |  | 100 | 2021-05-13 | 2021-01-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 2021-01-18 | Finished |  |  | 100 | 2020-05-08 | Finished | POWER SUPPLY DELAY |  | 2020-07-03 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2019-05-21 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-26 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000907 | 2019-05-21 | QC Passed
TAK0313-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P1(Bldg.A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2018-10-30 | 2020-04-05 | UAG-SN1-1000-2S2P105;5S/5F; | UAG-SN1 | 1000 | 105 | 5 | 5 |  | 1674550 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-30 | 2018-11-30 | Finished | [34 empty] | 2018-08-15 | 2018-08-28 | 2018-08-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-05 | 2018-10-25 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2020-10-26 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2019-08-25 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-09-07 | Finished |  |  | 2018-09-08 | Finished |  |  | 2018-09-10 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000247 | 2018-09-07 | QC Passed
TAC1401-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P1(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-15 | 2018-11-15 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-01-02 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-07-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-20 | Finished |  |  | 2021-07-19 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-06 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000252 | 2018-11-08 | QC Passed
TAC1413-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P1(Bldg.D) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-10 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2020-04-14 | 2000-01-01 | 2020-04-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-16 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-13 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | no pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000254 | 2018-11-13
TAC1412-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P10(BldgC) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-11-01 | 2018-11-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-20 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2020-11-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-11-16 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-09 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000253 | 2018-11-09 | QC Passed
TAC1402-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P2(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2019-02-12 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-01-02 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-07-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-20 | Finished |  |  | 2021-07-19 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-29 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000250 | 2018-10-24 | QC Passed
TAC1414-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P2(Bldg.D) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-10 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2020-03-28 | 2000-01-01 | 2020-03-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-16 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-13 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | no pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000254 | 2018-11-13
TAC1403-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P3(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-09-05 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-01-02 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-07-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-20 | Finished |  |  | 2021-07-19 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-29 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000250 | 2018-10-24 | QC Passed
TAC1415-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P3(Bldg.D) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-21 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2020-11-16 | 2000-01-01 | 2020-11-16 | Finished |  |  | 2021-09-08 | Finished | [10 empty] | 50 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-13 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 16 | 16 | 98.3 | Blue | [7 empty] | DME000254 | 2018-11-13
TAC1404-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P4(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-09-05 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-01-02 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-08-20 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-29 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000250 | 2018-10-24 | QC Passed
TAC1405-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P5(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-01-02 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-08-20 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-29 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Working |  |  | 2020-04-24 | Working |  | pass (defect) |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000250 | 2018-10-24
TAC1406-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P6(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-01-25 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-01-22 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-08-20 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-29 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000250 | 2018-10-24 | QC Passed
TAC1409-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P7(Bldg.C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-11-01 | 2018-11-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-20 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2020-11-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-11-16 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-09 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000253 | 2018-11-09 | QC Passed
TAC1410-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P8(Bldg.C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-11-01 | 2018-11-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-20 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2020-11-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-11-16 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-09 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000253 | 2018-11-09 | QC Passed
TAC1411-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | P9(Bldg.C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P105;10S/10F; | VFI-II | 1600 | 105 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-11-01 | 2018-11-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-20 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2020-11-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-11-16 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-09 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000253 | 2018-11-09 | QC Passed
TAJ0314-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | S1(Bldg.A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2018-10-30 | 2020-04-05 | UAG-SN1-1000-2PCO60;4S/4F; | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1658500 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-10-06 | 2018-11-01 | Finished | [34 empty] | 2018-08-15 | 2018-08-28 | 2018-08-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-05 | 2019-06-05 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-01 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2019-08-25 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-09-07 | Finished |  |  | 2018-09-08 | Finished |  |  | 2018-09-10 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | no pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000247 | 2018-09-07
TAC1407-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | S1(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P60;10S/10F; | VFI-II | 1600 | 60 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-06-05 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-03-22 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-29 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000250 | 2018-10-24 | QC Passed
TAC1416-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | S1(Bldg.D) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P60;10S/10F; | VFI-II | 1600 | 60 | 10 | 10 |  | 2172100 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-05 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-05 | 2019-05-31 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2020-03-25 | 2000-01-01 | 2020-03-25 | Finished |  |  | 2021-09-08 | Finished | [10 empty] | 50 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-26 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 16 | 16 | 98.3 | Blue | [7 empty] | DME000255 | 2018-11-26
TAC1408-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | S2(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P60;10S/10F; | VFI-II | 1600 | 60 | 10 | 10 |  | 2188150 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-25 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-25 | 2019-05-30 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-03-22 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-29 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000250 | 2018-10-24 | QC Passed
TAC1417-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | S2(Bldg.D) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | VFI-II-1600-2S2P60;10S/10F; | VFI-II | 1600 | 60 | 10 | 10 |  | 2172100 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-05 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-05 | 2019-05-31 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2020-03-26 | 2000-01-01 | 2020-03-26 | Finished |  |  | 2021-09-08 | Finished | [10 empty] | 50 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-11-26 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 16 | 16 | 98.3 | Blue | [7 empty] | DME000255 | 2018-11-26
TBL0115-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | S3(Bldg.B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2019-02-28 | 2020-04-05 | OUG-ON1-600-2PCO60;2S/2F; | OUG-ON1 | 600 | 60 | 2 | 2 |  | 1230500 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-11-30 | 2018-09-28 | 2018-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-15 | 2019-05-25 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2021-05-13 | 2021-07-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-14 | Finished |  |  | 100 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-24 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-28 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DME000251 | 2018-10-24 | QC Passed
TEC0115-TH | SHE | 21000908 | HO | ส่งมอบแล้ว | - | TH170003 | Walailak University | S4(Bldg.C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-04-05 | 2018-08-15 | 2018-10-30 | 2020-04-05 | DF-200-S/B30;2S/2F; | DF | 200 | 30 | 2 | 2 |  | 321000 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2018-11-25 | 2018-11-25 | Finished | [34 empty] | 2018-08-15 | 2019-05-16 | 2019-05-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-01 | 2019-02-16 | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-11-30 | Finished |  |  | 100 | [41 empty] | 2018-11-30 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | [18 empty] | 0 | 2019-11-05 | Finished | INSTALLATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2019-03-10 | Finished |  |  | 2019-05-16 | Finished |  |  | 2019-05-16 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | dumb |  |  |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue | [7 empty] | DME000262 | 2019-03-19
TFA1125-TH | SHE | 21000909 | HO | ส่งมอบแล้ว | - | TH180212 | Iconsiam Retail (ADD) | ES (Add Extension) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Atcha Wongrak | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2017-09-07 | 2018-09-17 | 2018-10-17 | 2020-10-30 | 1200SX-N;30;4500; | SX-N |  |  |  |  | 4500 | 1712000 | Bangkok | เขตคลองสาน | 1900-01-01 | [20 empty] | 2018-12-15 | Finished | [14 empty] | 2018-09-07 | 2018-10-26 | 2018-10-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-06-22 | 2018-07-30 | [41 empty] | 2018-06-22 | Finished |  |  | 2018-06-25 | Finished |  |  | 2018-06-28 | Finished |  |  | 2018-07-05 | Finished |  |  | 2018-07-10 | Finished |  |  | 2018-07-12 | Finished |  |  | 2018-07-15 | Finished |  |  | 2018-07-20 | Finished |  |  | 2018-07-25 | Finished |  |  | 2018-07-30 | Finished |  |  | 100 | 2018-07-30 | 2018-11-15 | 2018-11-15 | Finished |  |  | 2018-11-15 | 2018-11-15 | Finished |  |  | 2019-01-15 | Finished |  |  | 2019-02-25 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 100 | 2020-10-16 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2020-10-28 | Finished |  |  | 2018-06-05 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2018-10-10 | Finished |  |  | 2018-10-26 | Finished |  |  | 2018-10-31 | Finished |  |  | 2020-10-28 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-01-11 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [9 empty] | QC Passed
TFA1130-TH | SHE | 21000914 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | ES-01 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2018-10-15 | 2018-12-15 | 2020-05-30 | 1200SX-EN;35;4500; | SX-EN |  |  |  |  | 4500 | 2033000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-07-30 | [20 empty] | 2019-07-23 | Finished | [14 empty] | 2016-12-01 | 2018-10-20 | 2018-10-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-23 | 2019-08-07 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-01-10 | 2020-01-10 | Finished |  |  | 2019-11-11 | 2020-01-10 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-14 | Finished |  |  | 100 | 2020-02-12 | 2000-01-01 | 2020-02-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-09-14 | Finished |  |  | 100 | 2020-07-20 | Finished | CONSTRUCTION DELAY |  | 2020-09-03 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2018-10-18 | Finished |  |  | 2018-10-27 | Finished |  |  | 2018-10-29 | Finished |  |  | 2020-09-03 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | pass (defect) |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue
TFA1131-TH | SHE | 21000914 | HO | ส่งมอบแล้ว | - | TH160134 | Central Investigation Bureau | ES-02 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 |  | SIRIRAT YUANGNGAM | 2016-03-26 | 2018-10-15 | 2018-12-15 | 2020-05-30 | 1200SX-EN;35;4500; | SX-EN |  |  |  |  | 4500 | 2033000 | Nonthaburi | ตำบลบ้านใหม่ อำเภอปากเกร็ด | 2019-07-30 | [20 empty] | 2019-08-03 | Finished | [14 empty] | 2016-12-01 | 2018-10-20 | 2018-10-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-03 | 2019-08-17 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 2020-01-10 | 2020-01-10 | Finished |  |  | 2019-11-11 | 2020-01-10 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-14 | Finished |  |  | 100 | 2020-02-12 | 2000-01-01 | 2020-02-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-09-14 | Finished |  |  | 100 | 2020-07-20 | Finished | CONSTRUCTION DELAY |  | 2020-09-03 | Finished |  |  | 2017-06-24 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2018-10-18 | Finished |  |  | 2018-10-27 | Finished |  |  | 2018-10-29 | Finished |  |  | 2020-09-03 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-26 | Working |  |  | 2021-01-26 | Working |  | pass (defect) |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue
TAC1469-TH | SHE | 21000918 | HO | ส่งมอบแล้ว | - | TH180097 | National Housing Authority | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Sittichoke Boonpa | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2018-08-01 | 2018-11-07 | 2019-01-01 | 2020-06-30 | VFI-II-1000-2PCO60;8S/8F; | VFI-II | 1000 | 60 | 8 | 8 |  | 1337500 | Bangkok | เขตบางกะปิ | 2019-05-30 | [36 empty] | 2018-11-07 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-12 | 2019-03-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-12-06 | 2018-12-06 | Finished |  |  | 2018-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-06-30 | Finished |  |  | 2020-07-24 | Finished |  |  | 2018-09-19 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2018-12-03 | Finished |  |  | 2018-12-04 | Finished |  |  | 2018-12-11 | Finished |  |  | 2020-07-24 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue | [7 empty] | DSE000902 | 2018-12-03 | QC Passed
TAC1470-TH | SHE | 21000918 | HO | ส่งมอบแล้ว | - | TH180097 | National Housing Authority | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Sittichoke Boonpa | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2018-08-01 | 2018-11-07 | 2019-01-01 | 2020-06-30 | VFI-II-1000-2PCO60;8S/8F; | VFI-II | 1000 | 60 | 8 | 8 |  | 1337500 | Bangkok | เขตบางกะปิ | 2019-05-30 | [36 empty] | 2018-11-07 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-12 | 2019-03-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-12-06 | 2018-12-06 | Finished |  |  | 2018-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-06-30 | Finished |  |  | 2020-07-24 | Finished |  |  | 2018-09-19 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2018-12-03 | Finished |  |  | 2018-12-04 | Finished |  |  | 2018-12-11 | Finished |  |  | 2020-07-24 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue | [7 empty] | DSE000902 | 2018-12-03 | QC Passed
TAJ0644-TH | SHE | 21000923 | HO | ส่งมอบแล้ว | - | TH200058 | Siriwitthaya Mahidol University | EL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-11-25 | 2020-03-24 | 2020-11-19 |  | UAG-SN1-1600-2PCO105;7S/7F; | UAG-SN1 | 1600 | 105 | 7 | 7 |  | 2354000 | Nakhon Pathom | ถนนพุทธมณฑลสาย 4 ตำบลศาลายา | 2020-08-25 | 2020-10-23 | Finished | [34 empty] | 2020-07-24 | 2020-07-24 | 2020-07-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-25 | 2020-09-23 | 2020-10-24 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-30 | Finished |  |  | 100 | [41 empty] | 2020-11-30 | 2020-12-04 | 2020-12-04 | Finished |  |  | 2020-07-24 | 2021-01-15 | Finished |  |  | 2021-01-17 | Finished |  |  | 2021-01-21 | Finished |  |  | 100 | 2020-05-15 | 2021-06-10 | 2020-05-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-02-25 | Finished | H/O DOCUMENT DELAY |  | 2021-02-24 | Finished |  |  | 2019-12-18 | Finished | [18 empty] | 2020-07-24 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000912 | 2020-07-24 | QC Passed
TAJ0645-TH | SHE | 21000923 | HO | ส่งมอบแล้ว | - | TH200058 | Siriwitthaya Mahidol University | EL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-11-25 | 2020-03-24 | 2020-11-19 |  | UAG-SN1-1600-2PCO105;7S/7F; | UAG-SN1 | 1600 | 105 | 7 | 7 |  | 2354000 | Nakhon Pathom | ถนนพุทธมณฑลสาย 4 ตำบลศาลายา | 2020-08-25 | 2020-10-23 | Finished | [34 empty] | 2020-07-24 | 2020-07-24 | 2020-07-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-25 | 2020-09-23 | 2020-10-24 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-30 | Finished |  |  | 100 | [41 empty] | 2020-11-30 | 2020-12-08 | 2020-12-08 | Finished |  |  | 2020-07-24 | 2021-01-16 | Finished |  |  | 2021-01-19 | Finished |  |  | 2021-01-23 | Finished |  |  | 100 | 2020-05-15 | 2021-06-10 | 2020-05-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-02-25 | Finished | H/O DOCUMENT DELAY |  | 2021-02-24 | Finished |  |  | 2019-12-18 | Finished | [18 empty] | 2020-07-24 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000912 | 2020-07-24 | QC Passed
TAJ0646-TH | SHE | 21000923 | HO | ส่งมอบแล้ว | - | TH200058 | Siriwitthaya Mahidol University | EL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-11-25 | 2020-03-24 | 2020-07-22 |  | UAG-SN1-1600-2PCO105;7S/7F; | UAG-SN1 | 1600 | 105 | 7 | 7 |  | 2354000 | Nakhon Pathom | ถนนพุทธมณฑลสาย 4 ตำบลศาลายา | 2020-03-27 | 2020-04-10 | Finished | [34 empty] | 2020-03-24 | 2020-03-26 | 2020-03-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-05-21 | 2020-04-10 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-08 | Finished |  |  | 100 | [41 empty] | 2020-05-08 | 2020-05-18 | 2020-05-18 | Finished |  |  | 2020-05-23 | 2020-05-18 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-21 | Finished |  |  | 100 | 2021-05-13 | 2021-06-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2020-12-20 | Finished | H/O DOCUMENT DELAY |  | 2020-11-30 | Finished |  |  | 2019-12-18 | Finished | [18 empty] | 2020-03-26 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000910 | 2020-03-26 | QC Passed
TAJ0647-TH | SHE | 21000923 | HO | ส่งมอบแล้ว | - | TH200058 | Siriwitthaya Mahidol University | EL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-11-25 | 2020-03-24 | 2020-07-22 |  | UAG-SN1-1600-2PCO105;7S/7F; | UAG-SN1 | 1600 | 105 | 7 | 7 |  | 2354000 | Nakhon Pathom | ถนนพุทธมณฑลสาย 4 ตำบลศาลายา | 2020-03-27 | 2020-04-10 | Finished | [34 empty] | 2020-03-24 | 2020-03-26 | 2020-03-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-05-21 | 2020-04-10 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-09 | Finished |  |  | 100 | [41 empty] | 2020-05-09 | 2020-05-18 | 2020-05-18 | Finished |  |  | 2020-05-23 | 2020-05-18 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-21 | Finished |  |  | 100 | 2021-05-13 | 2021-06-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2020-12-20 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-11-30 | Finished |  |  | 2019-12-18 | Finished | [18 empty] | 2020-03-26 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000910 | 2020-03-26 | QC Passed
TBL0228-TH | SHE | 21000923 | HO | ส่งมอบแล้ว | - | TH200058 | Siriwitthaya Mahidol University | EL-05 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-11-25 | 2020-03-24 | 2021-02-17 |  | OUG-ON1-1350-2PCO105;9S/9F; | OUG-ON1 | 1350 | 105 | 9 | 9 |  | 2033000 | Nakhon Pathom | ถนนพุทธมณฑลสาย 4 ตำบลศาลายา | 2020-11-04 | 2021-01-24 | Finished | [34 empty] | 2020-11-04 | 2020-11-13 | 2020-11-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-04 | 2020-12-20 | 2021-01-25 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-02-06 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-13 | Finished |  |  | 100 | [41 empty] | 2021-02-13 | 2020-12-09 | 2020-12-09 | Finished |  |  | 2020-12-10 | 2021-02-19 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-26 | Finished |  |  | 100 | 2021-03-05 | 2021-06-10 | 2021-03-05 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-03-15 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-04-30 | Finished |  |  | 2019-12-18 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-17 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 0 | 0 | 100 | Blue | [7 empty] | DSE000913 | 2020-11-13 | QC Passed
TAC1727-TH | SHE | 21000924 | HO | ส่งมอบแล้ว | - | TH200111 | แฟลตนายทหารชั้นสัญญาบัตร (48 ครอบครัว) | L1(B1) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-03-17 | 2020-07-02 | 2020-09-01 |  | VFI-II-550-2PCO60;7S/7F; | VFI-II | 550 | 60 | 7 | 7 |  | 1100000 | Chon Buri | อ.เกาะจันทร์ | 2020-09-01 | 2020-09-01 | Finished | [34 empty] | 2020-07-02 | 2020-07-03 | 2020-07-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-03 | 2020-08-14 | 2020-10-10 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-17 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-11-05 | Finished |  |  | 100 | [41 empty] | 2020-11-05 | 2020-11-18 | 2020-11-18 | Finished |  |  | 2020-08-15 | 2020-11-18 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-26 | Finished |  |  | 100 | 2020-12-14 | 2021-02-15 | 2020-12-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-15 | Finished | [6 empty] | 90 | 2021-02-15 | Finished | CONSTRUCTION DELAY |  | 2021-02-08 | Finished |  |  | 2020-05-14 | Finished | [10 empty] | 2020-09-30 | Finished | [6 empty] | 2020-07-07 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-10 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  | pass | 2021-03-12 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue | [7 empty] | DSE000911 | 2020-07-07 | QC Passed
TAC1728-TH | SHE | 21000924 | HO | ส่งมอบแล้ว | - | TH200111 | แฟลตนายทหารชั้นสัญญาบัตร (48 ครอบครัว) | L1(B2) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-03-17 | 2020-07-02 | 2020-09-01 |  | VFI-II-550-2PCO60;7S/7F; | VFI-II | 550 | 60 | 7 | 7 |  | 1100000 | Chon Buri | อ.เกาะจันทร์ | 2020-09-01 | 2020-09-01 | Finished | [34 empty] | 2020-07-02 | 2020-07-03 | 2020-07-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-03 | 2020-08-14 | 2020-10-10 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-17 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-11-05 | Finished |  |  | 100 | [41 empty] | 2020-11-05 | 2020-11-18 | 2020-11-18 | Finished |  |  | 2020-08-15 | 2020-11-19 | Finished |  |  | 2020-11-27 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-14 | 2021-02-15 | 2020-12-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-15 | Finished | [6 empty] | 90 | 2021-02-15 | Finished | CONSTRUCTION DELAY |  | 2021-02-08 | Finished |  |  | 2020-05-14 | Finished | [10 empty] | 2020-09-30 | Finished | [6 empty] | 2020-07-07 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-10 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  | pass | 2021-03-12 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue | [7 empty] | DSE000911 | 2020-07-07 | QC Passed
TAC1729-TH | SHE | 21000924 | HO | ส่งมอบแล้ว | - | TH200111 | แฟลตนายทหารชั้นสัญญาบัตร (48 ครอบครัว) | L1(B3) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-03-17 | 2020-07-02 | 2020-09-01 |  | VFI-II-550-2PCO60;7S/7F; | VFI-II | 550 | 60 | 7 | 7 |  | 1100000 | Chon Buri | อ.เกาะจันทร์ | 2020-09-01 | 2020-09-01 | Finished | [34 empty] | 2020-07-02 | 2020-07-03 | 2020-07-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-03 | 2020-08-14 | 2020-09-01 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-14 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | [41 empty] | 2020-09-25 | 2020-11-20 | 2020-11-20 | Finished |  |  | 2020-08-15 | 2020-11-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-14 | 2021-02-15 | 2020-12-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-15 | Finished | [6 empty] | 90 | 2021-02-15 | Finished | CONSTRUCTION DELAY |  | 2021-02-08 | Finished |  |  | 2020-05-14 | Finished | [10 empty] | 2020-09-30 | Finished | [6 empty] | 2020-07-07 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-10 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  | pass | 2021-03-12 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue | [7 empty] | DSE000911 | 2020-07-07 | QC Passed
TAJ0077-TH | HET | 61000002 | HO | ส่งมอบแล้ว | - | TH179178 | UNIO SERITHAI | EL1 (A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2017-03-13 | 2017-07-20 | 2017-09-30 | 2958101 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1016500 | Bangkok | เขตบึงกุ่ม | 2958101 | 2017-09-28 | Finished | [34 empty] | 2017-07-15 | 2017-11-13 | 2017-11-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-12-20 | 2018-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-15 | 2018-02-15 | Finished |  |  | 2018-02-15 | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-02-15 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-15 | Finished | [6 empty] | 90 | 2019-06-11 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-06-04 | Finished |  |  | 2017-05-11 | Finished | [18 empty] | 2017-11-09 | Finished |  |  | 2017-11-13 | Finished |  |  | 2017-11-15 | Finished |  |  | 2019-06-04 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-16 | Finished |  | pass | 2020-04-16 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20000080 | 2017-07-15 |  |  |  | HDME000027 | 2017-11-09 | QC Passed
TAJ0078-TH | HET | 61000002 | HO | ส่งมอบแล้ว | - | TH179178 | UNIO SERITHAI | EL2 (A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2017-03-13 | 2017-07-20 | 2017-09-30 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1016500 | Bangkok | เขตบึงกุ่ม | 1900-01-01 | 2017-09-28 | Finished | [34 empty] | 2017-07-15 | 2017-11-13 | 2017-11-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-12-20 | 2018-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-02-15 | 2018-02-15 | Finished |  |  | 2018-02-15 | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2019-06-11 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2019-06-04 | Finished |  |  | 2017-05-11 | Finished | [18 empty] | 2017-11-09 | Finished |  |  | 2017-11-13 | Finished |  |  | 2017-11-15 | Finished |  |  | 2019-06-04 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-16 | Finished |  | pass | 2020-04-16 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000080 | 2017-07-15 |  |  |  | HDME000027 | 2017-11-09 | QC Passed
TEB0054-TH | HET | 61000013 | Install | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L10 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2018-11-18 | 2021-11-30 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-03-01 | [36 empty] | 2018-10-03 | 2021-03-16 | 2021-03-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-03-01 | 2022-03-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [18 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2018-10-03
TEB0055-TH | HET | 61000013 | Install | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L11 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2019-01-18 | 2021-11-30 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-03-01 | [36 empty] | 2018-12-03 | 2021-03-16 | 2021-03-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-03-01 | 2022-03-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [18 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2018-12-03
TEB0056-TH | HET | 61000013 |  | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L12 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2019-01-18 | 2022-11-25 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-04-01 | [36 empty] | 2022-04-01 | 2022-04-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-04-01 | 2022-04-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-04-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-04-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [10 empty] | 2022-04-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2018-12-03
TEB0057-TH | HET | 61000013 |  | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L13 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2019-03-18 | 2022-11-25 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-04-01 | [36 empty] | 2022-04-01 | 2022-04-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-04-01 | 2022-04-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-04-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-04-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [10 empty] | 2022-04-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2019-02-03
TEB0058-TH | HET | 61000013 |  | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L14 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2019-03-18 | 2022-11-25 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-06-01 | [36 empty] | 2022-06-01 | 2022-06-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-06-01 | 2022-06-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-06-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-06-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [10 empty] | 2022-04-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2019-02-03
TEB0059-TH | HET | 61000013 |  | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L15 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2019-05-03 | 2022-11-25 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-06-01 | [36 empty] | 2022-06-01 | 2022-06-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-06-01 | 2022-06-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-06-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-06-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [10 empty] | 2022-05-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2019-04-03
TEB0060-TH | HET | 61000013 |  | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L16 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2019-05-03 | 2022-11-25 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-06-01 | [36 empty] | 2022-06-01 | 2022-06-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-06-01 | 2022-06-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-06-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-06-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [10 empty] | 2022-05-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2019-04-03
TEB0061-TH | HET | 61000013 |  | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L17 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2019-05-03 | 2022-11-25 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-06-01 | [36 empty] | 2022-06-01 | 2022-06-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-06-01 | 2022-06-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-06-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-06-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [10 empty] | 2022-05-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2019-04-03
TEB0052-TH | HET | 61000013 | HO | ส่งมอบแล้ว | - | TH179190 | The Urban Reserve | L8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2018-09-18 | 2020-07-01 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2021-10-01 | [36 empty] | 2018-08-03 | 2019-10-09 | 2019-10-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-15 | 2021-05-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-01 | 2021-06-01 | Finished |  |  | 2021-06-01 | 2021-06-02 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-04 | Finished |  |  | 100 | 2021-05-21 | 2021-06-11 | 2021-05-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-11 | Finished | [6 empty] | 90 | 2021-07-25 | Finished | CONSTRUCTION DELAY |  | 2021-06-10 | Finished |  |  | 2017-06-08 | Finished | [10 empty] | 2021-06-10 | Finished | [6 empty] | 2019-10-09 | Finished |  |  | 2019-10-09 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20000207 | 2018-08-03 | [5 empty] | QC Passed
TEB0053-TH | HET | 61000013 | Install | ยังอยู่ในสัญญา HO | - | TH179190 | The Urban Reserve | L9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-05-03 | 2017-07-18 | 2018-11-18 | 2021-11-30 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 3 | 3 |  | 900000 | Bangkok | เขตสวนหลวง | 2022-03-01 | [36 empty] | 2018-10-03 | 2021-03-16 | 2021-03-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-03-01 | 2022-03-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-06-08 | Finished | [18 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20000207 | 2018-10-03
TAC1068-TH | HET | 61000026 | Install | ยังอยู่ในสัญญา HO | - | TH179219 | Flying Training School | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Siraprapa Sihamart | 2017-06-07 | 2017-09-22 | 2017-10-22 | 2021-10-04 | VFI-1000-CO60,60S/3F | VFI-II | 1000 | 60 | 3 | 3 |  | 1450000 | Nakhon Phanom | อำเภอเมือง | 2017-10-06 | 2017-10-06 | Finished | [34 empty] | 2017-09-22 | 2017-10-02 | 2017-10-02 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2017-10-06 | 2017-10-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2020-09-03 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-07-08 | Finished | [10 empty] | 2022-03-22 | Finished | [6 empty] | 2017-10-04 | Finished |  |  | 2017-11-23 | Finished |  |  | 2017-11-29 | Finished | [22 empty] | 417 | 89 | 16 | 16 | 538 | 0 | 89 | 16 | 16 | 121 | 77.51 | Yellow |  |  | 20000401 | 2017-09-22 |  |  |  | HDME000012 | 2017-10-04
TAD0260-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | BL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2021-02-22 | B-1000-2S90,90S/9F | B-II(VFI-II) | 1000 | 90 | 9 | 9 |  | 2140000 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-30 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-07-01 | 2018-07-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2018-09-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-05-27 | 2020-05-27 | Finished |  |  | 2020-05-27 | 2020-05-29 | Finished |  |  | 2020-05-31 | Finished |  |  | 2020-06-01 | Finished |  |  | 100 | 2020-07-20 | 2020-08-28 | 2020-07-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-28 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-02-15 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-25 | Finished |  |  | 2018-07-01 | Finished |  |  | 2018-07-04 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000207 | 2018-06-25 | QC Passed
TAD0261-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | BL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2020-11-28 | B-1000-2S90,90S/13F | B-II(VFI-II) | 1000 | 90 | 13 | 13 |  | 2140000 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-30 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-07-01 | 2018-07-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2018-09-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-05-27 | 2020-05-27 | Finished |  |  | 2020-05-27 | 2020-05-29 | Finished |  |  | 2020-05-31 | Finished |  |  | 2020-06-01 | Finished |  |  | 100 | 2020-07-20 | 2021-02-15 | 2020-07-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-31 | Finished |  |  | 2021-02-15 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2020-10-27 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-25 | Finished |  |  | 2018-07-01 | Finished |  |  | 2018-07-04 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000207 | 2018-06-25 | QC Passed
TAD0262-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | BL3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2020-11-28 | B-1000-2S90,90S/13F | B-II(VFI-II) | 1000 | 90 | 13 | 13 |  | 2140000 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-30 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-07-01 | 2018-07-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2018-09-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-05-27 | 2020-05-27 | Finished |  |  | 2020-05-27 | 2020-05-29 | Finished |  |  | 2020-05-31 | Finished |  |  | 2020-06-01 | Finished |  |  | 100 | 2020-07-20 | 2021-02-15 | 2020-07-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-31 | Finished |  |  | 2021-02-15 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2020-10-27 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-25 | Finished |  |  | 2018-07-01 | Finished |  |  | 2018-07-04 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000207 | 2018-06-25 | QC Passed
TAJ0121-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | FL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2021-02-22 | P-1500-2S90,90S/14F | UAG-SN1 | 1500 | 90 | 14 | 14 |  | 1950000 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-30 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-06-23 | 2018-06-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2019-01-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-06-27 | 2020-06-27 | Finished |  |  | 2020-06-27 | 2020-06-30 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 100 | 2021-05-13 | 2021-04-08 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-02-15 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-06-23 | Finished |  |  | 2018-06-26 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 806 | 96 | 32 | 20 | 954 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000201 | 2018-06-19 | QC Passed
TAC1073-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | PL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2021-02-22 | VFI-1600-CO90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2407500 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-23 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-06-23 | 2018-06-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2018-09-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-07-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-30 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-02-15 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-06-23 | Finished |  |  | 2018-06-26 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000201 | 2018-06-19 | QC Passed
TAC1074-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | PL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2021-02-22 | VFI-1600-CO90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2407500 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-23 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-06-23 | 2018-06-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2018-09-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-07-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-30 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-02-15 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-06-23 | Finished |  |  | 2018-06-26 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000201 | 2018-06-19 | QC Passed
TAC1075-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | PL3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2021-02-22 | VFI-1600-CO90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2407500 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-23 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-06-23 | 2018-06-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2018-09-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-07-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-30 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-02-15 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-06-23 | Finished |  |  | 2018-06-26 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000201 | 2018-06-19 | QC Passed
TAC1076-TH | HET | 61000034 | HO | ส่งมอบแล้ว | - | TH189007 | รพ.มหาราช นครราชสีมา | PL4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-28 | 2018-05-28 | 2018-12-28 | 2021-02-22 | VFI-1600-CO90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2407500 | Nakhon Ratchasima | อ.เมืองนครราชสีมา | 2018-06-23 | 2018-05-25 | Finished | [34 empty] | 2018-05-13 | 2018-06-23 | 2018-06-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-28 | 2018-09-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-07-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-30 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-02-15 | Finished |  |  | 2017-07-21 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-06-23 | Finished |  |  | 2018-06-26 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  | pass | 2021-04-23 | Finished |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000482 | 2018-05-13 |  |  |  | HDME000201 | 2018-06-19 | QC Passed
TAJ0122-TH | HET | 61000036 | HO | ยังอยู่ในสัญญา HO | - | TH179229 | Room 28 Hotel | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-06-30 | 2017-10-30 | 2017-11-30 | 2021-10-20 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1200000 | Chiang Rai | อำเภอเมืองเชียงราย | 2017-10-14 | 2017-10-15 | Finished | [34 empty] | 2017-10-15 | 2017-12-06 | 2017-12-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-10-15 | 2018-01-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-10-29 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-27 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-07-08 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2017-12-08 | Finished |  |  | 2017-12-28 | Finished |  |  | 2018-01-17 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 16 | 16 | 113 | 76.31 | Green |  |  | 20000484 | 2017-10-15 |  |  |  | HDME000033 | 2017-12-08
TAC1106-TH | HET | 61000059 | Test | เลยสัญญา HO | - | TH179247 | Office of The Attoney General (Chumpare) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2017-08-01 | 2017-12-01 | 2018-01-01 | 2021-09-25 | VFI-1000-CO60,60S/2F | VFI-II | 1000 | 60 | 2 | 2 |  | 1337500 | Khon Kaen | อำเภอชุมแพ | 2018-01-16 | 2018-01-16 | Finished | [34 empty] | 2017-11-24 | 2018-01-11 | 2018-01-11 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2018-01-15 | 2018-01-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-04-17 | 2018-04-17 | Finished |  |  | 2018-04-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2019-04-21 | 2000-01-01 | 2019-04-21 | Finished |  |  | 2019-04-21 | Finished |  |  | 2019-04-21 | Finished | [6 empty] | 90 | 2021-11-30 | Working | ADJUSTMENT DEFECT RECTIFICATION DELAY | [5 empty] | 2017-08-19 | Finished | [10 empty] | 2022-03-22 | Finished | [6 empty] | 2018-01-12 | Finished |  |  | 2018-01-19 | Finished |  |  | 2018-01-22 | Finished | [22 empty] | 362 | 88 | 16 | 16 | 482 | 0 | 0 | 0 | 1 | 1 | 99.79 | Red |  |  | 20000716 | 2017-11-24 |  |  |  | HDME000054 | 2018-01-12
TAJ0130-TH | HET | 61000063 | HO | ส่งมอบแล้ว | - | TH179242 | บริษัท ซิสเต็มส์ ดอท คอม จำกัด | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2017-07-27 | 2017-11-27 | 2018-01-11 | 2020-01-01 | P-600-CO60D,60S/3F | UAG-SN1 | 600 | 60 | 3 | 3 |  | 1177000 | Bangkok | แขวงบางนา เขตบางนา | 1900-01-01 | 2017-11-27 | Finished | [34 empty] | 2017-11-20 | 2017-11-29 | 2017-11-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2017-12-17 | 2018-01-01 | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 100 | [41 empty] | 2018-01-01 | 2018-03-25 | 2018-03-25 | Finished |  |  | 2018-03-25 | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-09 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-24 | Finished |  |  | 2021-06-09 | Finished |  |  | 100 | 2020-03-20 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2020-04-08 | Finished |  |  | 2017-08-26 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2017-12-26 | Finished |  |  | 2018-10-14 | Finished |  |  | 2018-10-18 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-16 | Finished |  | pass | 2020-06-16 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000724 | 2017-11-20 |  |  |  | HDME000043 | 2017-12-26 | QC Passed
TEB0063-TH | HET | 61000081 | HO | ยังอยู่ในสัญญา HO | - | TH179259 | Home Khun Pornchai | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-08-31 | 2017-12-31 | 2018-01-31 | 2021-12-25 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 1050000 | Bangkok | เขตบึงกุ่ม | 2018-11-10 | 2018-11-10 | Finished | [34 empty] | 2017-12-16 | 2017-12-19 | 2017-12-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-30 | 2019-01-10 | 2018-11-25 | Finished |  |  | 2018-11-28 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-12-05 | Finished |  |  | 2018-12-09 | Finished |  |  | 2018-12-14 | Finished |  |  | 2018-12-18 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-26 | Finished |  |  | 2019-01-07 | Finished |  |  | 100 | [41 empty] | 2019-01-07 | 1900-01-01 | 2019-01-07 | Waiting | POWER SUPPLY DELAY |  | 2021-12-10 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2017-09-13 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2017-12-19 | Finished |  |  | 2018-01-24 | Finished |  |  | 2018-01-25 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 16 | 16 | 87 | 66.15 | Green |  |  | 20000848 | 2017-12-16 |  |  |  | HDME000035 | 2017-12-19
TFA0970-TH | HET | 61000093 | HO | ส่งมอบแล้ว | - | TH189018 | Gateway Bangsue | ESC33 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2017-01-31 | 2018-01-03 | 2018-08-31 | 2020-10-31 | 1200SX-EN,R5.5M,D35 | SX-EN |  |  |  |  | 5500 | 1082840 | Bangkok | แขวงบางซื่อ เขตบางซื่อ | 2020-05-20 | [20 empty] | 2020-06-21 | Finished | [14 empty] | 2018-01-04 | 2018-04-18 | 2020-03-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-01 | 2020-06-20 | [41 empty] | 2020-06-20 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-08 | Finished |  |  | 2020-08-09 | Finished |  |  | 2020-08-10 | Finished |  |  | 100 | 2020-08-10 | 2020-08-11 | 2020-08-11 | Finished |  |  | 2020-07-13 | 2020-08-11 | Finished |  |  | 2020-08-11 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2020-08-28 | 2021-04-02 | 2020-08-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-19 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2020-11-06 | Finished | CONSTRUCTION DELAY |  | 2020-11-23 | Finished |  |  | 2017-10-12 | Finished | [18 empty] | 2018-04-05 | Finished |  |  | 2018-04-28 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  | pass | 2021-06-08 | Finished |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000988 | 2018-01-04 |  |  |  | HDME000130 | 2018-04-05 | QC Passed
TFA0971-TH | HET | 61000093 | HO | ส่งมอบแล้ว | - | TH189018 | Gateway Bangsue | ESC34 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2017-01-31 | 2018-01-03 | 2018-08-31 | 2020-10-31 | 1200SX-EN,R5.5M,D35 | SX-EN |  |  |  |  | 5500 | 1082840 | Bangkok | แขวงบางซื่อ เขตบางซื่อ | 2020-05-20 | [20 empty] | 2020-06-21 | Finished | [14 empty] | 2018-01-04 | 2018-04-18 | 2020-03-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-01 | 2020-06-20 | [41 empty] | 2020-06-20 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-08 | Finished |  |  | 2020-08-09 | Finished |  |  | 2020-08-10 | Finished |  |  | 100 | 2020-08-10 | 2020-08-11 | 2020-08-11 | Finished |  |  | 2020-07-13 | 2020-08-11 | Finished |  |  | 2020-08-11 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2020-08-28 | 2021-04-02 | 2020-08-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-19 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2020-11-06 | Finished | CONSTRUCTION DELAY |  | 2020-11-23 | Finished |  |  | 2017-10-12 | Finished | [18 empty] | 2018-04-05 | Finished |  |  | 2018-04-28 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  | pass | 2021-06-08 | Finished |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20000988 | 2018-01-04 |  |  |  | HDME000130 | 2018-04-05 | QC Passed
TAC1195-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-FL-05 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1600-CO105,105S/15F | VFI-II | 1600 | 105 | 14 | 15 |  | 2782000 | Bangkok | เขตดุสิต | 2020-06-10 | 2020-09-28 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-30 | 2020-12-05 | 2020-10-10 | Finished |  |  | 2020-12-29 | Finished |  |  | 2020-12-29 | Finished |  |  | 2020-12-29 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-24 | Finished |  |  | 100 | [41 empty] | 2020-10-24 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-05-23 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000177 | 2018-05-23 | QC Passed
TAC1216-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-FL-12 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1600-CO105,105S/15F | VFI-II | 1600 | 105 | 14 | 15 |  | 2782000 | Bangkok | เขตดุสิต | 2020-06-10 | 2020-10-06 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-30 | 2020-12-05 | 2020-10-28 | Finished |  |  | 2020-12-29 | Finished |  |  | 2020-12-29 | Finished |  |  | 2020-12-29 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | [41 empty] | 2020-10-27 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2000-01-01 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-05-23 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Working |  |  | 2021-05-05 | Working |  | no pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000177 | 2018-05-23
TAC1184-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-02/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 11 | 12 |  | 2707100 | Bangkok | เขตดุสิต | 2020-06-10 | 2020-08-24 | Finished | [34 empty] | 2018-06-24 | 2018-07-12 | 2018-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-11-25 | 2020-08-28 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-03 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-09 | Finished |  |  | 100 | [41 empty] | 2020-09-09 | 2020-11-26 | 2020-11-26 | Finished |  |  | 2020-11-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2021-04-30 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-07-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000226 | 2018-07-11 | QC Passed
TAC1186-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-02/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 3 | 12 |  | 2418200 | Bangkok | เขตดุสิต | 2020-06-10 | 2020-08-24 | Finished | [34 empty] | 2018-06-24 | 2018-07-12 | 2018-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-11-25 | 2020-08-28 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-03 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-09 | Finished |  |  | 100 | [41 empty] | 2020-09-09 | 2020-11-26 | 2020-11-26 | Finished |  |  | 2020-11-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-07-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Working |  |  | 2021-06-22 | Working |  | pass (defect) |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 2 | 2 | 99.81 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000226 | 2018-07-11
TAC1185-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-02/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 11 | 12 |  | 2707100 | Bangkok | เขตดุสิต | 2020-06-10 | 2020-08-24 | Finished | [34 empty] | 2018-06-24 | 2018-07-12 | 2018-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-11-25 | 2020-08-28 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-03 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-09 | Finished |  |  | 100 | [41 empty] | 2020-09-09 | 2020-11-26 | 2020-11-26 | Finished |  |  | 2020-11-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2021-04-30 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-07-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000226 | 2018-07-11 | QC Passed
TAC1187-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-03/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-24 | Finished | [34 empty] | 2018-06-24 | 2018-07-12 | 2018-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-28 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-28 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-12 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000227 | 2018-07-12 | QC Passed
TAC1188-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-03/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-24 | Finished | [34 empty] | 2018-06-24 | 2018-07-12 | 2018-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-28 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-28 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2000-01-01 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Working |  |  | 2021-05-05 | Working |  | pass (defect) |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17
TAC1189-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-03/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-24 | Finished | [34 empty] | 2018-06-24 | 2018-07-12 | 2018-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-28 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-28 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-12 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-18 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000227 | 2018-07-12 | QC Passed
TAC1190-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-03/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-24 | Finished | [34 empty] | 2018-06-24 | 2018-07-12 | 2018-07-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-28 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-28 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-12 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-18 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000227 | 2018-07-12 | QC Passed
TAC1191-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-04/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-30 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-25 | 2020-05-10 | 2020-03-08 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | [41 empty] | 2020-04-17 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-06-25 | 2020-09-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-27 | 2021-03-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 2 | 2 | 99.84 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17 | QC Passed
TAC1192-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-04/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-30 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-25 | 2020-05-10 | 2020-03-08 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | [41 empty] | 2020-04-17 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-06-25 | 2020-09-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-27 | 2021-03-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 2 | 2 | 99.84 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17 | QC Passed
TAC1193-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-04/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-30 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-25 | 2020-05-10 | 2020-03-08 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | [41 empty] | 2020-04-17 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-06-25 | 2020-09-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-27 | 2021-03-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 2 | 2 | 99.84 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17 | QC Passed
TAC1194-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-04/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-30 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-25 | 2020-05-10 | 2020-03-08 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | [41 empty] | 2020-04-17 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-06-25 | 2020-09-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-27 | 2021-03-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 2 | 2 | 99.84 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17 | QC Passed
TAC1196-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-06/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/14F | VFI-II | 1350 | 150 | 13 | 14 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-01 | 2019-11-22 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-23 | 2020-05-05 | 1900-01-01 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-02-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-10 | 2020-07-10 | Finished |  |  | 2020-07-05 | 2020-07-22 | Finished |  |  | 2020-09-11 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-02 | 2021-05-14 | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2021-05-14 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-21 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 2 | 2 | 99.83 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000175 | 2018-05-21 | QC Passed
TAC1197-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-06/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/14F | VFI-II | 1350 | 150 | 13 | 14 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-01 | 2019-11-22 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-23 | 2020-05-05 | 1900-01-01 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-02-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-10 | 2020-07-10 | Finished |  |  | 2020-07-05 | 2020-07-22 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-27 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-21 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 2 | 2 | 99.83 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000175 | 2018-05-21 | QC Passed
TAC1198-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-06/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/14F | VFI-II | 1350 | 150 | 13 | 14 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-01 | 2019-11-22 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-23 | 2020-05-05 | 1900-01-01 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-02-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-10 | 2020-07-10 | Finished |  |  | 2020-07-05 | 2020-07-22 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-27 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-21 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 2 | 2 | 99.83 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000175 | 2018-05-21 | QC Passed
TAC1199-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-07/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/14F | VFI-II | 1350 | 150 | 13 | 14 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-03 | 2019-11-26 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-27 | 2020-05-10 | 1900-01-01 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-02-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-01-30 | Finished |  |  | 100 | [41 empty] | 2020-01-30 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-05-16 | 2020-07-14 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-18 | Finished |  |  | 100 | 2020-09-14 | 2021-05-14 | 2020-09-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-05-14 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-23 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000177 | 2018-05-23 | QC Passed
TAC1200-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-07/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/14F | VFI-II | 1350 | 150 | 13 | 14 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-03 | 2019-11-26 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-27 | 2020-05-10 | 1900-01-01 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-02-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-01-30 | Finished |  |  | 100 | [41 empty] | 2020-01-30 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-05-16 | 2020-07-14 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-16 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-23 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 2 | 2 | 99.83 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000177 | 2018-05-23 | QC Passed
TAC1201-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-07/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/14F | VFI-II | 1350 | 150 | 13 | 14 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-03 | 2019-11-26 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-27 | 2020-05-10 | 1900-01-01 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-02-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-01-30 | Finished |  |  | 100 | [41 empty] | 2020-01-30 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-05-16 | 2020-07-14 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-16 | Finished |  |  | 100 | 2020-09-14 | 2021-03-26 | 2020-09-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-23 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000177 | 2018-05-23 | QC Passed
TAC1202-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-08/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/13F | VFI-II | 1350 | 150 | 3 | 13 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-05 | 2020-01-16 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-17 | 2020-05-19 | 2020-01-27 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | [41 empty] | 2020-05-22 | 2020-07-07 | 2020-07-07 | Finished |  |  | 2020-07-15 | 2020-07-10 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-10-07 | Finished |  |  | 100 | 2021-05-13 | 2021-04-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-21 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000175 | 2018-05-21 | QC Passed
TAC1203-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-08/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/13F | VFI-II | 1350 | 150 | 3 | 13 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-05 | 2020-01-16 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-17 | 2020-05-19 | 2020-01-27 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | [41 empty] | 2020-05-22 | 2020-07-07 | 2020-07-07 | Finished |  |  | 2020-07-15 | 2020-07-10 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-10-07 | Finished |  |  | 100 | 2021-05-13 | 2021-04-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-21 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000175 | 2018-05-21 | QC Passed
TAC1204-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-08/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/13F | VFI-II | 1350 | 150 | 3 | 13 |  | 2707100 | Bangkok | เขตดุสิต | 2019-10-05 | 2020-01-16 | Finished | [34 empty] | 2018-05-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-17 | 2020-05-19 | 2020-01-27 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | [41 empty] | 2020-05-22 | 2020-07-07 | 2020-07-07 | Finished |  |  | 2020-07-15 | 2020-07-10 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-10-07 | Finished |  |  | 100 | 2021-05-13 | 2021-04-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-05-21 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-05-01 |  |  |  | HDME000175 | 2018-05-21 | QC Passed
TAC1205-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-09/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-25 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-20 | 2020-05-15 | 2020-03-14 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-11 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-23 | Finished |  |  | 100 | [41 empty] | 2020-03-23 | 2020-09-16 | 2020-09-16 | Finished |  |  | 2020-07-10 | 2020-09-18 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2000-01-01 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Working |  |  | 2021-05-05 | Working |  | pass (defect) |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17
TAC1206-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-09/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-25 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-20 | 2020-05-15 | 2020-03-14 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-11 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-23 | Finished |  |  | 100 | [41 empty] | 2020-03-23 | 2020-09-16 | 2020-09-16 | Finished |  |  | 2020-07-10 | 2020-09-18 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-04-20 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-20 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17 | QC Passed
TAC1207-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-09/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-25 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-20 | 2020-05-15 | 2020-03-14 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-11 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-23 | Finished |  |  | 100 | [41 empty] | 2020-03-23 | 2020-09-16 | 2020-09-16 | Finished |  |  | 2020-07-10 | 2020-09-18 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-04-30 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17 | QC Passed
TAC1208-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-09/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2019-11-25 | 2020-02-18 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-20 | 2020-05-15 | 2020-03-14 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-11 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-23 | Finished |  |  | 100 | [41 empty] | 2020-03-23 | 2020-09-16 | 2020-09-16 | Finished |  |  | 2020-07-10 | 2020-09-18 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-04-30 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000237 | 2018-07-17 | QC Passed
TAC1209-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-10/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-26 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-30 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-19 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 2 | 2 | 99.84 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000240 | 2018-07-19 | QC Passed
TAC1210-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-10/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-26 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-30 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-19 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000240 | 2018-07-19 | QC Passed
TAC1211-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-10/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-26 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-30 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-19 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000240 | 2018-07-19 | QC Passed
TAC1212-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-10/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/15F | VFI-II | 1350 | 150 | 12 | 15 |  | 2675000 | Bangkok | เขตดุสิต | 2020-07-28 | 2020-10-26 | Finished | [34 empty] | 2018-06-24 | 2018-07-17 | 2018-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-12-05 | 2020-10-30 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-12-06 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-07-19 | Finished |  |  | 2018-09-15 | Finished |  |  | 2018-09-19 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 1080 | 109 | 32 | 20 | 1241 | 0 | 0 | 0 | 2 | 2 | 99.84 | Blue |  |  | 20001160 | 2018-06-24 |  |  |  | HDME000240 | 2018-07-19 | QC Passed
TAC1213-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-11/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 11 | 12 |  | 2739200 | Bangkok | เขตดุสิต | 2020-04-20 | 2020-05-17 | Finished | [34 empty] | 2018-08-25 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-05 | 2020-05-21 | Finished |  |  | 2020-08-30 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-08-11 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | [41 empty] | 2020-07-30 | 2020-10-07 | 2020-10-07 | Finished |  |  | 2020-08-07 | 2020-10-09 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-09-20 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-08-25 |  |  |  | HDME000299 | 2018-09-20 | QC Passed
TAC1214-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-11/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 11 | 12 |  | 2739200 | Bangkok | เขตดุสิต | 2020-04-20 | 2020-05-17 | Finished | [34 empty] | 2018-08-25 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-05 | 2020-05-21 | Finished |  |  | 2020-08-30 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-08-11 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | [41 empty] | 2020-07-30 | 2020-10-07 | 2020-10-07 | Finished |  |  | 2020-08-07 | 2020-10-30 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2000-01-01 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-09-20 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Working |  |  | 2021-06-22 | Working |  | pass (defect) |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-08-25 |  |  |  | HDME000299 | 2018-09-20
TAC1215-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-11/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 11 | 12 |  | 2739200 | Bangkok | เขตดุสิต | 2020-04-20 | 2020-05-17 | Finished | [34 empty] | 2018-08-25 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-05 | 2020-05-21 | Finished |  |  | 2020-08-30 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-08-11 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | [41 empty] | 2020-07-30 | 2020-10-07 | 2020-10-07 | Finished |  |  | 2020-08-07 | 2020-10-30 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-09-20 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-08-25 |  |  |  | HDME000299 | 2018-09-20 | QC Passed
TAC1217-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-FL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 |  | VFI-1600-CO90,90S/10F | VFI-II | 1600 | 90 | 9 | 10 |  | 1658500 | Bangkok | เขตดุสิต | 2018-08-31 | 2019-03-03 | Finished | [34 empty] | 2018-02-01 | 2018-04-11 | 2018-04-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-03-12 | 2018-10-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-06-20 | 2019-06-20 | Finished |  |  | 2019-06-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-08 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000100 | 2018-03-08 | QC Passed
TAC1226-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-FL-07 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-05-19 | VFI-1600-CO90,90S/10F | VFI-II | 1600 | 90 | 9 | 10 |  | 1658500 | Bangkok | เขตดุสิต | 2020-01-10 | 2020-02-03 | Finished | [34 empty] | 2018-02-01 | 2018-03-22 | 2018-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-25 | 2020-04-18 | 2020-01-31 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-03-21 | Finished |  |  | 2020-04-09 | Finished |  |  | 100 | [41 empty] | 2020-04-09 | 2020-05-08 | 2020-05-08 | Finished |  |  | 2020-04-25 | 2020-05-08 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-06-01 | Finished |  |  | 100 | 2020-05-29 | 2020-08-20 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-17 | Finished |  |  | 2020-08-20 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-22 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000120 | 2018-03-22 | QC Passed
TAC1218-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-05/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-04-11 | 2018-04-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-04-24 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-08 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000100 | 2018-03-08 | QC Passed
TAC1219-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-05/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-04-11 | 2018-04-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2019-11-08 | 2020-04-24 | 2019-11-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-08 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000100 | 2018-03-08 | QC Passed
TAC1220-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-05/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-04-11 | 2018-04-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2019-11-08 | 2020-04-24 | 2019-11-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-08 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000100 | 2018-03-08 | QC Passed
TAC1221-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-05/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-03-22 | 2018-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2019-11-08 | 2020-04-24 | 2019-11-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-22 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000120 | 2018-03-22 | QC Passed
TAC1222-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-06/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-03-22 | 2018-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-10-11 | 2020-04-24 | 2020-10-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-22 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000120 | 2018-03-22 | QC Passed
TAC1223-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-06/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-03-22 | 2018-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-10-11 | 2020-04-24 | 2020-10-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-22 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000120 | 2018-03-22 | QC Passed
TAC1224-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-06/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-03-22 | 2018-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-10-11 | 2020-04-24 | 2020-10-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-22 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000120 | 2018-03-22 | QC Passed
TAC1225-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-06/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2020-03-24 | VFI-1350-CO105,105S/10F | VFI-II | 1350 | 105 | 8 | 10 |  | 1637100 | Bangkok | เขตดุสิต | 2018-08-31 | 2018-10-05 | Finished | [34 empty] | 2018-02-01 | 2018-03-22 | 2018-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-14 | 2019-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-11 | 2019-04-11 | Finished |  |  | 2019-04-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-03-16 | 2020-04-24 | 2020-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-08 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-22 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000120 | 2018-03-22 | QC Passed
TAE0999-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-12 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2021-04-19 | UAG-1000-CO60,60S/2F | UAG | 1000 | 60 | 2 | 2 |  | 1926000 | Bangkok | เขตดุสิต | 2020-05-05 | 2020-05-22 | Finished | [34 empty] | 2018-08-25 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-23 | 2020-05-15 | 2020-05-25 | Finished |  |  | 2020-05-26 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-05-29 | Finished |  |  | 2020-06-06 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | [41 empty] | 2020-06-04 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2020-05-20 | 2020-06-23 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2020-08-31 | 2021-03-26 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-05-31 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-10-05 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 345 | 79 | 16 | 16 | 456 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-08-25 |  |  |  | HDME000316 | 2018-10-05 | QC Passed
TAE0997-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-SL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 |  | UAG-1000-CO60,60S/2F | UAG | 1000 | 60 | 2 | 2 |  | 1230500 | Bangkok | เขตดุสิต | 2019-04-10 | 2019-05-20 | Finished | [34 empty] | 2018-04-01 | 2018-05-21 | 2018-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-25 | 2018-12-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-06-04 | 2019-06-04 | Finished |  |  | 2019-06-04 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-01-06 | 2020-12-28 | 2020-01-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-12-28 | Finished |  |  | 100 | 2020-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-05-28 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-07 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 345 | 79 | 16 | 16 | 456 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-04-01 |  |  |  | HDME000179 | 2018-05-28 | QC Passed
TAC1174-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-FL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1600-CO90,90S/9F | VFI-II | 1600 | 90 | 8 | 9 |  | 1658500 | Bangkok | เขตดุสิต | 2019-01-10 | 2019-02-23 | Finished | [34 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-24 | 2019-05-05 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-05-08 | 2019-05-08 | Finished |  |  | 2019-05-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | PARTIAL DELIVERY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-13 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-03 |  |  |  | HDME000072 | 2018-02-13 | QC Passed
TAC1183-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-FL-06 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-12-25 | VFI-1600-CO90,90S/9F | VFI-II | 1600 | 90 | 8 | 9 |  | 1658500 | Bangkok | เขตดุสิต | 2018-03-07 | 2018-05-08 | Finished | [34 empty] | 2018-02-01 | 2018-02-26 | 2018-02-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-05-12 | 2019-02-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-02-15 | 2019-02-15 | Finished |  |  | 2019-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 100 | 2019-08-29 | Finished | PARTIAL DELIVERY |  | 2020-03-10 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-24 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000093 | 2018-02-24 | QC Passed
TAC1175-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-04/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-03-25 | Finished | [34 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-03-28 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-11-30 | 2018-11-30 | Finished |  |  | 2018-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-13 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-03 |  |  |  | HDME000072 | 2018-02-13 | QC Passed
TAC1176-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-04/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-03-25 | Finished | [34 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-03-28 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-11-30 | 2018-11-30 | Finished |  |  | 2018-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-13 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-03 |  |  |  | HDME000072 | 2018-02-13 | QC Passed
TAC1177-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-04/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-03-25 | Finished | [34 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-03-28 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-11-30 | 2018-11-30 | Finished |  |  | 2018-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-13 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-03 |  |  |  | HDME000072 | 2018-02-13 | QC Passed
TAC1178-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-04/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-03-25 | Finished | [34 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-03-28 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-11-30 | 2018-11-30 | Finished |  |  | 2018-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-13 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-03 |  |  |  | HDME000072 | 2018-02-13 | QC Passed
TAC1179-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-05/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-04-09 | Finished | [34 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | Finished | STORE AREA | [13 empty] | 2018-04-18 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-12 | 2019-01-12 | Finished |  |  | 2019-01-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-13 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-03 |  |  |  | HDME000072 | 2018-02-13 | QC Passed
TAC1180-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-05/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-04-09 | Finished | [34 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-04-18 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-12 | 2019-01-12 | Finished |  |  | 2019-01-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-13 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-03 |  |  |  | HDME000072 | 2018-02-13 | QC Passed
TAC1181-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-05/3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-04-09 | Finished | [34 empty] | 2018-02-01 | 2018-02-26 | 2018-02-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-04-18 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-12 | 2019-01-12 | Finished |  |  | 2019-01-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-24 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000093 | 2018-02-24 | QC Passed
TAC1182-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-05/4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-09-16 | VFI-1350-CO105,105S/9F | VFI-II | 1350 | 105 | 8 | 9 |  | 1605000 | Bangkok | เขตดุสิต | 2018-03-05 | 2018-04-09 | Finished | [34 empty] | 2018-02-01 | 2018-02-26 | 2018-02-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-04-18 | 2019-01-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-12 | 2019-01-12 | Finished |  |  | 2019-01-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2019-08-29 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-09-16 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-02-24 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-02-17 |  |  |  | HDME000093 | 2018-02-24 | QC Passed
TAE0998-TH | HET | 61000107 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-11 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-02-01 | 2019-06-30 | 2019-12-25 | UAG-750-CO60,60S/2F | UAG | 750 | 60 | 2 | 2 |  | 963000 | Bangkok | เขตดุสิต | 2018-10-05 | 2018-10-13 | Finished | [34 empty] | 2018-03-01 | 2018-03-22 | 2018-03-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-16 | 2019-05-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-05-26 | 2019-05-26 | Finished |  |  | 2019-05-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2019-12-30 | Finished |  |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-03-22 | Finished |  |  | 2018-04-24 | Finished |  |  | 2018-04-30 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Working |  |  | 2020-04-27 | Working |  | pass (defect) |  |  |  |  | 345 | 79 | 16 | 16 | 456 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001160 | 2018-03-01 |  |  |  | HDME000120 | 2018-03-22
THA0089-TH | HET | 61000110 | HO | ส่งมอบแล้ว | - | TH189059 | Interlink Tower | 10(Hight Zone) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-04-26 | 2018-03-31 | 2019-09-30 |  | UVF-1350-CO300,300S/40F | UVF | 1350 | 300 | 18 | 40 |  | 8476540 | Bangkok | แขวงบางนา เขตบางนา | 2018-09-01 | 2019-06-01 | Finished | [34 empty] | 2019-05-01 | 2018-10-02 | 2018-10-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-01 | 2019-10-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-15 | 2020-02-15 | Finished |  |  | 2019-09-15 | 1900-01-01 | Finished |  |  | 2020-03-01 | Finished |  |  | 2020-03-15 | Finished |  |  | 100 | 2021-05-13 | 2021-06-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-13 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2019-09-28 | Finished | INSTALLATION DELAY |  | 2020-03-26 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2019-11-07 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-15 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass |  |  |  |  | 2319 | 122 | 72 | 48 | 2561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001190 | 2019-05-01 |  |  |  | HDME000699 | 2019-11-07 | QC Passed
TBK0096-TH | HET | 61000110 | HO | ส่งมอบแล้ว | - | TH189059 | Interlink Tower | 4(Low Zone) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-04-26 | 2018-03-31 | 2019-09-29 |  | HVF-900-CO240,240S/15F | HVF-5 | 900 | 240 | 15 | 15 |  | 4837470 | Bangkok | แขวงบางนา เขตบางนา | 2018-09-01 | 2019-11-10 | Finished | [34 empty] | 2020-09-01 | 2019-08-26 | 2019-08-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-10 | 2019-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-09 | 2019-12-09 | Finished |  |  | 2019-12-09 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-04-26 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-26 | Finished |  |  | 100 | 2019-11-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-04-13 | Finished |  |  | 2018-03-31 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2019-08-22 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-08-28 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass |  |  |  |  | 1094 | 97 | 32 | 20 | 1243 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001190 | 2019-07-01 |  |  |  | HDME000631 | 2019-08-22 | QC Passed
THA0087-TH | HET | 61000110 | HO | ส่งมอบแล้ว | - | TH189059 | Interlink Tower | 8(Hight Zone) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-04-26 | 2018-03-31 | 2018-12-31 |  | UVF-1350-CO300,300S/40F | UVF | 1350 | 300 | 18 | 40 |  | 8476540 | Bangkok | แขวงบางนา เขตบางนา | 2018-06-01 | 2019-02-01 | Finished | [34 empty] | 2018-08-16 | 2018-10-02 | 2018-10-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-01 | 2019-09-24 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-08-20 | 2019-08-20 | Finished |  |  | 2019-08-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-07 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2019-11-10 | Finished | CUSTOMER DECORATION DELAY |  | 2020-02-24 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2019-05-10 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-27 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass |  |  |  |  | 2319 | 122 | 72 | 48 | 2561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001190 | 2018-08-01 |  |  |  | HDME000541 | 2019-05-10 | QC Passed
TBK0097-TH | HET | 61000110 | HO | ส่งมอบแล้ว | - | TH189059 | Interlink Tower | LS | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-04-26 | 2018-03-31 | 2019-12-31 |  | HVF-1600-CO180,180S/41F | HVF-5 | 1600 | 180 | 41 | 41 |  | 6826600 | Bangkok | แขวงบางนา เขตบางนา | 2020-04-15 | 2020-05-01 | Finished | [34 empty] | 2020-09-01 | 2020-01-14 | 2020-01-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-01 | 2020-10-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-09-01 | 2020-09-01 | Finished |  |  | 2020-06-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-12-15 | Finished |  |  | 2021-02-24 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2020-01-13 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-21 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  | pass | 2021-03-12 | Finished |  |  | 2368 | 123 | 80 | 48 | 2619 | 0 | 0 | 0 | 4 | 4 | 99.85 | Blue |  |  | 20001190 | 2019-09-01 |  |  |  | HDME000765 | 2020-01-13 | QC Passed
TAC1237-LA | HET | 61000120 | Install | ยังอยู่ในสัญญา HO | - | LA189001 | ST Bank and Hotel at Pak Se | L1A | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | SUCHART CHAOWARAT | 2017-09-05 | 2019-02-10 | 2019-05-10 | 2021-10-30 | VFI-1000-CO90,90S/10F | VFI-II | 1000 | 90 | 10 | 10 |  | 52960 | Pak Se | สปป ลาว | 2018-11-08 | 2018-12-20 | Finished | [34 empty] | 2018-11-20 | 2019-01-22 | 2019-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-22 | 2019-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-09-01 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-24 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 24 | 16 | 40 | 95.74 | Green |  |  | 20001279 | 2018-11-20
TAC1238-LA | HET | 61000120 | Install | ยังอยู่ในสัญญา HO | - | LA189001 | ST Bank and Hotel at Pak Se | L1B | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | SUCHART CHAOWARAT | 2017-09-05 | 2019-02-10 | 2019-05-10 | 2021-10-30 | VFI-1000-CO90,90S/10F | VFI-II | 1000 | 90 | 10 | 10 |  | 52960 | Pak Se | สปป ลาว | 2018-11-08 | 2018-12-20 | Finished | [34 empty] | 2018-11-20 | 2019-01-22 | 2019-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-22 | 2019-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-09-01 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-24 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 24 | 16 | 40 | 95.74 | Green |  |  | 20001279 | 2018-11-20
TAC1235-LA | HET | 61000120 | HO | ส่งมอบแล้ว | - | LA189001 | ST Bank and Hotel at Pak Se | L2A | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | SUCHART CHAOWARAT | 2017-09-05 | 2019-02-10 | 2019-05-10 | 2020-12-30 | VFI-1000-CO90,90S/9F | VFI-II | 1000 | 90 | 9 | 9 |  | 50800 | Pak Se | สปป ลาว | 2018-12-18 | 2018-12-20 | Finished | [34 empty] | 2018-11-20 | 2019-01-22 | 2019-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-18 | 2019-02-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-15 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2018-09-01 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-24 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-15 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 24 | 16 | 40 | 95.46 | Blue |  |  | 20001279 | 2018-11-20
TAC1236-LA | HET | 61000120 | HO | ส่งมอบแล้ว | - | LA189001 | ST Bank and Hotel at Pak Se | L2B | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | SUCHART CHAOWARAT | 2017-09-05 | 2019-02-10 | 2019-05-10 | 2020-12-30 | VFI-1000-CO90,90S/9F | VFI-II | 1000 | 90 | 9 | 9 |  | 50800 | Pak Se | สปป ลาว | 2019-03-13 | 2018-12-20 | Finished | [34 empty] | 2018-11-20 | 2019-01-22 | 2019-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-18 | 2019-02-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-15 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2018-09-01 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-24 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 24 | 16 | 40 | 95.46 | Blue |  |  | 20001279 | 2018-11-20
TAC1239-LA | HET | 61000120 | Install | ยังอยู่ในสัญญา HO | - | LA189001 | ST Bank and Hotel at Pak Se | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | SUCHART CHAOWARAT | 2017-09-05 | 2019-02-10 | 2019-05-10 | 2021-10-30 | VFI-750-CO90,90S/10F | VFI-II | 750 | 90 | 10 | 10 |  | 51160 | Pak Se | สปป ลาว | 2019-03-05 | 2019-03-05 | Finished | [34 empty] | 2018-11-20 | 2019-01-22 | 2019-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-25 | 2019-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-09-01 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-24 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 24 | 16 | 40 | 95.74 | Green |  |  | 20001279 | 2018-11-20
TAK0171-TH | HET | 61000123 | HO | เลยสัญญา HO | - | TH189070 | Baan Chaichookiat | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Yosvaris Limmethaphant | 2017-10-31 | 2018-05-31 | 2018-07-31 | 2021-09-20 | B-1000-2S60,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1525000 | Udon Thani | อำเภอเมือง | 2018-05-31 | 2018-05-31 | Finished | [34 empty] | 2018-05-24 | 2018-09-27 | 2018-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-10 | 2018-10-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 2019-01-07 | 1900-01-01 | 2019-01-07 | Waiting | POWER SUPPLY DELAY |  | 2021-10-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2017-11-17 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2018-09-21 | Finished |  |  | 2018-09-28 | Finished |  |  | 2018-09-28 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 16 | 16 | 112 | 74.07 | Red |  |  | 20001362 | 2018-05-24 |  |  |  | HDME000300 | 2018-09-21
TAJ0176-TH | HET | 61000136 | HO | ส่งมอบแล้ว | - | TH189079 | Office Suan Plu | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2017-10-31 | 2018-08-31 | 2018-10-15 | 2021-01-31 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1305400 | Bangkok | แขวงทุ่งมหาเมฆ เขตสาทร | 2018-08-31 | 2018-08-31 | Finished | [34 empty] | 2018-08-24 | 2018-10-19 | 2018-10-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-01 | 2019-01-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-01-01 | 2021-01-01 | Finished |  |  | 2021-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-01-31 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2017-12-11 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-10-17 | Finished |  |  | 2018-10-19 | Finished |  |  | 2018-10-25 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20001528 | 2018-08-24 |  |  |  | HDME000333 | 2018-10-17 | QC Passed
TBL0067-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-PL-03/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1350-CO60,60S/4F | OUG-ON1 | 1350 | 60 | 3 | 4 |  | 2247000 | Bangkok | เขตดุสิต | 2019-04-03 | 2019-05-27 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-26 | 2020-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-07-10 | 2019-07-10 | Finished |  |  | 2019-07-10 | 1900-01-01 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | 2020-02-28 | 2021-03-01 | 2020-02-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0068-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-PL-03/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1350-CO60,60S/4F | OUG-ON1 | 1350 | 60 | 3 | 4 |  | 2247000 | Bangkok | เขตดุสิต | 2019-04-03 | 2019-05-27 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-26 | 2020-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-07-10 | 2019-07-10 | Finished |  |  | 2019-07-10 | 1900-01-01 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | 2021-05-13 | 2021-04-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0069-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-PL-04/1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1350-CO60,60S/4F | OUG-ON1 | 1350 | 60 | 3 | 4 |  | 2247000 | Bangkok | เขตดุสิต | 2019-04-03 | 2019-06-12 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-18 | 2020-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-07-25 | 2019-07-25 | Finished |  |  | 2019-07-25 | 1900-01-01 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | 2020-02-28 | 2021-02-12 | 2020-02-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0070-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-PL-04/2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1350-CO60,60S/4F | OUG-ON1 | 1350 | 60 | 3 | 4 |  | 2247000 | Bangkok | เขตดุสิต | 2019-04-03 | 2019-06-12 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-18 | 2020-01-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-07-25 | 2019-07-25 | Finished |  |  | 2019-07-25 | 1900-01-01 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | 2021-05-13 | 2021-04-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0065-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2020-04-30 | OUG-1150-CO60,60S/5F | OUG-ON1 | 1150 | 60 | 3 | 5 |  | 2065100 | Bangkok | เขตดุสิต | 2018-12-25 | 2019-01-31 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-05 | 2020-02-19 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-08-18 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 1900-01-01 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-08-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Working |  |  | 2021-06-22 | Working |  | pass (defect) |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14
TBL0066-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2020-04-30 | OUG-1600-CO90,90S/10F | OUG-ON1 | 1600 | 90 | 5 | 10 |  | 2407500 | Bangkok | เขตดุสิต | 2019-11-15 | 2019-11-25 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-08 | 2020-04-20 | 2020-02-12 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-08-17 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-03-19 | Finished |  |  | 100 | [41 empty] | 2020-03-19 | 2020-03-20 | 2020-03-20 | Finished |  |  | 2020-03-16 | 2020-04-13 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-03-19 | 2021-04-09 | 2021-03-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 755 | 89 | 24 | 16 | 884 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0071-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-SL-05 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO90,90S/10F | OUG-ON1 | 1600 | 90 | 5 | 10 |  | 2407500 | Bangkok | เขตดุสิต | 2019-02-12 | 2019-03-18 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-25 | 2020-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-05 | 2020-03-05 | Finished |  |  | 2020-03-05 | 1900-01-01 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-04-09 | Finished |  |  | 100 | 2020-09-25 | 2000-01-01 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Working |  |  | 2021-06-22 | Working |  | no pass |  |  |  |  | 755 | 89 | 24 | 16 | 884 | 0 | 0 | 0 | 1 | 1 | 99.89 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14
TBL0072-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-SL-06 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1150-CO60,60S/5F | OUG-ON1 | 1150 | 60 | 3 | 5 |  | 2065100 | Bangkok | เขตดุสิต | 2019-02-12 | 2019-03-18 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-25 | 2020-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-15 | 2020-03-15 | Finished |  |  | 2020-03-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-22 | 2021-03-01 | 2020-09-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-03-01 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0073-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-SL-07 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO60,60S/2F | OUG-ON1 | 1600 | 60 | 2 | 2 |  | 2300500 | Bangkok | เขตดุสิต | 2019-03-16 | 2019-04-29 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-03 | 2019-09-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-01 | 2020-02-01 | Finished |  |  | 2020-02-01 | 1900-01-01 | Finished |  |  | 2020-02-03 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-01 | 2021-02-04 | 2021-03-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-20 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0086-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CA-SL-08 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO60,60S/2F | OUG-ON1 | 1600 | 60 | 2 | 2 |  | 2300500 | Bangkok | เขตดุสิต | 2019-03-16 | 2019-04-29 | Finished | [34 empty] | 2018-04-15 | 2018-10-04 | 2018-10-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-03 | 2019-08-09 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-08-10 | 2019-08-10 | Finished |  |  | 2019-08-10 | 1900-01-01 | Finished |  |  | 2020-02-03 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-20 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0074-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CB-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2021-04-19 | OUG-1150-CO60,60S/4F | OUG-ON1 | 1150 | 60 | 3 | 4 |  | 2011600 | Bangkok | เขตดุสิต | 2019-10-15 | 2019-12-07 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-16 | 2020-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-17 | 2020-03-17 | Finished |  |  | 2020-03-17 | 2020-05-21 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-08-20 | Finished |  |  | 100 | 2021-03-01 | 2021-03-09 | 2021-03-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-14 | Finished |  |  | 2021-03-09 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0075-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CC-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2021-04-19 | OUG-1150-2S60,60S/2F | OUG-ON1 | 1150 | 60 | 2 | 2 |  | 1958100 | Bangkok | เขตดุสิต | 2019-06-20 | 2019-12-09 | Finished | [34 empty] | 2018-04-15 | 2018-09-19 | 2018-09-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-12 | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-06-21 | 2020-06-21 | Finished |  |  | 2020-06-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-30 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2021-06-30 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0076-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | CC-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2021-04-19 | OUG-1150-CO60,60S/3F | OUG-ON1 | 1150 | 60 | 3 | 3 |  | 2011600 | Bangkok | เขตดุสิต | 2019-09-30 | 2019-10-05 | Finished | [34 empty] | 2018-08-15 | 2018-10-04 | 2018-10-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-10 | 2019-12-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-06-21 | 2020-06-21 | Finished |  |  | 2020-06-20 | 2020-10-27 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-04 | 2021-04-09 | 2021-02-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | 2021-04-30 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-08-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0079-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-08 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 6 | 7 |  | 2728500 | Bangkok | เขตดุสิต | 2019-04-18 | 2019-04-27 | Finished | [34 empty] | 2018-04-01 | 2018-09-02 | 2018-09-02 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2019-06-12 | 2019-10-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-22 | 2019-11-22 | Finished |  |  | 2019-11-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-11-12 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-01 |  |  |  | HDME000359 | 2018-11-12 | QC Passed
TBL0080-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-09 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 7 | 7 |  | 2675000 | Bangkok | เขตดุสิต | 2019-04-18 | 2019-04-25 | Finished | [34 empty] | 2018-04-01 | 2018-09-02 | 2018-09-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-12 | 2019-10-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-11-22 | 2019-11-22 | Finished |  |  | 2019-11-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-11-12 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-01 |  |  |  | HDME000359 | 2018-11-12 | QC Passed
TBL0081-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-10 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 6 | 7 |  | 2707100 | Bangkok | เขตดุสิต | 2019-04-21 | 2019-04-29 | Finished | [34 empty] | 2018-04-01 | 2018-09-02 | 2018-09-02 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2019-07-07 | 2019-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-01 | 2019-12-01 | Finished |  |  | 2019-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-03-26 | 2020-05-29 | 2020-03-26 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-11-12 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-01 |  |  |  | HDME000359 | 2018-11-12 | QC Passed
TBL0082-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-PL-11 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 6 | 7 |  | 2675000 | Bangkok | เขตดุสิต | 2019-04-21 | 2019-04-22 | Finished | [34 empty] | 2018-04-01 | 2018-09-02 | 2018-09-02 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2019-07-07 | 2019-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-01 | 2019-12-01 | Finished |  |  | 2019-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-01 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0077-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2021-04-19 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 2193500 | Bangkok | เขตดุสิต | 2019-01-31 | 2019-04-05 | Finished | [34 empty] | 2018-04-01 | 2018-09-02 | 2018-09-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-04-15 | 2019-06-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 1900-01-01 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-02-18 | Finished |  |  | 100 | 2020-05-29 | 2021-04-02 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-29 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2021-05-31 | Finished | H/O DOCUMENT DELAY |  | 2021-06-04 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2018-10-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-01 |  |  |  | HDME000328 | 2018-10-11 | QC Passed
TBL0078-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | N-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO60,60S/5F | OUG-ON1 | 1600 | 60 | 3 | 5 |  | 2428900 | Bangkok | เขตดุสิต | 2019-01-31 | 2019-05-18 | Finished | [34 empty] | 2018-04-01 | 2018-09-02 | 2018-09-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-21 | 2019-07-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-27 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-10-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-01 |  |  |  | HDME000328 | 2018-10-11 | QC Passed
TBL0061-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-07 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2019-12-25 | OUG-1600-CO60,60S/7F | OUG-ON1 | 1600 | 60 | 5 | 7 |  | 2354000 | Bangkok | เขตดุสิต | 2018-10-03 | 2018-10-05 | Finished | [34 empty] | 2018-03-01 | 2018-07-24 | 2018-07-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-10 | 2019-02-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-03-10 | 2019-03-10 | Finished |  |  | 2019-03-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2019-12-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-10-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Working |  |  | 2020-04-27 | Working |  | pass (defect) |  |  |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-03-01 |  |  |  | HDME000328 | 2018-10-11
TBL0063-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-09 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2019-12-25 | OUG-1600-CO60,60S/7F | OUG-ON1 | 1600 | 60 | 5 | 7 |  | 2354000 | Bangkok | เขตดุสิต | 2018-11-20 | 2018-12-06 | Finished | [34 empty] | 2018-03-01 | 2018-07-24 | 2018-07-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-10 | 2019-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-05-14 | 2019-05-14 | Finished |  |  | 2019-05-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2019-12-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-10-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Working |  |  | 2020-04-27 | Working |  | pass (defect) |  |  |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-03-01 |  |  |  | HDME000328 | 2018-10-11
TBG0064-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-10 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2019-12-25 | OUG-1600-CO60,60S/7F | OUG | 1600 | 60 | 6 | 7 |  | 2407500 | Bangkok | เขตดุสิต | 2019-11-20 | 2018-12-10 | Finished | [34 empty] | 2018-10-23 | 2018-08-10 | 2018-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-19 | 2019-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-05-18 | 2019-05-18 | Finished |  |  | 2019-05-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2019-12-30 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-12-18 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Working |  |  | 2020-04-27 | Working |  | pass (defect) |  |  |  |  | 619 | 87 | 24 | 16 | 746 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-10-23 |  |  |  | HDME000418 | 2018-12-18
TBG0063-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-PL-8 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2019-12-25 | OUG-1600-CO60,60S/7F | OUG | 1600 | 60 | 6 | 7 |  | 2407500 | Bangkok | เขตดุสิต | 2019-11-20 | 2018-12-10 | Finished | [34 empty] | 2018-10-23 | 2018-08-10 | 2018-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-19 | 2019-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-05-18 | 2019-05-18 | Finished |  |  | 2019-05-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2019-12-30 | Finished | CONSTRUCTION DELAY |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-12-18 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Working |  |  | 2020-04-27 | Working |  | pass (defect) |  |  |  |  | 619 | 87 | 24 | 16 | 746 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-10-23 |  |  |  | HDME000418 | 2018-12-18
TBL0059-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 2193500 | Bangkok | เขตดุสิต | 2018-08-25 | 2018-09-05 | Finished | [34 empty] | 2018-03-01 | 2018-07-24 | 2018-07-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-15 | 2019-04-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-05-14 | 2019-05-14 | Finished |  |  | 2019-05-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2021-05-31 | Finished |  |  | 2021-01-29 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2018-10-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Working |  |  | 2021-06-22 | Working |  | pass (defect) |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-03-01 |  |  |  | HDME000328 | 2018-10-11
TBL0060-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2019-12-25 | OUG-1150-CO60,60S/5F | OUG-ON1 | 1150 | 60 | 4 | 5 |  | 2033000 | Bangkok | เขตดุสิต | 2018-09-08 | 2018-09-25 | Finished | [34 empty] | 2018-03-01 | 2018-07-24 | 2018-07-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-01 | 2019-04-24 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-05-15 | 2019-05-15 | Finished |  |  | 2019-05-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2019-12-30 | Finished |  |  | 2019-12-25 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-10-11 | Finished |  |  | 2018-10-18 | Finished |  |  | 2018-10-31 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Working |  |  | 2020-04-27 | Working |  | pass (defect) |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-03-01 |  |  |  | HDME000328 | 2018-10-11
TBJ0012-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-SL-12 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | F-4000-3U30,30S/2F | F(H)-EL | 4000 | 30 | 2 | 2 |  | 3680800 | Bangkok | เขตดุสิต | 2018-12-15 | 2019-01-10 | Finished | [34 empty] | 2018-04-15 | 2018-08-10 | 2018-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-14 | 2019-03-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-20 | 2019-04-20 | Finished |  |  | 2019-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-10-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-10-19 | Finished |  |  | 100 | 2020-09-30 | Finished | CONSTRUCTION DELAY |  | 2020-09-30 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-12-18 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2020-09-30 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 446 | 91 | 24 | 20 | 581 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000418 | 2018-12-18 | QC Passed
TBJ0013-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | S-SL-13 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 |  | F-4000-3U30,30S/2F | F(H)-EL | 4000 | 30 | 2 | 2 |  | 3680800 | Bangkok | เขตดุสิต | 2018-12-15 | 2019-01-10 | Finished | [34 empty] | 2018-04-15 | 2018-08-10 | 2018-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-14 | 2019-03-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-20 | 2019-04-20 | Finished |  |  | 2019-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-10-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-10-19 | Finished |  |  | 100 | 2020-09-30 | Finished | CONSTRUCTION DELAY |  | 2020-09-30 | Finished |  |  | 2018-01-11 | Finished | [18 empty] | 2018-12-18 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2020-09-30 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 446 | 91 | 24 | 20 | 581 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-04-15 |  |  |  | HDME000418 | 2018-12-18 | QC Passed
TBL0083-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | TS-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2021-04-19 | OUG-1350-CO90,90S/3F | OUG-ON1 | 1350 | 90 | 3 | 3 |  | 2214900 | Bangkok | เขตดุสิต | 2020-05-05 | 2020-05-04 | Finished | [34 empty] | 2018-08-15 | 2018-10-04 | 2018-10-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-30 | 2020-06-03 | 2020-05-06 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-26 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-23 | Finished |  |  | 100 | [41 empty] | 2020-05-23 | 2020-06-18 | 2020-06-18 | Finished |  |  | 2020-06-09 | 2020-06-19 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-25 | Finished |  |  | 100 | 2020-08-31 | 2021-03-26 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-05-31 | Finished | H/O DOCUMENT DELAY |  | 2021-05-17 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-05-17 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-08-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0084-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | TS-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2021-04-19 | OUG-1350-CO90,90S/3F | OUG-ON1 | 1350 | 90 | 3 | 3 |  | 2214900 | Bangkok | เขตดุสิต | 2020-05-05 | 2020-05-04 | Finished | [34 empty] | 2018-08-15 | 2018-10-04 | 2018-10-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-30 | 2020-06-03 | 2020-05-06 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-26 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-23 | Finished |  |  | 100 | [41 empty] | 2020-05-23 | 2020-06-18 | 2020-06-18 | Finished |  |  | 2020-06-09 | 2020-06-19 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-26 | Finished |  |  | 100 | 2020-08-31 | 2021-03-26 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-05-31 | Finished | H/O DOCUMENT DELAY |  | 2021-05-17 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-05-17 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-08-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TBL0085-TH | HET | 61000144 | HO | ส่งมอบแล้ว | - | TH189057 | New Parliament | TS-SL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2013-11-09 | 2018-03-01 | 2019-06-30 | 2021-04-19 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 2300500 | Bangkok | เขตดุสิต | 2020-03-10 | 2020-03-09 | Finished | [34 empty] | 2018-08-15 | 2018-10-04 | 2018-10-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-09 | 2020-04-24 | 2020-03-12 | Finished |  |  | 2020-04-01 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-21 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-28 | Finished |  |  | 100 | [41 empty] | 2020-03-28 | 2020-09-23 | 2020-09-23 | Finished |  |  | 2020-04-27 | 2020-09-24 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-10-05 | Finished |  |  | 100 | 2020-10-27 | 2021-03-26 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-05-31 | Finished | H/O DOCUMENT DELAY |  | 2021-05-17 | Finished |  |  | 2018-01-11 | Finished | [10 empty] | 2021-05-17 | Finished | [6 empty] | 2018-11-14 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-28 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001535 | 2018-08-15 |  |  |  | HDME000370 | 2018-11-14 | QC Passed
TAJ0193-TH | HET | 61000145 | HO | ส่งมอบแล้ว | - | TH189086 | JUPITER TREVI RESORT AND SPA | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | DOUNGYIWA PHOLDEE | 2017-11-23 | 2018-06-23 | 2018-08-23 | 2020-08-11 | P-600-CO60D,60S/2F | UAG-SN1 | 600 | 60 | 2 | 2 |  | 1070000 | Nakhon Ratchasima | อำเภอปากช่อง | 2017-07-03 | 2018-09-01 | Finished | [34 empty] | 2018-06-16 | 2018-07-03 | 2018-07-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-01 | 2018-10-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-30 | 2019-12-30 | Finished |  |  | 2019-12-30 | 2019-12-24 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-29 | Finished |  |  | 100 | 2021-05-13 | 2020-09-24 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-24 | Finished |  |  | 100 | 2020-03-23 | Finished | POWER SUPPLY DELAY |  | 2020-08-04 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2018-06-22 | Finished |  |  | 2018-07-03 | Finished |  |  | 2018-07-04 | Finished |  |  | 2020-08-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001576 | 2018-06-16 |  |  |  | HDME000204 | 2018-06-22 | QC Passed
TAJ0194-TH | HET | 61000145 | HO | ส่งมอบแล้ว | - | TH189086 | JUPITER TREVI RESORT AND SPA | EL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | DOUNGYIWA PHOLDEE | 2017-11-23 | 2018-06-23 | 2018-08-23 | 2020-08-11 | P-600-CO60D,60S/2F | UAG-SN1 | 600 | 60 | 2 | 2 |  | 1070000 | Nakhon Ratchasima | อำเภอปากช่อง | 2017-07-03 | 2018-09-01 | Finished | [34 empty] | 2018-06-16 | 2018-07-03 | 2018-07-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-01 | 2018-10-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-30 | 2019-12-30 | Finished |  |  | 2019-12-30 | 2019-12-24 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-29 | Finished |  |  | 100 | 2021-05-13 | 2020-09-24 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-01-14 | Finished |  |  | 2020-09-24 | Finished |  |  | 100 | 2020-03-23 | Finished | POWER SUPPLY DELAY |  | 2020-08-04 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2018-06-22 | Finished |  |  | 2018-07-03 | Finished |  |  | 2018-07-04 | Finished |  |  | 2020-08-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001576 | 2018-06-16 |  |  |  | HDME000204 | 2018-06-22 | QC Passed
TAJ0195-TH | HET | 61000145 | HO | ส่งมอบแล้ว | - | TH189086 | JUPITER TREVI RESORT AND SPA | EL3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | DOUNGYIWA PHOLDEE | 2017-11-23 | 2018-06-23 | 2018-08-23 | 2020-08-11 | P-600-CO60D,60S/2F | UAG-SN1 | 600 | 60 | 2 | 2 |  | 1070000 | Nakhon Ratchasima | อำเภอปากช่อง | 2017-07-03 | 2018-09-01 | Finished | [34 empty] | 2018-06-16 | 2018-07-03 | 2018-07-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-01 | 2018-10-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-30 | 2019-12-30 | Finished |  |  | 2019-12-30 | 2019-12-24 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-29 | Finished |  |  | 100 | 2021-05-13 | 2021-06-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-01-14 | Finished |  |  | 2021-06-04 | Finished |  |  | 100 | 2020-03-23 | Finished | POWER SUPPLY DELAY |  | 2020-08-04 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2018-06-22 | Finished |  |  | 2018-07-03 | Finished |  |  | 2018-07-04 | Finished |  |  | 2020-08-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001576 | 2018-06-16 |  |  |  | HDME000204 | 2018-06-22 | QC Passed
TFA1054-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R3.2M,D30 | SX-EN |  |  |  |  | 3200 | 1070000 | Bangkok | เขตห้วยขวาง | 2018-12-23 | [20 empty] | 2018-12-23 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-10-15 | 2019-10-15 | Finished |  |  | 2019-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-11-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-19 | Finished |  |  | 100 | 2020-03-15 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1063-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตห้วยขวาง | 2018-12-20 | [20 empty] | 2018-12-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-09-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1064-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES11 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตห้วยขวาง | 2018-12-20 | [20 empty] | 2018-12-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-09-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1065-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES12 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตห้วยขวาง | 2018-12-20 | [20 empty] | 2018-12-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-09-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1055-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R3.2M,D30 | SX-EN |  |  |  |  | 3200 | 1070000 | Bangkok | เขตห้วยขวาง | 2019-01-20 | [20 empty] | 2019-01-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-10-15 | 2019-10-15 | Finished |  |  | 2019-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-09-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1056-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R6.2M,D30 | SX-EN |  |  |  |  | 6200 | 1364250 | Bangkok | เขตห้วยขวาง | 2019-01-20 | [20 empty] | 2019-01-20 | Finished | [14 empty] | 2018-07-15 | 2018-09-20 | 2018-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-10 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-21 | Finished |  |  | 2018-09-26 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000296 | 2018-09-18 | QC Passed
TFA1057-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R6.2M,D30 | SX-EN |  |  |  |  | 6200 | 1364250 | Bangkok | เขตห้วยขวาง | 2019-01-20 | [20 empty] | 2019-01-20 | Finished | [14 empty] | 2018-07-15 | 2018-09-20 | 2018-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-10 | Finished |  |  | 100 | 2021-05-13 | 2020-09-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-09-18 | Finished |  |  | 2018-09-21 | Finished |  |  | 2018-09-26 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000296 | 2018-09-18 | QC Passed
TFA1058-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R6.5M,D30 | SX-EN |  |  |  |  | 6500 | 1417750 | Bangkok | เขตห้วยขวาง | 2019-01-20 | [20 empty] | 2019-01-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-10 | Finished |  |  | 100 | 2021-05-13 | 2020-09-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1059-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R6.5M,D30 | SX-EN |  |  |  |  | 6500 | 1417750 | Bangkok | เขตห้วยขวาง | 2018-12-20 | [20 empty] | 2018-12-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-10 | Finished |  |  | 100 | 2021-05-13 | 2020-09-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1060-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตห้วยขวาง | 2018-12-20 | [20 empty] | 2018-12-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 2020-02-04 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2021-08-04 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1061-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตห้วยขวาง | 2018-12-20 | [20 empty] | 2018-12-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 2020-02-04 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 2 | 2 | 99.72 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TFA1062-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | ES9 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตห้วยขวาง | 2018-12-20 | [20 empty] | 2018-12-20 | Finished | [14 empty] | 2018-07-15 | 2018-08-13 | 2018-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-24 | 2019-04-24 | [41 empty] | 2018-12-24 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-05 | Finished |  |  | 2019-02-28 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-22 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-15 | Finished |  |  | 100 | 2019-04-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-02-01 | Finished |  |  | 2020-02-04 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-10 | Finished |  |  | 2018-08-13 | Finished |  |  | 2018-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001637 | 2018-07-15 |  |  |  | HDME000260 | 2018-08-10 | QC Passed
TEC0108-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | DW01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | DT-100S-B30,30S/9F | DT | 100 | 30 | 9 | 9 |  | 321000 | Bangkok | เขตห้วยขวาง | 2020-02-20 | 2020-02-20 | Finished | [34 empty] | 2018-07-15 | 2019-01-17 | 2019-01-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-19 | 2019-12-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-01 | 2020-01-01 | Finished |  |  | 2020-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2020-11-15 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2019-01-15 | Finished |  |  | 2019-01-17 | Finished |  |  | 2019-01-23 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | dumb |  |  |  |  | 366 | 0 | 24 | 0 | 390 | 0 | 0 | 24 | 0 | 24 | 93.85 | Blue |  |  | 20001762 | 2018-07-15 |  |  |  | HDME000441 | 2019-01-15
TBK0098-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | PL01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | HVF-1000-CO180,180S/22F | HVF-5 | 1000 | 180 | 18 | 22 |  | 4192750 | Bangkok | เขตห้วยขวาง | 2018-12-20 | 2018-12-20 | Finished | [34 empty] | 2018-07-15 | 2018-12-03 | 2018-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-29 | 2019-07-20 | 2019-03-29 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-05-05 | Finished |  |  | 2019-05-15 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-10 | Finished |  |  | 2019-06-20 | Finished |  |  | 2019-07-15 | Finished |  |  | 100 | [41 empty] | 2019-07-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2019-12-26 | Finished |  |  | 2020-01-01 | Finished |  |  | 2020-01-10 | Finished |  |  | 100 | 2021-05-13 | 2020-07-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-07-17 | Finished |  |  | 100 | 2020-08-26 | Finished | CONSTRUCTION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-12-18 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-24 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1437 | 109 | 48 | 24 | 1618 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001639 | 2018-07-15 |  |  |  | HDME000419 | 2018-12-18 | QC Passed
TBK0099-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | PL02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | HVF-1000-CO180,180S/22F | HVF-5 | 1000 | 180 | 18 | 22 |  | 4192750 | Bangkok | เขตห้วยขวาง | 2019-02-20 | 2019-02-20 | Finished | [34 empty] | 2018-07-15 | 2018-12-03 | 2018-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-29 | 2019-07-20 | 2019-03-29 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-05-05 | Finished |  |  | 2019-05-15 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-10 | Finished |  |  | 2019-06-20 | Finished |  |  | 2019-07-15 | Finished |  |  | 100 | [41 empty] | 2019-07-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2019-12-26 | Finished |  |  | 2020-01-01 | Finished |  |  | 2020-01-10 | Finished |  |  | 100 | 2021-05-13 | 2020-07-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-07-17 | Finished |  |  | 100 | 2020-08-26 | Finished | CONSTRUCTION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-12-18 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-24 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1437 | 109 | 48 | 24 | 1618 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001639 | 2018-07-15 |  |  |  | HDME000419 | 2018-12-18 | QC Passed
TBK0100-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | PL03 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | HVF-1000-CO180,180S/22F | HVF-5 | 1000 | 180 | 18 | 22 |  | 4192750 | Bangkok | เขตห้วยขวาง | 2019-02-20 | 2019-02-20 | Finished | [34 empty] | 2018-07-15 | 2018-12-03 | 2018-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-29 | 2019-07-20 | 2019-03-29 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-05-05 | Finished |  |  | 2019-05-15 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-10 | Finished |  |  | 2019-06-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2019-12-26 | Finished |  |  | 2020-01-01 | Finished |  |  | 2020-01-10 | Finished |  |  | 100 | 2021-05-13 | 2020-07-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-07-17 | Finished |  |  | 100 | 2020-08-26 | Finished | CUSTOMER DECORATION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-12-18 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-24 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1437 | 109 | 48 | 24 | 1618 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001639 | 2018-07-15 |  |  |  | HDME000419 | 2018-12-18 | QC Passed
TBK0101-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | PL04 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | HVF-1000-CO180,180S/22F | HVF-5 | 1000 | 180 | 18 | 22 |  | 4192750 | Bangkok | เขตห้วยขวาง | 2019-07-30 | 2019-03-29 | Finished | [34 empty] | 2018-07-15 | 2018-12-03 | 2018-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-29 | 2019-07-20 | 2019-03-29 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-05-05 | Finished |  |  | 2019-05-15 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-10 | Finished |  |  | 2019-06-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2019-12-26 | Finished |  |  | 2020-01-01 | Finished |  |  | 2020-01-10 | Finished |  |  | 100 | 2021-05-13 | 2020-07-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-07-17 | Finished |  |  | 100 | 2020-08-26 | Finished | CUSTOMER DECORATION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-12-18 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-24 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1437 | 109 | 48 | 24 | 1618 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001639 | 2018-07-15 |  |  |  | HDME000419 | 2018-12-18 | QC Passed
TBL0087-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | PL05 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | OUG-1000-CO105,105S/14F | OUG-ON1 | 1000 | 105 | 9 | 14 |  | 1498000 | Bangkok | เขตห้วยขวาง | 2019-07-30 | 2019-03-29 | Finished | [34 empty] | 2018-07-15 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-29 | 2019-07-20 | 2019-03-29 | Finished |  |  | 2019-04-05 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-05-05 | Finished |  |  | 2019-05-15 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-10 | Finished |  |  | 2019-06-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2019-12-26 | Finished |  |  | 2020-01-01 | Finished |  |  | 2020-01-10 | Finished |  |  | 100 | 2021-05-13 | 2021-02-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 100 | 2020-08-26 | Finished | CONSTRUCTION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-10-18 | Finished |  |  | 2018-11-08 | Finished |  |  | 2018-11-13 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 967 | 100 | 32 | 20 | 1119 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001639 | 2018-07-15 |  |  |  | HDME000334 | 2018-10-18 | QC Passed
TBL0088-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | PL06 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | OUG-1000-CO105,105S/14F | OUG-ON1 | 1000 | 105 | 9 | 14 |  | 1498000 | Bangkok | เขตห้วยขวาง | 2019-02-20 | 2019-02-20 | Finished | [34 empty] | 2018-07-15 | 2018-11-08 | 2018-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-29 | 2019-07-20 | 2019-03-29 | Finished |  |  | 2019-04-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-05-05 | Finished |  |  | 2019-05-15 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-10 | Finished |  |  | 2019-06-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2019-12-26 | Finished |  |  | 2020-01-01 | Finished |  |  | 2020-01-10 | Finished |  |  | 100 | 2021-05-13 | 2020-07-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-07-17 | Finished |  |  | 100 | 2020-08-26 | Finished | CONSTRUCTION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-10-18 | Finished |  |  | 2018-11-08 | Finished |  |  | 2018-11-13 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 967 | 100 | 32 | 20 | 1119 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001639 | 2018-07-15 |  |  |  | HDME000334 | 2018-10-18 | QC Passed
TAC1266-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | SL01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | VFI-1600-2S105,105S/23F | VFI-II | 1600 | 105 | 23 | 23 |  | 2782000 | Bangkok | เขตห้วยขวาง | 2019-02-20 | 2019-02-20 | Finished | [34 empty] | 2018-07-15 | 2018-08-23 | 2018-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-15 | 2019-04-30 | 2019-03-15 | Finished |  |  | 2019-03-17 | Finished |  |  | 2019-03-20 | Finished |  |  | 2019-03-25 | Finished |  |  | 2019-04-10 | Finished |  |  | 2019-04-15 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-04-23 | Finished |  |  | 2019-04-26 | Finished |  |  | 2019-04-30 | Finished |  |  | 100 | [41 empty] | 2019-04-30 | 2019-07-15 | 2019-07-15 | Finished |  |  | 2019-07-15 | 2019-07-16 | Finished |  |  | 2019-07-19 | Finished |  |  | 2019-07-21 | Finished |  |  | 100 | 2021-05-13 | 2020-05-07 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-10-18 | Finished |  |  | 2020-05-07 | Finished |  |  | 100 | 2020-03-15 | Finished | CUSTOMER DECORATION DELAY |  | 2019-09-24 | Finished |  |  | 2018-05-02 | Finished | [18 empty] | 2018-08-22 | Finished |  |  | 2018-08-29 | Finished |  |  | 2018-08-29 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1522 | 115 | 48 | 24 | 1709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001757 | 2018-07-15 |  |  |  | HDME000271 | 2018-08-22 | QC Passed
TAC1267-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | SL02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | VFI-1600-2S105,105S/23F | VFI-II | 1600 | 105 | 23 | 23 |  | 2782000 | Bangkok | เขตห้วยขวาง | 2019-02-20 | 2019-02-20 | Finished | [34 empty] | 2018-07-15 | 2018-08-23 | 2018-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-15 | 2019-04-30 | 2019-03-15 | Finished |  |  | 2019-03-17 | Finished |  |  | 2019-03-20 | Finished |  |  | 2019-03-25 | Finished |  |  | 2019-04-10 | Finished |  |  | 2019-04-15 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-04-23 | Finished |  |  | 2019-04-26 | Finished |  |  | 2019-04-30 | Finished |  |  | 100 | [41 empty] | 2019-04-30 | 2019-07-15 | 2019-07-15 | Finished |  |  | 2019-07-15 | 2019-07-16 | Finished |  |  | 2019-07-19 | Finished |  |  | 2019-07-21 | Finished |  |  | 100 | 2021-05-13 | 2020-05-07 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-10-18 | Finished |  |  | 2020-05-07 | Finished |  |  | 100 | 2020-03-15 | Finished | CUSTOMER DECORATION DELAY |  | 2019-09-24 | Finished |  |  | 2018-05-02 | Finished | [18 empty] | 2018-08-22 | Finished |  |  | 2018-08-29 | Finished |  |  | 2018-08-29 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1522 | 115 | 48 | 24 | 1709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001757 | 2018-07-15 |  |  |  | HDME000271 | 2018-08-22 | QC Passed
TAC1270-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | SL03 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | VFI-1600-2S105,105S/23F | VFI-II | 1600 | 105 | 23 | 23 |  | 2782000 | Bangkok | เขตห้วยขวาง | 2019-07-30 | 2019-03-29 | Finished | [34 empty] | 2018-07-15 | 2018-08-23 | 2018-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-04-01 | 2019-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-06-02 | 2019-06-02 | Finished |  |  | 2019-06-02 | 2019-06-03 | Finished |  |  | 2019-02-05 | Finished |  |  | 2019-02-14 | Finished |  |  | 100 | 2021-05-13 | 2020-05-07 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-10-18 | Finished |  |  | 2020-05-07 | Finished |  |  | 100 | 2019-07-30 | Finished | CUSTOMER DECORATION DELAY |  | 2019-09-24 | Finished |  |  | 2018-05-02 | Finished | [18 empty] | 2018-08-22 | Finished |  |  | 2018-08-29 | Finished |  |  | 2018-08-29 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1522 | 115 | 48 | 24 | 1709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001757 | 2018-07-15 |  |  |  | HDME000271 | 2018-08-22 | QC Passed
TAC1268-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | SL04 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | VFI-1600-2S105,105S/23F | VFI-II | 1600 | 105 | 19 | 23 |  | 2568000 | Bangkok | เขตห้วยขวาง | 2019-02-20 | 2019-02-20 | Finished | [34 empty] | 2018-07-15 | 2018-08-23 | 2018-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-19 | 2019-12-31 | 2019-09-19 | Finished |  |  | 2019-09-25 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-20 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-15 | Finished |  |  | 2019-12-30 | Finished |  |  | 100 | [41 empty] | 2019-12-30 | 2020-01-01 | 2020-01-01 | Finished |  |  | 2020-01-01 | 2019-01-02 | Finished |  |  | 2019-02-10 | Finished |  |  | 2019-02-20 | Finished |  |  | 100 | 2020-06-12 | 2020-07-17 | 2020-06-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-17 | Finished | [6 empty] | 90 | 2020-08-26 | Finished | CUSTOMER DECORATION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-22 | Finished |  |  | 2018-08-29 | Finished |  |  | 2018-08-29 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1522 | 115 | 48 | 24 | 1709 | 0 | 0 | 0 | 2 | 2 | 99.88 | Blue |  |  | 20001757 | 2018-07-15 |  |  |  | HDME000271 | 2018-08-22 | QC Passed
TAC1269-TH | HET | 61000146 | HO | ส่งมอบแล้ว | - | TH189076 | Praram 9 Hospital | SL05 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2017-07-03 | 2018-07-31 | 2019-01-14 | 2020-10-30 | VFI-1600-2S105,105S/23F | VFI-II | 1600 | 105 | 19 | 23 |  | 2568000 | Bangkok | เขตห้วยขวาง | 2019-07-30 | 2019-03-29 | Finished | [34 empty] | 2018-07-15 | 2018-08-23 | 2018-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-19 | 2019-12-31 | 2019-09-19 | Finished |  |  | 2019-09-25 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-20 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-15 | Finished |  |  | 2019-12-30 | Finished |  |  | 100 | [41 empty] | 2019-12-30 | 2020-01-01 | 2020-01-01 | Finished |  |  | 2020-01-01 | 2019-01-02 | Finished |  |  | 2019-02-10 | Finished |  |  | 2019-02-20 | Finished |  |  | 100 | 2020-06-12 | 2020-07-17 | 2020-06-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-17 | Finished | [6 empty] | 90 | 2020-08-26 | Finished | CUSTOMER DECORATION DELAY |  | 2020-08-20 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2018-08-22 | Finished |  |  | 2018-08-29 | Finished |  |  | 2018-08-29 | Finished |  |  | 2020-08-20 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1522 | 115 | 48 | 24 | 1709 | 0 | 0 | 0 | 2 | 2 | 99.88 | Blue |  |  | 20001757 | 2018-07-15 |  |  |  | HDME000271 | 2018-08-22 | QC Passed
TFA1077-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | 1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1337500 | Phuket | ตำบลรัษฎา | 2018-03-14 | [20 empty] | 2018-04-29 | Finished | [14 empty] | 2018-03-14 | 2018-05-22 | 2018-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-16 | 2018-09-07 | [41 empty] | 2018-05-01 | Finished |  |  | 2018-05-02 | Finished |  |  | 2018-05-03 | Finished |  |  | 2018-05-04 | Finished |  |  | 2018-05-05 | Finished |  |  | 2018-05-11 | Finished |  |  | 2018-05-12 | Finished |  |  | 2018-05-13 | Finished |  |  | 2018-05-14 | Finished |  |  | 2018-05-15 | Finished |  |  | 100 | 2018-05-15 | 2018-09-08 | 2018-09-08 | Finished |  |  | 2018-09-08 | 2019-03-05 | Finished |  |  | 2019-03-08 | Finished |  |  | 2019-03-10 | Finished |  |  | 100 | 2019-03-01 | 2000-01-01 | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished | [6 empty] | 90 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-05-18 | Finished |  |  | 2018-05-22 | Finished |  |  | 2018-05-23 | Finished | [22 empty] | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 2 | 2 | 99.72 | Red |  |  | 20001778 | 2018-03-14 |  |  |  | HDME000172 | 2018-05-18
TFA1078-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | 2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1337500 | Phuket | ตำบลรัษฎา | 2018-03-14 | [20 empty] | 2018-04-29 | Finished | [14 empty] | 2018-03-14 | 2018-05-22 | 2018-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-16 | 2018-09-07 | [41 empty] | 2018-05-01 | Finished |  |  | 2018-05-02 | Finished |  |  | 2018-05-03 | Finished |  |  | 2018-05-04 | Finished |  |  | 2018-05-05 | Finished |  |  | 2018-05-11 | Finished |  |  | 2018-05-12 | Finished |  |  | 2018-05-13 | Finished |  |  | 2018-05-14 | Finished |  |  | 2018-05-15 | Finished |  |  | 100 | 2018-05-15 | 2018-09-08 | 2018-09-08 | Finished |  |  | 2018-09-08 | 2019-03-05 | Finished |  |  | 2019-03-08 | Finished |  |  | 2019-03-10 | Finished |  |  | 100 | 2019-03-01 | 2000-01-01 | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished | [6 empty] | 90 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-05-18 | Finished |  |  | 2018-05-22 | Finished |  |  | 2018-05-23 | Finished | [22 empty] | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 2 | 2 | 99.72 | Red |  |  | 20001778 | 2018-03-14 |  |  |  | HDME000172 | 2018-05-18
TFA1079-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | 3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1337500 | Phuket | ตำบลรัษฎา | 2018-03-14 | [20 empty] | 2018-04-29 | Finished | [14 empty] | 2018-03-14 | 2018-05-22 | 2018-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-16 | 2018-09-07 | [41 empty] | 2018-04-30 | Finished |  |  | 2018-05-02 | Finished |  |  | 2018-05-03 | Finished |  |  | 2018-05-04 | Finished |  |  | 2018-05-05 | Finished |  |  | 2018-05-06 | Finished |  |  | 2018-05-07 | Finished |  |  | 2018-05-08 | Finished |  |  | 2018-05-09 | Finished |  |  | 2018-05-10 | Finished |  |  | 100 | 2018-05-10 | 2018-09-08 | 2018-09-08 | Finished |  |  | 2018-09-08 | 2019-03-06 | Finished |  |  | 2019-03-09 | Finished |  |  | 2019-03-10 | Finished |  |  | 100 | 2019-03-01 | 2000-01-01 | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished | [6 empty] | 90 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-05-18 | Finished |  |  | 2018-05-22 | Finished |  |  | 2018-05-23 | Finished | [22 empty] | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 2 | 2 | 99.72 | Red |  |  | 20001778 | 2018-03-14 |  |  |  | HDME000172 | 2018-05-18
TFA1080-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | 4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | 1200SX-EN,R5M,D30 | SX-EN |  |  |  |  | 5000 | 1337500 | Phuket | ตำบลรัษฎา | 2018-03-14 | [20 empty] | 2018-04-29 | Finished | [14 empty] | 2018-03-14 | 2018-05-22 | 2018-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-16 | 2018-09-07 | [41 empty] | 2018-04-30 | Finished |  |  | 2018-05-02 | Finished |  |  | 2018-05-03 | Finished |  |  | 2018-05-04 | Finished |  |  | 2018-05-05 | Finished |  |  | 2018-05-06 | Finished |  |  | 2018-05-07 | Finished |  |  | 2018-05-08 | Finished |  |  | 2018-05-09 | Finished |  |  | 2018-05-10 | Finished |  |  | 100 | 2018-05-10 | 2018-09-08 | 2018-09-08 | Finished |  |  | 2018-09-08 | 2019-03-06 | Finished |  |  | 2019-03-09 | Finished |  |  | 2019-03-10 | Finished |  |  | 100 | [18 empty] | 0 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-05-18 | Finished |  |  | 2018-05-22 | Finished |  |  | 2018-05-23 | Finished | [22 empty] | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 16 | 21 | 37 | 94.78 | Red |  |  | 20001778 | 2018-03-14 |  |  |  | HDME000172 | 2018-05-18
TEC0109-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | D1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | DF-100S-B30,30S/8F | DF | 100 | 30 | 8 | 8 |  | 428000 | Phuket | ตำบลรัษฎา | 2018-03-22 | 2018-05-20 | Finished | [34 empty] | 2018-03-22 | 2018-12-24 | 2018-12-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-16 | 2018-09-10 | 2018-05-24 | Finished |  |  | 2018-05-25 | Finished |  |  | 2018-05-26 | Finished |  |  | 2018-05-27 | Finished |  |  | 2018-05-28 | Finished |  |  | 2018-05-29 | Finished |  |  | 2018-05-30 | Finished |  |  | 2018-05-31 | Finished |  |  | 2018-06-01 | Finished |  |  | 2018-06-02 | Finished |  |  | 100 | [41 empty] | 2018-06-02 | 2018-09-11 | 2018-09-11 | Finished |  |  | 2018-09-11 | 2018-06-03 | Finished |  |  | 2018-06-03 | Finished |  |  | 2018-06-05 | Finished |  |  | 100 | [18 empty] | 0 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-10-30 | Finished |  |  | 2018-12-24 | Finished |  |  | 2018-12-25 | Finished | [22 empty] | 338 | 0 | 24 | 0 | 362 | 0 | 0 | 24 | 0 | 24 | 93.37 | Red |  |  | 20001718 | 2018-03-22 |  |  |  | HDME000347 | 2018-10-30
TAJ0197-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | L1 (bld.4 fl.) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1444500 | Phuket | ตำบลรัษฎา | 2022-01-15 | [36 empty] | 2018-03-22 | 2018-06-08 | 2018-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-01-15 | 2022-03-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-02 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-06-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-06-05 | Finished |  |  | 2018-06-08 | Finished |  |  | 2018-06-21 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20001716 | 2018-04-29 |  |  |  | HDME000181 | 2018-06-05
TAJ0198-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | L2 (bld.4 fl.) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | P-1000-CO60W1,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1498000 | Phuket | ตำบลรัษฎา | 2022-01-15 | [36 empty] | 2018-03-22 | 2018-06-08 | 2018-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-01-15 | 2022-02-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-02 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-06-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-06-05 | Finished |  |  | 2018-06-08 | Finished |  |  | 2018-06-21 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20001716 | 2018-04-29 |  |  |  | HDME000181 | 2018-06-05
TAE1180-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | L3 (bld.8 fl.) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | UAG-900-CO90,90S/9F | UAG-11G-A | 900 | 90 | 9 | 9 |  | 1605000 | Phuket | ตำบลรัษฎา | 2018-04-29 | 2018-05-20 | Finished | [34 empty] | 2018-04-29 | 2018-05-03 | 2018-05-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-21 | 2018-08-19 | 2018-05-21 | Finished |  |  | 2018-05-24 | Finished |  |  | 2018-05-26 | Finished |  |  | 2018-05-30 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-04 | Finished |  |  | 2018-06-07 | Finished |  |  | 2018-06-08 | Finished |  |  | 2018-06-10 | Finished |  |  | 2018-06-13 | Finished |  |  | 100 | [41 empty] | 2018-06-13 | 2018-08-20 | 2018-08-20 | Finished |  |  | 2018-08-20 | 2019-03-05 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-03-14 | Finished |  |  | 100 | 2019-03-01 | 2000-01-01 | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished | [6 empty] | 90 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-05-04 | Finished |  |  | 2018-05-03 | Finished |  |  | 2018-05-22 | Finished | [22 empty] | 731 | 84 | 24 | 16 | 855 | 0 | 0 | 0 | 1 | 1 | 99.88 | Red |  |  | 20001716 | 2018-03-30 |  |  |  | HDME000154 | 2018-05-04
TAE1181-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | L4 (bld.8 fl.) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | UAG-900-CO90,90S/9F | UAG-11G-A | 900 | 90 | 9 | 9 |  | 1605000 | Phuket | ตำบลรัษฎา | 2018-04-29 | 2018-05-20 | Finished | [34 empty] | 2018-04-29 | 2018-05-03 | 2018-05-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-21 | 2018-08-19 | 2018-05-21 | Finished |  |  | 2018-05-24 | Finished |  |  | 2018-05-26 | Finished |  |  | 2018-05-30 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-04 | Finished |  |  | 2018-06-07 | Finished |  |  | 2018-06-08 | Finished |  |  | 2018-06-10 | Finished |  |  | 2018-06-13 | Finished |  |  | 100 | [41 empty] | 2018-06-13 | 2018-08-20 | 2018-08-20 | Finished |  |  | 2018-08-20 | 2019-03-07 | Finished |  |  | 2019-03-12 | Finished |  |  | 2019-03-14 | Finished |  |  | 100 | 2019-03-01 | 2000-01-01 | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished |  |  | 2019-03-01 | Finished | [6 empty] | 90 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-05-04 | Finished |  |  | 2018-05-03 | Finished |  |  | 2018-05-22 | Finished | [22 empty] | 731 | 84 | 24 | 16 | 855 | 0 | 0 | 0 | 1 | 1 | 99.88 | Red |  |  | 20001716 | 2018-03-30 |  |  |  | HDME000154 | 2018-05-04
TAE1182-TH | HET | 61000153 | HO | เลยสัญญา HO | - | TH189090 | Phuket Rajabhat University | L5 (bld.8 fl.) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2017-11-29 | 2018-03-29 | 2018-08-29 | 2020-09-24 | UAG-1000-CO90,90S/9F | UAG-11G-A | 1000 | 90 | 9 | 9 |  | 1658500 | Phuket | ตำบลรัษฎา | 2018-04-29 | 2018-04-29 | Finished | [34 empty] | 2018-04-29 | 2018-05-03 | 2018-05-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-06-11 | 2018-07-04 | 2018-04-29 | Finished |  |  | 2018-05-30 | Finished |  |  | 2018-05-31 | Finished |  |  | 2018-06-01 | Finished |  |  | 2018-06-02 | Finished |  |  | 2018-06-03 | Finished |  |  | 2018-06-04 | Finished |  |  | 2018-06-05 | Finished |  |  | 2018-06-06 | Finished |  |  | 2018-06-07 | Finished |  |  | 100 | [41 empty] | 2018-06-07 | 2018-07-10 | 2018-07-10 | Finished |  |  | 2018-07-10 | 2019-02-10 | Finished |  |  | 2019-02-15 | Finished |  |  | 2019-02-17 | Finished |  |  | 100 | 2018-11-07 | 2000-01-01 | 2018-11-07 | Finished |  |  | 2018-11-07 | Finished |  |  | 2018-11-07 | Finished | [6 empty] | 90 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-02-01 | Finished | [18 empty] | 2018-05-04 | Finished |  |  | 2018-05-03 | Finished |  |  | 2018-05-22 | Finished | [22 empty] | 731 | 84 | 24 | 16 | 855 | 0 | 0 | 0 | 1 | 1 | 99.88 | Red |  |  | 20001716 | 2018-03-30 |  |  |  | HDME000154 | 2018-05-04
TBK0106-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-2S180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 2018-10-21 | 2018-10-21 | Finished | [34 empty] | 2018-08-24 | 2018-11-16 | 2018-11-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-14 | 2019-05-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-22 | 2019-01-22 | Finished |  |  | 2019-01-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-24 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2019-10-01 | Finished | CUSTOMER DECORATION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-24 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000378 | 2018-11-19 | QC Passed
TAC1292-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL10 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | VFI-750-CO120,120S/26F | VFI-II | 750 | 120 | 26 | 26 |  | 3200000 | Bangkok | เขตบางกอกน้อย | 2018-10-21 | 2018-10-21 | Finished | [34 empty] | 2018-05-25 | 2018-11-22 | 2018-11-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-14 | 2019-05-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-07-01 | 2019-07-01 | Finished |  |  | 2019-07-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-01-15 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-13 | Finished |  | pass |  |  |  |  | 1688 | 118 | 56 | 24 | 1886 | 0 | 0 | 0 | 2 | 2 | 99.89 | Blue |  |  | 20001719 | 2018-05-25 |  |  |  | HDME000384 | 2018-11-21 | QC Passed
TBL0098-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL11 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | OUG-1600-2S60,60S/2F | OUG-ON1 | 1600 | 60 | 2 | 2 |  | 2100000 | Bangkok | เขตบางกอกน้อย | 2020-02-19 | 2020-02-28 | Finished | [34 empty] | 2018-05-02 | 2019-07-26 | 2019-07-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2019-12-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-02 | 2020-01-02 | Finished |  |  | 2020-01-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-03-01 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001717 | 2018-05-02 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0107-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL2-1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 27 | 27 |  | 6850000 | Bangkok | เขตบางกอกน้อย | 2018-10-21 | 2018-10-21 | Finished | [34 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-02 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0108-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL2-2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 27 | 27 |  | 6850000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-02 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0109-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL2-3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 27 | 27 |  | 6850000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-02 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0110-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL2-4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 27 | 27 |  | 6850000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-02 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0111-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL3-1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-14 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | 2020-05-20 | 2021-05-20 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-05 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0112-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL3-2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-14 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0113-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL3-3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-14 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0114-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL3-4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-CO180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-14 | 2020-01-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-02-22 | 2020-02-22 | Finished |  |  | 2020-02-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-17 | Finished |  |  | 100 | 2020-05-20 | 2021-05-20 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-05 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0115-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL4-1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-2S180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | 2019-06-27 | Finished | [34 empty] | 2018-08-24 | 2018-12-14 | 2018-12-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-27 | 2020-02-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-28 | 2020-03-28 | Finished |  |  | 2020-03-28 | 1900-01-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-20 | 2021-05-20 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2021-02-15 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000428 | 2018-12-21 | QC Passed
TBK0116-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL4-2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-2S180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 1900-01-01 | 2019-06-27 | Finished | [34 empty] | 2018-08-24 | 2018-12-14 | 2018-12-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-27 | 2020-02-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-28 | 2020-03-28 | Finished |  |  | 2020-03-28 | 1900-01-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-20 | 2021-05-20 | 2020-05-20 | Finished |  |  | 2020-10-09 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2021-02-15 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000428 | 2018-12-21 | QC Passed
TBK0117-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL4-3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-2S180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 6950000 | Bangkok | เขตบางกอกน้อย | 1900-01-01 | 2019-06-27 | Finished | [34 empty] | 2018-08-24 | 2018-12-14 | 2018-12-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-27 | 2020-02-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-28 | 2020-03-28 | Finished |  |  | 2020-03-28 | 1900-01-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-20 | 2021-05-24 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2021-02-15 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000428 | 2018-12-21 | QC Passed
TBK0118-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL5-1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-2S180,180S/27F | HVF-5 | 1600 | 180 | 27 | 27 |  | 6850000 | Bangkok | เขตบางกอกน้อย | 1900-01-01 | 2019-06-27 | Finished | [34 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-06 | 2020-02-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-28 | 2020-03-28 | Finished |  |  | 2020-03-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-30 | Finished |  |  | 100 | 2020-06-20 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0119-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL5-2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-2S180,180S/27F | HVF-5 | 1600 | 180 | 27 | 27 |  | 6850000 | Bangkok | เขตบางกอกน้อย | 2018-10-21 | 2018-10-21 | Finished | [34 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-06 | 2020-02-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-28 | 2020-03-28 | Finished |  |  | 2020-03-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-30 | Finished |  |  | 100 | 2020-06-20 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0120-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL5-3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-12-28 |  | HVF-1600-2S180,180S/27F | HVF-5 | 1600 | 180 | 27 | 27 |  | 6850000 | Bangkok | เขตบางกอกน้อย | 2018-10-21 | 2018-10-21 | Finished | [34 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-06 | 2020-02-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-28 | 2020-03-28 | Finished |  |  | 2020-03-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-30 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-30 | Finished |  |  | 100 | 2020-06-20 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBK0121-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL6 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | HVF-1800-2S180,180S/29F | HVF-5 | 1800 | 180 | 29 | 29 |  | 7350000 | Bangkok | เขตบางกอกน้อย | 2020-06-01 | [36 empty] | 2018-08-24 | 2019-04-07 | 2019-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-01 | 2020-10-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2020-02-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2021-05-20 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001970 | 2018-08-24 |  |  |  | HDME000427 | 2018-12-21 | QC Passed
TBL0094-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL7-1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | OUG-1600-CO90,90S/5F | OUG-ON1 | 1600 | 90 | 5 | 5 |  | 2400000 | Bangkok | เขตบางกอกน้อย | 2018-10-11 | 2018-10-12 | Finished | [34 empty] | 2018-05-02 | 2018-08-18 | 2018-08-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-12 | 2018-12-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-12-07 | 2018-12-07 | Finished |  |  | 2018-12-07 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2019-08-15 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001717 | 2018-05-02 |  |  |  | HDME000393 | 2018-12-03 | QC Passed
TBL0095-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL7-2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | OUG-1600-CO90,90S/5F | OUG-ON1 | 1600 | 90 | 5 | 5 |  | 2400000 | Bangkok | เขตบางกอกน้อย | 1900-01-01 | 2018-09-12 | Finished | [34 empty] | 2018-05-02 | 2018-08-18 | 2018-08-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-12 | 2018-12-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-29 | 2019-01-29 | Finished |  |  | 2019-01-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2019-08-15 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001717 | 2018-05-02 |  |  |  | HDME000393 | 2018-12-03 | QC Passed
TBL0096-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL8-1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | OUG-1600-CO90,90S/5F | OUG-ON1 | 1600 | 90 | 5 | 5 |  | 2400000 | Bangkok | เขตบางกอกน้อย | 1900-01-01 | 2018-09-12 | Finished | [34 empty] | 2018-05-02 | 2018-08-18 | 2018-08-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-12 | 2018-12-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-12-07 | 2018-12-07 | Finished |  |  | 2018-12-07 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2019-08-15 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001717 | 2018-05-02 |  |  |  | HDME000393 | 2018-12-03 | QC Passed
TBL0097-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL8-2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | OUG-1600-CO90,90S/5F | OUG-ON1 | 1600 | 90 | 5 | 5 |  | 2400000 | Bangkok | เขตบางกอกน้อย | 1900-01-01 | 2018-09-12 | Finished | [34 empty] | 2018-05-02 | 2018-08-18 | 2018-08-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-12 | 2018-12-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-29 | 2019-01-29 | Finished |  |  | 2019-01-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2019-08-15 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001717 | 2018-05-02 |  |  |  | HDME000393 | 2018-12-03 | QC Passed
TAC1291-TH | HET | 61000156 | HO | ส่งมอบแล้ว | - | TH189049 | รพ.ศิริราช [อ.นวมิทรบพิตร 84 พรรษา] | EL9 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2017-08-28 | 2018-05-02 | 2018-08-31 |  | VFI-750-CO120,120S/26F | VFI-II | 750 | 120 | 26 | 26 |  | 3200000 | Bangkok | เขตบางกอกน้อย | 2019-10-21 | [36 empty] | 2018-05-25 | 2018-11-22 | 2018-11-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-14 | 2019-05-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-07-01 | 2019-07-01 | Finished |  |  | 2019-07-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-05 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-05 | Finished |  |  | 100 | 2020-01-15 | Finished | CONSTRUCTION DELAY |  | 2020-05-08 | Finished |  |  | 2018-05-24 | Finished | [18 empty] | 2018-12-25 | Finished |  |  | 2019-04-01 | Finished |  |  | 2019-04-01 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-24 | Finished |  | pass |  |  |  |  | 1688 | 118 | 56 | 24 | 1886 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20001719 | 2018-05-25 |  |  |  | HDME000384 | 2018-11-21 | QC Passed
TAC1293-TH | HET | 61000158 | HO | ส่งมอบแล้ว | - | TH189099 | Nakhon Si Thammarat Hospital Dormitory | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2017-12-18 | 2018-05-18 | 2018-07-18 |  | VFI-900-CO90,90S/7F | VFI-II | 900 | 90 | 7 | 7 |  | 1498000 | Nakhon Si Thammarat | ตำบลในเมือง | 2018-05-15 | 2018-05-15 | Finished | [34 empty] | 2018-05-03 | 2018-08-06 | 2018-08-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-04 | 2018-10-19 | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 2018-01-01 | Finished |  |  | 100 | [41 empty] | 2018-01-01 | 2018-10-10 | 2018-10-10 | Finished |  |  | 2018-10-10 | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 2019-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2019-08-13 | Finished | OTHERS |  | 2019-11-06 | Finished |  |  | 2018-01-09 | Finished | [18 empty] | 2018-08-09 | Finished |  |  | 2018-08-31 | Finished |  |  | 2018-08-31 | Finished |  |  | 2019-11-06 | Finished | [13 empty] | no pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20001755 | 2018-05-03 |  |  |  | HDME000257 | 2018-08-09
TAJ0202-TH | HET | 61000163 | HO | ส่งมอบแล้ว | - | TH189106 | Residence @Pratunam | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2017-12-21 | 2018-03-21 | 2018-04-21 | 2020-07-08 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1050000 | Bangkok | แขวงพญาไท | 2018-05-15 | 2018-05-04 | Finished | [34 empty] | 2018-03-14 | 2018-05-04 | 2018-05-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-06-04 | 2018-07-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-10-03 | 2018-10-03 | Finished |  |  | 2018-10-03 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-09-28 | Finished | POWER SUPPLY DELAY |  | 2020-07-20 | Finished |  |  | 2018-02-01 | Finished | [18 empty] | 2018-05-02 | Finished |  |  | 2018-05-04 | Finished |  |  | 2018-05-04 | Finished |  |  | 2020-07-20 | Finished | [13 empty] | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20001785 | 2018-03-14 |  |  |  | HDME000149 | 2018-05-02 | QC Passed
TAC1307-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | EL-A-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-08-20 | 2021-03-21 | VFI-1350-CO120,120S/13F | VFI-II | 1350 | 120 | 9 | 13 |  | 2080000 | Bangkok | เขตจตุจักร | 2018-09-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-25 | 2018-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-01 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-06-25 | 2019-06-25 | Finished |  |  | 2019-06-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-01-10 | 2000-01-01 | 2020-01-10 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2020-04-30 | Finished | POWER SUPPLY DELAY |  | 2020-06-12 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-08-10 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-08-14 | Finished |  |  | 2020-06-12 | Finished | [13 empty] | no pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 20 | 20 | 98.23 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000261 | 2018-08-10
TAC1308-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | FL-A-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-09-15 | 2021-05-29 | VFI-1600-CO105,105S/14F | VFI-II | 1600 | 105 | 14 | 14 |  | 1880000 | Bangkok | เขตจตุจักร | 2018-07-24 | 2018-10-20 | Finished | [34 empty] | 2018-08-08 | 2018-06-25 | 2018-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-24 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-08-21 | 2018-08-21 | Finished |  |  | 2018-08-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-21 | 2021-05-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-04-29 | Finished | POWER SUPPLY DELAY |  | 2021-04-30 | Finished |  |  | 2018-04-04 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2018-06-27 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002201 | 2018-07-05 |  |  |  | HDME000212 | 2018-06-27 | QC Passed
TAC1312-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | FL-B-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-09-15 | 2021-05-29 | VFI-1600-CO60,60S/9F | VFI-II | 1600 | 60 | 9 | 9 |  | 1735000 | Bangkok | เขตจตุจักร | 2018-07-24 | 2018-10-20 | Finished | [34 empty] | 2018-08-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-24 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-08-21 | 2018-08-21 | Finished |  |  | 2018-08-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-11 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-04-29 | Finished | POWER SUPPLY DELAY |  | 2021-04-30 | Finished |  |  | 2018-04-04 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2018-06-27 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-06-28 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002202 | 2018-07-05 |  |  |  | HDME000212 | 2018-06-27 | QC Passed
TAC1302-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | FL-C-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-09-15 | 2021-05-29 | VFI-1600-CO60,60S/8F | VFI-II | 1600 | 60 | 8 | 8 |  | 1710000 | Bangkok | เขตจตุจักร | 2018-07-24 | 2018-10-20 | Finished | [34 empty] | 2018-08-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-24 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-08-21 | 2018-08-21 | Finished |  |  | 2018-08-21 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-10-02 | 2021-06-21 | 2020-10-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-04-29 | Finished | POWER SUPPLY DELAY |  | 2021-04-30 | Finished |  |  | 2018-04-04 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2018-07-17 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002200 | 2018-07-05 |  |  |  | HDME000238 | 2018-07-17 | QC Passed
TAC1303-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-A-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-06-08 |  | VFI-1350-CO120,120S/13F | VFI-II | 1350 | 120 | 13 | 13 |  | 2130000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-25 | 2018-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-20 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-01 | 2019-04-01 | Finished |  |  | 2019-04-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2019-10-02 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-08-10 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-08-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000261 | 2018-08-10 | QC Passed
TAC1304-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-A-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-07-05 |  | VFI-1350-CO120,120S/13F | VFI-II | 1350 | 120 | 13 | 13 |  | 2130000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-25 | 2018-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-20 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-01 | 2019-04-01 | Finished |  |  | 2019-04-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2019-10-02 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-08-10 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-08-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000261 | 2018-08-10 | QC Passed
TAC1305-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-A-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-08-20 |  | VFI-1350-CO120,120S/13F | VFI-II | 1350 | 120 | 13 | 13 |  | 2130000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-25 | 2018-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-20 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-01 | 2019-04-01 | Finished |  |  | 2019-04-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-17 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2019-10-02 | Finished | POWER SUPPLY DELAY |  | 2020-03-10 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-25 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-03-10 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000206 | 2018-06-25 | QC Passed
TAC1306-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-A-4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-08-20 |  | VFI-1350-CO120,120S/13F | VFI-II | 1350 | 120 | 13 | 13 |  | 2130000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-25 | 2018-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-20 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-01 | 2019-04-01 | Finished |  |  | 2019-04-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-17 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2019-10-02 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-25 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000206 | 2018-06-25 | QC Passed
TAC1309-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-B-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-06-08 |  | VFI-1350-CO105,105S/7F | VFI-II | 1350 | 105 | 7 | 7 |  | 1680000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-01 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-16 | 2019-01-16 | Finished |  |  | 2019-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2019-10-02 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000200 | 2018-06-19 | QC Passed
TAC1310-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-B-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-08-20 |  | VFI-1350-CO105,105S/7F | VFI-II | 1350 | 105 | 7 | 7 |  | 1680000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-01 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-16 | 2019-01-16 | Finished |  |  | 2019-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2019-10-02 | Finished | POWER SUPPLY DELAY |  | 2020-03-11 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-03-11 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000200 | 2018-06-19 | QC Passed
TAC1311-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-B-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-07-05 |  | VFI-1350-CO105,105S/7F | VFI-II | 1350 | 105 | 7 | 7 |  | 1680000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-10-20 | Finished | [34 empty] | 2018-05-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-01 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-01-16 | 2019-01-16 | Finished |  |  | 2019-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2019-10-02 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000200 | 2018-06-19 | QC Passed
TAC1299-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-C-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-06-08 |  | VFI-1350-CO105,105S/7F | VFI-II | 1350 | 105 | 7 | 7 |  | 1680000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-09-12 | Finished | [34 empty] | 2018-05-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-01 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-03-18 | 2019-03-18 | Finished |  |  | 2019-03-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-17 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2020-03-08 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000200 | 2018-06-19 | QC Passed
TAC1300-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-C-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-08-20 |  | VFI-1350-CO105,105S/7F | VFI-II | 1350 | 105 | 7 | 7 |  | 1680000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-09-12 | Finished | [34 empty] | 2018-05-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-01 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-03-18 | 2019-03-18 | Finished |  |  | 2019-03-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-07-15 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2020-03-08 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000200 | 2018-06-19 | QC Passed
TAC1301-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-C-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-07-05 |  | VFI-1350-CO105,105S/7F | VFI-II | 1350 | 105 | 7 | 7 |  | 1680000 | Bangkok | เขตจตุจักร | 1900-01-01 | 2018-09-12 | Finished | [34 empty] | 2018-05-08 | 2018-06-20 | 2018-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-09-01 | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-03-18 | 2019-03-18 | Finished |  |  | 2019-03-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | 2020-03-08 | Finished | POWER SUPPLY DELAY |  | 2020-02-21 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-19 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2020-02-21 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-08 |  |  |  | HDME000200 | 2018-06-19 | QC Passed
TAJ0203-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-D-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-06-01 | 2021-03-21 | P-1000-CO105W1,105S/6F | UAG-SN1 | 1000 | 105 | 6 | 6 |  | 1030000 | Bangkok | เขตจตุจักร | 2018-12-21 | 2018-10-20 | Finished | [34 empty] | 2018-04-08 | 2018-06-14 | 2018-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-21 | 2019-08-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-01 | 2019-09-01 | Finished |  |  | 2019-09-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-02-18 | 2000-01-01 | 2020-02-18 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-02-28 | Finished | CONSTRUCTION DELAY |  | 2021-02-28 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-11 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2021-02-28 | Finished | [13 empty] | no pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-10 |  |  |  | HDME000189 | 2018-06-11
TAJ0204-TH | HET | 61000166 | HO | ส่งมอบแล้ว | - | TH189095 | Primo Posto | PL-D-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2017-07-19 | 2018-04-05 | 2018-06-01 | 2021-03-21 | P-1000-CO105W1,105S/6F | UAG-SN1 | 1000 | 105 | 6 | 6 |  | 1030000 | Bangkok | เขตจตุจักร | 2018-12-21 | 2018-10-20 | Finished | [34 empty] | 2018-04-08 | 2018-06-14 | 2018-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-21 | 2019-08-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-01 | 2019-09-01 | Finished |  |  | 2019-09-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-02-28 | Finished | PARTIAL DELIVERY |  | 2021-02-28 | Finished |  |  | 2018-04-04 | Finished | [18 empty] | 2018-06-11 | Finished |  |  | 2018-09-06 | Finished |  |  | 2018-09-14 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002035 | 2018-05-10 |  |  |  | HDME000189 | 2018-06-11 | QC Passed
TAD0324-TH | HET | 61000192 | HO | ส่งมอบแล้ว | - | TH189132 | รพ.ท่าโรงช้าง [อ.ผู้ป่วยใน 144 เตียง] | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2018-02-08 | 2018-11-08 | 2019-03-08 |  | B-1000-2S90,90S/8F | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1979500 | Surat Thani | อำเภอพุนพิน | 2018-12-20 | 2018-11-28 | Finished | [34 empty] | 2018-11-01 | 2018-12-20 | 2018-12-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-22 | 2019-02-22 | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 100 | [41 empty] | 2018-11-01 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2019-06-04 | 2000-01-01 | 2019-06-04 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-04 | Finished | [6 empty] | 90 | 2019-05-03 | Finished | INSTALLATION DELAY |  | 2019-06-06 | Finished |  |  | 2018-02-20 | Finished | [18 empty] | 2018-12-11 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-21 | Finished |  |  | 2019-06-06 | Finished | [13 empty] | no pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20002100 | 2018-11-01 |  |  |  | HDME000407 | 2018-12-11
TAD0325-TH | HET | 61000192 | HO | ส่งมอบแล้ว | - | TH189132 | รพ.ท่าโรงช้าง [อ.ผู้ป่วยใน 144 เตียง] | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2018-02-08 | 2018-11-08 | 2019-03-08 |  | B-1000-2S90,90S/8F | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1979500 | Surat Thani | อำเภอพุนพิน | 2018-12-20 | 2018-11-28 | Finished | [34 empty] | 2018-11-01 | 2018-12-20 | 2018-12-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-22 | 2019-02-22 | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 100 | [41 empty] | 2018-11-01 | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 2019-03-02 | Finished |  |  | 100 | 2019-06-04 | 2000-01-01 | 2019-06-04 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-04 | Finished | [6 empty] | 90 | 2019-05-03 | Finished | INSTALLATION DELAY |  | 2019-06-06 | Finished |  |  | 2018-02-20 | Finished | [18 empty] | 2018-12-11 | Finished |  |  | 2018-12-20 | Finished |  |  | 2018-12-21 | Finished |  |  | 2019-06-06 | Finished | [13 empty] | no pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20002100 | 2018-11-01 |  |  |  | HDME000407 | 2018-12-11
TAJ0233-TH | HET | 61000195 | HO | ส่งมอบแล้ว | - | TH189139 | โรงแรมอ่าวนางบีซายน์ รีสอร์ท | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2018-02-05 | 2018-08-05 | 2018-10-05 | 2020-12-24 | P-600-CO60D,60S/3F | UAG-SN1 | 600 | 60 | 3 | 3 |  | 1230500 | Krabi | อำเภอเมืองกระบี่ | 2018-05-11 | 2018-05-11 | Finished | [34 empty] | 2018-07-29 | 2018-10-22 | 2018-10-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-11 | 2019-06-15 | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-01 | Finished |  |  | 100 | [41 empty] | 2018-11-01 | 2020-08-19 | 2020-08-19 | Finished |  |  | 2020-08-19 | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-19 | Finished |  |  | 100 | 2020-07-01 | 2020-09-08 | 2020-07-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-08 | Finished | [6 empty] | 90 | 2020-12-15 | Finished | POWER SUPPLY DELAY |  | 2020-12-30 | Finished |  |  | 2018-02-20 | Finished | [10 empty] | 2020-09-15 | Finished | [6 empty] | 2018-10-17 | Finished |  |  | 2018-12-04 | Finished |  |  | 2018-12-11 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20002083 | 2018-07-29 |  |  |  | HDME000332 | 2018-10-17 | QC Passed
TAJ0236-TH | HET | 61000197 | HO | ส่งมอบแล้ว | - | TH189136 | Siaminter Hotel @ Ratchawithi | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-12-29 | 2018-06-29 | 2018-09-29 |  | P-600-CO60W,60S/6F | UAG-SN1 | 600 | 60 | 6 | 6 |  | 963000 | Bangkok | เขตราชเทวี | 2019-04-22 | 2019-04-22 | Finished | [34 empty] | 2018-06-22 | 2019-03-14 | 2019-03-14 | Finished | PAYMENT DELAY | [13 empty] | 2019-04-16 | 2019-05-05 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-07-19 | 2019-07-19 | Finished |  |  | 2019-07-19 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2019-08-18 | Finished | CUSTOMER PAYMENT DELAY |  | 2019-08-15 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2019-03-11 | Finished |  |  | 2019-03-14 | Finished |  |  | 2019-03-18 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  | pass | 2019-09-24 | Finished |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002101 | 2018-06-22 |  |  |  | HDME000490 | 2019-03-11 | QC Passed
TAJ0237-TH | HET | 61000197 | HO | ส่งมอบแล้ว | - | TH189136 | Siaminter Hotel @ Ratchawithi | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2017-12-29 | 2018-06-29 | 2018-09-29 |  | P-600-CO60W,60S/6F | UAG-SN1 | 600 | 60 | 6 | 6 |  | 963000 | Bangkok | เขตราชเทวี | 2019-09-15 | [36 empty] | 2018-06-22 | 2019-03-14 | 2019-03-14 | Finished | PAYMENT DELAY | [13 empty] | 2019-12-11 | 2019-12-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-15 | 2020-01-15 | Finished |  |  | 2020-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2020-02-18 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-02-21 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2019-03-11 | Finished |  |  | 2019-03-14 | Finished |  |  | 2019-03-18 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass | 2020-08-25 | Finished |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002101 | 2018-06-22 |  |  |  | HDME000490 | 2019-03-11 | QC Passed
TBK0125-TH | HET | 61000201 | Install | เลยสัญญา HO | - | TH189117 | Siamese Sukhumvit 48 | F1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2017-10-03 | 2018-10-30 | 2018-12-31 | 2021-09-25 | HVF-1000-CO210,210S/41F | HVF-5 | 1000 | 210 | 41 | 41 |  | 5617500 | Bangkok | แขวงพระโขนง | 2019-02-14 | 2019-03-28 | Finished | [34 empty] | 2018-08-16 | 2019-04-18 | 2019-04-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-15 | 2019-10-31 | 2019-02-15 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-30 | Finished |  |  | 2019-04-14 | Finished |  |  | 2019-04-14 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-08-17 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | [41 empty] | 2020-02-15 | 2020-02-10 | 2020-02-10 | Finished |  |  | 2020-01-20 | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-21 | Finished | [6 empty] | 90 | 2021-09-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-03-19 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-03-19 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-04-23 | Finished | [17 empty] | pass |  |  |  |  | 2368 | 123 | 80 | 48 | 2619 | 0 | 0 | 0 | 4 | 4 | 99.85 | Red |  |  | 20002138 | 2018-08-16 |  |  |  | HDME000501 | 2019-03-19
TAE1183-TH | HET | 61000201 | Install | เลยสัญญา HO | - | TH189117 | Siamese Sukhumvit 48 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2017-10-03 | 2018-10-30 | 2019-01-28 | 2021-09-25 | UAG-1000-CO90,90S/8F | UAG-11G-A | 1000 | 90 | 8 | 8 |  | 1364250 | Bangkok | แขวงพระโขนง | 2019-11-15 | 2020-01-10 | Finished | [34 empty] | 2018-10-15 | 2019-12-03 | 2019-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-01 | 2019-12-20 | 2019-12-01 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-25 | Finished |  |  | 100 | [41 empty] | 2020-02-25 | 2019-12-02 | 2019-12-02 | Finished |  |  | 2019-12-02 | 2019-12-02 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-19 | Finished |  |  | 100 | 2020-08-21 | 2021-08-18 | 2020-08-21 | Finished |  |  | 2021-08-21 | Finished |  |  | 2021-08-18 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-03-19 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-12-02 | Finished |  |  | 2019-12-09 | Finished |  |  | 2019-12-10 | Finished | [17 empty] | pass |  |  |  |  | 676 | 84 | 24 | 16 | 800 | 0 | 0 | 0 | 1 | 1 | 99.88 | Red |  |  | 20002139 | 2018-10-15 |  |  |  | HDME000738 | 2019-12-02 | QC Passed
TAE1184-TH | HET | 61000201 | Install | เลยสัญญา HO | - | TH189117 | Siamese Sukhumvit 48 | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2017-10-03 | 2018-10-30 | 2019-01-28 | 2021-09-25 | UAG-1000-CO90,90S/8F | UAG-11G-A | 1000 | 90 | 8 | 8 |  | 1364250 | Bangkok | แขวงพระโขนง | 2019-11-15 | 2020-01-10 | Finished | [34 empty] | 2018-10-15 | 2019-12-03 | 2019-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-01 | 2019-12-20 | 2019-12-01 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-25 | Finished |  |  | 100 | [41 empty] | 2020-02-25 | 2019-12-02 | 2019-12-02 | Finished |  |  | 2019-12-02 | 2019-12-02 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-20 | Finished |  |  | 100 | 2020-08-21 | 2021-08-18 | 2020-08-21 | Finished |  |  | 2021-08-21 | Finished |  |  | 2021-08-18 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-03-19 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-12-02 | Finished |  |  | 2019-12-09 | Finished |  |  | 2019-12-10 | Finished | [17 empty] | pass |  |  |  |  | 676 | 84 | 24 | 16 | 800 | 0 | 0 | 0 | 1 | 1 | 99.88 | Red |  |  | 20002139 | 2018-10-15 |  |  |  | HDME000738 | 2019-12-02 | QC Passed
TBK0122-TH | HET | 61000201 | Install | เลยสัญญา HO | - | TH189117 | Siamese Sukhumvit 48 | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2017-10-03 | 2018-10-30 | 2018-12-31 | 2021-09-25 | HVF-1000-CO240,240S/40F | HVF-5 | 1000 | 240 | 40 | 40 |  | 5885000 | Bangkok | แขวงพระโขนง | 2019-02-14 | 2019-05-16 | Finished | [34 empty] | 2018-08-16 | 2019-06-08 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-15 | 2019-11-30 | 2019-02-15 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-05-13 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-08-17 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | [41 empty] | 2020-02-15 | 2020-02-15 | 2020-02-15 | Finished |  |  | 2020-02-21 | 2020-02-15 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-03-09 | Finished |  |  | 100 | 2021-04-09 | 2021-05-28 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-28 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-03-19 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-07-03 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-16 | Finished | [17 empty] | pass |  |  |  |  | 2319 | 122 | 72 | 48 | 2561 | 0 | 0 | 0 | 4 | 4 | 99.84 | Red |  |  | 20002138 | 2018-08-16 |  |  |  | HDME000585 | 2019-07-03 | QC Passed
TBK0123-TH | HET | 61000201 | Install | เลยสัญญา HO | - | TH189117 | Siamese Sukhumvit 48 | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2017-10-03 | 2018-10-30 | 2019-01-28 | 2021-09-25 | HVF-1000-CO240,240S/40F | HVF-5 | 1000 | 240 | 40 | 40 |  | 5885000 | Bangkok | แขวงพระโขนง | 2019-02-14 | 2019-05-16 | Finished | [34 empty] | 2018-08-16 | 2019-06-08 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-15 | 2019-11-30 | 2019-02-15 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-05-13 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-08-17 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | [41 empty] | 2020-02-15 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 2020-03-21 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-04-03 | Finished |  |  | 100 | 2021-04-09 | 2021-07-02 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-03-19 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-07-03 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-16 | Finished | [17 empty] | pass |  |  |  |  | 2319 | 122 | 72 | 48 | 2561 | 0 | 0 | 0 | 4 | 4 | 99.84 | Red |  |  | 20002138 | 2018-08-16 |  |  |  | HDME000585 | 2019-07-03 | QC Passed
TBK0124-TH | HET | 61000201 | Install | เลยสัญญา HO | - | TH189117 | Siamese Sukhumvit 48 | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2017-10-03 | 2018-10-30 | 2019-01-28 | 2021-09-25 | HVF-1000-CO240,240S/40F | HVF-5 | 1000 | 240 | 40 | 40 |  | 5885000 | Bangkok | แขวงพระโขนง | 2019-02-14 | 2019-05-16 | Finished | [34 empty] | 2018-08-16 | 2019-06-08 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-15 | 2019-11-30 | 2019-02-15 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-24 | Finished |  |  | 2019-10-03 | Finished |  |  | 2019-10-03 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-17 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | [41 empty] | 2020-02-15 | 2020-03-20 | 2020-03-20 | Finished |  |  | 2019-12-25 | 2020-03-21 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-08-14 | Finished |  |  | 100 | 2021-04-09 | 2021-05-28 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-28 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-03-19 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-07-03 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-16 | Finished | [17 empty] | pass |  |  |  |  | 2319 | 122 | 72 | 48 | 2561 | 0 | 0 | 0 | 4 | 4 | 99.84 | Red |  |  | 20002138 | 2018-08-16 |  |  |  | HDME000585 | 2019-07-03 | QC Passed
TAJ0248-TH | HET | 61000217 | HO | ส่งมอบแล้ว | - | TH189157 | Cattle Lives Saving For Merit Foundation | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2018-03-02 | 2018-07-02 | 2018-08-02 | 2021-01-31 | P-600-CO60D,60S/3F | UAG-SN1 | 600 | 60 | 3 | 3 |  | 1284000 | Bangkok | เขตสาทร | 2018-07-02 | 2018-07-02 | Finished | [34 empty] | 2018-06-25 | 2018-07-20 | 2018-07-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-02 | 2018-07-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-02-15 | 2019-02-15 | Finished |  |  | 2019-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-25 | 2021-06-10 | 2021-01-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-01-31 | Finished | CONSTRUCTION DELAY |  | 2020-12-30 | Finished |  |  | 2018-03-19 | Finished | [18 empty] | 2018-07-18 | Finished |  |  | 2018-07-24 | Finished |  |  | 2018-07-25 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass | 2021-06-22 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002311 | 2018-06-25 |  |  |  | HDME000239 | 2018-07-18 | QC Passed
TAE1186-TH | HET | 61000226 | HO | ส่งมอบแล้ว | - | TH189165 | Intercontinental Phuket Resort | LFP-C | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2018-02-16 | 2018-07-15 | 2018-09-15 | 2020-06-04 | UAG-1000-CO60,60S/3F | UAG-11G-A | 1000 | 60 | 3 | 3 |  | 1337500 | Phuket | อำเภอกะทู้ | 1900-01-01 | 2018-07-16 | Finished | [34 empty] | 2018-07-15 | 2018-09-17 | 2018-09-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-17 | 2018-08-05 | 2018-09-21 | Finished |  |  | 2018-09-25 | Finished |  |  | 2018-09-27 | Finished |  |  | 2018-09-30 | Finished |  |  | 2018-10-01 | Finished |  |  | 2018-10-03 | Finished |  |  | 2018-10-04 | Finished |  |  | 2018-10-06 | Finished |  |  | 2018-10-08 | Finished |  |  | 2018-10-10 | Finished |  |  | 100 | [41 empty] | 2018-10-10 | 2019-02-01 | 2019-02-01 | Finished |  |  | 2019-02-01 | 2019-03-21 | Finished |  |  | 2019-04-17 | Finished |  |  | 2019-04-19 | Finished |  |  | 100 | 2021-05-13 | 2020-07-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2020-04-20 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-06-11 | Finished |  |  | 2018-06-21 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2018-09-17 | Finished |  |  | 2019-01-23 | Finished |  |  | 2019-01-24 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-15 | Finished |  | pass |  |  |  |  | 400 | 80 | 16 | 16 | 512 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002381 | 2018-07-15 |  |  |  | HDME000295 | 2018-09-17 | QC Passed
TAJ0264-TH | HET | 61000230 | HO | ยังอยู่ในสัญญา HO | - | TH189169 | Castello Della valle (Building C) | 1C | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2018-03-09 | 2018-10-09 | 2018-12-09 | 2021-10-10 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1070000 | Nakhon Ratchasima | ตำบลโป่งตาลอง | 2018-10-09 | 2018-10-16 | Finished | [34 empty] | 2018-10-02 | 2018-11-02 | 2018-11-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-16 | 2018-10-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-28 | 2000-01-01 | 2020-12-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-11 | Finished | [6 empty] | 90 | 2021-11-12 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-03-31 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2018-10-31 | Finished |  |  | 2018-11-01 | Finished |  |  | 2018-11-11 | Finished | [17 empty] | no pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Green |  |  | 20002426 | 2018-10-02 |  |  |  | HDME000351 | 2018-10-31
TAJ0265-TH | HET | 61000231 | HO | ส่งมอบแล้ว | - | TH189171 | Home Khun Tum | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2018-03-09 | 2018-07-09 | 2018-08-09 | 2020-06-02 | P-600-CO60D,60S/5F | UAG-SN1 | 600 | 60 | 5 | 5 |  | 1300000 | Bangkok | แขวงบางซื่อ | 2018-10-15 | 2018-11-09 | Finished | [34 empty] | 2018-07-02 | 2018-10-29 | 2018-10-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-15 | 2018-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-05-07 | 2020-05-07 | Finished |  |  | 2020-05-05 | 2020-05-08 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-05-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-20 | Finished |  |  | 2021-09-06 | Finished |  |  | 100 | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished |  |  | 2018-03-31 | Finished | [18 empty] | 2018-10-25 | Finished |  |  | 2018-11-14 | Finished |  |  | 2018-11-16 | Finished |  |  | 2020-06-23 | Finished | [13 empty] | no pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002425 | 2018-07-02 |  |  |  | HDME000340 | 2018-10-25
TEB0072-TH | HET | 61000240 | Install | เลยสัญญา HO | - | TH189180 | Baan Tiew Khao, Khao Yai (No. L1-L2) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2018-03-14 | 2018-06-14 | 2018-08-14 | 2021-09-25 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 4 | 4 |  | 1000000 | Nakhon Ratchasima | ตำบลหนองน้ำแดง | 2018-11-23 | 2019-01-07 | Finished | [34 empty] | 2018-05-30 | 2018-07-15 | 2018-07-15 | Finished | CONSTRUCTION STOP | [13 empty] | 2020-05-15 | 2020-05-30 | 2020-05-24 | Finished |  |  | 2020-05-24 | Finished |  |  | 2020-05-24 | Finished |  |  | 2020-05-24 | Finished |  |  | 2020-05-24 | Finished |  |  | 2020-05-24 | Finished |  |  | 2020-05-29 | Finished |  |  | 2020-05-29 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-03 | Finished |  |  | 100 | [41 empty] | 2020-06-03 | 2020-11-16 | 2020-11-16 | Finished |  |  | 2020-10-31 | 2020-11-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished |  |  | 2021-02-17 | Finished | [10 empty] | 50 | 2021-12-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-06-21 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2018-07-03 | Finished |  |  | 2018-08-01 | Finished |  |  | 2018-08-02 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 16 | 16 | 93.77 | Red |  |  | 20002565 | 2018-05-30 |  |  |  | HDME000217 | 2018-07-03
TEB0073-TH | HET | 61000240 | Install | ยังอยู่ในสัญญา HO | - | TH189180 | Baan Tiew Khao, Khao Yai (No. L1-L2) | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2018-03-14 | 2018-06-14 | 2018-08-14 | 2021-11-04 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 4 | 4 |  | 1000000 | Nakhon Ratchasima | ตำบลหนองน้ำแดง | 2021-10-01 | [36 empty] | 2018-05-30 | 2018-07-15 | 2018-07-15 | Finished | CONSTRUCTION STOP | [13 empty] | 2021-10-08 | 2021-11-07 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-17 | [12 empty] | 0 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished | [14 empty] | 25 | 2021-12-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-06-21 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2018-07-03 | Finished |  |  | 2018-08-01 | Finished |  |  | 2018-08-02 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 4 | 16 | 245 | 4.67 | Green |  |  | 20002565 | 2018-05-30 |  |  |  | HDME000217 | 2018-07-03
TAD0331-TH | HET | 61000241 | HO | ส่งมอบแล้ว | - | TH189179 | รพ.ศรีธัญญา กรมสุขภาพจิต | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2018-03-23 | 2018-11-23 | 2019-02-15 | 2020-04-15 | B-1000-2S105,105S/9F | B-II(VFI-II) | 1000 | 105 | 9 | 9 |  | 1701300 | Nonthaburi | อ.เมืองนนทบุรี | 2020-02-21 | 2020-02-21 | Finished | [34 empty] | 2018-11-15 | 2018-11-26 | 2018-11-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-21 | 2019-01-21 | 2019-04-05 | Finished |  |  | 2019-04-08 | Finished |  |  | 2019-04-10 | Finished |  |  | 2019-04-19 | Finished |  |  | 2019-04-23 | Finished |  |  | 2019-04-26 | Finished |  |  | 2019-04-28 | Finished |  |  | 2019-05-04 | Finished |  |  | 2019-05-08 | Finished |  |  | 2019-05-14 | Finished |  |  | 100 | [41 empty] | 2019-05-14 | 2019-09-14 | 2019-09-14 | Finished |  |  | 2019-09-14 | 2019-09-14 | Finished |  |  | 2020-01-06 | Finished |  |  | 2020-01-06 | Finished |  |  | 100 | 2020-05-07 | 2020-06-08 | 2020-05-07 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-08 | Finished |  |  | 100 | 2020-04-15 | Finished | POWER SUPPLY DELAY |  | 2020-04-17 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2018-12-10 | Finished |  |  | 2018-12-12 | Finished |  |  | 2018-12-21 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  | pass | 2020-06-17 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002614 | 2018-11-15 |  |  |  | HDME000404 | 2018-12-10 | QC Passed
TAD0334-TH | HET | 61000241 | HO | ส่งมอบแล้ว | - | TH189179 | รพ.ศรีธัญญา กรมสุขภาพจิต | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2018-03-23 | 2018-11-23 | 2019-02-15 | 2020-04-15 | B-1000-2S105,105S/9F | B-II(VFI-II) | 1000 | 105 | 9 | 9 |  | 1679900 | Nonthaburi | อ.เมืองนนทบุรี | 2020-02-21 | 2020-02-21 | Finished | [34 empty] | 2018-11-15 | 2018-11-26 | 2018-11-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-21 | 2019-08-21 | 2019-04-05 | Finished |  |  | 2019-04-08 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-04-24 | Finished |  |  | 2019-04-27 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-05-07 | Finished |  |  | 2019-05-12 | Finished |  |  | 2019-05-15 | Finished |  |  | 2019-05-20 | Finished |  |  | 100 | [41 empty] | 2019-05-20 | 2019-09-14 | 2019-09-14 | Finished |  |  | 2019-09-14 | 2019-09-14 | Finished |  |  | 2020-01-06 | Finished |  |  | 2020-01-06 | Finished |  |  | 100 | 2020-05-07 | 2020-06-08 | 2020-05-07 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-08 | Finished |  |  | 100 | 2020-04-15 | Finished | POWER SUPPLY DELAY |  | 2020-04-17 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2018-12-10 | Finished |  |  | 2018-12-12 | Finished |  |  | 2018-12-21 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  | pass | 2020-06-17 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002614 | 2018-11-15 |  |  |  | HDME000404 | 2018-12-10 | QC Passed
TAJ0270-TH | HET | 61000242 | HO | ส่งมอบแล้ว | - | TH189178 | M.N. Living Rama 8 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-03-20 | 2018-08-20 | 2018-10-20 | 2020-09-01 | P-600-CO60W,60S/6F | UAG-SN1 | 600 | 60 | 6 | 6 |  | 1080700 | Bangkok | แขวงบางขุนพรหม เขตพระนคร | 2018-08-20 | 2019-01-05 | Finished | [34 empty] | 2018-08-13 | 2018-09-24 | 2018-09-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-04 | 2020-04-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-04-15 | 2020-04-15 | Finished |  |  | 2020-04-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-18 | 2020-05-18 | 2020-05-18 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-18 | Finished | [6 empty] | 90 | 2020-09-01 | Finished | CONSTRUCTION DELAY |  | 2020-06-12 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2018-09-21 | Finished |  |  | 2018-10-31 | Finished |  |  | 2018-10-31 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20002564 | 2018-08-13 |  |  |  | HDME000301 | 2018-09-21 | QC Passed
TAJ0271-TH | HET | 61000242 | HO | ส่งมอบแล้ว | - | TH189178 | M.N. Living Rama 8 | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-03-20 | 2018-08-20 | 2018-10-20 | 2020-09-01 | P-600-CO60W,60S/7F | UAG-SN1 | 600 | 60 | 7 | 7 |  | 1091400 | Bangkok | แขวงบางขุนพรหม เขตพระนคร | 2018-08-20 | 2019-01-05 | Finished | [34 empty] | 2018-08-13 | 2018-09-24 | 2018-09-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-04 | 2020-04-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-04-15 | 2020-04-15 | Finished |  |  | 2020-04-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-05-18 | 2021-01-19 | 2020-05-18 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-18 | Finished |  |  | 2021-01-19 | Finished |  |  | 100 | 2020-09-01 | Finished | CONSTRUCTION DELAY |  | 2020-06-12 | Finished |  |  | 2018-05-02 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2018-09-21 | Finished |  |  | 2018-10-31 | Finished |  |  | 2018-10-31 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20002564 | 2018-08-13 |  |  |  | HDME000301 | 2018-09-21 | QC Passed
TAJ0280-TH | HET | 61000252 | HO | ยังอยู่ในสัญญา HO | - | TH199002 | Castello Della valle (Building A) | 1A | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2018-04-05 | 2019-01-05 | 2019-03-05 | 2021-10-10 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1070000 | Nakhon Ratchasima | ตำบลโป่งตาลอง | 2018-08-24 | 2018-08-25 | Finished | [34 empty] | 2018-12-29 | 2019-01-23 | 2019-01-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-01 | 2019-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-12-01 | 2020-12-01 | Finished |  |  | 2020-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-11 | 2000-01-01 | 2021-02-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished | [6 empty] | 90 | 2021-11-12 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-05-24 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-01-09 | Finished |  |  | 2019-01-23 | Finished |  |  | 2019-01-24 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Green |  |  | 20002763 | 2018-12-29 |  |  |  | HDME000434 | 2019-01-09
TAJ0281-TH | HET | 61000253 | HO | ยังอยู่ในสัญญา HO | - | TH199003 | Castello Della valle (Building D) | 1D | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2018-04-05 | 2019-03-05 | 2019-05-05 | 2021-10-10 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1070000 | Nakhon Ratchasima | ตำบลโป่งตาลอง | 2019-01-05 | 2019-02-01 | Finished | [34 empty] | 2019-02-26 | 2019-03-05 | 2019-03-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-01 | 2019-10-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-04-01 | 2020-04-01 | Finished |  |  | 2020-04-01 | 2020-04-04 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-07 | Finished |  |  | 100 | 2021-05-11 | 2000-01-01 | 2021-05-11 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-11 | Finished | [6 empty] | 90 | 2021-11-12 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-05-24 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-03-04 | Finished |  |  | 2019-03-05 | Finished |  |  | 2019-03-07 | Finished | [17 empty] | no pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 1 | 1 | 99.83 | Green |  |  | 20002762 | 2019-02-26 |  |  |  | HDME000485 | 2019-03-04
TAC1363-TH | HET | 61000262 | HO | ส่งมอบแล้ว | - | TH199005 | PS Surat Thani | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | TEERASAK JUNTHAWEE | 2018-04-15 | 2019-03-15 | 2019-05-15 | 2020-11-24 | VFI-750-CO60,60S/7F | VFI-II | 750 | 60 | 7 | 7 |  | 1391000 | Surat Thani | อำเภอเมืองสุราษฎร์ธานี | 2020-05-10 | 2020-04-24 | Finished | [34 empty] | 2019-03-08 | 2019-04-29 | 2019-04-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-10 | 2020-05-24 | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-05 | Finished |  |  | 100 | [41 empty] | 2020-06-05 | 2020-09-15 | 2020-09-15 | Finished |  |  | 2020-09-15 | 2020-09-15 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-26 | Finished |  |  | 100 | 2020-06-01 | 2000-01-01 | 2020-06-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-09-08 | Finished |  |  | 100 | 2020-10-10 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2018-08-02 | Finished | [18 empty] | 2019-04-29 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-05 | Finished |  |  | 2020-12-08 | Finished | [13 empty] | no pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003827 | 2019-03-08 |  |  |  | HDME000526 | 2019-04-29
TAJ0297-TH | HET | 61000269 | HO | ส่งมอบแล้ว | - | TH189202 | Bangkok Hospital (Building I) | I-03 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2017-12-20 | 2018-07-30 | 2018-09-30 |  | P-1500-CO90,90S/9F | UAG-SN1 | 1500 | 90 | 9 | 9 |  | 2250000 | Bangkok | ถนนเพชรบุรีตัดใหม่ | 2019-01-30 | 2019-01-28 | Finished | [34 empty] | 2018-08-20 | 2019-05-11 | 2019-05-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-04-29 | 2019-07-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-08-02 | 2019-08-02 | Finished |  |  | 2019-08-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-10 | Finished |  |  | 100 | 2020-02-25 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2020-03-10 | Finished |  |  | 2018-06-05 | Finished | [18 empty] | 2019-05-11 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-24 | Finished |  |  | 2020-03-10 | Finished | [13 empty] | no pass |  |  |  |  | 585 | 84 | 24 | 16 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003102 | 2018-08-20 |  |  |  | HDME000531 | 2019-05-11
TAD0344-TH | HET | 61000272 | HO | ส่งมอบแล้ว | - | TH199008 | Bangsaphan Hospital | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2018-05-04 | 2019-02-04 | 2019-05-04 | 2021-02-02 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1500000 | Prachuap Khiri Khan | อำเภอบางสะพาน | 2020-04-20 | 2020-04-20 | Finished | [34 empty] | 2019-01-28 | 2019-02-15 | 2019-02-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-20 | 2020-04-23 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | [41 empty] | 2020-06-24 | 2021-01-21 | 2021-01-21 | Finished |  |  | 2020-11-15 | 2021-01-21 | Finished |  |  | 2021-01-23 | Finished |  |  | 2020-01-26 | Finished |  |  | 100 | 2021-05-13 | 2021-05-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-02-15 | Finished | CONSTRUCTION DELAY |  | 2021-02-17 | Finished |  |  | 2018-05-31 | Finished | [10 empty] | 2021-02-17 | Finished | [6 empty] | 2019-02-11 | Finished |  |  | 2019-02-15 | Finished |  |  | 2019-02-21 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003069 | 2019-01-28 |  |  |  | HDME000466 | 2019-02-11 | QC Passed
TAD0345-TH | HET | 61000272 | HO | ส่งมอบแล้ว | - | TH199008 | Bangsaphan Hospital | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2018-05-04 | 2019-02-04 | 2019-05-04 | 2021-02-02 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1500000 | Prachuap Khiri Khan | อำเภอบางสะพาน | 2020-04-20 | 2020-04-20 | Finished | [34 empty] | 2019-01-28 | 2019-02-15 | 2019-02-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-20 | 2020-04-23 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | [41 empty] | 2020-06-24 | 2021-01-21 | 2021-01-21 | Finished |  |  | 2020-11-15 | 2021-01-22 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-28 | Finished |  |  | 100 | 2021-05-13 | 2021-05-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-02-15 | Finished | CONSTRUCTION DELAY |  | 2021-02-17 | Finished |  |  | 2018-05-31 | Finished | [10 empty] | 2021-02-17 | Finished | [6 empty] | 2019-02-11 | Finished |  |  | 2019-02-15 | Finished |  |  | 2019-02-21 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003069 | 2019-01-28 |  |  |  | HDME000466 | 2019-02-11 | QC Passed
TAJ0312-TH | HET | 61000276 | HO | ส่งมอบแล้ว | - | TH189210 | Ratchaphruek House 5 Floor | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 | Somsak Denpraphat | CHALIDA NONTHAPAORAYA | 2018-05-14 | 2018-10-14 | 2018-12-14 | 2020-10-10 | P-600-CO60D,60S/5F | UAG-SN1 | 600 | 60 | 5 | 5 |  | 1370000 | Bangkok | แขวงคูหาสวรรค์ | 2018-11-15 | 2018-11-15 | Finished | [34 empty] | 2018-10-07 | 2018-11-09 | 2018-11-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-15 | 2018-12-15 | 2018-11-15 | Finished |  |  | 2018-11-17 | Finished |  |  | 2018-11-19 | Finished |  |  | 2018-11-23 | Finished |  |  | 2018-11-27 | Finished |  |  | 2018-11-30 | Finished |  |  | 2018-12-03 | Finished |  |  | 2018-12-06 | Finished |  |  | 2018-12-10 | Finished |  |  | 2018-12-15 | Finished |  |  | 100 | [41 empty] | 2018-12-15 | 2020-05-18 | 2020-05-18 | Finished |  |  | 2020-07-17 | 2020-05-19 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-06-03 | Finished |  |  | 100 | 2020-06-12 | 2021-07-21 | 2020-06-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2020-11-15 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2018-06-05 | Finished | [18 empty] | 2018-11-07 | Finished |  |  | 2018-11-09 | Finished |  |  | 2018-11-13 | Finished |  |  | 2020-12-08 | Finished | [13 empty] | pass (defect) |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003103 | 2018-10-07 |  |  |  | HDME000353 | 2018-11-07 | QC Passed
TAJ0315-TH | HET | 61000278 | HO | ส่งมอบแล้ว | - | TH189211 | Building 7 Floor, Sukhumvit 38 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-05-15 | 2018-11-15 | 2019-02-15 |  | P-1000-CO60W2,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1267000 | Bangkok | เขตคลองเตย | 2019-02-15 | 2019-02-01 | Finished | [34 empty] | 2018-11-08 | 2019-01-16 | 2019-01-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-01 | 2019-05-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-20 | 2019-12-20 | Finished |  |  | 2019-12-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-03-20 | 2021-08-13 | 2020-03-20 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | 2020-02-25 | Finished | POWER SUPPLY DELAY |  | 2020-02-27 | Finished |  |  | 2018-05-31 | Finished | [18 empty] | 2019-01-14 | Finished |  |  | 2019-01-16 | Finished |  |  | 2019-01-17 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003109 | 2018-11-08 |  |  |  | HDME000439 | 2019-01-14 | QC Passed
TAJ0316-TH | HET | 61000278 | HO | ส่งมอบแล้ว | - | TH189211 | Building 7 Floor, Sukhumvit 38 | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2018-05-15 | 2018-11-15 | 2019-02-15 |  | P-1000-CO60W2,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1267000 | Bangkok | เขตคลองเตย | 2019-02-15 | 2019-02-01 | Finished | [34 empty] | 2018-11-08 | 2019-01-16 | 2019-01-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-01 | 2019-05-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-20 | 2019-12-20 | Finished |  |  | 2019-12-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-03-20 | 2000-01-01 | 2020-03-20 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | 2020-02-25 | Finished | POWER SUPPLY DELAY |  | 2020-02-27 | Finished |  |  | 2018-05-31 | Finished | [18 empty] | 2019-01-14 | Finished |  |  | 2019-01-16 | Finished |  |  | 2019-01-17 | Finished |  |  | 2020-02-27 | Finished | [13 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003109 | 2018-11-08 |  |  |  | HDME000439 | 2019-01-14
TAJ0319-TH | HET | 61000281 | HO | ส่งมอบแล้ว | - | TH189216 | อาคารบ้านพักอาศัย 3 ชั้น | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2018-05-18 | 2018-08-18 | 2018-09-18 | 2020-12-01 | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1144900 | Bangkok | เขตยานนาวา | 2018-08-18 | 2019-01-22 | Finished | [34 empty] | 2018-08-11 | 2018-08-30 | 2018-08-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-08-18 | 2018-08-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-10-01 | 2019-10-01 | Finished |  |  | 2019-10-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2019-06-21 | 2020-06-26 | 2019-06-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-26 | Finished | [6 empty] | 90 | 2021-03-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-29 | Finished |  |  | 2018-06-13 | Finished | [18 empty] | 2018-08-30 | Finished |  |  | 2018-08-30 | Finished |  |  | 2018-08-30 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  | pass | 2021-05-01 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20003150 | 2018-08-11 |  |  |  | HDME000277 | 2018-08-30 | QC Passed
TAJ0326-TH | HET | 61000288 | HO | ส่งมอบแล้ว | - | TH189222 | Building Beside Market Rama 5 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 | Somsak Denpraphat | KITTITUCH MONGKOLKULASAB | 2018-05-28 | 2018-09-28 | 2018-11-28 | 2020-10-10 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1190000 | Nonthaburi | อำเภอบางกรวย | 2020-03-14 | 2020-03-14 | Finished | [34 empty] | 2018-09-21 | 2018-11-02 | 2018-11-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-07-18 | 2019-08-18 | 2019-07-12 | Finished |  |  | 2019-07-15 | Finished |  |  | 2019-07-17 | Finished |  |  | 2019-07-19 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-07 | Finished |  |  | 100 | [41 empty] | 2019-08-07 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-06-05 | 2020-06-20 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-08 | Finished |  |  | 100 | 2021-05-13 | 2021-03-22 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | 2020-11-15 | Finished | OTHERS |  | 2020-12-08 | Finished |  |  | 2018-06-13 | Finished | [18 empty] | 2018-11-08 | Finished |  |  | 2018-11-15 | Finished |  |  | 2018-11-16 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003243 | 2018-09-21 |  |  |  | HDME000355 | 2018-11-08 | QC Passed
TFA1126-TH | HET | 61000298 | Delivery | ยังอยู่ในสัญญา HO | - | TH189235 | The Flower Land | ES1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2018-06-11 | 2018-10-11 | 2018-12-11 | 2022-01-01 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1391000 | Chon Buri | ตำบลหนองปรือ | 1900-01-01 | [36 empty] | 2018-09-26 | 2021-07-19 | 2021-07-19 | Finished | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONTRACT CANCELLATION | [5 empty] | 2018-06-21 | Finished | [18 empty] | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-20 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20003360 | 2018-09-26
TFA1127-TH | HET | 61000298 | Delivery | ยังอยู่ในสัญญา HO | - | TH189235 | The Flower Land | ES2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2018-06-11 | 2018-10-11 | 2018-12-11 | 2022-01-01 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1391000 | Chon Buri | ตำบลหนองปรือ | 1900-01-01 | [36 empty] | 2018-09-26 | 2021-07-19 | 2021-07-19 | Finished | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONTRACT CANCELLATION | [5 empty] | 2018-06-21 | Finished | [18 empty] | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-20 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20003360 | 2018-09-26
TAJ0333-TH | HET | 61000298 | Delivery | ยังอยู่ในสัญญา HO | - | TH189235 | The Flower Land | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2018-06-11 | 2018-10-11 | 2018-12-11 | 2022-01-01 | P-1000-CO60W2,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1177000 | Chon Buri | ตำบลหนองปรือ | 1900-01-01 | [36 empty] | 2018-09-26 | 2021-07-19 | 2021-07-19 | Finished | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONTRACT CANCELLATION | [5 empty] | 2018-06-21 | Finished | [18 empty] | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-20 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Green |  |  | 20003359 | 2018-10-04
TAK0351-TH | HET | 61000309 | HO | ส่งมอบแล้ว | - | TH189227 | Royal Thai Navy Sattahip | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2018-05-31 | 2018-09-30 | 2018-11-30 |  | B-1000-2S60,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1284000 | Chon Buri | จังหวัดชลบุรี | 2018-11-05 | 2018-11-05 | Finished | [34 empty] | 2018-09-23 | 2018-10-31 | 2018-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-10-31 | 2018-11-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2018-11-17 | 2018-11-17 | Finished |  |  | 2018-11-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2018-11-30 | Finished | POWER SUPPLY DELAY |  | 2019-02-21 | Finished |  |  | 2018-07-13 | Finished | [18 empty] | 2018-10-30 | Finished |  |  | 2018-10-31 | Finished |  |  | 2018-10-31 | Finished |  |  | 2019-02-21 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass | 2021-03-17 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20003486 | 2018-09-23 |  |  |  | HDME000343 | 2018-10-30 | QC Passed
TAJ0352-TH | HET | 61000311 | HO | ส่งมอบแล้ว | - | TH189244 | Liquor Store | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2018-06-20 | 2018-11-20 | 2019-01-20 | 2019-07-20 | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1637100 | Chiang Rai | ประเทศพม่า | 2018-11-15 | 2018-11-16 | Finished | [34 empty] | 2018-11-13 | 2018-12-22 | 2018-12-22 | Finished | SUPPLIER SHIPMENT DELAY | [13 empty] | 2017-11-01 | 2019-02-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-01 | 2019-09-01 | Finished |  |  | 2019-09-01 | 2019-02-09 | Finished |  |  | 2019-08-16 | Finished |  |  | 2019-08-25 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-02-21 | Finished | DELIVERY DELAY |  | 2020-02-21 | Finished |  |  | 2018-07-07 | Finished | [18 empty] | 2018-12-17 | Finished |  |  | 2018-12-22 | Finished |  |  | 2018-12-25 | Finished |  |  | 2020-02-21 | Finished | [13 empty] | no pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20003500 | 2018-11-13 |  |  |  | HDME000416 | 2018-12-17
TAJ0356-TH | HET | 61000316 | HO | ยังอยู่ในสัญญา HO | - | TH189248 | Office 5 Floor @ Khun Preecha | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | APHIRADA BUNKUEA | 2018-07-05 | 2018-10-20 | 2018-12-20 | 2021-10-25 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1177000 | Bangkok | อำเภอปากเกร็ด | 2020-04-01 | 2020-04-01 | Finished | [34 empty] | 2018-10-13 | 2018-11-20 | 2018-11-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-01 | 2020-05-05 | 2020-04-01 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-05 | Finished |  |  | 100 | [41 empty] | 2020-05-05 | 1900-01-01 | 2020-05-05 | Waiting | POWER SUPPLY DELAY |  | 2021-11-12 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-08-10 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2018-11-19 | Finished |  |  | 2018-11-27 | Finished |  |  | 2018-11-28 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 16 | 16 | 114 | 78.16 | Green |  |  | 20003688 | 2018-10-13 |  |  |  | HDME000376 | 2018-11-19
TAC1443-TH | HET | 61000317 | Install | ยังอยู่ในสัญญา HO | - | TH189251 | Phranakhon South Power Station | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2018-07-10 | 2018-10-25 | 2018-12-10 | 2021-12-12 | VFI-1000-CO60,60S/3F | VFI-II | 1000 | 60 | 3 | 3 |  | 1605000 | Samut Prakan | ตำบลบางโปรง | 2018-10-30 | 2018-12-13 | Finished | [34 empty] | 2018-10-18 | 2019-03-14 | 2018-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-12-13 | 2018-12-28 | 2018-12-15 | Finished |  |  | 2018-12-17 | Finished |  |  | 2018-12-19 | Finished |  |  | 2018-12-21 | Finished |  |  | 2018-12-23 | Finished |  |  | 2018-12-25 | Finished |  |  | 2018-12-26 | Finished |  |  | 2018-12-27 | Finished |  |  | 2018-12-27 | Finished |  |  | 2018-12-28 | Finished |  |  | 100 | [41 empty] | 2018-12-28 | 1900-01-01 | 2018-12-28 | Waiting | POWER SUPPLY DELAY |  | 2021-10-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-08-09 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2018-11-08 | Finished |  |  | 2018-11-13 | Finished |  |  | 2018-11-27 | Finished | [22 empty] | 417 | 89 | 16 | 16 | 538 | 0 | 89 | 16 | 16 | 121 | 77.51 | Green |  |  | 20003719 | 2018-10-18 |  |  |  | HDME000356 | 2018-11-08
TAC1444-TH | HET | 61000318 | HO | ส่งมอบแล้ว | - | TH189250 | Pre-Clinic RAMA | EL-01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-07-20 | 2019-01-20 | 2019-04-20 | 2020-10-30 | VFI-1600-CO90,90S/8F | VFI-II | 1600 | 90 | 8 | 8 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-11-08 | 2019-11-08 | Finished | [34 empty] | 2019-01-20 | 2019-01-29 | 2019-07-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-11 | 2019-12-16 | 2019-11-14 | Finished |  |  | 2019-11-17 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-27 | Finished |  |  | 2019-12-01 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-11 | Finished |  |  | 2019-12-16 | Finished |  |  | 2019-12-13 | Finished |  |  | 2019-11-14 | Finished |  |  | 100 | [41 empty] | 2019-11-14 | 2020-04-14 | 2020-04-14 | Finished |  |  | 2020-04-20 | 2020-04-21 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-13 | Finished |  |  | 100 | 2020-06-22 | 2021-08-09 | 2020-06-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-25 | Finished |  |  | 2021-08-09 | Finished |  |  | 100 | 2020-05-21 | Finished | CONSTRUCTION DELAY |  | 2020-05-22 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-07-10 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-12 | Finished |  |  | 2020-05-22 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003840 | 2019-01-20 |  |  |  | HDME000591 | 2019-07-10 | QC Passed
TAC1445-TH | HET | 61000318 | HO | ส่งมอบแล้ว | - | TH189250 | Pre-Clinic RAMA | EL-02 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-07-20 | 2019-01-20 | 2019-04-20 | 2020-10-30 | VFI-1600-CO90,90S/8F | VFI-II | 1600 | 90 | 8 | 8 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-11-08 | 2019-11-08 | Finished | [34 empty] | 2019-01-20 | 2019-01-29 | 2019-07-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-11 | 2019-12-16 | 2019-11-14 | Finished |  |  | 2019-11-17 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-27 | Finished |  |  | 2019-12-01 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-11 | Finished |  |  | 2019-12-16 | Finished |  |  | 2019-12-13 | Finished |  |  | 2019-11-14 | Finished |  |  | 100 | [41 empty] | 2019-11-14 | 2020-04-14 | 2020-04-14 | Finished |  |  | 2020-04-20 | 2020-04-21 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-13 | Finished |  |  | 100 | 2020-06-22 | 2021-04-05 | 2020-06-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-05 | Finished | [6 empty] | 90 | 2020-05-21 | Finished | CONSTRUCTION DELAY |  | 2020-05-22 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-07-10 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-12 | Finished |  |  | 2020-05-22 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20003840 | 2019-01-20 |  |  |  | HDME000591 | 2019-07-10 | QC Passed
TAC1446-TH | HET | 61000318 | HO | ส่งมอบแล้ว | - | TH189250 | Pre-Clinic RAMA | EL-03 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-07-20 | 2019-01-20 | 2019-04-20 | 2020-10-30 | VFI-1600-CO90,90S/8F | VFI-II | 1600 | 90 | 8 | 8 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-08-20 | 2019-08-20 | Finished | [34 empty] | 2019-01-20 | 2018-12-20 | 2019-07-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-26 | 2019-10-30 | 2019-08-31 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-18 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-10-06 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-10-12 | Finished |  |  | 2019-09-18 | Finished |  |  | 100 | [41 empty] | 2019-09-18 | 2020-03-31 | 2020-03-31 | Finished |  |  | 2020-04-05 | 2020-04-10 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2020-06-22 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-22 | Finished | [6 empty] | 90 | 2020-06-11 | Finished | CONSTRUCTION DELAY |  | 2020-06-23 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-07-10 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-12 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20003840 | 2019-01-20 |  |  |  | HDME000591 | 2019-07-10 | QC Passed
TAC1447-TH | HET | 61000318 | HO | ส่งมอบแล้ว | - | TH189250 | Pre-Clinic RAMA | EL-04 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-07-20 | 2019-01-20 | 2019-04-20 | 2020-10-30 | VFI-1600-CO90,90S/8F | VFI-II | 1600 | 90 | 8 | 8 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-08-20 | 2019-08-20 | Finished | [34 empty] | 2019-01-20 | 2019-06-22 | 2019-07-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-26 | 2019-10-30 | 2019-08-31 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-18 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-10-06 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-10-12 | Finished |  |  | 2019-09-18 | Finished |  |  | 100 | [41 empty] | 2019-09-18 | 2020-03-31 | 2020-03-31 | Finished |  |  | 2020-04-05 | 2020-04-10 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2020-06-22 | 2021-04-05 | 2020-06-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-05 | Finished | [6 empty] | 90 | 2020-06-11 | Finished | CONSTRUCTION DELAY |  | 2020-06-23 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-07-10 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-12 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20003840 | 2019-01-20 |  |  |  | HDME000591 | 2019-07-10 | QC Passed
TAC1448-TH | HET | 61000318 | HO | ส่งมอบแล้ว | - | TH189250 | Pre-Clinic RAMA | EL-05 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-07-20 | 2019-01-20 | 2019-04-20 | 2020-10-30 | VFI-1600-CO90,90S/8F | VFI-II | 1600 | 90 | 8 | 8 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-08-20 | 2019-08-20 | Finished | [34 empty] | 2019-01-20 | 2019-06-22 | 2019-07-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-26 | 2019-10-30 | 2019-08-31 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-18 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-10-06 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-10-12 | Finished |  |  | 2019-09-18 | Finished |  |  | 100 | [41 empty] | 2019-09-18 | 2020-03-31 | 2020-03-31 | Finished |  |  | 2020-04-05 | 2020-04-10 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2020-06-22 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-22 | Finished | [6 empty] | 90 | 2020-06-11 | Finished | CONSTRUCTION DELAY |  | 2020-06-23 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-07-10 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-12 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20003840 | 2019-01-20 |  |  |  | HDME000591 | 2019-07-10 | QC Passed
TBK0126-TH | HET | 61000318 | HO | ส่งมอบแล้ว | - | TH189250 | Pre-Clinic RAMA | EL-06 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-07-20 | 2019-01-20 | 2019-04-20 | 2021-06-11 | HVF-1600-2S120,120S/9F | HVF-5 | 1600 | 120 | 9 | 9 |  | 2354000 | Samut Prakan | อำเภอบางพลี | 2019-12-16 | 2019-12-16 | Finished | [34 empty] | 2019-01-20 | 2019-06-22 | 2019-07-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-16 | 2020-01-25 | 2019-12-18 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-26 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-13 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-17 | Finished |  |  | 100 | [41 empty] | 2020-01-17 | 2020-03-09 | 2020-03-09 | Finished |  |  | 2020-03-09 | 2020-03-12 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-18 | Finished |  |  | 100 | 2021-05-13 | 2021-08-09 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-17 | Finished |  |  | 2021-08-09 | Finished |  |  | 100 | 2021-07-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-05 | Finished |  |  | 2018-08-10 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2019-07-10 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-12 | Finished |  |  | 2021-08-05 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 800 | 93 | 24 | 16 | 933 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003840 | 2019-01-20 |  |  |  | HDME000591 | 2019-07-10 | QC Passed
TFA1132-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | ES1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1155600 | Samut Prakan | อำเภอบางพลี | 2019-02-07 | [20 empty] | 2019-02-07 | Finished | [14 empty] | 2018-10-29 | 2018-10-10 | 2019-02-06 | Finished | STORE AREA | [13 empty] | 2019-02-07 | 2019-03-09 | [41 empty] | 2019-02-10 | Finished |  |  | 2019-02-12 | Finished |  |  | 2019-02-14 | Finished |  |  | 2019-02-17 | Finished |  |  | 2019-02-18 | Finished |  |  | 2019-02-21 | Finished |  |  | 2019-02-24 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-03 | Finished |  |  | 2019-03-09 | Finished |  |  | 100 | 2019-03-09 | 2019-03-18 | 2019-03-18 | Finished |  |  | 2019-03-18 | 2019-03-19 | Finished |  |  | 2019-03-21 | Finished |  |  | 2019-03-22 | Finished |  |  | 100 | [18 empty] | 0 | 2019-04-04 | Finished | CONSTRUCTION DELAY |  | 2019-05-03 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-02-01 | Finished |  |  | 2019-02-06 | Finished |  |  | 2019-02-11 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  | pass | 2019-06-13 | Finished |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 16 | 21 | 37 | 93.98 | Blue |  |  | 20003721 | 2018-10-29 |  |  |  | HDME000455 | 2019-02-01
TFA1133-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | ES2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1155600 | Samut Prakan | อำเภอบางพลี | 2019-02-07 | [20 empty] | 2019-02-07 | Finished | [14 empty] | 2018-10-29 | 2019-02-20 | 2019-02-06 | Finished | STORE AREA | [13 empty] | 2019-02-07 | 2019-03-09 | [41 empty] | 2019-02-07 | Finished |  |  | 2019-02-12 | Finished |  |  | 2019-02-14 | Finished |  |  | 2019-02-17 | Finished |  |  | 2019-02-18 | Finished |  |  | 2019-02-21 | Finished |  |  | 2019-02-24 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-03 | Finished |  |  | 2019-03-09 | Finished |  |  | 100 | 2019-03-09 | 2019-03-18 | 2019-03-18 | Finished |  |  | 2019-03-18 | 2019-03-19 | Finished |  |  | 2019-03-21 | Finished |  |  | 2019-03-22 | Finished |  |  | 100 | [18 empty] | 0 | 2019-04-04 | Finished | CONSTRUCTION DELAY |  | 2019-05-03 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-02-01 | Finished |  |  | 2019-02-06 | Finished |  |  | 2019-02-11 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  | pass | 2019-06-13 | Finished |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 16 | 21 | 37 | 93.98 | Blue |  |  | 20003721 | 2018-10-29 |  |  |  | HDME000455 | 2019-02-01
TFA1134-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | ES3 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | 1200TX-EN,R4.5M,D30 | TX-EN |  |  |  |  | 4500 | 1096750 | Samut Prakan | อำเภอบางพลี | 2019-02-07 | [20 empty] | 2019-02-07 | Finished | [14 empty] | 2018-10-29 | 2019-04-10 | 2019-02-06 | Finished | STORE AREA | [13 empty] | 2019-02-07 | 2019-03-09 | [41 empty] | 2019-02-07 | Finished |  |  | 2019-02-12 | Finished |  |  | 2019-02-14 | Finished |  |  | 2019-02-17 | Finished |  |  | 2019-02-18 | Finished |  |  | 2019-02-21 | Finished |  |  | 2019-02-24 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-03 | Finished |  |  | 2019-03-09 | Finished |  |  | 100 | 2019-03-09 | 2019-03-18 | 2019-03-18 | Finished |  |  | 2019-03-18 | 2019-03-19 | Finished |  |  | 2019-03-21 | Finished |  |  | 2019-03-22 | Finished |  |  | 100 | [18 empty] | 0 | 2019-04-04 | Finished | CONSTRUCTION DELAY |  | 2019-05-03 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-02-01 | Finished |  |  | 2019-02-06 | Finished |  |  | 2019-02-11 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  | pass | 2019-06-13 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 16 | 21 | 37 | 93.4 | Blue |  |  | 20003721 | 2018-10-29 |  |  |  | HDME000455 | 2019-02-01
TFA1135-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | ES4 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | 1200TX-EN,R4.5M,D30 | TX-EN |  |  |  |  | 4500 | 1096750 | Samut Prakan | อำเภอบางพลี | 2019-02-07 | [20 empty] | 2019-02-07 | Finished | [14 empty] | 2018-10-29 | 2019-05-17 | 2019-02-06 | Finished | STORE AREA | [13 empty] | 2019-02-07 | 2019-03-09 | [41 empty] | 2019-02-07 | Finished |  |  | 2019-02-12 | Finished |  |  | 2019-02-14 | Finished |  |  | 2019-02-17 | Finished |  |  | 2019-02-18 | Finished |  |  | 2019-02-21 | Finished |  |  | 2019-02-24 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-03 | Finished |  |  | 2019-03-09 | Finished |  |  | 100 | 2019-03-09 | 2019-03-18 | 2019-03-18 | Finished |  |  | 2019-03-18 | 2019-03-19 | Finished |  |  | 2019-03-21 | Finished |  |  | 2019-03-22 | Finished |  |  | 100 | [18 empty] | 0 | 2019-04-04 | Finished | CONSTRUCTION DELAY |  | 2019-05-03 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-02-01 | Finished |  |  | 2019-02-06 | Finished |  |  | 2019-02-11 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  | pass | 2019-06-13 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 16 | 21 | 37 | 93.4 | Blue |  |  | 20003721 | 2018-10-29 |  |  |  | HDME000455 | 2019-02-01
TFA1136-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | ES5 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | 1200TX-EN,R4.5M,D30 | TX-EN |  |  |  |  | 4500 | 1096750 | Samut Prakan | อำเภอบางพลี | 2019-02-07 | [20 empty] | 2019-02-07 | Finished | [14 empty] | 2018-10-29 | 2019-05-17 | 2019-02-06 | Finished | STORE AREA | [13 empty] | 2019-02-07 | 2019-03-09 | [41 empty] | 2019-02-07 | Finished |  |  | 2019-02-12 | Finished |  |  | 2019-02-14 | Finished |  |  | 2019-02-17 | Finished |  |  | 2019-02-18 | Finished |  |  | 2019-02-21 | Finished |  |  | 2019-02-24 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-03 | Finished |  |  | 2019-03-09 | Finished |  |  | 100 | 2019-03-09 | 2019-04-22 | 2019-04-22 | Finished |  |  | 2019-04-22 | 2019-03-19 | Finished |  |  | 2019-03-21 | Finished |  |  | 2019-07-24 | Finished |  |  | 100 | [18 empty] | 0 | 2019-12-25 | Finished | CONSTRUCTION DELAY |  | 2020-01-21 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-02-01 | Finished |  |  | 2019-02-06 | Finished |  |  | 2019-02-11 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-24 | Finished |  | pass | 2020-01-24 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 16 | 21 | 37 | 93.4 | Blue |  |  | 20003721 | 2018-10-29 |  |  |  | HDME000455 | 2019-02-01
TFA1137-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | ES6 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | 1200TX-EN,R4.5M,D30 | TX-EN |  |  |  |  | 4500 | 1096750 | Samut Prakan | อำเภอบางพลี | 2019-02-07 | [20 empty] | 2019-02-07 | Finished | [14 empty] | 2018-10-29 | 2019-02-22 | 2019-02-06 | Finished | STORE AREA | [13 empty] | 2019-02-07 | 2019-03-09 | [41 empty] | 2019-02-07 | Finished |  |  | 2019-02-12 | Finished |  |  | 2019-02-14 | Finished |  |  | 2019-02-17 | Finished |  |  | 2019-02-18 | Finished |  |  | 2019-02-21 | Finished |  |  | 2019-02-24 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-03-03 | Finished |  |  | 2019-03-09 | Finished |  |  | 100 | 2019-03-09 | 2019-04-22 | 2019-04-22 | Finished |  |  | 2019-04-22 | 2019-03-19 | Finished |  |  | 2019-03-21 | Finished |  |  | 2019-07-12 | Finished |  |  | 100 | [18 empty] | 0 | 2019-12-25 | Finished | CONSTRUCTION DELAY |  | 2020-01-21 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-02-01 | Finished |  |  | 2019-02-06 | Finished |  |  | 2019-02-11 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-24 | Finished |  | pass | 2020-01-24 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 16 | 21 | 37 | 93.4 | Blue |  |  | 20003721 | 2018-10-29 |  |  |  | HDME000455 | 2019-02-01
TAC1449-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1600-2S105,105S/17F | VFI-II | 1600 | 105 | 17 | 17 |  | 2589400 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-02-07 | Finished | [34 empty] | 2019-01-13 | 2019-05-03 | 2019-01-24 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2019-07-12 | 2019-09-15 | 2019-07-20 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-09-15 | Finished |  |  | 2020-09-05 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | [41 empty] | 2019-08-30 | 2019-09-06 | 2019-09-06 | Finished |  |  | 2019-09-06 | 2019-09-09 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-27 | Finished |  |  | 100 | 2021-05-13 | 2021-02-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2019-10-07 | Finished | OTHERS |  | 2019-11-09 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-11-09 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished |  | pass | 2020-11-04 | Finished |  |  | 1190 | 110 | 40 | 20 | 1360 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003720 | 2019-01-13 |  |  |  | HDME000446 | 2019-01-22 | QC Passed
TAC1450-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1600-2S105,105S/17F | VFI-II | 1600 | 105 | 17 | 17 |  | 2589400 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-02-07 | Finished | [34 empty] | 2019-01-13 | 2019-05-03 | 2019-01-24 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2019-09-09 | 2019-11-02 | 2019-09-12 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-18 | Finished |  |  | 2019-09-22 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-16 | Finished |  |  | 2019-10-24 | Finished |  |  | 2019-10-28 | Finished |  |  | 2019-11-02 | Finished |  |  | 100 | [41 empty] | 2019-11-02 | 2019-10-10 | 2019-10-10 | Finished |  |  | 2019-10-10 | 2019-10-14 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-11-25 | Finished |  |  | 100 | 2021-05-13 | 2021-04-22 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-22 | Finished |  |  | 100 | 2019-12-04 | Finished | OTHERS |  | 2019-12-09 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-12-09 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  | pass | 2021-05-01 | Finished |  |  | 1190 | 110 | 40 | 20 | 1360 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003720 | 2019-01-13 |  |  |  | HDME000446 | 2019-01-22 | QC Passed
TAC1451-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1600-2S105,105S/17F | VFI-II | 1600 | 105 | 17 | 17 |  | 2589400 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-02-07 | Finished | [34 empty] | 2019-01-13 | 2019-05-03 | 2018-12-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2019-02-14 | 2019-04-26 | 2019-03-05 | Finished |  |  | 2019-03-08 | Finished |  |  | 2019-03-11 | Finished |  |  | 2019-03-15 | Finished |  |  | 2019-03-19 | Finished |  |  | 2019-03-25 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-04-26 | Finished |  |  | 100 | [41 empty] | 2019-04-26 | 2019-04-18 | 2019-04-18 | Finished |  |  | 2019-04-18 | 2019-04-21 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-05-07 | Finished |  |  | 100 | 2021-05-13 | 2020-09-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-28 | Finished |  |  | 100 | 2019-05-17 | Finished | CONSTRUCTION DELAY |  | 2019-06-06 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-25 | Finished |  | pass | 2019-06-25 | Finished |  |  | 1190 | 110 | 40 | 20 | 1360 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003720 | 2019-01-13 |  |  |  | HDME000446 | 2019-01-22 | QC Passed
TAC1452-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1600-2S105,105S/18F | VFI-II | 1600 | 105 | 18 | 18 |  | 2642900 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-02-07 | Finished | [34 empty] | 2019-01-13 | 2019-05-03 | 2018-12-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2019-07-12 | 2019-09-15 | 2019-07-20 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-09-15 | Finished |  |  | 2020-09-05 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | [41 empty] | 2019-08-30 | 2019-09-06 | 2019-09-06 | Finished |  |  | 2019-09-06 | 2019-09-09 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-27 | Finished |  |  | 100 | 2021-05-13 | 2021-02-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | 2019-10-07 | Finished | OTHERS |  | 2019-11-09 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-11-09 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  | pass | 2021-05-01 | Finished |  |  | 1246 | 111 | 40 | 20 | 1417 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003720 | 2019-01-13 |  |  |  | HDME000446 | 2019-01-22 | QC Passed
TAC1453-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L5 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1600-2S105,105S/18F | VFI-II | 1600 | 105 | 18 | 18 |  | 2642900 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-07-12 | Finished | [34 empty] | 2019-01-13 | 2019-08-17 | 2018-12-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2019-02-14 | 2019-04-26 | 2019-03-05 | Finished |  |  | 2019-03-08 | Finished |  |  | 2019-03-11 | Finished |  |  | 2019-03-15 | Finished |  |  | 2019-03-19 | Finished |  |  | 2019-03-25 | Finished |  |  | 2019-03-30 | Finished |  |  | 2019-03-10 | Finished |  |  | 2019-04-20 | Finished |  |  | 2019-04-26 | Finished |  |  | 100 | [41 empty] | 2019-04-26 | 2019-04-18 | 2019-04-18 | Finished |  |  | 2019-04-18 | 2019-04-21 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-05-07 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2019-05-17 | Finished | CONSTRUCTION DELAY |  | 2019-06-06 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-25 | Finished |  | pass | 2019-06-25 | Finished |  |  | 1246 | 111 | 40 | 20 | 1417 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20003720 | 2019-01-13 |  |  |  | HDME000446 | 2019-01-22 | QC Passed
TAC1454-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L6 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1000-CO90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1423100 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-09-20 | Finished | [34 empty] | 2018-10-16 | 2019-08-17 | 2018-10-29 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2018-12-17 | 2019-02-12 | 2018-12-22 | Finished |  |  | 2019-01-10 | Finished |  |  | 2019-01-13 | Finished |  |  | 2019-01-19 | Finished |  |  | 2019-01-23 | Finished |  |  | 2019-01-26 | Finished |  |  | 2018-12-26 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-30 | Finished |  |  | 2019-02-03 | Finished |  |  | 100 | [41 empty] | 2019-02-03 | 2019-03-11 | 2019-03-11 | Finished |  |  | 2019-03-11 | 2019-03-12 | Finished |  |  | 2019-03-17 | Finished |  |  | 2019-03-22 | Finished |  |  | 100 | [18 empty] | 0 | 2019-04-04 | Finished | CONSTRUCTION DELAY |  | 2019-05-03 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2018-11-14 | Finished |  |  | 2018-11-29 | Finished |  |  | 2018-11-29 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-24 | Finished |  | pass | 2019-07-24 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 24 | 16 | 40 | 94.81 | Blue |  |  | 20003720 | 2018-10-16 |  |  |  | HDME000364 | 2018-11-14
TAC1455-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L7 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1000-CO90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1423100 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-02-14 | Finished | [34 empty] | 2018-10-16 | 2019-08-17 | 2018-10-29 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2018-12-17 | 2019-02-12 | 2018-12-22 | Finished |  |  | 2019-01-10 | Finished |  |  | 2019-01-13 | Finished |  |  | 2019-01-19 | Finished |  |  | 2019-01-23 | Finished |  |  | 2019-01-26 | Finished |  |  | 2018-12-26 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-30 | Finished |  |  | 2019-02-03 | Finished |  |  | 100 | [41 empty] | 2019-02-03 | 2019-03-11 | 2019-03-11 | Finished |  |  | 2019-03-11 | 2019-03-12 | Finished |  |  | 2019-03-17 | Finished |  |  | 2019-03-22 | Finished |  |  | 100 | [18 empty] | 0 | 2019-04-04 | Finished | CONSTRUCTION DELAY |  | 2019-05-03 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2018-11-14 | Finished |  |  | 2018-11-29 | Finished |  |  | 2018-11-29 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-24 | Finished |  | pass | 2019-07-24 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 24 | 16 | 40 | 94.81 | Blue |  |  | 20003720 | 2018-10-16 |  |  |  | HDME000364 | 2018-11-14
TAC1456-TH | HET | 61000319 | HO | ส่งมอบแล้ว | - | TH189253 | Princ Hospital | L8 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-06-27 | 2018-10-16 | 2019-02-13 |  | VFI-1600-2S90,90S/7F | VFI-II | 1600 | 90 | 7 | 7 |  | 2011600 | Samut Prakan | อำเภอบางพลี | 2018-10-30 | 2019-07-12 | Finished | [34 empty] | 2019-01-13 | 2019-03-14 | 2018-12-18 | Finished | FACTORY PARTIAL SHIPMENT | [13 empty] | 2019-02-12 | 2019-02-26 | 2018-12-22 | Finished |  |  | 2019-01-10 | Finished |  |  | 2019-01-13 | Finished |  |  | 2019-01-19 | Finished |  |  | 2019-01-23 | Finished |  |  | 2019-01-26 | Finished |  |  | 2018-12-26 | Finished |  |  | 2018-12-30 | Finished |  |  | 2019-01-30 | Finished |  |  | 2019-02-03 | Finished |  |  | 100 | [41 empty] | 2019-02-03 | 2019-03-11 | 2019-03-11 | Finished |  |  | 2019-03-11 | 2019-03-12 | Finished |  |  | 2019-03-17 | Finished |  |  | 2019-03-22 | Finished |  |  | 100 | [18 empty] | 0 | 2019-04-04 | Finished | CONSTRUCTION DELAY |  | 2019-05-03 | Finished |  |  | 2018-08-10 | Finished | [18 empty] | 2019-01-22 | Finished |  |  | 2019-01-24 | Finished |  |  | 2019-01-28 | Finished |  |  | 2019-05-03 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-24 | Finished |  | pass | 2019-07-24 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 24 | 16 | 40 | 94.81 | Blue |  |  | 20003720 | 2019-01-13 |  |  |  | HDME000446 | 2019-01-22
TEB0077-TH | HET | 61000321 | HO | ยังอยู่ในสัญญา HO | - | TH189257 | Private Nirvana (AA) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2018-07-13 | 2018-12-13 | 2019-02-13 | 2022-07-01 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 950000 | Bangkok | แขวงคลองจั่น | 2022-04-30 | [36 empty] | 2018-11-28 | 2018-12-19 | 2018-12-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-05-01 | 2022-05-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 | 2018-12-28 |  |  |  | 2022-05-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-08-09 | Finished | [18 empty] | 2018-12-18 | Finished |  |  | 2018-12-19 | Finished |  |  | 2018-12-21 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20003829 | 2018-11-28 |  |  |  | HDME000420 | 2018-12-18
TAJ0361-TH | HET | 61000328 | HO | ส่งมอบแล้ว | - | TH189264 | Phrajadee Amphawan Temple | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2018-07-17 | 2018-12-10 | 2019-02-10 | 2020-04-10 | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1200000 | Sing Buri | อำเภอพรหมบุรี | 2019-01-05 | 2019-02-11 | Finished | [34 empty] | 2018-12-03 | 2018-12-14 | 2018-12-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-11 | 2019-03-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-04-19 | 2019-04-19 | Finished |  |  | 2019-04-19 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-06-28 | Finished | CONSTRUCTION DELAY |  | 2020-06-15 | Finished |  |  | 2018-09-18 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2018-12-13 | Finished |  |  | 2018-12-14 | Finished |  |  | 2018-12-18 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-13 | Finished |  | pass | 2020-07-13 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004024 | 2018-12-03 |  |  |  | HDME000411 | 2018-12-13 | QC Passed
TAJ0366-TH | HET | 61000336 | HO | ยังอยู่ในสัญญา HO | - | TH189269 | Home 4 FL. Khun Phornpinit Phornprapha | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2018-08-01 | 2018-12-01 | 2019-01-01 | 2021-09-30 | P-1000-CO60W2,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1546150 | Bangkok | แขวงพระโขนงเหนือ | 2019-01-27 | 2019-01-14 | Finished | [34 empty] | 2018-11-24 | 2018-12-24 | 2018-12-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-14 | 2019-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-25 | 2019-12-25 | Finished |  |  | 2019-12-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-04-02 | 2000-01-01 | 2020-04-02 | Finished | [14 empty] | 25 | 2021-09-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-09-01 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2018-12-19 | Finished |  |  | 2019-03-14 | Finished |  |  | 2019-03-18 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 4 | 16 | 20 | 95.81 | Green |  |  | 20004081 | 2018-11-24 |  |  |  | HDME000422 | 2018-12-19
TEC0127-TH | HET | 61000336 | HO | ยังอยู่ในสัญญา HO | - | TH189269 | Home 4 FL. Khun Phornpinit Phornprapha | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2018-08-01 | 2018-12-01 | 2019-01-01 | 2021-09-30 | DT-50P-B30,30S/4F | DT | 50 | 30 | 3 | 4 |  | 272850 | Bangkok | แขวงพระโขนงเหนือ | 2019-01-27 | 2019-01-27 | Finished | [34 empty] | 2018-11-24 | 2019-05-20 | 2019-05-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-28 | 2019-03-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-03-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2021-09-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-09-01 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2019-03-19 | Finished |  |  | 2019-05-31 | Finished |  |  | 2019-05-31 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Green |  |  | 20004090 | 2018-11-24 |  |  |  | HDME000499 | 2019-03-19
TAJ0370-TH | HET | 61000340 | HO | ส่งมอบแล้ว | - | TH189273 | Wat Bot | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Sittichoke Boonpa | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2018-08-16 | 2018-11-16 | 2018-12-31 | 2020-10-30 | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1000000 | Pathum Thani | อำเภอเมืองปทุมธานี | 2019-05-30 | [36 empty] | 2018-11-09 | 2019-01-07 | 2019-01-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-12 | 2019-03-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-06-10 | 2020-09-15 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-09-30 | Finished |  |  | 2020-09-22 | Finished |  |  | 2018-09-18 | Finished | [10 empty] | 2020-09-15 | Finished | [6 empty] | 2019-01-07 | Finished |  |  | 2019-01-07 | Finished |  |  | 2019-01-10 | Finished |  |  | 2020-09-22 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20004145 | 2018-11-09 |  |  |  | HDME000430 | 2019-01-07 | QC Passed
TAE1194-TH | HET | 61000351 | Install | เลยสัญญา HO | - | TH199018 | Ramkhamhaeng Hospital | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Thamnul Kongsar | 2018-08-30 | 2019-01-14 | 2019-03-15 |  | UAG-750-CO60,60S/2F | UAG-11G-A | 750 | 60 | 2 | 2 |  | 1337500 | Bangkok | แขวงหัวหมาก | 2021-12-20 | [36 empty] | 2021-05-20 | 2021-05-21 | 2021-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2021-12-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-24 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-05-10 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-28 | Finished | [22 empty] | 345 | 79 | 16 | 16 | 456 | 345 | 79 | 16 | 16 | 456 | 0 | Red |  |  | 20004317 | 2019-05-07 |  |  |  | HDME001217 | 2021-05-21
TAE1195-TH | HET | 61000351 | Install | เลยสัญญา HO | - | TH199018 | Ramkhamhaeng Hospital | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Thamnul Kongsar | 2018-08-30 | 2019-01-14 | 2019-03-15 |  | UAG-750-CO60,60S/2F | UAG-11G-A | 750 | 60 | 2 | 2 |  | 1337500 | Bangkok | แขวงหัวหมาก | 2021-12-20 | [36 empty] | 2021-05-20 | 2021-05-21 | 2021-05-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2021-12-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-24 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-05-10 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-28 | Finished | [22 empty] | 345 | 79 | 16 | 16 | 456 | 345 | 79 | 16 | 16 | 456 | 0 | Red |  |  | 20004317 | 2019-05-07 |  |  |  | HDME001217 | 2021-05-21
TBL0121-TH | HET | 61000361 | HO | ส่งมอบแล้ว | - | TH199027 | Phornprapha Residence | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2018-09-19 | 2019-02-19 | 2019-04-19 | 2020-06-08 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1712000 | Bangkok | แขวงพระโขนงเหนือ เขตวัฒนา | 2019-01-01 | 2019-01-21 | Finished | [34 empty] | 2019-02-12 | 2019-02-22 | 2019-02-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-03-15 | 2020-05-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-05-05 | 2020-05-05 | Finished |  |  | 2020-05-05 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-23 | 2021-03-23 | 2021-03-23 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished | [6 empty] | 90 | 2021-05-28 | Finished | POWER SUPPLY DELAY |  | 2021-06-01 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-06-01 | Finished | [6 empty] | 2019-02-21 | Finished |  |  | 2019-02-26 | Finished |  |  | 2019-02-27 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 1 | 1 | 99.8 | Blue |  |  | 20004571 | 2019-02-12 |  |  |  | HDME000478 | 2019-02-21 | QC Passed
TAJ0379-TH | HET | 61000363 | HO | ส่งมอบแล้ว | - | TH189281 | Trinity Hotel | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2018-09-14 | 2018-12-14 | 2019-01-29 | 2020-09-30 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1144900 | Bangkok | แขวงลาดยาว | 2019-03-01 | 2019-06-20 | Finished | [34 empty] | 2018-12-14 | 2019-02-20 | 2019-02-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-20 | 2019-07-18 | 2019-06-20 | Finished |  |  | 2019-06-22 | Finished |  |  | 2019-06-24 | Finished |  |  | 2019-06-27 | Finished |  |  | 2019-06-30 | Finished |  |  | 2019-07-02 | Finished |  |  | 2019-07-05 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-15 | Finished |  |  | 100 | [41 empty] | 2019-07-15 | 2020-04-24 | 2020-04-24 | Finished |  |  | 2020-03-30 | 2020-04-27 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-16 | Finished |  |  | 100 | 2020-04-23 | 2000-01-01 | 2020-04-23 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-07-23 | Finished |  |  | 2021-08-10 | Finished |  |  | 100 | 2021-02-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-31 | Finished |  |  | 2018-10-03 | Finished | [10 empty] | 2021-03-31 | Finished | [6 empty] | 2019-02-11 | Finished |  |  | 2019-02-20 | Finished |  |  | 2019-02-21 | Finished |  |  | 2021-03-31 | Finished | [13 empty] | in process (defect) |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004548 | 2018-12-14 |  |  |  | HDME000470 | 2019-02-11
TAJ0380-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | CP2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | P-1000-CO60W1,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 940000 | Bangkok | แขวงหัวหมาก | 2018-11-05 | 2018-11-08 | Finished | [34 empty] | 2019-04-14 | 2019-05-18 | 2019-05-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-20 | 2019-01-25 | 2018-11-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-10-28 | 2019-10-28 | Finished |  |  | 2020-03-05 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2021-05-13 | 2021-06-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-29 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2020-11-15 | Finished | POWER SUPPLY DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TAJ0381-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | CP3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | P-1000-CO60W1,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 940000 | Bangkok | แขวงหัวหมาก | 2019-01-05 | 2019-04-02 | Finished | [34 empty] | 2019-04-14 | 2019-05-18 | 2019-05-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-04-04 | 2019-05-15 | 2018-11-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-10-28 | 2019-10-28 | Finished |  |  | 2020-03-15 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2021-05-13 | 2021-06-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-29 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2020-11-15 | Finished | POWER SUPPLY DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TAC1495-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | FL1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | VFI-1600-CO150,150S/30F | VFI-II | 1600 | 150 | 30 | 30 |  | 4720000 | Bangkok | แขวงหัวหมาก | 2018-11-05 | 2018-11-08 | Finished | [34 empty] | 2019-04-14 | 2019-05-18 | 2019-05-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-20 | 2019-01-25 | 2018-11-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-10-28 | 2019-10-28 | Finished |  |  | 2020-03-05 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2021-05-13 | 2021-06-28 | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-06-28 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | POWER SUPPLY DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1909 | 121 | 56 | 24 | 2110 | 0 | 0 | 0 | 2 | 2 | 99.91 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TBK0130-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 25 | 27 |  | 5600850 | Bangkok | แขวงหัวหมาก | 2018-11-10 | 2018-11-11 | Finished | [34 empty] | 2019-04-14 | 2019-05-19 | 2019-05-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-05 | 2019-03-15 | 2019-07-25 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-10-28 | 2019-10-28 | Finished |  |  | 2019-07-20 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2020-05-29 | 2020-10-22 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-22 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | INSTALLATION DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 2 | 2 | 99.89 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TBK0131-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 25 | 27 |  | 5600850 | Bangkok | แขวงหัวหมาก | 2018-11-10 | 2018-11-11 | Finished | [34 empty] | 2019-04-14 | 2019-05-19 | 2019-05-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-05 | 2019-03-15 | 2019-07-25 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-10-28 | 2019-10-28 | Finished |  |  | 2019-07-20 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2020-05-29 | 2021-01-08 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-22 | Finished |  |  | 2021-01-08 | Finished |  |  | 100 | 2020-11-15 | Finished | INSTALLATION DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TBK0132-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 25 | 27 |  | 5600850 | Bangkok | แขวงหัวหมาก | 2018-11-10 | 2018-11-11 | Finished | [34 empty] | 2019-04-14 | 2019-05-25 | 2019-05-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-05 | 2019-03-15 | 2019-07-25 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-10-28 | 2019-10-28 | Finished |  |  | 2019-07-20 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2020-05-29 | 2020-10-22 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-22 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | INSTALLATION DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 2 | 2 | 99.89 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TBK0133-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | L4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 25 | 27 |  | 5600850 | Bangkok | แขวงหัวหมาก | 2018-11-10 | 2018-11-11 | Finished | [34 empty] | 2019-04-14 | 2019-05-25 | 2019-05-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-02-05 | 2019-03-15 | 2019-07-25 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-10-28 | 2019-10-28 | Finished |  |  | 2019-07-20 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2020-05-29 | 2020-10-22 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-22 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | INSTALLATION DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 2 | 2 | 99.89 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TBK0134-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | L5 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 25 | 27 |  | 5600850 | Bangkok | แขวงหัวหมาก | 2020-01-30 | 2018-12-12 | Finished | [34 empty] | 2019-04-14 | 2019-05-26 | 2019-05-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-06 | 2019-02-22 | 2019-07-25 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-02-25 | 2019-02-25 | Finished |  |  | 2019-02-25 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2020-05-29 | 2020-10-22 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-22 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | INSTALLATION DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 2 | 2 | 99.89 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TBK0135-TH | HET | 61000365 | HO | ส่งมอบแล้ว | - | TH199028 | Major Tower Rama-9 Ramkhumhang | L6 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | 2018-09-01 | 2019-04-21 | 2019-11-30 | 2020-07-15 | HVF-1600-CO180,180S/27F | HVF-5 | 1600 | 180 | 25 | 27 |  | 5600850 | Bangkok | แขวงหัวหมาก | 2020-01-30 | 2018-12-12 | Finished | [34 empty] | 2019-04-14 | 2019-05-26 | 2019-05-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-01-06 | 2019-02-22 | 2019-07-25 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 100 | [41 empty] | 2019-10-25 | 2019-02-25 | 2019-02-25 | Finished |  |  | 2019-02-25 | 2019-10-28 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2020-05-29 | 2020-10-22 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-22 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2021-05-08 | Finished |  |  | 2018-10-09 | Finished | [10 empty] | 2021-05-08 | Finished | [6 empty] | 2019-05-24 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-28 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 2 | 2 | 99.89 | Blue |  |  | 20004577 | 2019-04-14 |  |  |  | HDME000545 | 2019-05-24 | QC Passed
TAD0359-TH | HET | 61000371 | HO | ส่งมอบแล้ว | - | TH199034 | รพ.ตรัง [อ.บริการและจอดรถ 10 ชั้น] | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2018-08-25 | 2019-02-25 | 2019-05-25 |  | B-1000-2S90,90S/11F | B-II(VFI-II) | 1000 | 90 | 6 | 11 |  | 1765500 | Trang | อำเภอเมืองตรัง | 1900-01-01 | 2019-11-01 | Finished | [34 empty] | 2019-02-18 | 2019-03-14 | 2019-03-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2018-11-05 | 2020-06-30 | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 2019-11-01 | Finished |  |  | 100 | [41 empty] | 2019-11-01 | 2019-09-05 | 2019-09-05 | Finished |  |  | 2019-09-05 | 2019-09-05 | Finished |  |  | 2019-09-05 | Finished |  |  | 2019-10-15 | Finished |  |  | 100 | 2021-05-13 | 2020-11-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2019-12-06 | Finished |  |  | 2020-11-16 | Finished |  |  | 100 | 2019-11-25 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2020-02-27 | Finished |  |  | 2018-10-22 | Finished | [18 empty] | 2019-03-04 | Finished |  |  | 2019-03-15 | Finished |  |  | 2019-03-18 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-21 | Finished |  | pass | 2020-07-21 | Finished |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004663 | 2019-02-18 |  |  |  | HDME000486 | 2019-03-04 | QC Passed
TFA1144-TH | HET | 61000372 | Test | ยังอยู่ในสัญญา HO | - | TH199035 | 42C Banquet | 2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2018-10-01 | 2019-08-01 | 2019-11-01 | 2021-10-29 | 1200TX-EN,R3.15M,D35 | TX-EN |  |  |  |  | 3150 | 1059300 | Nakhon Sawan | ตำบลปากน้ำโพ | 2020-10-30 | [20 empty] | 2020-10-30 | Finished | [14 empty] | 2019-07-17 | 2019-08-17 | 2019-08-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-01 | 2020-12-01 | [41 empty] | 2020-11-04 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-17 | [12 empty] | 0 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished | [10 empty] | 50 | 2022-03-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-10-22 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2019-08-16 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-20 | Finished | [22 empty] | 482 | 32 | 16 | 14 | 544 | 0 | 32 | 0 | 14 | 46 | 91.54 | Green |  |  | 20004608 | 2019-07-17
TFA1145-TH | HET | 61000372 | Test | ยังอยู่ในสัญญา HO | - | TH199035 | 42C Banquet | 3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2018-10-01 | 2019-08-01 | 2019-11-01 | 2021-10-29 | 1200TX-EN,R5.7M,D35 | TX-EN |  |  |  |  | 5700 | 1155600 | Nakhon Sawan | ตำบลปากน้ำโพ | 2020-10-30 | [20 empty] | 2020-10-30 | Finished | [14 empty] | 2019-07-17 | 2019-08-17 | 2019-08-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-01 | 2020-12-01 | [41 empty] | 2020-11-04 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-17 | [12 empty] | 0 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [10 empty] | 50 | 2022-03-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-10-22 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2019-08-16 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-20 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 0 | 21 | 63 | 89.76 | Green |  |  | 20004608 | 2019-07-17
TBL0123-TH | HET | 61000372 | Test | ยังอยู่ในสัญญา HO | - | TH199035 | 42C Banquet | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2018-10-01 | 2019-08-01 | 2019-11-01 | 2021-10-29 | OUG-750-CO60,60S/3F | OUG-ON1 | 750 | 60 | 3 | 3 |  | 1598580 | Nakhon Sawan | ตำบลปากน้ำโพ | 2020-10-30 | 2020-10-30 | Finished | [34 empty] | 2019-07-17 | 2019-08-17 | 2019-08-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-15 | 2021-01-25 | 2019-12-26 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-28 | Finished |  |  | 2019-12-29 | Finished |  |  | 2019-12-30 | Finished |  |  | 2019-12-31 | Finished |  |  | 2020-01-01 | Finished |  |  | 2020-01-02 | Finished |  |  | 2020-01-03 | Finished |  |  | 2020-01-04 | Finished |  |  | 100 | [41 empty] | 2020-01-04 | 1900-01-01 | 2020-01-04 | Waiting | POWER SUPPLY DELAY |  | 2021-11-17 | [12 empty] | 0 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [10 empty] | 50 | 2022-03-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2018-10-22 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2019-08-16 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-20 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 0 | 16 | 100 | 80 | Green |  |  | 20004609 | 2019-07-17
TFB0050-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.1 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R60.1M,D0 | EXH-NL |  |  |  |  | 60100 | 6072250 | Samut Prakan | อำเภอบางพลี | 2019-06-25 | [20 empty] | 2019-07-11 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-11 | 2019-09-30 | [41 empty] | 2019-07-12 | Finished |  |  | 2019-07-17 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-07-27 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-16 | Finished |  |  | 2019-08-21 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-06-15 | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-13 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1638 | 84 | 48 | 168 | 1938 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000563 | 2019-06-13
TFB0068-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.10 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-01 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-01 | 2019-08-30 | [41 empty] | 2019-07-02 | Finished |  |  | 2019-07-07 | Finished |  |  | 2019-07-12 | Finished |  |  | 2019-07-17 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-07-27 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0069-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.11 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-07 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-07 | 2019-08-30 | [41 empty] | 2019-07-08 | Finished |  |  | 2019-07-13 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29
TFB0051-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.2 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R60.1M,D0 | EXH-NL |  |  |  |  | 60100 | 6072250 | Samut Prakan | อำเภอบางพลี | 2019-06-25 | [20 empty] | 2019-07-10 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-10 | 2019-09-30 | [41 empty] | 2019-07-11 | Finished |  |  | 2019-07-16 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-06-15 | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-13 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1638 | 84 | 48 | 168 | 1938 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000563 | 2019-06-13
TFB0061-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.3 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-12 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-12 | 2019-09-30 | [41 empty] | 2019-07-13 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-22 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-06-15 | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-07 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-13 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000561 | 2019-06-07
TFB0062-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.4 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-09 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-09 | 2019-09-30 | [41 empty] | 2019-07-10 | Finished |  |  | 2019-07-15 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-25 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-14 | Finished |  |  | 2019-08-19 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-06-15 | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-22 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-13 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000563 | 2019-06-13 | QC Passed
TFB0063-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.5 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-04 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-04 | 2019-08-30 | [41 empty] | 2019-07-05 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-15 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-25 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-14 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-06-02 | 2020-06-02 | Finished |  |  | 2020-05-20 | 2020-06-02 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0064-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.6 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-02 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-02 | 2019-08-30 | [41 empty] | 2019-07-03 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-13 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-06-02 | 2020-06-02 | Finished |  |  | 2020-06-15 | 2020-06-02 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29
TFB0065-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.7 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-05 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-05 | 2019-08-30 | [41 empty] | 2019-07-06 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-16 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0066-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.8 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-08 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-08 | 2019-08-30 | [41 empty] | 2019-07-09 | Finished |  |  | 2019-07-14 | Finished |  |  | 2019-07-19 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-08-03 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-18 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0067-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-2.9 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-03 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-03 | 2019-08-30 | [41 empty] | 2019-07-04 | Finished |  |  | 2019-07-09 | Finished |  |  | 2019-07-14 | Finished |  |  | 2019-07-19 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-08-03 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0078-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.1 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-10-14 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-14 | 2020-01-31 | [41 empty] | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-04 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-19 | Finished |  |  | 2019-11-24 | Finished |  |  | 2020-01-31 | Finished |  |  | 100 | 2020-01-31 | 2020-06-02 | 2020-06-02 | Finished |  |  | 2020-06-15 | 2020-06-02 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-06 | Finished |  |  | 100 | 2020-08-31 | 2021-08-03 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02 | QC Passed
TFB0079-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.2 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-10-14 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-14 | 2020-01-31 | [41 empty] | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-04 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-19 | Finished |  |  | 2019-11-24 | Finished |  |  | 2020-01-31 | Finished |  |  | 100 | 2020-01-31 | 2020-06-02 | 2020-06-02 | Finished |  |  | 2020-05-20 | 2020-06-02 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-06 | Finished |  |  | 100 | 2020-08-09 | 2021-08-03 | 2020-08-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-12 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000596 | 2019-07-12 | QC Passed
TFB0080-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.3 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-24 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-24 | 2019-11-30 | [41 empty] | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-09 | Finished |  |  | 2019-09-14 | Finished |  |  | 2019-09-19 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-04 | Finished |  |  | 2019-11-30 | Finished |  |  | 100 | 2019-11-30 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-12 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000596 | 2019-07-12 | QC Passed
TFB0081-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.4 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-24 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-24 | 2019-11-30 | [41 empty] | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-09 | Finished |  |  | 2019-09-14 | Finished |  |  | 2019-09-19 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-04 | Finished |  |  | 2019-11-30 | Finished |  |  | 100 | 2019-11-30 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-12 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000596 | 2019-07-12 | QC Passed
TFB0082-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.5 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-26 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-26 | 2019-10-31 | [41 empty] | 2019-08-27 | Finished |  |  | 2019-08-31 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-12 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-10-31 | Finished |  |  | 100 | 2019-10-31 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-12 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000596 | 2019-07-12 | QC Passed
TFB0083-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.6 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-26 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-26 | 2019-10-31 | [41 empty] | 2019-08-27 | Finished |  |  | 2019-08-31 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-12 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-10-31 | Finished |  |  | 100 | 2019-10-31 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-25 | 2020-04-30 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-12 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000596 | 2019-07-12 | QC Passed
TFB0084-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.7 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-22 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-22 | 2019-10-31 | [41 empty] | 2019-08-23 | Finished |  |  | 2019-08-28 | Finished |  |  | 2019-09-02 | Finished |  |  | 2019-09-07 | Finished |  |  | 2019-09-12 | Finished |  |  | 2019-09-17 | Finished |  |  | 2019-09-22 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-31 | Finished |  |  | 100 | 2019-10-31 | 2020-05-11 | 2020-05-11 | Finished |  |  | 2020-05-20 | 2020-05-11 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-13 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-20 | Finished |  |  | 2019-06-24 | Finished |  |  | 2019-06-26 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000572 | 2019-06-20 | QC Passed
TFB0085-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HE-3.8 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-22 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-22 | 2019-10-31 | [41 empty] | 2019-08-23 | Finished |  |  | 2019-08-28 | Finished |  |  | 2019-09-02 | Finished |  |  | 2019-09-07 | Finished |  |  | 2019-09-12 | Finished |  |  | 2019-09-17 | Finished |  |  | 2019-09-22 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-31 | Finished |  |  | 100 | 2019-10-31 | 2020-05-11 | 2020-05-11 | Finished |  |  | 2020-05-20 | 2020-05-11 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-13 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-20 | Finished |  |  | 2019-06-24 | Finished |  |  | 2019-06-26 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000572 | 2019-06-20 | QC Passed
TFB0048-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.1 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R60.1M,D0 | EXH-NL |  |  |  |  | 60100 | 6072250 | Samut Prakan | อำเภอบางพลี | 2019-06-25 | [20 empty] | 2019-07-17 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-17 | 2019-09-30 | [41 empty] | 2019-07-18 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-22 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-05-12 | 2020-05-12 | Finished |  |  | 2020-05-20 | 2020-05-12 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-13 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1638 | 84 | 48 | 168 | 1938 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000563 | 2019-06-13
TFB0059-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.10 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-08 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-08 | 2019-08-30 | [41 empty] | 2019-07-09 | Finished |  |  | 2019-07-14 | Finished |  |  | 2019-07-19 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-08-03 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-18 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0060-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.11 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-07 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-07 | 2019-08-30 | [41 empty] | 2019-07-08 | Finished |  |  | 2019-07-13 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0049-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.2 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R60.1M,D0 | EXH-NL |  |  |  |  | 60100 | 6072250 | Samut Prakan | อำเภอบางพลี | 2019-06-25 | [20 empty] | 2019-07-19 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-18 | 2019-09-30 | [41 empty] | 2019-07-19 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-08-03 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-18 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-28 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-05-12 | 2020-05-12 | Finished |  |  | 2020-05-20 | 2020-05-12 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-13 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1638 | 84 | 48 | 168 | 1938 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000563 | 2019-06-13 | QC Passed
TFB0052-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.3 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-16 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-16 | 2019-09-30 | [41 empty] | 2019-07-17 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-07-27 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-16 | Finished |  |  | 2019-08-21 | Finished |  |  | 2019-08-26 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-20 | Finished |  |  | 2019-06-24 | Finished |  |  | 2019-06-26 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000572 | 2019-06-20
TFB0053-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.4 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-23 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-23 | 2019-09-30 | [41 empty] | 2019-07-24 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-08-03 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-18 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-28 | Finished |  |  | 2019-09-02 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-05-12 | 2020-05-12 | Finished |  |  | 2020-05-20 | 2020-05-12 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02 | QC Passed
TFB0054-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.5 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-12 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-12 | 2019-09-30 | [41 empty] | 2019-07-13 | Finished |  |  | 2019-07-18 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-22 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-07 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-13 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000561 | 2019-06-07
TFB0055-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.6 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-11 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-11 | 2019-08-30 | [41 empty] | 2019-07-12 | Finished |  |  | 2019-07-17 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-07-27 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-16 | Finished |  |  | 2019-08-21 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-07 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-13 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000561 | 2019-06-07 | QC Passed
TFB0056-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.7 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-10 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-10 | 2019-08-30 | [41 empty] | 2019-07-11 | Finished |  |  | 2019-07-16 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-07 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-13 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000561 | 2019-06-07
TFB0057-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.8 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-09 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-09 | 2019-08-30 | [41 empty] | 2019-07-10 | Finished |  |  | 2019-07-15 | Finished |  |  | 2019-07-20 | Finished |  |  | 2019-07-25 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-14 | Finished |  |  | 2019-08-19 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-07 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-13 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000561 | 2019-06-07 | QC Passed
TFB0058-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-2.9 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.1M,D0 | EXH-NL |  |  |  |  | 50100 | 5510500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-07-05 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-05 | 2019-08-30 | [41 empty] | 2019-07-06 | Finished |  |  | 2019-07-11 | Finished |  |  | 2019-07-16 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-30 | Finished |  |  | 100 | 2019-08-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-04-29 |  |  |  | HDME000549 | 2019-05-29 | QC Passed
TFB0070-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.1 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-10-19 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-19 | 2019-12-30 | [41 empty] | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-04 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-19 | Finished |  |  | 2019-11-24 | Finished |  |  | 2019-11-29 | Finished |  |  | 2019-12-30 | Finished |  |  | 100 | 2019-12-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02 | QC Passed
TFB0071-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.2 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-10-19 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-19 | 2019-12-30 | [41 empty] | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-04 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-19 | Finished |  |  | 2019-11-24 | Finished |  |  | 2019-11-29 | Finished |  |  | 2019-12-30 | Finished |  |  | 100 | 2019-12-30 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02
TFB0072-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.3 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-08-30 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-30 | 2019-11-15 | [41 empty] | 2019-08-31 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-12 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-11-15 | Finished |  |  | 100 | 2019-11-15 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02
TFB0073-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.4 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-08-30 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-30 | 2019-11-15 | [41 empty] | 2019-08-31 | Finished |  |  | 2019-09-04 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-12 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-11-15 | Finished |  |  | 100 | 2019-11-15 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02
TFB0074-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.5 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-08-18 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-18 | 2019-11-15 | [41 empty] | 2019-08-19 | Finished |  |  | 2019-08-24 | Finished |  |  | 2019-08-29 | Finished |  |  | 2019-09-03 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-18 | Finished |  |  | 2019-09-23 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-11-15 | Finished |  |  | 100 | 2019-11-15 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02
TFB0075-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.6 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | [20 empty] | 2019-08-18 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-18 | 2019-11-15 | [41 empty] | 2019-08-19 | Finished |  |  | 2019-08-24 | Finished |  |  | 2019-08-29 | Finished |  |  | 2019-09-03 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-18 | Finished |  |  | 2019-09-23 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-11-15 | Finished |  |  | 100 | 2019-11-15 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-18 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-02 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000584 | 2019-07-02
TFB0076-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.7 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-20 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-20 | 2019-11-15 | [41 empty] | 2019-08-21 | Finished |  |  | 2019-08-26 | Finished |  |  | 2019-08-31 | Finished |  |  | 2019-09-05 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-25 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-11-15 | Finished |  |  | 100 | 2019-11-15 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-18 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-05-13 | 2021-08-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-20 | Finished |  |  | 2019-06-24 | Finished |  |  | 2019-06-26 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000572 | 2019-06-20 | QC Passed
TFB0077-TH | HET | 61000374 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | TR-HW-3.8 |  |  | 1 | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-02-15 | 2020-02-15 | 2021-04-23 | 1200EXH-EN,R50.5M,D0 | EXH-NL |  |  |  |  | 50500 | 5724500 | Samut Prakan | อำเภอบางพลี | 2019-08-05 | [20 empty] | 2019-08-20 | Finished | [14 empty] | 2019-02-01 | 2019-02-01 | 2019-06-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-20 | 2019-11-15 | [41 empty] | 2019-08-21 | Finished |  |  | 2019-08-26 | Finished |  |  | 2019-08-31 | Finished |  |  | 2019-09-05 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-25 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-11-15 | Finished |  |  | 100 | 2019-11-15 | 2020-05-16 | 2020-05-16 | Finished |  |  | 2020-05-20 | 2020-05-16 | Finished |  |  | 2020-05-18 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-20 | Finished |  |  | 2019-06-24 | Finished |  |  | 2019-06-26 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1386 | 74 | 40 | 140 | 1640 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20004613 | 2019-05-29 |  |  |  | HDME000572 | 2019-06-20
TBL0126-TH | HET | 61000378 | HO | ส่งมอบแล้ว | - | TH199039 | โรงพยาบาลราชพิพัฒน์ [อ.อเนกประสงค์] | PL3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | KITTITUCH MONGKOLKULASAB | 2018-10-15 | 2019-04-19 | 2019-09-15 | 2020-08-11 | OUG-1600-2S60,60S/8F | OUG-ON1 | 1600 | 60 | 8 | 8 |  | 2600000 | Bangkok | แขวงบางไผ่ เขตบางแค | 2019-10-05 | 2019-10-05 | Finished | [34 empty] | 2019-04-12 | 2019-05-30 | 2019-04-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-05 | 2019-11-28 | 2019-10-06 | Finished |  |  | 2019-10-08 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-29 | Finished |  |  | 2019-11-04 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-20 | Finished |  |  | 2019-11-24 | Finished |  |  | 100 | [41 empty] | 2019-11-24 | 2020-01-14 | 2020-01-14 | Finished |  |  | 2020-01-14 | 2020-01-14 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-24 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-03-26 | Finished | POWER SUPPLY DELAY |  | 2020-04-17 | Finished |  |  | 2018-11-07 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2019-04-25 | Finished |  |  | 2019-02-25 | Finished |  |  | 2019-04-26 | Finished |  |  | 2020-04-17 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 649 | 88 | 24 | 16 | 777 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20004865 | 2019-04-12 |  |  |  | HDME000527 | 2019-04-25 | QC Passed
TBL0127-TH | HET | 61000378 | HO | ส่งมอบแล้ว | - | TH199039 | โรงพยาบาลราชพิพัฒน์ [อ.อเนกประสงค์] | PL4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | KITTITUCH MONGKOLKULASAB | 2018-10-15 | 2019-04-19 | 2019-09-15 | 2020-08-11 | OUG-1600-2S60,60S/9F | OUG-ON1 | 1600 | 60 | 9 | 9 |  | 3000000 | Bangkok | แขวงบางไผ่ เขตบางแค | 2019-10-05 | 2019-10-05 | Finished | [34 empty] | 2019-05-24 | 2019-05-30 | 2019-06-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-05 | 2019-11-28 | 2019-10-06 | Finished |  |  | 2019-10-08 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-29 | Finished |  |  | 2019-11-04 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-20 | Finished |  |  | 2019-11-24 | Finished |  |  | 100 | [41 empty] | 2019-11-24 | 2020-01-14 | 2020-01-14 | Finished |  |  | 2020-01-14 | 2020-01-14 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-20 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-03-26 | Finished | POWER SUPPLY DELAY |  | 2020-04-17 | Finished |  |  | 2018-11-07 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2019-06-13 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-14 | Finished |  |  | 2020-04-17 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20004865 | 2019-05-24 |  |  |  | HDME000567 | 2019-06-13 | QC Passed
TAJ0398-TH | HET | 61000383 | HO | ยังอยู่ในสัญญา HO | - | TH209001 | Residence 5Fl., Ngamwongwan 44 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Chanyuth Soithong | 2018-09-27 | 2020-02-27 | 2020-04-27 | 2021-11-30 | P-600-CO60W,60S/6F | UAG-SN1 | 600 | 60 | 5 | 6 |  | 1177000 | Bangkok | แขวงลาดยาว | 2021-11-30 | [36 empty] | 2020-02-20 | 2020-02-21 | 2020-02-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2021-12-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2018-10-22 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-25 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Green |  |  | 20004837 | 2020-02-20 |  |  |  | HDME000798 | 2020-02-21
TEC0131-TH | HET | 61000397 | Install | ยังอยู่ในสัญญา HO | - | TH199058 | Melia Chiang Mai | D7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2018-10-09 | 2019-05-01 | 2020-02-28 | 2021-11-05 | DF-300S-B30,30S/2F | DF | 300 | 30 | 2 | 2 |  | 449400 | Chiang Mai | Tambon Chang KhlanChang Khlan | 2019-07-10 | 2019-08-25 | Finished | [34 empty] | 2019-08-26 | 2019-09-20 | 2019-09-20 | Finished | SPECIFICATION REVISION | [13 empty] | 2019-08-25 | 2019-09-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-16 | 2019-09-16 | Finished |  |  | 2019-09-16 | 2019-09-17 | Finished |  |  | 2019-09-19 | Finished |  |  | 2019-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-05-03 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-09-17 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-09-30 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Green |  |  | 20008004 | 2019-08-26 |  |  |  | HDME000654 | 2019-09-17
TEC0132-TH | HET | 61000397 | Install | ยังอยู่ในสัญญา HO | - | TH199058 | Melia Chiang Mai | D8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2018-10-09 | 2019-05-01 | 2020-02-28 | 2021-11-05 | DF-300S-B30,30S/2F | DF | 300 | 30 | 2 | 2 |  | 449400 | Chiang Mai | Tambon Chang KhlanChang Khlan | 2019-11-30 | 2019-08-25 | Finished | [34 empty] | 2019-08-26 | 2019-09-20 | 2019-09-20 | Finished | SPECIFICATION REVISION | [13 empty] | 2019-08-25 | 2019-09-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-16 | 2019-09-16 | Finished |  |  | 2019-09-16 | 2019-09-18 | Finished |  |  | 2019-09-19 | Finished |  |  | 2019-09-21 | Finished |  |  | 100 | [18 empty] | 0 | 2021-11-30 | Working | CONTRACT CANCELLATION | [5 empty] | 2019-05-03 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-09-17 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-09-30 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Green |  |  | 20008004 | 2019-08-26 |  |  |  | HDME000654 | 2019-09-17
TAC1508-TH | HET | 61000397 | HO | ส่งมอบแล้ว | - | TH199058 | Melia Chiang Mai | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2018-10-09 | 2019-05-01 | 2020-02-28 |  | VFI-1000-CO105,105S/19F | VFI-II | 1000 | 105 | 19 | 19 |  | 2493100 | Chiang Mai | Tambon Chang KhlanChang Khlan | 2019-06-30 | 2019-11-01 | Finished | [34 empty] | 2019-10-22 | 2019-10-31 | 2019-10-31 | Finished | SPECIFICATION REVISION | [13 empty] | 2019-11-01 | 2019-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-01 | 2019-12-01 | Finished |  |  | 2019-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2020-02-28 | Finished | TESTING DELAY |  | 2020-02-29 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2019-10-25 | Finished |  |  | 2019-10-31 | Finished |  |  | 2019-10-31 | Finished |  |  | 2020-02-29 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-04 | Finished |  | pass |  |  |  |  | 1301 | 112 | 40 | 20 | 1473 | 0 | 0 | 40 | 20 | 60 | 95.93 | Blue |  |  | 20008005 | 2019-10-22 |  |  |  | HDME000691 | 2019-10-25
TAC1509-TH | HET | 61000397 | HO | ส่งมอบแล้ว | - | TH199058 | Melia Chiang Mai | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2018-10-09 | 2019-05-01 | 2020-02-28 |  | VFI-1000-CO105,105S/19F | VFI-II | 1000 | 105 | 19 | 19 |  | 2493100 | Chiang Mai | Tambon Chang KhlanChang Khlan | 2019-07-10 | 2019-11-01 | Finished | [34 empty] | 2019-10-22 | 2019-10-31 | 2019-10-31 | Finished | SPECIFICATION REVISION | [13 empty] | 2019-11-01 | 2019-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-12-01 | 2019-12-01 | Finished |  |  | 2019-12-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2020-02-28 | Finished | TESTING DELAY |  | 2020-02-29 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2019-10-25 | Finished |  |  | 2019-10-31 | Finished |  |  | 2019-10-31 | Finished |  |  | 2020-02-29 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-04 | Finished |  | pass |  |  |  |  | 1301 | 112 | 40 | 20 | 1473 | 0 | 0 | 40 | 20 | 60 | 95.93 | Blue |  |  | 20008005 | 2019-10-22 |  |  |  | HDME000691 | 2019-10-25
TAC1510-TH | HET | 61000397 | HO | ส่งมอบแล้ว | - | TH199058 | Melia Chiang Mai | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2018-10-09 | 2019-05-01 | 2020-02-28 |  | VFI-1600-2S105,105S/20F | VFI-II | 1600 | 105 | 20 | 20 |  | 3210000 | Chiang Mai | Tambon Chang KhlanChang Khlan | 2019-06-30 | 2019-05-29 | Finished | [34 empty] | 2019-05-28 | 2019-06-04 | 2019-06-04 | Finished | SPECIFICATION REVISION | [13 empty] | 2019-05-29 | 2019-06-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-06-30 | 2019-06-30 | Finished |  |  | 2019-06-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2019-09-30 | Finished | CONSTRUCTION DELAY |  | 2019-10-15 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2019-06-03 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-11 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-18 | Finished |  |  | 2019-10-18 | Finished |  |  | 2019-10-18 | Finished |  | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 40 | 24 | 64 | 95.83 | Blue |  |  | 20005286 | 2019-05-28 |  |  |  | HDME000551 | 2019-06-03
TFA1219-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-1.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R8.65M,D30 | SX-NL |  |  |  |  | 8650 | 2835500 | Samut Prakan | อำเภอบางพลี | 2020-02-01 | [20 empty] | 2020-02-01 | Finished | [14 empty] | 2019-03-15 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-01 | 2020-03-06 | [41 empty] | 2020-02-03 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-03-06 | Finished |  |  | 100 | 2020-03-06 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 819 | 42 | 24 | 28 | 913 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19
TFA1220-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-1.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R8.65M,D30 | SX-NL |  |  |  |  | 8650 | 2835500 | Samut Prakan | อำเภอบางพลี | 2020-02-01 | [20 empty] | 2020-02-01 | Finished | [14 empty] | 2019-03-15 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-01 | 2020-03-06 | [41 empty] | 2020-02-03 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-03-06 | Finished |  |  | 100 | 2020-03-06 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2020-08-09 | 2000-01-01 | 2020-08-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 819 | 42 | 24 | 28 | 913 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19
TFA1174-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-2.2(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.1M,D30 | SX-NL |  |  |  |  | 5100 | 1444500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-04 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-12-31 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-23 | 2020-06-23 | Finished |  |  | 2020-06-30 | 2020-06-24 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-29 | Finished |  |  | 100 | 2020-08-31 | 2000-01-01 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19
TFA1175-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-2.2(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.1M,D30 | SX-NL |  |  |  |  | 5100 | 1444500 | Samut Prakan | อำเภอบางพลี | 2019-10-15 | [20 empty] | 2019-10-15 | Finished | [14 empty] | 2019-03-15 | 2019-04-04 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-12-31 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-23 | 2020-06-23 | Finished |  |  | 2020-06-30 | 2020-06-24 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-29 | Finished |  |  | 100 | 2020-08-31 | 2000-01-01 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19
TFA1178-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-2.3 (A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.1M,D30 | SX-NL |  |  |  |  | 5100 | 1551500 | Samut Prakan | อำเภอบางพลี | 2019-08-14 | [20 empty] | 2019-08-14 | Finished | [14 empty] | 2019-03-15 | 2019-04-05 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-01 | 2019-11-20 | [41 empty] | 2019-10-03 | Finished |  |  | 2019-10-06 | Finished |  |  | 2019-10-09 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-13 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1179-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-2.3 (B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.1M,D30 | SX-NL |  |  |  |  | 5100 | 1551500 | Samut Prakan | อำเภอบางพลี | 2019-08-14 | [20 empty] | 2019-08-14 | Finished | [14 empty] | 2019-03-15 | 2019-04-05 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-01 | 2019-11-20 | [41 empty] | 2019-10-03 | Finished |  |  | 2019-10-06 | Finished |  |  | 2019-10-09 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-13 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01 | QC Passed
TFA1169-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-3.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-03 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-06-22 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2020-07-02 | 2000-01-01 | 2020-07-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19
TFA1170-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-3.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-03 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-06-22 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2020-07-02 | 2021-07-23 | 2020-07-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19 | QC Passed
TFA1176-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-3.2(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-10-15 | [20 empty] | 2019-10-15 | Finished | [14 empty] | 2019-03-15 | 2019-04-04 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-11-20 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01 | QC Passed
TFA1177-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-3.2(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-10-15 | [20 empty] | 2019-10-15 | Finished | [14 empty] | 2019-03-15 | 2019-04-04 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-11-20 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1161-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-4.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6M,D30 | SX-NL |  |  |  |  | 6000 | 1765500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-02 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-21 | 2020-06-21 | Finished |  |  | 2020-06-30 | 2020-06-22 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2020-02-24 | 2000-01-01 | 2020-02-24 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19
TFA1162-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-4.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6M,D30 | SX-NL |  |  |  |  | 6000 | 1765500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-02 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-06-22 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2020-07-02 | 2000-01-01 | 2020-07-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19
TFA1180-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-09-15 | [20 empty] | 2019-09-15 | Finished | [14 empty] | 2019-03-15 | 2019-04-05 | 2019-09-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-14 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-05 | Finished |  |  | 2019-09-05 | Finished |  |  | 2019-09-16 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000643 | 2019-09-05 | QC Passed
TFA1189-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-02-29 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-28 | Finished |  |  | 2019-01-07 | Finished |  |  | 2019-01-15 | Finished |  |  | 2019-01-28 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-17 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-29 | Finished |  |  | 100 | 2020-02-29 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27
TFA1190-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-11 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27
TFA1191-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-12 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27 | QC Passed
TFA1192-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-13 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27
TFA1193-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-14 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27 | QC Passed
TFA1194-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-15 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27
TFA1195-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-16 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27
TFA1196-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-17 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-10-31 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-15 | 2020-02-29 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-28 | Finished |  |  | 2019-01-07 | Finished |  |  | 2019-01-15 | Finished |  |  | 2019-01-28 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-17 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-29 | Finished |  |  | 100 | 2020-02-29 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04
TFA1197-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-18 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-10-31 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-15 | 2020-02-29 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-28 | Finished |  |  | 2019-01-07 | Finished |  |  | 2019-01-15 | Finished |  |  | 2019-01-28 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-17 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-29 | Finished |  |  | 100 | 2020-02-29 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04
TFA1198-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-19 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-10-31 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04 | QC Passed
TFA1181-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-04-05 | 2019-09-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-02-15 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-04 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2020-08-31 | 2021-07-23 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-05 | Finished |  |  | 2019-09-05 | Finished |  |  | 2019-09-16 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000643 | 2019-09-05 | QC Passed
TFA1199-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-20 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-10-31 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04 | QC Passed
TFA1200-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-21 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04 | QC Passed
TFA1201-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-22 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04 | QC Passed
TFA1202-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-23 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04 | QC Passed
TFA1203-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-24 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04 | QC Passed
TFA1204-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-25 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-01-31 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-04 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04 | QC Passed
TFA1205-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-26 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-01-31 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-04 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-04 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000673 | 2019-10-04
TFA1206-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-27 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1207-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-28 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-07-15 | 2020-06-21 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1208-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-29 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1182-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-10-01 | [20 empty] | 2019-10-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-05 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-01 | 2020-01-31 | [41 empty] | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-15 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-30 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-31 | Finished |  |  | 100 | 2020-01-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-14 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19
TFA1209-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-30 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-07-15 | 2020-06-21 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01 | QC Passed
TFA1210-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-31 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1211-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-32 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-07-15 | 2020-06-21 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1212-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-33 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1213-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-34 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-07-15 | 2020-06-21 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1214-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-35 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1215-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-36 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-10-31 | Finished | [14 empty] | 2019-03-15 | 2019-11-04 | 2019-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-12-31 | [41 empty] | 2019-11-03 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-21 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-19 | 2020-06-19 | Finished |  |  | 2020-07-15 | 2020-06-21 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-12 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000697 | 2019-11-01
TFA1183-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-04-05 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-02-15 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-04 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19 | QC Passed
TFA1184-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-03-15 | 2019-04-05 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-01 | 2020-01-31 | [41 empty] | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-15 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-30 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-31 | Finished |  |  | 100 | 2020-01-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-14 | Finished |  |  | 100 | 2020-12-10 | 2021-07-23 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-04 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19 | QC Passed
TFA1185-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-02-15 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-04 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19
TFA1186-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-01 | 2020-01-31 | [41 empty] | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-15 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-30 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-31 | Finished |  |  | 100 | 2020-01-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-06-30 | 2020-06-11 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-14 | Finished |  |  | 100 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-04 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27
TFA1187-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-02-15 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-04 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-01 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27
TFA1188-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-9 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6.5M,D30 | SX-NL |  |  |  |  | 6500 | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-03-15 | 2019-09-26 | 2019-09-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-01 | 2020-01-31 | [41 empty] | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-15 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-30 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-31 | Finished |  |  | 100 | 2020-01-31 | 2020-06-09 | 2020-06-09 | Finished |  |  | 2020-08-20 | 2020-06-11 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000663 | 2019-09-27 | QC Passed
TFA1216-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-1.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R8.65M,D30 | SX-NL |  |  |  |  | 8650 | 2835500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-03-06 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-30 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-03-06 | Finished |  |  | 100 | 2020-03-06 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2020-08-22 | 2000-01-01 | 2020-08-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 819 | 42 | 24 | 28 | 913 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19
TFA1217-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-1.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R8.65M,D30 | SX-NL |  |  |  |  | 8650 | 2835500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-03-06 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-30 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-03-06 | Finished |  |  | 100 | 2020-03-06 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 819 | 42 | 24 | 28 | 913 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19
TFA1218-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-1.1(C) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R8.65M,D30 | SX-NL |  |  |  |  | 8650 | 2835500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-03-15 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-03-06 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-30 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-03-06 | Finished |  |  | 100 | 2020-03-06 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-19 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 819 | 42 | 24 | 28 | 913 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000655 | 2019-09-19
TFA1171-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-2.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.1M,D30 | SX-NL |  |  |  |  | 5100 | 1444500 | Samut Prakan | อำเภอบางพลี | 2019-10-15 | [20 empty] | 2019-10-15 | Finished | [14 empty] | 2019-03-15 | 2019-04-04 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-12-31 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1172-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-2.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.1M,D30 | SX-NL |  |  |  |  | 5100 | 1444500 | Samut Prakan | อำเภอบางพลี | 2019-10-15 | [20 empty] | 2019-10-15 | Finished | [14 empty] | 2019-03-15 | 2019-04-04 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-12-31 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1173-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-2.1(C) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.1M,D30 | SX-NL |  |  |  |  | 5100 | 1444500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-04 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-12-31 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1163-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-3.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-02 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-05 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1164-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-3.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-03 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-05 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1165-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-3.2(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-03 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1166-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-3.2(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-03 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1167-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-3.3(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-14 | [20 empty] | 2019-08-14 | Finished | [14 empty] | 2019-03-15 | 2019-04-03 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-11-20 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-06-22 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01 | QC Passed
TFA1168-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-3.3(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R5.7M,D30 | SX-NL |  |  |  |  | 5700 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-08-14 | [20 empty] | 2019-08-14 | Finished | [14 empty] | 2019-03-15 | 2019-04-03 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-11-20 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-06-22 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1157-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-4.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6M,D30 | SX-NL |  |  |  |  | 6000 | 1765500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-02 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-15 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01
TFA1158-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-4.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6M,D30 | SX-NL |  |  |  |  | 6000 | 1765500 | Samut Prakan | อำเภอบางพลี | 2019-08-01 | [20 empty] | 2019-08-01 | Finished | [14 empty] | 2019-03-15 | 2019-04-02 | 2019-08-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-01 | 2019-09-30 | [41 empty] | 2019-08-03 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-10 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2019-09-30 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-15 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-01 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-08 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000608 | 2019-08-01 | QC Passed
TFA1159-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-4.2(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6M,D30 | SX-NL |  |  |  |  | 6000 | 1765500 | Samut Prakan | อำเภอบางพลี | 2019-08-14 | [20 empty] | 2019-08-14 | Finished | [14 empty] | 2019-03-15 | 2019-04-02 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-11-20 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-15 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19 | QC Passed
TFA1160-TH | HET | 61000398 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-4.2(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-03-30 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R6M,D30 | SX-NL |  |  |  |  | 6000 | 1765500 | Samut Prakan | อำเภอบางพลี | 2019-08-14 | [20 empty] | 2019-08-14 | Finished | [14 empty] | 2019-03-15 | 2019-04-02 | 2019-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-15 | 2019-11-20 | [41 empty] | 2019-10-17 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-11 | Finished |  |  | 2019-11-15 | Finished |  |  | 2019-11-20 | Finished |  |  | 100 | 2019-11-20 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-07-15 | 2020-07-03 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished | [6 empty] | 90 | 2021-05-31 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 693 | 42 | 24 | 21 | 780 | 0 | 0 | 0 | 2 | 2 | 99.74 | Blue |  |  | 20005319 | 2019-03-15 |  |  |  | HDME000600 | 2019-07-19
TBL0177-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | Conc.-D-01 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 2 | 4 |  | 1498000 | Samut Prakan | อำเภอบางพลี | 2020-01-20 | 2020-01-21 | Finished | [34 empty] | 2019-05-30 | 2019-08-10 | 2019-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-20 | 2020-06-30 | 2020-05-22 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | [41 empty] | 2020-06-17 | 2020-12-01 | 2020-12-01 | Finished |  |  | 2020-09-10 | 2020-12-05 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 100 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-09 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000613 | 2019-08-09
TBL0178-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | Conc.-D-02 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 2 | 4 |  | 1498000 | Samut Prakan | อำเภอบางพลี | 2020-01-20 | 2020-01-21 | Finished | [34 empty] | 2019-05-30 | 2019-08-10 | 2019-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-20 | 2020-06-30 | 2020-05-22 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | [41 empty] | 2020-06-17 | 2020-12-01 | 2020-12-01 | Finished |  |  | 2020-09-10 | 2020-12-05 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 100 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-09 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000613 | 2019-08-09
TBL0179-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | Conc.-D-03 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 2 | 4 |  | 1658500 | Samut Prakan | อำเภอบางพลี | 2020-01-20 | 2020-01-21 | Finished | [34 empty] | 2019-05-30 | 2019-08-10 | 2019-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-20 | 2020-06-30 | 2020-06-10 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-28 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | [41 empty] | 2020-07-01 | 2020-12-03 | 2020-12-03 | Finished |  |  | 2020-09-10 | 2020-12-09 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-09 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000613 | 2019-08-09
TBL0180-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | Conc.-D-04 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 2 | 4 |  | 1658500 | Samut Prakan | อำเภอบางพลี | 2020-01-20 | 2020-01-21 | Finished | [34 empty] | 2019-05-30 | 2019-08-10 | 2019-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-20 | 2020-06-30 | 2020-06-10 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-28 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | [41 empty] | 2020-07-01 | 2020-12-03 | 2020-12-03 | Finished |  |  | 2020-09-10 | 2020-12-09 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-09 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000613 | 2019-08-09
TBL0137-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | EL-HW-11(LF21) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1391000 | Samut Prakan | อำเภอบางพลี | 2019-09-20 | 2019-09-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-14 | 2019-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-19 | 2019-11-16 | 2019-07-22 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-06 | Finished |  |  | 100 | [41 empty] | 2019-08-06 | 2019-08-17 | 2019-08-17 | Finished |  |  | 2019-08-17 | 2019-08-22 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-14 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-07 | Finished |  |  | 2019-05-14 | Finished |  |  | 2019-05-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000536 | 2019-05-07
TBL0138-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-1(LF9) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/5F | OUG-ON1 | 2000 | 60 | 3 | 5 |  | 1872500 | Samut Prakan | อำเภอบางพลี | 2019-09-20 | 2019-09-20 | Finished | [34 empty] | 2019-05-30 | 2019-06-14 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-19 | 2019-11-16 | 2019-07-22 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-16 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-10 | Finished |  |  | 100 | [41 empty] | 2019-08-10 | 2019-08-20 | 2019-08-20 | Finished |  |  | 2019-08-20 | 2019-08-25 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-28 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-10 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000562 | 2019-06-10
TBL0146-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-10(LF19) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-09-20 | 2019-09-20 | Finished | [34 empty] | 2019-05-30 | 2019-06-14 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-05 | 2019-11-16 | 2019-08-08 | Finished |  |  | 2019-08-24 | Finished |  |  | 2019-08-26 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-18 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-22 | Finished |  |  | 100 | [41 empty] | 2019-08-22 | 2019-08-06 | 2019-08-06 | Finished |  |  | 2019-08-06 | 2019-08-11 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2020-02-11 | 2000-01-01 | 2020-02-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-31 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-10 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000562 | 2019-06-10
TBL0147-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-11(LF16) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1391000 | Samut Prakan | อำเภอบางพลี | 2019-09-04 | 2019-09-04 | Finished | [34 empty] | 2019-05-30 | 2019-05-14 | 2019-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-15 | 2019-11-16 | 2019-07-18 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-06 | Finished |  |  | 100 | [41 empty] | 2019-08-06 | 2019-08-20 | 2019-08-20 | Finished |  |  | 2019-08-20 | 2019-08-25 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-07 | Finished |  |  | 2019-05-14 | Finished |  |  | 2019-05-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000536 | 2019-05-07
TBL0148-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-12(LF17) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1391000 | Samut Prakan | อำเภอบางพลี | 2019-09-04 | 2019-09-04 | Finished | [34 empty] | 2019-05-30 | 2019-05-14 | 2019-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-15 | 2019-11-16 | 2019-07-18 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-06 | Finished |  |  | 100 | [41 empty] | 2019-08-06 | 2019-08-20 | 2019-08-20 | Finished |  |  | 2019-08-20 | 2019-09-14 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-07 | Finished |  |  | 2019-05-14 | Finished |  |  | 2019-05-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000536 | 2019-05-07
TBL0139-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-2(LF10) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/5F | OUG-ON1 | 2000 | 60 | 3 | 5 |  | 1872500 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-14 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-19 | 2019-11-16 | 2019-07-22 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-16 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-10 | Finished |  |  | 100 | [41 empty] | 2019-08-10 | 2019-08-20 | 2019-08-20 | Finished |  |  | 2019-08-20 | 2019-08-25 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-28 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-10 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000562 | 2019-06-10
TBL0140-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-3(LF4) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/4F | OUG-ON1 | 2000 | 60 | 3 | 4 |  | 2140000 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | 2019-06-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-14 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-17 | 2019-11-16 | 2019-07-20 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-07-25 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-08 | Finished |  |  | 100 | [41 empty] | 2019-08-08 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 2019-09-15 | Finished |  |  | 2020-06-06 | Finished |  |  | 2020-06-16 | Finished |  |  | 100 | 2020-05-06 | 2000-01-01 | 2020-05-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-10 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000562 | 2019-06-10
TBL0141-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-4(LF5) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/4F | OUG-ON1 | 2000 | 60 | 3 | 4 |  | 2140000 | Samut Prakan | อำเภอบางพลี | 2019-06-30 | 2019-06-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-14 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-17 | 2019-11-16 | 2019-07-20 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-07-25 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-08 | Finished |  |  | 100 | [41 empty] | 2019-08-08 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 2019-10-26 | Finished |  |  | 2020-06-06 | Finished |  |  | 2020-06-16 | Finished |  |  | 100 | 2020-02-28 | 2000-01-01 | 2020-02-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-10 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000562 | 2019-06-10
TBL0142-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-6(LF2) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 5 | 6 |  | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-18 | 2019-11-16 | 2019-09-21 | Finished |  |  | 2019-10-18 | Finished |  |  | 2019-10-20 | Finished |  |  | 2019-10-23 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-10-02 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-08 | Finished |  |  | 2019-10-11 | Finished |  |  | 2019-10-13 | Finished |  |  | 100 | [41 empty] | 2019-10-13 | 2019-10-26 | 2019-10-26 | Finished |  |  | 2019-10-26 | 2019-11-08 | Finished |  |  | 2020-07-26 | Finished |  |  | 2020-08-10 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0143-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-7(LF3) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 5 | 6 |  | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-31 | 2019-11-16 | 2019-09-03 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-28 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-13 | Finished |  |  | 2019-09-15 | Finished |  |  | 2019-09-17 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-22 | Finished |  |  | 100 | [41 empty] | 2019-09-22 | 2019-10-03 | 2019-10-03 | Finished |  |  | 2019-10-03 | 2019-10-09 | Finished |  |  | 2020-07-26 | Finished |  |  | 2020-08-10 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0144-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-8(LF22) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/2F | OUG-ON1 | 2000 | 60 | 2 | 2 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-07-15 | 2019-07-15 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-23 | 2019-11-16 | 2019-08-26 | Finished |  |  | 2019-09-12 | Finished |  |  | 2019-09-14 | Finished |  |  | 2019-09-16 | Finished |  |  | 2019-08-29 | Finished |  |  | 2019-09-01 | Finished |  |  | 2019-09-03 | Finished |  |  | 2019-09-05 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-10 | Finished |  |  | 100 | [41 empty] | 2019-09-10 | 2019-09-20 | 2019-09-20 | Finished |  |  | 2019-09-20 | 2019-09-25 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | 2020-01-20 | 2021-07-02 | 2020-01-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05 | QC Passed
TBL0145-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HE-9(LF18) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-07-15 | 2019-07-15 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-05 | 2019-11-16 | 2019-08-08 | Finished |  |  | 2019-08-24 | Finished |  |  | 2019-08-26 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-18 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-22 | Finished |  |  | 100 | [41 empty] | 2019-08-22 | 2019-08-06 | 2019-08-06 | Finished |  |  | 2019-08-06 | 2019-08-11 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0149-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-06-01 | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0158-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-10 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-08-07 | 2019-08-07 | Finished |  |  | 2019-06-01 | 2019-08-07 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-12-17 | Finished |  |  | 100 | 2020-01-06 | 2000-01-01 | 2020-01-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0159-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-11 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-09-05 | 2019-09-05 | Finished |  |  | 2019-06-01 | 2019-09-05 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-10-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0160-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-12 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-08-14 | 2019-08-14 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-12-09 | Finished |  |  | 100 | 2019-12-16 | 2000-01-01 | 2019-12-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0161-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-13 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-20 | 2019-08-30 | 2019-05-22 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-19 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-16 | Finished |  |  | 100 | [41 empty] | 2019-06-16 | 2019-09-03 | 2019-09-03 | Finished |  |  | 2019-06-01 | 2019-09-19 | Finished |  |  | 2019-10-07 | Finished |  |  | 2019-10-07 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0162-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-14 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-25 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-25 | 2019-08-30 | 2019-05-27 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-23 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-07 | Finished |  |  | 2019-06-11 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-16 | Finished |  |  | 2019-06-20 | Finished |  |  | 100 | [41 empty] | 2019-06-20 | 2019-07-31 | 2019-07-31 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-12-09 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0163-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-15 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-25 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-25 | 2019-08-30 | 2019-05-27 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-23 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-07 | Finished |  |  | 2019-06-11 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-16 | Finished |  |  | 2019-06-20 | Finished |  |  | 100 | [41 empty] | 2019-06-20 | 2019-06-01 | 2019-06-01 | Finished |  |  | 2019-06-01 | 2019-09-13 | Finished |  |  | 2019-10-03 | Finished |  |  | 2019-10-03 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0164-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-16 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-09 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-09 | 2019-08-30 | 2019-05-11 | Finished |  |  | 2019-05-23 | Finished |  |  | 2019-06-08 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-16 | Finished |  |  | 2019-05-21 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-28 | Finished |  |  | 2019-06-01 | Finished |  |  | 2019-06-05 | Finished |  |  | 100 | [41 empty] | 2019-06-05 | 2019-07-05 | 2019-07-05 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-12-09 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0165-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-17 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-20 | 2019-08-30 | 2019-05-22 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-01 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-07 | Finished |  |  | 2019-06-11 | Finished |  |  | 100 | [41 empty] | 2019-06-11 | 2019-06-01 | 2019-06-01 | Finished |  |  | 2019-06-01 | 2019-10-02 | Finished |  |  | 2019-10-08 | Finished |  |  | 2019-10-08 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0166-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-18 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-09 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-09 | 2019-08-30 | 2019-05-11 | Finished |  |  | 2019-05-23 | Finished |  |  | 2019-06-08 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-16 | Finished |  |  | 2019-05-21 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-28 | Finished |  |  | 2019-06-01 | Finished |  |  | 2019-06-05 | Finished |  |  | 100 | [41 empty] | 2019-06-05 | 2019-07-04 | 2019-07-04 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 2019-11-25 | Finished |  |  | 2019-11-25 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0167-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-19 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-20 | 2019-08-30 | 2019-05-22 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-19 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-16 | Finished |  |  | 100 | [41 empty] | 2019-06-16 | 2019-09-19 | 2019-09-19 | Finished |  |  | 2019-06-01 | 2019-09-19 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-26 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0150-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-2 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-08-14 | 2019-08-14 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-13 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0168-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-20 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-20 | 2019-08-30 | 2019-05-22 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-19 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-16 | Finished |  |  | 100 | [41 empty] | 2019-06-16 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-06-01 | 2019-11-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-25 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0169-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-21 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-20 | 2019-08-30 | 2019-05-22 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-19 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-16 | Finished |  |  | 100 | [41 empty] | 2019-06-16 | 2019-09-03 | 2019-09-03 | Finished |  |  | 2019-06-01 | 2019-09-19 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-24 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0170-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-22 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-09 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-09 | 2019-08-30 | 2019-05-11 | Finished |  |  | 2019-05-23 | Finished |  |  | 2019-06-08 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-16 | Finished |  |  | 2019-05-21 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-28 | Finished |  |  | 2019-06-01 | Finished |  |  | 2019-06-05 | Finished |  |  | 100 | [41 empty] | 2019-06-05 | 2019-06-26 | 2019-06-26 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-12-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0171-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-23 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-20 | 2019-08-30 | 2019-05-22 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-19 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-16 | Finished |  |  | 100 | [41 empty] | 2019-06-16 | 2019-08-22 | 2019-08-22 | Finished |  |  | 2019-06-01 | 2019-09-02 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-09-24 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0172-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-24 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-09 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-09 | 2019-08-30 | 2019-05-11 | Finished |  |  | 2019-05-23 | Finished |  |  | 2019-06-08 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-16 | Finished |  |  | 2019-05-21 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-28 | Finished |  |  | 2019-06-01 | Finished |  |  | 2019-06-05 | Finished |  |  | 100 | [41 empty] | 2019-06-05 | 2019-07-01 | 2019-07-01 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-11-22 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0173-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-25 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-20 | 2019-08-30 | 2019-05-22 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-19 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-06 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-06-16 | Finished |  |  | 100 | [41 empty] | 2019-06-16 | 2019-06-26 | 2019-06-26 | Finished |  |  | 2019-06-01 | 2019-09-04 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-09-06 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0174-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-26 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-09 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-09 | 2019-08-30 | 2019-05-11 | Finished |  |  | 2019-05-23 | Finished |  |  | 2019-06-08 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-16 | Finished |  |  | 2019-05-21 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-28 | Finished |  |  | 2019-06-01 | Finished |  |  | 2019-06-05 | Finished |  |  | 100 | [41 empty] | 2019-06-05 | 2019-06-02 | 2019-06-02 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 2019-10-28 | Finished |  |  | 2019-11-07 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0175-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-27 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-25 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-25 | 2019-08-30 | 2019-05-27 | Finished |  |  | 2019-06-09 | Finished |  |  | 2019-06-23 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-07 | Finished |  |  | 2019-06-11 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-16 | Finished |  |  | 2019-06-20 | Finished |  |  | 100 | [41 empty] | 2019-06-20 | 2019-08-14 | 2019-08-14 | Finished |  |  | 2019-06-01 | 2019-08-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-09-02 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0176-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-28 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-09 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-09 | 2019-08-30 | 2019-05-11 | Finished |  |  | 2019-05-23 | Finished |  |  | 2019-06-08 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-16 | Finished |  |  | 2019-05-21 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-28 | Finished |  |  | 2019-06-01 | Finished |  |  | 2019-06-05 | Finished |  |  | 100 | [41 empty] | 2019-06-05 | 2019-07-03 | 2019-07-03 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-23 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0151-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-3 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-06-01 | 2019-06-01 | Finished |  |  | 2019-06-01 | 2019-10-07 | Finished |  |  | 2019-10-11 | Finished |  |  | 2019-10-11 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0152-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-4 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-08-13 | 2019-08-13 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-12-13 | Finished |  |  | 100 | 2020-01-06 | 2000-01-01 | 2020-01-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0153-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-5 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-06-01 | 2019-06-01 | Finished |  |  | 2019-06-01 | 2019-10-04 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-15 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0154-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-6 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-08-13 | 2019-08-13 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-12-02 | Finished |  |  | 100 | 2021-05-13 | 2021-07-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02 | QC Passed
TBL0155-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-7 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-09-09 | 2019-09-09 | Finished |  |  | 2019-06-01 | 2019-09-09 | Finished |  |  | 2019-10-21 | Finished |  |  | 2019-10-21 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0156-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-8 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-08-07 | 2019-08-07 | Finished |  |  | 2019-06-01 | 2019-08-29 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-12-02 | Finished |  |  | 100 | 2019-12-16 | 2000-01-01 | 2019-12-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0157-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HF-9 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1465900 | Samut Prakan | อำเภอบางพลี | 2019-04-22 | 2019-05-13 | Finished | [34 empty] | 2019-05-30 | 2019-05-30 | 2019-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-05-13 | 2019-08-30 | 2019-05-15 | Finished |  |  | 2019-05-27 | Finished |  |  | 2019-06-12 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-05-20 | Finished |  |  | 2019-05-25 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-06-02 | Finished |  |  | 2019-06-05 | Finished |  |  | 2019-06-09 | Finished |  |  | 100 | [41 empty] | 2019-06-09 | 2019-09-05 | 2019-09-05 | Finished |  |  | 2019-06-01 | 2019-09-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-09-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-21 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-04-02 | Finished |  |  | 2019-04-11 | Finished |  |  | 2019-04-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000512 | 2019-04-02
TBL0128-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-1(LF6) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/4F | OUG-ON1 | 2000 | 60 | 3 | 4 |  | 2140000 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-18 | 2019-11-16 | 2019-07-20 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-04 | Finished |  |  | 100 | [41 empty] | 2019-08-04 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2020-06-10 | 2019-08-20 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-08 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0136-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-10(LF20) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1391000 | Samut Prakan | อำเภอบางพลี | 2019-09-20 | 2019-09-20 | Finished | [34 empty] | 2019-05-30 | 2019-05-14 | 2019-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-19 | 2019-11-16 | 2019-07-22 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-29 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-04 | Finished |  |  | 2019-08-06 | Finished |  |  | 100 | [41 empty] | 2019-08-06 | 2019-08-17 | 2019-08-17 | Finished |  |  | 2019-08-17 | 2019-08-22 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-14 | Finished |  |  | 100 | 2020-04-20 | 2021-07-05 | 2020-04-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-05-07 | Finished |  |  | 2019-05-14 | Finished |  |  | 2019-05-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000536 | 2019-05-07 | QC Passed
TBL0135-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-12(LF52) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/2F | OUG-ON1 | 2000 | 60 | 2 | 2 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-14 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-20 | 2019-11-16 | 2019-07-22 | Finished |  |  | 2019-07-25 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-08-12 | Finished |  |  | 2019-07-25 | Finished |  |  | 2019-07-27 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-05 | Finished |  |  | 2019-08-07 | Finished |  |  | 100 | [41 empty] | 2019-08-07 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 2019-08-20 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-11 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-10 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000562 | 2019-06-10
TBL0129-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-2(LF7) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/4F | OUG-ON1 | 2000 | 60 | 3 | 4 |  | 2140000 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-18 | 2019-11-16 | 2019-07-20 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-04 | Finished |  |  | 100 | [41 empty] | 2019-08-04 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 2019-08-20 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-08 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0130-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-4(LF11) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 5 | 6 |  | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-08-15 | 2019-08-15 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-18 | 2019-11-16 | 2019-07-20 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-04 | Finished |  |  | 100 | [41 empty] | 2019-08-04 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 2019-08-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2020-05-12 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0131-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-5(LF12) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 5 | 6 |  | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-08-15 | 2019-08-15 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-18 | 2019-11-16 | 2019-07-20 | Finished |  |  | 2019-08-07 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-09 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-07-31 | Finished |  |  | 2019-08-02 | Finished |  |  | 2019-08-04 | Finished |  |  | 100 | [41 empty] | 2019-08-04 | 2019-08-15 | 2019-08-15 | Finished |  |  | 2019-08-15 | 2019-10-06 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2020-05-12 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0132-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-7(LF14) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 5 | 6 |  | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-05 | 2019-11-16 | 2019-08-08 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-02 | Finished |  |  | 2019-09-06 | Finished |  |  | 2019-08-11 | Finished |  |  | 2019-08-16 | Finished |  |  | 2019-08-20 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-27 | Finished |  |  | 100 | [41 empty] | 2019-08-27 | 2019-09-10 | 2019-09-10 | Finished |  |  | 2019-09-10 | 2020-09-06 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-10 | Finished |  |  | 100 | 2020-08-09 | 2000-01-01 | 2020-08-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0133-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-8(LF15) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 5 | 6 |  | 2300500 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-06 | 2019-06-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-25 | 2019-11-16 | 2019-09-27 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-24 | Finished |  |  | 2019-10-28 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-08 | Finished |  |  | 2019-10-11 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-19 | Finished |  |  | 100 | [41 empty] | 2019-10-19 | 2019-09-10 | 2019-09-10 | Finished |  |  | 2019-09-10 | 2020-09-06 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-10 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2020-02-12 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-05 | Finished |  |  | 2019-06-14 | Finished |  |  | 2019-06-17 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000556 | 2019-06-05
TBL0134-TH | HET | 61000403 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | HW-9,12(LF23) | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2018-06-08 | 2019-06-06 | 2019-10-28 | 2021-04-23 | OUG-2000-CO60,60S/2F | OUG-ON1 | 2000 | 60 | 2 | 2 |  | 2033000 | Samut Prakan | อำเภอบางพลี | 2019-07-30 | 2019-07-30 | Finished | [34 empty] | 2019-05-30 | 2019-06-14 | 2019-06-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-18 | 2019-11-16 | 2019-07-20 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-08 | Finished |  |  | 2019-07-22 | Finished |  |  | 2019-07-24 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-30 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-03 | Finished |  |  | 100 | [41 empty] | 2019-08-03 | 2019-08-11 | 2019-08-11 | Finished |  |  | 2019-08-11 | 2019-08-16 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-11 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-06-10 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-20 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005365 | 2019-05-30 |  |  |  | HDME000562 | 2019-06-10
TAC1512-TH | HET | 61000406 | HO | ส่งมอบแล้ว | - | TH199064 | Bangkok Thai Tower | PL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2018-11-23 | 2019-03-10 | 2020-04-23 | 2020-05-23 | VFI-1350-CO150,150S/17F | VFI-II | 1350 | 150 | 17 | 17 |  | 5082500 | Bangkok | เขตราชเทวี | 2020-02-01 | 2020-02-01 | Finished | [34 empty] | 2020-01-01 | 2020-02-16 | 2020-02-16 | Finished | OTHERS | [13 empty] | 2020-02-17 | 2020-04-10 | 2020-03-14 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-13 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 100 | [41 empty] | 2020-04-20 | 2020-04-17 | 2020-04-17 | Finished |  |  | 2020-04-11 | 2020-04-17 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-25 | Finished |  |  | 100 | 2021-05-13 | 2020-12-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-12-10 | Finished |  |  | 100 | 2020-10-01 | Finished | POWER SUPPLY DELAY |  | 2020-08-11 | Finished |  |  | 2019-01-31 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2020-02-15 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1190 | 110 | 40 | 20 | 1360 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005443 | 2019-12-01 |  |  |  | HDME000790 | 2020-02-15 | QC Passed
TAC1513-TH | HET | 61000406 | HO | ส่งมอบแล้ว | - | TH199064 | Bangkok Thai Tower | PL-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2018-11-23 | 2019-03-10 | 2020-01-23 | 2020-05-23 | VFI-1350-CO150,150S/17F | VFI-II | 1350 | 150 | 17 | 17 |  | 3177900 | Bangkok | เขตราชเทวี | 2019-09-29 | 2019-09-29 | Finished | [34 empty] | 2019-10-01 | 2019-09-28 | 2019-09-28 | Finished | OTHERS | [13 empty] | 2019-11-14 | 2020-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-01-16 | 2020-01-16 | Finished |  |  | 2020-01-16 | 2020-01-30 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-10 | Finished |  |  | 100 | 2021-05-13 | 2020-06-26 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-26 | Finished |  |  | 100 | 2020-10-01 | Finished | TESTING DELAY |  | 2020-08-11 | Finished |  |  | 2019-01-31 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2019-09-28 | Finished |  |  | 2019-11-19 | Finished |  |  | 2019-11-20 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1190 | 110 | 40 | 20 | 1360 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005443 | 2019-09-21 |  |  |  | HDME000666 | 2019-09-28 | QC Passed
TAC1514-TH | HET | 61000406 | HO | ส่งมอบแล้ว | - | TH199064 | Bangkok Thai Tower | PL-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2018-11-23 | 2019-03-10 | 2019-10-23 | 2020-05-23 | VFI-1350-CO150,150S/17F | VFI-II | 1350 | 150 | 17 | 17 |  | 3177900 | Bangkok | เขตราชเทวี | 2019-06-29 | 2019-06-29 | Finished | [34 empty] | 2019-07-01 | 2019-06-28 | 2019-06-28 | Finished | [14 empty] | 2019-07-22 | 2019-09-23 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2019-09-24 | 2019-09-24 | Finished |  |  | 2019-09-24 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-12-10 | Finished |  |  | 100 | 2019-01-11 | Finished | TESTING DELAY |  | 2019-11-13 | Finished |  |  | 2019-01-31 | Finished | [18 empty] | 2019-06-29 | Finished |  |  | 2019-07-02 | Finished |  |  | 2019-07-03 | Finished |  |  | 2019-11-13 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  | pass |  |  |  |  | 1190 | 110 | 40 | 20 | 1360 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005443 | 2019-07-01 |  |  |  | HDME000583 | 2019-06-29 | QC Passed
TBK0136-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building A 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO240,240S/62F | HVF-5 | 1000 | 240 | 40 | 62 |  | 7169000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-11-16 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2021-01-15 | 2020-11-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 3397 | 145 | 112 | 76 | 3730 | 0 | 116 | 28 | 76 | 220 | 94.1 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0137-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building A 2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO240,240S/62F | HVF-5 | 1000 | 240 | 40 | 62 |  | 7169000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-11-16 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2021-01-15 | 2020-11-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 3397 | 145 | 112 | 76 | 3730 | 0 | 116 | 28 | 76 | 220 | 94.1 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0138-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building A 3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO240,240S/62F | HVF-5 | 1000 | 240 | 40 | 62 |  | 7169000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-11-16 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2021-01-15 | 2020-11-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 3397 | 145 | 112 | 76 | 3730 | 0 | 116 | 28 | 76 | 220 | 94.1 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0142-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building A 4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO180,180S/31F | HVF-5 | 1000 | 180 | 30 | 31 |  | 5831500 | Bangkok | แขวงห้วยขวาง | 2020-03-01 | 2020-04-10 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-07-30 | 2020-06-09 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | [41 empty] | 2020-07-01 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2020-09-30 | 2020-11-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 16 | 32 | 48 | 97.7 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0143-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building A 5 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO180,180S/31F | HVF-5 | 1000 | 180 | 30 | 31 |  | 5831500 | Bangkok | แขวงห้วยขวาง | 2020-03-01 | 2020-04-10 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-07-30 | 2020-06-09 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | [41 empty] | 2020-07-01 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2020-09-30 | 2020-11-13 | Finished |  |  | 2020-11-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 16 | 32 | 48 | 97.7 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0144-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building A 6 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO180,180S/31F | HVF-5 | 1000 | 180 | 30 | 31 |  | 5831500 | Bangkok | แขวงห้วยขวาง | 2020-03-01 | 2020-04-10 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-07-30 | 2020-06-09 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | [41 empty] | 2020-07-01 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2020-09-30 | 2020-11-14 | Finished |  |  | 2020-11-19 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-12 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 16 | 32 | 48 | 97.7 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0148-TH | HET | 61000409 | HO | ส่งมอบแล้ว | - | TH209003 | One 9 Five Asoke-Rama 9 | Building A 7 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1600-2S240,240S/63F | HVF-5 | 1600 | 240 | 63 | 63 |  | 8025000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-11-16 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2021-01-15 | 2020-11-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-03-15 | Finished | CONSTRUCTION DELAY |  | 2021-04-09 | Finished |  |  | 2019-10-12 | Finished | [10 empty] | 2021-04-09 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished |  |  | 2021-04-09 | Finished | [13 empty] | no qc |  |  |  |  | 3446 | 147 | 112 | 76 | 3781 | 0 | 0 | 28 | 76 | 104 | 97.25 | Blue |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0139-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building B 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO240,240S/62F | HVF-5 | 1000 | 240 | 40 | 62 |  | 7169000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-10-25 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2021-01-15 | 2020-11-10 | Finished | [14 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 80 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 80 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 3397 | 145 | 112 | 76 | 3730 | 679 | 29 | 28 | 76 | 812 | 78.23 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0140-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building B 2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO240,240S/62F | HVF-5 | 1000 | 240 | 40 | 62 |  | 7169000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-10-25 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2021-01-15 | 2020-11-10 | Finished | [14 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 80 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 80 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 3397 | 145 | 112 | 76 | 3730 | 679 | 29 | 28 | 76 | 812 | 78.23 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0141-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building B 3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO240,240S/62F | HVF-5 | 1000 | 240 | 40 | 62 |  | 7169000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-10-25 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2021-01-15 | 2020-11-10 | Finished | [14 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 80 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 80 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 3397 | 145 | 112 | 76 | 3730 | 679 | 29 | 28 | 76 | 812 | 78.23 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0145-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building B 4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO180,180S/31F | HVF-5 | 1000 | 180 | 30 | 31 |  | 5831500 | Bangkok | แขวงห้วยขวาง | 2020-03-01 | 2020-04-10 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-07-30 | 2020-06-09 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2020-09-30 | 2020-11-15 | Finished |  |  | 2020-11-22 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-20 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2019-10-12 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 16 | 32 | 48 | 97.7 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0146-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building B 5 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO180,180S/31F | HVF-5 | 1000 | 180 | 30 | 31 |  | 5831500 | Bangkok | แขวงห้วยขวาง | 2020-03-01 | 2020-04-10 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-07-30 | 2020-06-09 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2020-09-30 | 2020-11-16 | Finished |  |  | 2020-11-24 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-20 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-10-12 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 16 | 32 | 48 | 97.7 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0147-TH | HET | 61000409 | Install | เลยสัญญา HO | - | TH209003 | One 9 Five Asoke-Rama 9 | Building B 6 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1000-CO180,180S/31F | HVF-5 | 1000 | 180 | 30 | 31 |  | 5831500 | Bangkok | แขวงห้วยขวาง | 2020-03-01 | 2020-04-10 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-10 | 2020-07-30 | 2020-06-09 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2020-09-30 | 2020-11-17 | Finished |  |  | 2020-11-26 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-20 | Working | H/O DOCUMENT DELAY | [5 empty] | 2019-10-12 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 16 | 32 | 48 | 97.7 | Red |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TBK0149-TH | HET | 61000409 | HO | ส่งมอบแล้ว | - | TH209003 | One 9 Five Asoke-Rama 9 | Building B 7 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2018-11-15 | 2020-03-15 | 2020-11-15 |  | HVF-1600-2S240,240S/63F | HVF-5 | 1600 | 240 | 63 | 63 |  | 8025000 | Bangkok | แขวงห้วยขวาง | 2020-08-15 | 2020-11-10 | Finished | [34 empty] | 2020-03-15 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2021-01-15 | 2020-11-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-01-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-03-15 | Finished | CONSTRUCTION DELAY |  | 2021-04-09 | Finished |  |  | 2019-10-12 | Finished | [10 empty] | 2021-04-09 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished |  |  | 2021-04-09 | Finished | [13 empty] | no qc |  |  |  |  | 3446 | 147 | 112 | 76 | 3781 | 0 | 0 | 28 | 76 | 104 | 97.25 | Blue |  |  | 20008894 | 2020-03-26 |  |  |  | HDME000836 | 2020-03-27
TAJ0425-TH | HET | 61000410 | HO | ยังอยู่ในสัญญา HO | - | TH199068 | Home Khun Tanachai Soi Udom Suk 31 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Prapaipim Netnonthai | 2018-11-09 | 2019-05-09 | 2019-07-09 | 2021-12-01 | P-1000-CO60W1,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1391000 | Bangkok | แขวงบางจาก | 2019-06-01 | 2019-06-10 | Finished | [34 empty] | 2019-05-02 | 2019-05-08 | 2019-05-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-10 | 2019-06-28 | 2019-06-12 | Finished |  |  | 2019-06-13 | Finished |  |  | 2019-06-15 | Finished |  |  | 2019-06-17 | Finished |  |  | 2019-06-19 | Finished |  |  | 2019-06-21 | Finished |  |  | 2019-06-23 | Finished |  |  | 2019-06-25 | Finished |  |  | 2019-06-26 | Finished |  |  | 2019-06-28 | Finished |  |  | 100 | [41 empty] | 2019-06-28 | 1900-01-01 | 2019-06-28 | Waiting | POWER SUPPLY DELAY |  | 2021-10-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-02-23 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2019-05-29 | Finished |  |  | 2019-05-29 | Finished |  |  | 2019-05-30 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 16 | 16 | 112 | 74.07 | Green |  |  | 20005537 | 2019-05-02 |  |  |  | HDME000546 | 2019-05-29
TFA1231-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-01 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R12.2M,D30 | SX-NL |  |  |  |  | 12200 | 3317000 | Samut Prakan | อำเภอบางพลี | 2020-02-01 | [20 empty] | 2020-02-01 | Finished | [14 empty] | 2019-04-25 | 2019-10-29 | 2019-10-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-01 | 2020-03-30 | [41 empty] | 2020-02-03 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-12-16 | 2020-12-16 | Finished |  |  | 2020-11-20 | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | 2020-06-10 | 2000-01-01 | 2020-06-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-29 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1134 | 53 | 32 | 35 | 1254 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000693 | 2019-10-29
TFA1232-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-02 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R12.2M,D30 | SX-NL |  |  |  |  | 12200 | 3317000 | Samut Prakan | อำเภอบางพลี | 2020-02-01 | [20 empty] | 2020-02-01 | Finished | [14 empty] | 2019-04-25 | 2019-10-29 | 2019-10-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-01 | 2020-03-30 | [41 empty] | 2020-02-03 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-12-16 | 2020-12-16 | Finished |  |  | 2020-11-20 | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | 2020-06-06 | 2021-08-03 | 2020-06-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-29 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1134 | 53 | 32 | 35 | 1254 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000693 | 2019-10-29 | QC Passed
TFA1233-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-03 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R12.2M,D30 | SX-NL |  |  |  |  | 12200 | 3317000 | Samut Prakan | อำเภอบางพลี | 2020-02-01 | [20 empty] | 2020-02-01 | Finished | [14 empty] | 2019-04-25 | 2019-10-29 | 2019-10-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-01 | 2020-03-30 | [41 empty] | 2020-02-03 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-12-17 | 2020-12-17 | Finished |  |  | 2020-11-20 | 2020-12-17 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-20 | Finished |  |  | 100 | 2020-06-10 | 2000-01-01 | 2020-06-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-29 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1134 | 53 | 32 | 35 | 1254 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000693 | 2019-10-29
TFA1234-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-04 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R12.2M,D30 | SX-NL |  |  |  |  | 12200 | 3317000 | Samut Prakan | อำเภอบางพลี | 2020-02-01 | [20 empty] | 2020-02-01 | Finished | [14 empty] | 2019-04-25 | 2019-10-29 | 2019-10-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-01 | 2020-03-30 | [41 empty] | 2020-02-03 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-12-17 | 2020-12-17 | Finished |  |  | 2020-11-20 | 2020-12-17 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-20 | Finished |  |  | 100 | 2020-06-10 | 2000-01-01 | 2020-06-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-29 | Finished |  |  | 2019-11-06 | Finished |  |  | 2019-11-07 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1134 | 53 | 32 | 35 | 1254 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000693 | 2019-10-29
TFA1258-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-05 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R9.3M,D30 | SX-NL |  |  |  |  | 9300 | 3049500 | Samut Prakan | อำเภอบางพลี | 2020-06-15 | [20 empty] | 2020-06-15 | Finished | [14 empty] | 2019-04-25 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-15 | 2020-07-15 | [41 empty] | 2020-06-15 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-18 | Finished |  |  | 100 | 2020-10-18 | 2020-12-10 | 2020-12-10 | Finished |  |  | 2020-11-20 | 2020-12-13 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 100 | 2021-05-13 | 2020-12-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-29 | Finished | [6 empty] | 90 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-13 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 882 | 42 | 24 | 28 | 976 | 0 | 0 | 0 | 2 | 2 | 99.8 | Blue |  |  | 20006019 | 2019-04-25 |  |  |  | HDME000650 | 2019-09-13 | QC Passed
TFA1259-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-06 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R9.3M,D30 | SX-NL |  |  |  |  | 9300 | 3049500 | Samut Prakan | อำเภอบางพลี | 2020-06-15 | [20 empty] | 2020-06-15 | Finished | [14 empty] | 2019-04-25 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-15 | 2020-07-15 | [41 empty] | 2020-06-15 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-18 | Finished |  |  | 100 | 2020-10-18 | 2020-12-10 | 2020-12-10 | Finished |  |  | 2020-11-20 | 2020-12-13 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-17 | Finished |  |  | 100 | 2021-05-13 | 2021-05-06 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-06 | Finished | [6 empty] | 90 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-13 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 882 | 42 | 24 | 28 | 976 | 0 | 0 | 0 | 2 | 2 | 99.8 | Blue |  |  | 20006019 | 2019-04-25 |  |  |  | HDME000650 | 2019-09-13 | QC Passed
TFA1260-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-07 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R9.3M,D30 | SX-NL |  |  |  |  | 9300 | 3049500 | Samut Prakan | อำเภอบางพลี | 2020-06-15 | [20 empty] | 2020-06-15 | Finished | [14 empty] | 2019-04-25 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-15 | 2020-07-15 | [41 empty] | 2020-06-15 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-18 | Finished |  |  | 100 | 2020-10-18 | 2020-12-10 | 2020-12-10 | Finished |  |  | 2020-11-20 | 2020-12-14 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | 2021-05-13 | 2021-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-04 | Finished | [6 empty] | 90 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-13 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 882 | 42 | 24 | 28 | 976 | 0 | 0 | 0 | 2 | 2 | 99.8 | Blue |  |  | 20006019 | 2019-04-25 |  |  |  | HDME000650 | 2019-09-13 | QC Passed
TFA1261-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ESC-08 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R3.5M,D30 | SX-NL |  |  |  |  | 3500 | 1391000 | Samut Prakan | อำเภอบางพลี | 2020-06-15 | [20 empty] | 2020-06-15 | Finished | [14 empty] | 2019-04-25 | 2019-09-20 | 2019-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-15 | 2020-07-15 | [41 empty] | 2020-06-15 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 100 | 2020-10-08 | 2020-12-10 | 2020-12-10 | Finished |  |  | 2020-11-20 | 2020-12-14 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-19 | Finished |  |  | 100 | 2021-05-13 | 2021-05-06 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-06 | Finished | [6 empty] | 90 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-09-13 | Finished |  |  | 2019-09-20 | Finished |  |  | 2019-09-24 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 567 | 32 | 16 | 14 | 629 | 0 | 0 | 0 | 1 | 1 | 99.84 | Blue |  |  | 20006019 | 2019-04-25 |  |  |  | HDME000650 | 2019-09-13 | QC Passed
TFA1255-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HE-2.1(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R13.75M,D30 | SX-NL |  |  |  |  | 13750 | 3370500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-04-25 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-03-30 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-03 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 1197 | 53 | 32 | 35 | 1317 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006019 | 2019-04-25 |  |  |  | HDME000675 | 2019-10-03
TFA1256-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HE-2.1(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R13.75M,D30 | SX-NL |  |  |  |  | 13750 | 3370500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-04-25 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-03-30 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-03 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 1197 | 53 | 32 | 35 | 1317 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006019 | 2019-04-25 |  |  |  | HDME000675 | 2019-10-03
TFA1257-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HE-2.1(C) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R13.75M,D30 | SX-NL |  |  |  |  | 13750 | 3370500 | Samut Prakan | อำเภอบางพลี | 2019-12-23 | [20 empty] | 2019-12-23 | Finished | [14 empty] | 2019-04-25 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-23 | 2020-03-30 | [41 empty] | 2019-12-25 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-03 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1197 | 53 | 32 | 35 | 1317 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006019 | 2019-04-25 |  |  |  | HDME000675 | 2019-10-03
TFA1239-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HE-3.3(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.4M,D30 | SX-NL |  |  |  |  | 5400 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-11-15 | [20 empty] | 2019-11-15 | Finished | [14 empty] | 2019-04-25 | 2019-08-13 | 2019-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-30 | 2019-12-31 | [41 empty] | 2019-12-01 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000614 | 2019-08-08
TFA1240-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HE-3.3(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.4M,D30 | SX-NL |  |  |  |  | 5400 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-11-15 | [20 empty] | 2019-11-15 | Finished | [14 empty] | 2019-04-25 | 2019-08-13 | 2019-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-30 | 2019-12-31 | [41 empty] | 2019-12-01 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-30 | 2020-06-17 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000614 | 2019-08-08
TFA1241-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HW-2.2(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R13.75M,D30 | SX-NL |  |  |  |  | 13750 | 3370500 | Samut Prakan | อำเภอบางพลี | 2020-01-15 | [20 empty] | 2020-01-15 | Finished | [14 empty] | 2019-04-25 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-30 | [41 empty] | 2020-01-17 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-09 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-03 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1197 | 53 | 32 | 35 | 1317 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000675 | 2019-10-03
TFA1242-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HW-2.2(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1200SX-NL,R13.75M,D30 | SX-NL |  |  |  |  | 13750 | 3370500 | Samut Prakan | อำเภอบางพลี | 2020-01-15 | [20 empty] | 2020-01-15 | Finished | [14 empty] | 2019-04-25 | 2019-10-10 | 2019-10-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-30 | [41 empty] | 2020-01-17 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-13 | Finished |  |  | 100 | 2020-04-13 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-08-20 | 2020-08-23 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-10-03 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 1197 | 53 | 32 | 35 | 1317 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000675 | 2019-10-03
TFA1235-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HW-3.4(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.4M,D30 | SX-NL |  |  |  |  | 5400 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-04-25 | 2019-08-13 | 2019-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-30 | 2019-12-31 | [41 empty] | 2019-12-01 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-07-30 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000614 | 2019-08-08
TFA1236-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HW-3.4(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.4M,D30 | SX-NL |  |  |  |  | 5400 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-04-25 | 2019-08-13 | 2019-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-30 | 2019-12-31 | [41 empty] | 2019-12-01 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-07-30 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000614 | 2019-08-08
TFA1237-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HW-3.5(A) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.4M,D30 | SX-NL |  |  |  |  | 5400 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-04-25 | 2019-08-13 | 2019-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-30 | 2019-12-31 | [41 empty] | 2019-12-01 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-07-30 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000614 | 2019-08-08
TFA1238-TH | HET | 61000417 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | ES-HW-3.5(B) |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Phumiphat Siprajan | 2018-06-08 | 2019-05-10 | 2019-10-28 | 2021-04-23 | 1000SX-NL,R5.4M,D30 | SX-NL |  |  |  |  | 5400 | 1658500 | Samut Prakan | อำเภอบางพลี | 2019-11-30 | [20 empty] | 2019-11-30 | Finished | [14 empty] | 2019-04-25 | 2019-08-13 | 2019-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-30 | 2019-12-31 | [41 empty] | 2019-12-01 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-20 | Finished |  |  | 2019-12-23 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-31 | Finished |  |  | 100 | 2019-12-31 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-07-30 | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2019-08-08 | Finished |  |  | 2019-08-13 | Finished |  |  | 2019-08-14 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | pass (defect) |  |  |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005617 | 2019-04-25 |  |  |  | HDME000614 | 2019-08-08
TAJ0432-TH | HET | 61000423 | HO | ส่งมอบแล้ว | - | TH199084 | Home 2 fl (Talingchan) | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-02-15 | 2019-06-15 | 2019-08-15 | 2020-12-16 | P-1600-CO60,60S/2F | UAG-SN1 | 1600 | 60 | 2 | 2 |  | 1337500 | Bangkok | เขตตลิ่งชัน | 2019-07-07 | 2019-07-10 | Finished | [34 empty] | 2019-06-08 | 2019-07-08 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-30 | 2019-10-15 | 2019-09-30 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-01-03 | Finished |  |  | 2019-10-05 | Finished |  |  | 2019-10-07 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-12 | Finished |  |  | 2019-10-13 | Finished |  |  | 2019-10-14 | Finished |  |  | 2019-10-15 | Finished |  |  | 100 | [41 empty] | 2019-10-15 | 2021-01-11 | 2021-01-11 | Finished |  |  | 2020-11-20 | 2021-01-11 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-14 | Finished |  |  | 100 | 2021-01-29 | 2021-06-10 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-02-15 | Finished | POWER SUPPLY DELAY |  | 2021-01-29 | Finished |  |  | 2019-03-07 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2019-07-08 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass | 2021-06-22 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006296 | 2019-06-08 |  |  |  | HDME000587 | 2019-07-08 | QC Passed
TAJ0433-TH | HET | 61000424 | HO | ยังอยู่ในสัญญา HO | - | TH199086 | Tiara Place | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2020-01-23 | 2020-09-23 | 2020-11-23 | 2021-11-30 | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1337500 | Bangkok | แขวงจอมพล | 2020-11-23 | 2021-03-15 | Finished | [34 empty] | 2020-09-23 | 2021-02-16 | 2021-02-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-15 | 2021-04-15 | 2021-02-18 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-15 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-03 | Finished |  |  | 2021-05-06 | Finished |  |  | 100 | [41 empty] | 2021-05-06 | 1900-01-01 | 2021-05-06 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2021-05-10 | 2000-01-01 | 2021-05-10 | Finished | [14 empty] | 25 | 2021-11-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-31 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 83 | 6 | 16 | 105 | 83.06 | Green |  |  | 20011724 | 2020-09-23 |  |  |  | HDME001132 | 2021-02-16
TAJ0437-TH | HET | 61000428 | Test | ยังอยู่ในสัญญา HO | - | TH199089 | Building Khun Chakkrit 1 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Chonticha Angsuwichitkun | 2019-04-23 | 2019-07-23 | 2019-09-23 | 2021-10-26 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1250000 | Bangkok | แขวงวงศ์สว่าง | 2022-01-22 | [36 empty] | 2019-07-16 | 2019-08-06 | 2019-08-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-01-23 | 2022-02-22 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-22 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-03 | Finished | [18 empty] | 2019-08-06 | Finished |  |  | 2019-08-06 | Finished |  |  | 2019-08-07 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Green |  |  | 20007031 | 2019-07-16 |  |  |  | HDME000610 | 2019-08-06
TAD0371-TH | HET | 61000435 |  | ยังอยู่ในสัญญา HO | - | TH199093 | Chulabhorn Pathum Thani Building | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-08 | 2019-05-08 | 2019-07-08 | 2022-01-15 | B-1000-2S60,60S/4F | B-II(VFI-II) | 1000 | 60 | 4 | 4 |  | 1819000 | Pathum Thani | อำเภอคลองหลวง | 2022-01-15 | [36 empty] | 2019-04-17 | 2019-09-20 |  |  | PAYMENT DELAY | [13 empty] | 2022-04-01 | 2022-05-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-09-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-09-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-01-31 | Finished | [50 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Green |  |  | 20005844 | 2019-04-17
TAD0372-TH | HET | 61000435 |  | ยังอยู่ในสัญญา HO | - | TH199093 | Chulabhorn Pathum Thani Building | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-08 | 2019-05-08 | 2019-07-08 | 2022-01-15 | B-1000-2S60,60S/4F | B-II(VFI-II) | 1000 | 60 | 4 | 4 |  | 1819000 | Pathum Thani | อำเภอคลองหลวง | 2022-01-15 | [36 empty] | 2019-04-17 | 2019-09-20 |  |  | PAYMENT DELAY | [13 empty] | 2022-04-01 | 2022-05-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-09-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-09-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-01-31 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Green |  |  | 20005844 | 2019-04-17
TAJ0443-TH | HET | 61000437 | HO | ส่งมอบแล้ว | - | TH199097 | Suncity Condominium | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | ANUSSARA POLDONGNOK | 2019-02-01 | 2019-07-01 | 2019-09-01 | 2020-05-01 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1337500 | Bangkok | เขตบางกอกน้อย | 2020-04-10 | 2020-04-10 | Finished | [34 empty] | 2019-06-24 | 2019-06-27 | 2019-06-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-07-01 | 2019-08-17 | 2019-07-05 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-19 | Finished |  |  | 2019-07-23 | Finished |  |  | 2019-07-26 | Finished |  |  | 2019-07-28 | Finished |  |  | 2019-07-04 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-14 | Finished |  |  | 100 | [41 empty] | 2019-07-14 | 2020-04-16 | 2020-04-16 | Finished |  |  | 2019-04-06 | 2020-04-19 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-30 | Finished |  |  | 100 | 2020-05-20 | 2000-01-01 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-17 | Finished | [6 empty] | 90 | 2020-05-05 | Finished | POWER SUPPLY DELAY |  | 2020-05-12 | Finished |  |  | 2019-02-23 | Finished | [10 empty] | 2020-05-15 | Finished | [6 empty] | 2019-06-27 | Finished |  |  | 2019-06-27 | Finished |  |  | 2019-06-28 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Working |  |  | 2020-08-13 | Working |  | pass (defect) |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20006298 | 2019-06-24 |  |  |  | HDME000578 | 2019-06-27
TAJ0456-TH | HET | 61000438 | HO | ส่งมอบแล้ว | - | TH199096 | Apartment 9 PK (Ramkhamhaeng Soi 5) | No.1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-01-12 | 2019-05-12 | 2019-07-12 | 2020-11-12 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1100000 | Bangkok | เขตสวนหลวง | 2020-05-02 | 2020-05-02 | Finished | [34 empty] | 2019-05-05 | 2019-07-08 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-15 | 2020-05-17 | 2020-06-29 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-27 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | [41 empty] | 2020-07-31 | 2020-12-07 | 2020-12-07 | Finished |  |  | 2020-10-12 | 2020-12-08 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-10 | Finished |  |  | 100 | 2020-07-03 | 2021-07-19 | 2020-07-03 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-07-19 | Finished |  |  | 100 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2021-02-22 | Finished |  |  | 2019-02-08 | Finished | [18 empty] | 2019-07-08 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005809 | 2019-05-05 |  |  |  | HDME000592 | 2019-07-08 | QC Passed
TAJ0457-TH | HET | 61000438 | HO | ส่งมอบแล้ว | - | TH199096 | Apartment 9 PK (Ramkhamhaeng Soi 5) | No.2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-01-12 | 2019-05-12 | 2019-07-12 | 2020-11-12 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1100000 | Bangkok | เขตสวนหลวง | 2020-05-02 | 2020-05-02 | Finished | [34 empty] | 2019-05-05 | 2019-07-08 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-15 | 2020-05-17 | 2020-06-16 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-30 | Finished |  |  | 100 | [41 empty] | 2020-06-30 | 2020-12-07 | 2020-12-07 | Finished |  |  | 2020-10-12 | 2021-02-05 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-10 | Finished |  |  | 100 | 2020-08-21 | 2021-02-19 | 2020-08-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished | [6 empty] | 90 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2021-02-22 | Finished |  |  | 2019-02-08 | Finished | [18 empty] | 2019-07-08 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20005809 | 2019-05-05 |  |  |  | HDME000592 | 2019-07-08 | QC Passed
TAJ0458-TH | HET | 61000438 | HO | ส่งมอบแล้ว | - | TH199096 | Apartment 9 PK (Ramkhamhaeng Soi 5) | No.3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-01-12 | 2019-05-12 | 2019-07-12 | 2020-11-12 | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1200000 | Bangkok | เขตสวนหลวง | 2020-05-02 | 2020-05-02 | Finished | [34 empty] | 2019-05-05 | 2019-07-08 | 2019-07-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-15 | 2020-05-17 | 2020-07-04 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-16 | Finished |  |  | 2020-07-17 | Finished |  |  | 2020-07-18 | Finished |  |  | 100 | [41 empty] | 2020-07-18 | 2020-12-07 | 2020-12-07 | Finished |  |  | 2020-10-12 | 2021-02-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-08-21 | 2021-07-09 | 2020-08-21 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-07-09 | Finished |  |  | 100 | 2021-05-15 | Finished | CONSTRUCTION DELAY |  | 2021-06-30 | Finished |  |  | 2019-02-08 | Finished | [10 empty] | 2021-06-30 | Finished | [6 empty] | 2019-07-08 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2021-06-30 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005809 | 2019-05-05 |  |  |  | HDME000592 | 2019-07-08 | QC Passed
TAC1534-TH | HET | 61000443 | HO | ส่งมอบแล้ว | - | TH199101 | ม.ราชภัฎจันทรเกษม | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2019-01-22 | 2019-05-22 | 2019-07-22 | 2019-12-26 | VFI-1600-2S60,60S/6F | VFI-II | 1600 | 60 | 6 | 6 |  | 1640310 | Bangkok | เขตจตุจักร | 2019-09-26 | 2020-05-21 | Finished | [34 empty] | 2019-05-15 | 2019-05-30 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-18 | 2019-07-15 | 2019-06-18 | Finished |  |  | 2019-06-20 | Finished |  |  | 2019-06-27 | Finished |  |  | 2019-06-30 | Finished |  |  | 2019-07-02 | Finished |  |  | 2019-07-05 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-12 | Finished |  |  | 2019-07-15 | Finished |  |  | 100 | [41 empty] | 2019-07-15 | 2019-11-30 | 2019-11-30 | Finished |  |  | 2019-11-30 | 2019-11-30 | Finished |  |  | 2019-12-05 | Finished |  |  | 2019-12-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-16 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2019-12-25 | Finished | POWER SUPPLY DELAY |  | 2020-01-21 | Finished |  |  | 2019-03-20 | Finished | [18 empty] | 2019-05-30 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-05-31 | Finished |  |  | 2020-01-21 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005970 | 2019-05-15 |  |  |  | HDME000547 | 2019-05-30 | QC Passed
TAC1535-TH | HET | 61000443 | HO | ส่งมอบแล้ว | - | TH199101 | ม.ราชภัฎจันทรเกษม | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2019-01-22 | 2019-05-22 | 2019-07-22 | 2019-12-26 | VFI-1600-2S60,60S/6F | VFI-II | 1600 | 60 | 6 | 6 |  | 1640310 | Bangkok | เขตจตุจักร | 2019-03-01 | 2020-05-21 | Finished | [34 empty] | 2019-05-15 | 2019-05-30 | 2019-05-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-06-18 | 2019-07-15 | 2019-06-18 | Finished |  |  | 2019-06-20 | Finished |  |  | 2019-06-27 | Finished |  |  | 2019-06-30 | Finished |  |  | 2019-07-02 | Finished |  |  | 2019-07-05 | Finished |  |  | 2019-07-08 | Finished |  |  | 2019-07-10 | Finished |  |  | 2019-07-12 | Finished |  |  | 2019-07-15 | Finished |  |  | 100 | [41 empty] | 2019-07-15 | 2019-11-30 | 2019-11-30 | Finished |  |  | 2019-11-30 | 2019-11-30 | Finished |  |  | 2019-12-05 | Finished |  |  | 2019-12-15 | Finished |  |  | 100 | 2021-05-13 | 2021-07-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-16 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2019-12-25 | Finished | POWER SUPPLY DELAY |  | 2020-01-21 | Finished |  |  | 2019-03-20 | Finished | [18 empty] | 2019-05-30 | Finished |  |  | 2019-05-30 | Finished |  |  | 2019-05-31 | Finished |  |  | 2020-01-21 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005970 | 2019-05-15 |  |  |  | HDME000547 | 2019-05-30 | QC Passed
TAC1536-TH | HET | 61000453 | HO | ส่งมอบแล้ว | - | TH199051 | METRIS LADPRAO | L1/FL | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2018-09-14 | 2019-08-18 | 2020-03-31 |  | VFI-1000-2S150,150S/31F | VFI-II | 1000 | 150 | 23 | 31 |  | 3200000 | Bangkok | แขวงจอมพล เขตจตุจักร | 2019-10-02 | 2019-10-02 | Finished | [34 empty] | 2019-08-01 | 2019-10-13 | 2019-08-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-15 | 2019-11-30 | 2019-08-20 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-29 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-17 | Finished |  |  | 100 | [41 empty] | 2019-11-17 | 2019-12-11 | 2019-12-11 | Finished |  |  | 2019-12-11 | 2019-12-14 | Finished |  |  | 2019-12-24 | Finished |  |  | 2019-12-27 | Finished |  |  | 100 | 2021-05-13 | 2021-04-09 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | 2020-06-02 | Finished | CONSTRUCTION DELAY |  | 2020-06-29 | Finished |  |  | 2019-02-23 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2019-09-22 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-09-30 | Finished |  |  | 2020-06-29 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-04 | Finished |  | pass | 2021-03-04 | Finished |  |  | 1964 | 122 | 64 | 32 | 2182 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005986 | 2019-08-01 |  |  |  | HDME000659 | 2019-09-22 | QC Passed
TAC1537-TH | HET | 61000453 | HO | ส่งมอบแล้ว | - | TH199051 | METRIS LADPRAO | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2018-09-14 | 2019-08-18 | 2020-03-31 |  | VFI-1000-CO150,150S/31F | VFI-II | 1000 | 150 | 23 | 31 |  | 2703700 | Bangkok | แขวงจอมพล เขตจตุจักร | 2019-10-02 | 2019-10-02 | Finished | [34 empty] | 2019-08-01 | 2019-09-27 | 2019-08-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-15 | 2019-11-30 | 2019-08-20 | Finished |  |  | 2019-10-10 | Finished |  |  | 2019-10-15 | Finished |  |  | 2019-10-19 | Finished |  |  | 2019-10-25 | Finished |  |  | 2019-10-29 | Finished |  |  | 2019-11-08 | Finished |  |  | 2019-11-30 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-17 | Finished |  |  | 100 | [41 empty] | 2019-11-17 | 2019-12-11 | 2019-12-11 | Finished |  |  | 2019-12-11 | 2019-12-15 | Finished |  |  | 2019-12-24 | Finished |  |  | 2019-12-27 | Finished |  |  | 100 | 2020-04-17 | 2020-11-13 | 2020-04-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 100 | 2020-06-02 | Finished | CONSTRUCTION DELAY |  | 2020-06-29 | Finished |  |  | 2019-02-23 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2019-09-22 | Finished |  |  | 2019-09-30 | Finished |  |  | 2019-09-30 | Finished |  |  | 2020-06-29 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-04 | Finished |  | pass | 2021-03-04 | Finished |  |  | 1964 | 122 | 64 | 32 | 2182 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20005986 | 2019-08-01 |  |  |  | HDME000659 | 2019-09-22 | QC Passed
TAC1538-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-28 | VFI-1000-CO60,60S/6F | VFI-II | 1000 | 60 | 6 | 6 |  | 1321450 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 583 | 91 | 24 | 16 | 714 | 583 | 91 | 24 | 16 | 714 | 0 | Red |  |  | 20006095 | 2019-05-23
TAC1539-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-29 | VFI-1000-CO60,60S/6F | VFI-II | 1000 | 60 | 6 | 6 |  | 1321450 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 583 | 91 | 24 | 16 | 714 | 583 | 91 | 24 | 16 | 714 | 0 | Red |  |  | 20006095 | 2019-05-23
TAC1540-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-30 | VFI-1000-CO60,60S/7F | VFI-II | 1000 | 60 | 7 | 7 |  | 1342850 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20006095 | 2019-05-23
TAC1541-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-30 | VFI-1000-CO60,60S/7F | VFI-II | 1000 | 60 | 7 | 7 |  | 1342850 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20006095 | 2019-05-23
TAC1542-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-30 | VFI-1000-CO60,60S/7F | VFI-II | 1000 | 60 | 7 | 7 |  | 1342850 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20006095 | 2019-05-23
TAC1543-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-30 | VFI-1000-CO60,60S/7F | VFI-II | 1000 | 60 | 7 | 7 |  | 1342850 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20006095 | 2019-05-23
TAC1544-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-30 | VFI-1000-CO60,60S/7F | VFI-II | 1000 | 60 | 7 | 7 |  | 1342850 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20006095 | 2019-05-23
TAC1545-TH | HET | 61000459 |  | เลยสัญญา HO | - | TH199118 | Royal Thai Armed Forces (Government House at Thung Si K | 8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Orawan Kwanpheng | 2019-01-30 | 2019-05-30 | 2019-08-30 | 2021-03-30 | VFI-1000-CO60,60S/7F | VFI-II | 1000 | 60 | 7 | 7 |  | 1342850 | Bangkok | จังหวัดกรุงเทพมหานคร 10210 | 2022-06-25 | [36 empty] | 2019-05-23 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-06-26 | 2022-07-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2019-02-23 | Finished |  |  | 2021-10-12 | Finished | [46 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20006095 | 2019-05-23
TBL0185-TH | HET | 61000460 | HO | ส่งมอบแล้ว | - | TH199119 | Trang Airport [ท่าอากาศยานตรัง] | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2019-01-24 | 2019-05-24 | 2019-06-24 | 2021-04-30 | OUG-1050-CO60,60S/2F | OUG-ON1 | 1050 | 60 | 2 | 2 |  | 1819000 | Trang | อ.เมืองตรัง | 2020-10-03 | 2020-11-10 | Finished | [34 empty] | 2019-05-17 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-01 | 2020-11-23 | 2020-11-10 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-07 | Finished |  |  | 100 | [41 empty] | 2020-12-07 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2021-03-15 | 2021-03-15 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | 2021-03-22 | 2021-05-10 | 2021-03-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-05-10 | Finished |  |  | 100 | 2021-04-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-31 | Finished |  |  | 2019-03-07 | Finished | [10 empty] | 2021-03-31 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  | pass | 2021-05-21 | Finished |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006282 | 2019-05-17 |  |  |  | HDME001017 | 2020-10-28 | QC Passed
TAC1549-TH | HET | 61000464 | HO | ส่งมอบแล้ว | - | TH199124 | Sri Fueng Fung Building | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-02-04 | 2019-07-10 | 2019-09-30 | 2020-01-31 | VFI-1150-CO105,105S/14F | VFI-II | 1150 | 105 | 14 | 14 |  | 2755250 | Bangkok | เขตบางรัก | 2019-08-12 | 2019-09-20 | Finished | [34 empty] | 2019-06-27 | 2019-08-10 | 2019-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-20 | 2019-12-15 | 2019-09-22 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-06 | Finished |  |  | 2019-10-13 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-31 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-13 | Finished |  |  | 2019-11-17 | Finished |  |  | 2019-11-21 | Finished |  |  | 100 | [41 empty] | 2019-11-21 | 2020-01-17 | 2020-01-17 | Finished |  |  | 2020-01-17 | 2020-01-18 | Finished |  |  | 2020-01-19 | Finished |  |  | 2019-01-20 | Finished |  |  | 100 | 2020-03-09 | 2020-09-25 | 2020-03-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-02-20 | Finished | CONSTRUCTION DELAY |  | 2020-02-28 | Finished |  |  | 2019-02-23 | Finished | [18 empty] | 2019-08-10 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-14 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-22 | Finished |  | pass | 2020-10-22 | Finished |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006182 | 2019-07-10 |  |  |  | HDME000615 | 2019-08-10 | QC Passed
TAC1550-TH | HET | 61000464 | HO | ส่งมอบแล้ว | - | TH199124 | Sri Fueng Fung Building | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-02-04 | 2019-07-10 | 2019-09-30 | 2020-01-31 | VFI-1150-CO105,105S/14F | VFI-II | 1150 | 105 | 14 | 14 |  | 2755250 | Bangkok | เขตบางรัก | 2019-08-12 | 2019-09-20 | Finished | [34 empty] | 2019-06-27 | 2019-08-10 | 2019-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-20 | 2019-12-15 | 2019-09-22 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-06 | Finished |  |  | 2019-10-13 | Finished |  |  | 2019-10-22 | Finished |  |  | 2019-10-31 | Finished |  |  | 2019-11-09 | Finished |  |  | 2019-11-13 | Finished |  |  | 2019-11-17 | Finished |  |  | 2019-11-21 | Finished |  |  | 100 | [41 empty] | 2019-11-21 | 2020-01-17 | 2020-01-17 | Finished |  |  | 2020-01-17 | 2020-01-18 | Finished |  |  | 2020-01-19 | Finished |  |  | 2019-01-20 | Finished |  |  | 100 | 2020-03-09 | 2020-09-25 | 2020-03-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-02-20 | Finished | CONSTRUCTION DELAY |  | 2020-02-29 | Finished |  |  | 2019-02-23 | Finished | [18 empty] | 2019-08-10 | Finished |  |  | 2019-08-10 | Finished |  |  | 2019-08-14 | Finished |  |  | 2020-02-29 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-22 | Finished |  | pass | 2020-10-22 | Finished |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006182 | 2019-07-10 |  |  |  | HDME000615 | 2019-08-10 | QC Passed
TAC1551-TH | HET | 61000464 | HO | ส่งมอบแล้ว | - | TH199124 | Sri Fueng Fung Building | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-02-04 | 2019-07-10 | 2019-12-27 | 2020-08-24 | VFI-1150-CO105,105S/14F | VFI-II | 1150 | 105 | 14 | 14 |  | 2755250 | Bangkok | เขตบางรัก | 2020-01-30 | 2020-02-29 | Finished | [34 empty] | 2019-06-27 | 2019-10-09 | 2019-10-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-30 | 2020-04-24 | 2020-04-09 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | [41 empty] | 2020-05-02 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-04-25 | 2020-07-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | 2020-07-02 | 2020-10-20 | 2020-07-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-10-20 | Finished |  |  | 100 | 2020-08-20 | Finished | CONSTRUCTION DELAY |  | 2020-08-18 | Finished |  |  | 2019-02-23 | Finished | [18 empty] | 2019-10-09 | Finished |  |  | 2019-10-18 | Finished |  |  | 2019-10-21 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  | pass | 2021-04-09 | Finished |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006182 | 2019-09-27 |  |  |  | HDME000678 | 2019-10-09 | QC Passed
TAC1552-TH | HET | 61000464 | HO | ส่งมอบแล้ว | - | TH199124 | Sri Fueng Fung Building | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-02-04 | 2019-07-10 | 2019-12-27 | 2021-01-24 | VFI-1150-CO105,105S/14F | VFI-II | 1150 | 105 | 14 | 14 |  | 2755250 | Bangkok | เขตบางรัก | 2020-01-30 | 2020-02-29 | Finished | [34 empty] | 2019-06-27 | 2019-10-09 | 2019-10-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-30 | 2020-04-24 | 2020-04-09 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-02 | Finished |  |  | 100 | [41 empty] | 2020-05-02 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-04-25 | 2020-07-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-02 | 2021-04-02 | 2020-07-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | 2020-10-15 | Finished | POWER SUPPLY DELAY |  | 2020-12-28 | Finished |  |  | 2019-02-23 | Finished | [18 empty] | 2019-10-09 | Finished |  |  | 2019-10-18 | Finished |  |  | 2019-10-21 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | pass | 2021-04-19 | Finished |  |  | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006182 | 2019-09-27 |  |  |  | HDME000678 | 2019-10-09 | QC Passed
TEB0089-TH | HET | 61000475 | HO | ส่งมอบแล้ว | - | TH199139 | Thai Flour Mill Industry (Home Lift) | P1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2019-02-18 | 2019-05-15 | 2019-06-15 | 2020-10-30 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 4 | 4 |  | 1498000 | Samut Prakan | ตำบลสำโรงใต้ | 2019-10-24 | 2020-01-10 | Finished | [34 empty] | 2019-05-01 | 2020-03-30 | 2019-06-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-16 | 2020-01-25 | 2020-01-16 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-19 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-01-22 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-25 | Finished |  |  | 100 | [41 empty] | 2020-01-25 | 2020-01-26 | 2020-01-26 | Finished |  |  | 2020-01-26 | 2020-01-26 | Finished |  |  | 2020-01-29 | Finished |  |  | 2020-01-31 | Finished |  |  | 100 | 2021-05-13 | 2021-07-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-28 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-02-25 | Finished | CONSTRUCTION DELAY |  | 2021-02-19 | Finished |  |  | 2019-03-14 | Finished | [10 empty] | 2021-02-19 | Finished | [6 empty] | 2019-06-04 | Finished |  |  | 2019-06-04 | Finished |  |  | 2019-06-06 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006469 | 2019-05-01 |  |  |  | HDME000554 | 2019-06-04 | QC Passed
TAJ0554-TH | HET | 61000480 | HO | ส่งมอบแล้ว | - | TH199143 | The Circle Link Group Office | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2019-05-01 | 2019-09-01 | 2019-12-01 | 2020-08-24 | P-1000-CO60W2,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1200000 | Bangkok | แขวงมักกะสัน เขตราชเทวี | 2020-03-24 | [36 empty] | 2019-08-25 | 2019-09-08 | 2019-09-08 | Finished | STORE AREA | [13 empty] | 2020-04-07 | 2020-05-25 | 2020-04-13 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-27 | Finished |  |  | 100 | [41 empty] | 2020-04-27 | 2020-05-12 | 2020-05-12 | Finished |  |  | 2020-05-26 | 2020-06-13 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2020-09-29 | 2020-10-26 | 2020-09-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2020-10-25 | Finished | CONSTRUCTION DELAY |  | 2020-09-29 | Finished |  |  | 2019-06-12 | Finished | [18 empty] | 2019-09-05 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-09 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  | pass | 2020-10-14 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007431 | 2019-08-25 |  |  |  | HDME000642 | 2019-09-05 | QC Passed
TAJ0555-TH | HET | 61000480 | HO | ส่งมอบแล้ว | - | TH199143 | The Circle Link Group Office | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2019-05-01 | 2019-09-01 | 2019-12-01 | 2020-12-24 | P-1500-2S60,60S/8F | UAG-SN1 | 1500 | 60 | 8 | 8 |  | 1400000 | Bangkok | แขวงมักกะสัน เขตราชเทวี | 2020-03-24 | 2020-04-16 | Finished | [34 empty] | 2019-08-25 | 2019-09-08 | 2019-09-08 | Finished | STORE AREA | [13 empty] | 2020-04-07 | 2020-05-25 | 2020-04-17 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-05-06 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 100 | [41 empty] | 2020-05-17 | 2020-05-12 | 2020-05-12 | Finished |  |  | 2020-05-26 | 2020-06-13 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2021-01-08 | 2021-03-12 | 2021-01-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2019-06-12 | Finished | [18 empty] | 2019-09-05 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-09 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007431 | 2019-08-25 |  |  |  | HDME000642 | 2019-09-05 | QC Passed
TAJ0556-TH | HET | 61000480 | HO | ส่งมอบแล้ว | - | TH199143 | The Circle Link Group Office | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2019-05-01 | 2019-09-01 | 2019-12-01 | 2020-08-24 | P-1500-2S60,60S/8F | UAG-SN1 | 1500 | 60 | 8 | 8 |  | 1400000 | Bangkok | แขวงมักกะสัน เขตราชเทวี | 2020-03-24 | [36 empty] | 2019-08-25 | 2019-09-08 | 2019-09-08 | Finished | STORE AREA | [13 empty] | 2020-04-07 | 2020-05-25 | 2020-04-17 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-05-06 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-17 | Finished |  |  | 100 | [41 empty] | 2020-05-17 | 2020-06-02 | 2020-06-02 | Finished |  |  | 2020-05-26 | 2020-06-13 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2020-09-29 | 2020-09-29 | 2020-09-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-29 | Finished | [6 empty] | 90 | 2020-10-25 | Finished | CONSTRUCTION DELAY |  | 2020-09-29 | Finished |  |  | 2019-06-12 | Finished | [18 empty] | 2019-09-05 | Finished |  |  | 2019-09-08 | Finished |  |  | 2019-09-09 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  | pass | 2020-10-14 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20007431 | 2019-08-25 |  |  |  | HDME000642 | 2019-09-05 | QC Passed
TFA1262-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ESC-1-1-1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-08-31 | 2021-01-15 | 1200TX-EN,R5.6M,D30 | TX-EN |  |  |  |  | 5600 | 1100000 | Bangkok | เขตบึงกุ่ม | 2019-09-10 | [20 empty] | 2019-09-10 | Finished | [14 empty] | 2019-06-30 | 2019-09-21 | 2019-07-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-18 | 2019-10-05 | [41 empty] | 2019-09-20 | Finished |  |  | 2019-09-22 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-10-03 | Finished |  |  | 2019-10-04 | Finished |  |  | 2019-10-05 | Finished |  |  | 100 | 2019-10-05 | 2020-01-23 | 2020-01-23 | Finished |  |  | 2020-12-11 | 2020-01-24 | Finished |  |  | 2020-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-05 | Finished | [6 empty] | 90 | 2021-02-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2019-05-03 | Finished | [10 empty] | 2021-03-10 | Finished | [6 empty] | 2019-07-21 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | pass (defect) |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 2 | 2 | 99.67 | Blue |  |  | 20006546 | 2019-06-30 |  |  |  | HDME000601 | 2019-07-21
TFA1263-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ESC-1-1-2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-08-31 | 2021-01-15 | 1200TX-EN,R5.6M,D30 | TX-EN |  |  |  |  | 5600 | 1100000 | Bangkok | เขตบึงกุ่ม | 2019-09-10 | [20 empty] | 2019-09-10 | Finished | [14 empty] | 2019-06-30 | 2019-09-21 | 2019-07-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-18 | 2019-10-05 | [41 empty] | 2019-09-20 | Finished |  |  | 2019-09-22 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-10-03 | Finished |  |  | 2019-10-04 | Finished |  |  | 2019-10-05 | Finished |  |  | 100 | 2019-10-05 | 2020-01-23 | 2020-01-23 | Finished |  |  | 2020-12-11 | 2020-01-24 | Finished |  |  | 2020-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-05 | Finished | [6 empty] | 90 | 2021-02-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2019-05-03 | Finished | [10 empty] | 2021-03-10 | Finished | [6 empty] | 2019-07-21 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | pass (defect) |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 2 | 2 | 99.67 | Blue |  |  | 20006546 | 2019-06-30 |  |  |  | HDME000601 | 2019-07-21
TFA1264-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ESC-2-1-1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-08-31 | 2021-01-15 | 1200TX-EN,R4.2M,D30 | TX-EN |  |  |  |  | 4200 | 1050000 | Bangkok | เขตบึงกุ่ม | 2019-09-10 | [20 empty] | 2019-09-10 | Finished | [14 empty] | 2019-06-30 | 2019-11-08 | 2019-07-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-18 | 2019-10-05 | [41 empty] | 2019-09-20 | Finished |  |  | 2019-09-22 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-10-03 | Finished |  |  | 2019-10-04 | Finished |  |  | 2019-10-05 | Finished |  |  | 100 | 2019-10-05 | 2020-01-23 | 2020-01-23 | Finished |  |  | 2020-12-11 | 2020-01-24 | Finished |  |  | 2020-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-05 | Finished | [6 empty] | 90 | 2021-02-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2019-05-03 | Finished | [10 empty] | 2021-03-10 | Finished | [6 empty] | 2019-07-21 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | pass (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20006546 | 2019-06-30 |  |  |  | HDME000601 | 2019-07-21
TFA1265-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ESC-2-1-2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-08-31 | 2021-01-15 | 1200TX-EN,R4.2M,D30 | TX-EN |  |  |  |  | 4200 | 1050000 | Bangkok | เขตบึงกุ่ม | 2019-09-10 | [20 empty] | 2019-09-10 | Finished | [14 empty] | 2019-06-30 | 2019-12-02 | 2019-07-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-18 | 2019-10-05 | [41 empty] | 2019-09-20 | Finished |  |  | 2019-09-22 | Finished |  |  | 2019-09-24 | Finished |  |  | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-09-29 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-10-03 | Finished |  |  | 2019-10-04 | Finished |  |  | 2019-10-05 | Finished |  |  | 100 | 2019-10-05 | 2020-01-23 | 2020-01-23 | Finished |  |  | 2020-12-11 | 2020-01-24 | Finished |  |  | 2020-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-05 | Finished | [6 empty] | 90 | 2021-02-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2019-05-03 | Finished | [10 empty] | 2021-03-10 | Finished | [6 empty] | 2019-07-21 | Finished |  |  | 2019-07-21 | Finished |  |  | 2019-07-23 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | pass (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20006546 | 2019-06-30 |  |  |  | HDME000601 | 2019-07-21
TEC0133-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | DT1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-15 | DT-100S-B30,30S/11F | DT | 100 | 30 | 11 | 11 |  | 374999.5 | Bangkok | เขตบึงกุ่ม | 2020-09-08 | 2020-12-15 | Finished | [34 empty] | 2019-06-26 | 2019-11-14 | 2020-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-28 | 2020-05-30 | 2020-12-15 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-12-19 | Finished |  |  | 100 | [41 empty] | 2020-12-19 | 2021-01-30 | 2021-01-30 | Finished |  |  | 2020-12-10 | 2020-01-31 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-03 | Finished |  |  | 100 | [18 empty] | 0 | 2021-02-17 | Finished | CONSTRUCTION DELAY |  | 2021-02-19 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-09-19 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-23 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | dumb |  |  |  |  | 421 | 0 | 32 | 0 | 453 | 0 | 0 | 32 | 0 | 32 | 92.94 | Blue |  |  | 20006707 | 2019-06-26 |  |  |  | HDME000980 | 2020-09-19
TEC0134-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | DT2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-15 | DT-100S-B30,30S/11F | DT | 100 | 30 | 11 | 11 |  | 374999.5 | Bangkok | เขตบึงกุ่ม | 2020-09-08 | 2020-12-15 | Finished | [34 empty] | 2019-06-26 | 2019-11-14 | 2020-09-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-28 | 2020-05-30 | 2020-12-15 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-12-19 | Finished |  |  | 100 | [41 empty] | 2020-12-19 | 2021-01-30 | 2021-01-30 | Finished |  |  | 2020-12-10 | 2020-01-31 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-03 | Finished |  |  | 100 | [18 empty] | 0 | 2021-02-17 | Finished | CONSTRUCTION DELAY |  | 2021-02-19 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-09-19 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-23 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | dumb |  |  |  |  | 421 | 0 | 32 | 0 | 453 | 0 | 0 | 32 | 0 | 32 | 92.94 | Blue |  |  | 20006707 | 2019-06-26 |  |  |  | HDME000980 | 2020-09-19
TBL0190-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-1-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-03-15 | OUG-1600-2S105,105S/13F | OUG-ON1 | 1600 | 105 | 13 | 13 |  | 2250000.33 | Bangkok | เขตบึงกุ่ม | 2020-05-25 | 2020-06-15 | Finished | [34 empty] | 2019-08-10 | 2020-06-18 | 2020-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-28 | 2020-05-30 | 2020-06-12 | Finished |  |  | 2020-08-12 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | [41 empty] | 2020-07-29 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-09-10 | 2020-09-19 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | 2021-02-19 | 2000-01-01 | 2021-02-19 | Finished | [14 empty] | 25 | 2021-03-06 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-06-18 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | in process (defect) |  |  |  |  | 914 | 99 | 32 | 20 | 1065 | 0 | 0 | 8 | 20 | 28 | 97.37 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000904 | 2020-06-18
TBL0191-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-1-2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-03-15 | OUG-1600-2S105,105S/13F | OUG-ON1 | 1600 | 105 | 13 | 13 |  | 2250000.33 | Bangkok | เขตบึงกุ่ม | 2020-05-25 | 2020-06-15 | Finished | [34 empty] | 2019-08-10 | 2020-06-18 | 2020-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-28 | 2020-05-30 | 2020-06-12 | Finished |  |  | 2020-08-12 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | [41 empty] | 2020-07-29 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-09-10 | 2020-09-19 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-29 | Finished |  |  | 100 | 2021-02-19 | 2000-01-01 | 2021-02-19 | Finished | [14 empty] | 25 | 2021-03-06 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-06-18 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | in process (defect) |  |  |  |  | 914 | 99 | 32 | 20 | 1065 | 0 | 0 | 8 | 20 | 28 | 97.37 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000904 | 2020-06-18
TBL0192-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-1-3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-03-15 | OUG-1600-2S105,105S/13F | OUG-ON1 | 1600 | 105 | 13 | 13 |  | 2250000.34 | Bangkok | เขตบึงกุ่ม | 2020-05-25 | 2020-06-15 | Finished | [34 empty] | 2019-08-10 | 2020-06-18 | 2020-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-28 | 2020-05-30 | 2020-06-12 | Finished |  |  | 2020-08-12 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | [41 empty] | 2020-07-29 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-09-10 | 2020-09-25 | Finished |  |  | 2020-10-25 | Finished |  |  | 2021-01-10 | Finished |  |  | 100 | 2021-02-19 | 2000-01-01 | 2021-02-19 | Finished |  |  | 2021-03-26 | Finished | [10 empty] | 50 | 2021-03-06 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-06-18 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | in process (defect) |  |  |  |  | 914 | 99 | 32 | 20 | 1065 | 0 | 0 | 0 | 20 | 20 | 98.12 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000904 | 2020-06-18
TBL0193-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-2-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-15 | OUG-1600-2S105,105S/6F | OUG-ON1 | 1600 | 105 | 6 | 6 |  | 1950000 | Bangkok | เขตบึงกุ่ม | 2020-09-05 | 2020-06-11 | Finished | [34 empty] | 2019-08-10 | 2019-12-02 | 2020-03-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-08 | 2020-05-10 | 2020-05-02 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-01-30 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-30 | Finished |  |  | 2020-09-03 | Finished |  |  | 100 | [41 empty] | 2020-09-03 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-10-15 | 2021-01-18 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-23 | Finished |  |  | 100 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished | [6 empty] | 90 | 2021-01-23 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-03-24 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | in process (defect) |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000828 | 2020-03-24
TBL0194-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-3-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-30 | OUG-1050-2S105,105S/13F | OUG-ON1 | 1050 | 105 | 13 | 13 |  | 1625000 | Bangkok | เขตบึงกุ่ม | 2020-09-05 | 2021-01-18 | Finished | [34 empty] | 2019-08-10 | 2019-11-14 | 2020-06-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-28 | 2020-05-30 | 2020-11-20 | Finished |  |  | 2020-12-01 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-02-07 | Finished |  |  | 2020-12-10 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | [41 empty] | 2021-01-29 | 2021-01-29 | 2021-01-29 | Finished |  |  | 2020-11-30 | 2021-01-31 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-08 | Finished |  |  | 100 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 90 | 2021-03-13 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-06-27 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | no qc |  |  |  |  | 914 | 99 | 32 | 20 | 1065 | 0 | 0 | 0 | 2 | 2 | 99.81 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000911 | 2020-06-27
TBL0195-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-3-2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-30 | OUG-1050-2S105,105S/14F | OUG-ON1 | 1050 | 105 | 14 | 14 |  | 1675000 | Bangkok | เขตบึงกุ่ม | 2020-09-05 | 2021-01-18 | Finished | [34 empty] | 2019-08-10 | 2019-11-14 | 2020-06-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-28 | 2020-05-30 | 2020-11-20 | Finished |  |  | 2020-12-01 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-02-07 | Finished |  |  | 2020-12-10 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | [41 empty] | 2021-01-29 | 2021-01-29 | 2021-01-29 | Finished |  |  | 2020-11-30 | 2021-01-31 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-05 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 90 | 2021-03-10 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-06-27 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | no qc |  |  |  |  | 967 | 100 | 32 | 20 | 1119 | 0 | 0 | 0 | 2 | 2 | 99.82 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000911 | 2020-06-27
TAK0505-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-4-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-30 | B-1000-2S105,105S/13F | UAG-SN1 | 1000 | 105 | 13 | 13 |  | 1724999 | Bangkok | เขตบึงกุ่ม | 2020-08-31 | 2021-01-18 | Finished | [34 empty] | 2019-06-26 | 2019-11-14 | 2020-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-10 | 2020-05-30 | 2020-12-15 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-02-06 | Finished |  |  | 2021-02-06 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-22 | Finished |  |  | 100 | [41 empty] | 2021-01-22 | 2021-01-23 | 2021-01-23 | Finished |  |  | 2020-12-10 | 2021-01-24 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-20 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-08-27 | Finished | [10 empty] | 50 | 2021-02-20 | Finished | CONSTRUCTION DELAY |  | 2021-02-28 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-07-29 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-30 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | no qc |  |  |  |  | 762 | 95 | 32 | 20 | 909 | 0 | 0 | 0 | 20 | 20 | 97.8 | Blue |  |  | 20006706 | 2019-06-26 |  |  |  | HDME000931 | 2020-07-24
TAK0506-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-5-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-30 | B-1000-2S105,105S/13F | UAG-SN1 | 1000 | 105 | 13 | 13 |  | 1725001 | Bangkok | เขตบึงกุ่ม | 2020-09-15 | 2021-01-18 | Finished | [34 empty] | 2019-06-26 | 2019-11-14 | 2020-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-10 | 2020-03-28 | 2020-12-15 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-02-06 | Finished |  |  | 2021-02-06 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-22 | Finished |  |  | 100 | [41 empty] | 2021-01-22 | 2021-01-23 | 2021-01-23 | Finished |  |  | 2020-12-20 | 2021-01-24 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-20 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-08-27 | Finished | [10 empty] | 50 | 2021-02-20 | Finished | CONSTRUCTION DELAY |  | 2021-02-28 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-07-29 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-30 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Working |  |  | 2021-04-19 | Working |  | no qc |  |  |  |  | 762 | 95 | 32 | 20 | 909 | 0 | 0 | 0 | 20 | 20 | 97.8 | Blue |  |  | 20006706 | 2019-06-26 |  |  |  | HDME000931 | 2020-07-24
TBL0196-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-6-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-15 | OUG-1050-2S105,105S/9F | OUG-ON1 | 1050 | 105 | 9 | 9 |  | 1400000 | Bangkok | เขตบึงกุ่ม | 2020-04-27 | 2020-06-11 | Finished | [34 empty] | 2019-08-10 | 2019-11-14 | 2020-03-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-08 | 2020-05-10 | 2020-04-18 | Finished |  |  | 2020-06-29 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-17 | Finished |  |  | 100 | [41 empty] | 2020-07-17 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 2020-10-17 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-03 | Finished |  |  | 100 | 2020-09-14 | 2021-07-09 | 2020-09-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-09 | Finished |  |  | 100 | 2021-01-15 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-03-24 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | pass |  |  |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000828 | 2020-03-24 | QC Passed
TBL0197-TH | HET | 61000482 | HO | ส่งมอบแล้ว | - | TH199146 | รพ.นวเวช อินเตอร์เนชั่นแนล | ELE-6-2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chanyuth Soithong | 2019-02-28 | 2019-07-15 | 2019-10-31 | 2021-01-15 | OUG-1050-2S105,105S/9F | OUG-ON1 | 1050 | 105 | 9 | 9 |  | 1400000 | Bangkok | เขตบึงกุ่ม | 2020-04-27 | 2020-06-11 | Finished | [34 empty] | 2019-08-10 | 2019-11-14 | 2020-03-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-08 | 2020-05-10 | 2020-04-18 | Finished |  |  | 2020-06-29 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-17 | Finished |  |  | 100 | [41 empty] | 2020-07-17 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 2020-10-17 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-03 | Finished |  |  | 100 | 2020-11-27 | 2021-07-09 | 2020-11-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-07-09 | Finished |  |  | 100 | 2021-01-15 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2019-05-03 | Finished | [18 empty] | 2020-03-24 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | pass |  |  |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006706 | 2019-08-10 |  |  |  | HDME000828 | 2020-03-24 | QC Passed
TAJ0499-TH | HET | 61000484 | HO | ส่งมอบแล้ว | - | TH199148 | The Best @ Siam Hotel | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2019-03-15 | 2019-09-15 | 2019-11-15 | 2021-05-31 | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1100000 | Bangkok | เพชรบุรี | 2019-08-05 | 2020-06-01 | Finished | [34 empty] | 2019-09-08 | 2019-11-19 | 2019-11-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-01 | 2019-11-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-06-16 | 2020-06-16 | Finished |  |  | 2020-06-16 | 2020-06-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-18 | 2021-06-18 | 2021-06-18 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-18 | Finished | [6 empty] | 90 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-06-22 | Finished |  |  | 2019-03-26 | Finished | [10 empty] | 2021-06-22 | Finished | [6 empty] | 2019-11-19 | Finished |  |  | 2019-11-19 | Finished |  |  | 2019-11-20 | Finished |  |  | 2021-06-22 | Finished | [13 empty] | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20006583 | 2019-09-08 |  |  |  | HDME000720 | 2019-11-19 | QC Passed
TAJ0501-TH | HET | 61000485 | HO | ส่งมอบแล้ว | - | TH199150 | Aparment 6 Fl., Soi Sukhumvit 53 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-03-14 | 2019-08-29 | 2019-10-14 | 2020-06-04 | P-750-CO90,90S/6F | UAG-SN1 | 750 | 90 | 6 | 6 |  | 1200000 | Bangkok | เขตวัฒนา | 2019-11-01 | 2019-11-01 | Finished | [34 empty] | 2019-08-22 | 2019-09-11 | 2019-09-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-18 | 2020-06-05 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-05-20 | 2020-07-28 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-08-06 | Finished |  |  | 100 | 2021-05-13 | 2021-07-12 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2020-08-25 | Finished | POWER SUPPLY DELAY |  | 2020-09-18 | Finished |  |  | 2019-04-10 | Finished | [18 empty] | 2019-09-11 | Finished |  |  | 2019-09-11 | Finished |  |  | 2019-09-16 | Finished |  |  | 2020-09-18 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006618 | 2019-08-22 |  |  |  | HDME000649 | 2019-09-11 | QC Passed
TEB0100-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 10 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-08-30 | 2022-12-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-07-30 | [36 empty] | 2022-07-30 | 2022-07-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-07-30 | 2022-08-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-07-15
TEB0101-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 11 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-09-30 | 2022-12-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-09-30 | [36 empty] | 2022-09-30 | 2022-09-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-09-30 | 2022-10-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-10-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-10-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2022-04-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-08-15
TEB0102-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 12 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-09-30 | 2022-12-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-09-30 | [36 empty] | 2022-09-30 | 2022-09-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-09-30 | 2022-10-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-10-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-10-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2022-04-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-08-15
TEB0103-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 13 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2021-01-30 | 2022-12-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-11-30 | [36 empty] | 2022-11-30 | 2022-11-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-11-30 | 2022-12-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2022-05-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-12-15
TEB0104-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 14 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2021-01-30 | 2022-12-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-11-30 | [36 empty] | 2022-11-30 | 2022-11-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-11-30 | 2022-12-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2022-05-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-12-15
TEB0105-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 15 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2021-02-28 | 2022-12-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-11-30 | [36 empty] | 2022-11-30 | 2022-11-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-11-30 | 2022-12-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2022-06-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2021-01-15
TEB0106-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 16 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2021-02-28 | 2022-12-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-11-30 | [36 empty] | 2022-11-30 | 2022-11-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-11-30 | 2022-12-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2022-06-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2021-01-15
TEB0093-TH | HET | 61000491 | HO | ส่งมอบแล้ว | - | TH199130 | The Welton Rama III | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2019-10-30 | 2021-05-20 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2019-07-16 | 2020-10-07 | Finished | [34 empty] | 2019-09-15 | 2019-12-04 | 2019-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-07 | 2020-10-30 | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-11 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-13 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-15 | Finished |  |  | 100 | [41 empty] | 2020-10-15 | 2021-05-03 | 2021-05-03 | Finished |  |  | 2020-11-01 | 2021-05-04 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-06 | Finished |  |  | 100 | 2021-05-13 | 2021-05-24 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-24 | Finished | [6 empty] | 90 | 2021-02-28 | Finished | CONSTRUCTION DELAY |  | 2021-05-28 | Finished |  |  | 2019-05-28 | Finished | [10 empty] | 2021-05-28 | Finished | [6 empty] | 2019-12-04 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-06 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20006703 | 2019-09-15 |  |  |  | HDME000742 | 2019-12-04 | QC Passed
TEB0094-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2019-10-30 | 2021-11-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2019-07-16 | 2020-10-07 | Finished | [34 empty] | 2019-09-15 | 2019-12-04 | 2019-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-07 | 2020-10-30 | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-11 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-13 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-15 | Finished |  |  | 100 | [41 empty] | 2020-10-15 | 1900-01-01 | 2020-10-15 | Waiting | POWER SUPPLY DELAY |  | 2022-01-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2019-12-04 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-06 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 16 | 16 | 87 | 66.15 | Green |  |  | 20006703 | 2019-09-15 |  |  |  | HDME000742 | 2019-12-04
TEB0095-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-02-29 | 2022-06-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2021-04-01 | 2021-04-01 | Finished | [34 empty] | 2020-01-15 | 2019-09-06 | 2020-12-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-01 | 2021-04-09 | 2021-04-02 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 1900-01-01 | 2021-04-09 | Waiting | POWER SUPPLY DELAY |  | 2022-04-10 | [12 empty] | 0 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2022-04-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-12-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-30 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 4 | 16 | 75 | 70.82 | Green |  |  | 20006703 | 2020-01-15 |  |  |  | HDME001082 | 2020-12-28
TEB0096-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-02-29 | 2022-06-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2021-04-01 | 2021-04-01 | Finished | [34 empty] | 2020-01-15 | 2019-11-12 | 2020-12-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-01 | 2021-04-09 | 2021-04-02 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 1900-01-01 | 2021-04-09 | Waiting | POWER SUPPLY DELAY |  | 2022-04-10 | [12 empty] | 0 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2022-04-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-12-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-30 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 4 | 16 | 75 | 70.82 | Green |  |  | 20006703 | 2020-01-15 |  |  |  | HDME001082 | 2020-12-28
TEB0097-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-03-30 | 2022-06-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-05-30 | [36 empty] | 2020-02-15 | 2019-11-12 | 2021-08-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-05-30 | 2022-06-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-06-10 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-06-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [18 empty] | 2021-08-04 | Finished |  |  | 2021-08-06 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-02-15
TEB0098-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-03-30 | 2022-06-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-05-30 | [36 empty] | 2020-02-15 | 2019-11-12 | 2021-08-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-05-30 | 2022-06-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-06-10 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-06-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [18 empty] | 2021-08-04 | Finished |  |  | 2021-08-06 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-02-15
TEB0099-TH | HET | 61000491 | Install | ยังอยู่ในสัญญา HO | - | TH199130 | The Welton Rama III | 9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-03-20 | 2019-08-30 | 2020-08-30 | 2022-06-28 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | แขวงช่องนนทรี เขตยานนาวา | 2022-07-30 | [36 empty] | 2022-07-30 | 2022-07-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-07-30 | 2022-08-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-08-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-08-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-28 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20006703 | 2020-07-15
TFA1266-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | ES-1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 6 |  | 1 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | 1200TX-EN,R4.9M,D35 | TX-EN |  |  |  |  | 4900 | 1122633 | Bangkok | เขตบางนา | 2020-02-28 | [20 empty] | 2020-02-28 | Finished | [14 empty] | 2019-10-16 | 2019-11-02 | 2019-11-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-17 | 2019-10-30 | [41 empty] | 2019-11-20 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-22 | Finished |  |  | 2019-11-23 | Finished |  |  | 2019-11-24 | Finished |  |  | 2019-11-25 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-27 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-11-29 | Finished |  |  | 100 | 2019-11-29 | 2020-04-10 | 2020-04-10 | Finished |  |  | 2020-04-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-01-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-22 | Finished |  |  | 2021-01-19 | Finished |  |  | 100 | 2020-02-28 | Finished | POWER SUPPLY DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-02 | Finished |  |  | 2019-11-06 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006741 | 2019-10-16 |  |  |  | HDME000696 | 2019-11-01 | QC Passed
TFA1267-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | ES-2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 6 |  | 1 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | 1200TX-EN,R5.5M,D35 | TX-EN |  |  |  |  | 5500 | 1140888 | Bangkok | เขตบางนา | 2020-02-28 | [20 empty] | 2020-02-28 | Finished | [14 empty] | 2019-10-16 | 2019-11-02 | 2019-11-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-10-17 | 2019-10-30 | [41 empty] | 2019-11-20 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-22 | Finished |  |  | 2019-11-23 | Finished |  |  | 2019-11-24 | Finished |  |  | 2019-11-25 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-27 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-11-29 | Finished |  |  | 100 | 2019-11-29 | 2020-04-10 | 2020-04-10 | Finished |  |  | 2020-04-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-06-22 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-22 | Finished | [6 empty] | 90 | 2020-04-27 | Finished | POWER SUPPLY DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2019-11-01 | Finished |  |  | 2019-11-02 | Finished |  |  | 2019-11-06 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 2 | 2 | 99.67 | Blue |  |  | 20006741 | 2019-10-16 |  |  |  | HDME000696 | 2019-11-01 | QC Passed
TEC0135-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | CL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | DF-50S-B30,30S/8F | DF | 50 | 30 | 8 | 8 |  | 2920672 | Bangkok | เขตบางนา | 2020-02-28 | 2020-02-28 | Finished | [34 empty] | 2019-10-23 | 2020-03-30 | 2020-03-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-20 | 2020-03-20 | 2020-03-04 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-03 | Finished |  |  | 100 | [41 empty] | 2020-05-03 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2020-04-27 | Finished | CONSTRUCTION DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | dumb |  |  |  |  | 338 | 0 | 24 | 0 | 362 | 0 | 0 | 24 | 0 | 24 | 93.37 | Blue |  |  | 20007687 | 2019-11-15 |  |  |  | HDME000835 | 2020-03-27
TEC0136-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | CL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | DF-50S-B30,30S/8F | DF | 50 | 30 | 8 | 8 |  | 2920672 | Bangkok | เขตบางนา | 2020-02-28 | 2020-02-28 | Finished | [34 empty] | 2019-10-23 | 2020-03-30 | 2020-03-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-20 | 2020-03-20 | 2020-03-04 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-03 | Finished |  |  | 100 | [41 empty] | 2020-05-03 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2020-04-27 | Finished | CONSTRUCTION DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | dumb |  |  |  |  | 338 | 0 | 24 | 0 | 362 | 0 | 0 | 24 | 0 | 24 | 93.37 | Blue |  |  | 20007687 | 2019-11-15 |  |  |  | HDME000835 | 2020-03-27
TEC0137-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | DT | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | DT-200P-B30,30S/5F | DT | 200 | 30 | 5 | 5 |  | 775493 | Bangkok | เขตบางนา | 2020-02-28 | 2020-02-28 | Finished | [34 empty] | 2019-10-23 | 2020-03-30 | 2020-03-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-20 | 2020-03-20 | 2020-04-03 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-13 | Finished |  |  | 100 | [41 empty] | 2020-09-13 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [18 empty] | 0 | 2020-11-15 | Finished | CONSTRUCTION DELAY |  | 2020-11-24 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-11-24 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | dumb |  |  |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20007687 | 2019-11-15 |  |  |  | HDME000835 | 2020-03-27
TAC1573-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | FL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | VFI-1600-CO105,105S/12F | VFI-II | 1600 | 105 | 12 | 12 |  | 2099233 | Bangkok | เขตบางนา | 2020-02-28 | 2020-02-28 | Finished | [34 empty] | 2019-12-07 | 2020-01-18 | 2020-01-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-20 | 2020-03-20 | 2020-02-27 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-15 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-04-10 | Finished |  |  | 100 | [41 empty] | 2020-04-10 | 2020-04-15 | 2020-04-15 | Finished |  |  | 2020-04-10 | 2020-04-17 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-27 | Finished |  |  | 100 | 2021-05-13 | 2020-11-09 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-11-09 | Finished |  |  | 100 | 2020-05-27 | Finished | CONSTRUCTION DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-01-18 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007686 | 2019-12-15 |  |  |  | HDME000768 | 2020-01-18 | QC Passed
TAC1570-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | P1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 12 | 12 |  | 2418681.5 | Bangkok | เขตบางนา | 2020-02-28 | 2020-02-28 | Finished | [34 empty] | 2019-12-07 | 2020-01-18 | 2020-01-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-20 | 2020-03-20 | 2020-02-27 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-04-03 | Finished |  |  | 100 | [41 empty] | 2020-04-03 | 2020-04-09 | 2020-04-09 | Finished |  |  | 2020-04-10 | 2020-04-14 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-05-13 | 2020-10-05 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-10-05 | Finished |  |  | 100 | 2020-05-27 | Finished | CONSTRUCTION DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-01-18 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007686 | 2019-12-15 |  |  |  | HDME000768 | 2020-01-18 | QC Passed
TAC1571-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | P2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 12 | 12 |  | 2418681.5 | Bangkok | เขตบางนา | 2020-02-28 | 2020-02-28 | Finished | [34 empty] | 2019-12-07 | 2020-01-18 | 2020-01-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-20 | 2020-03-20 | 2020-02-27 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-04-03 | Finished |  |  | 100 | [41 empty] | 2020-04-03 | 2020-04-09 | 2020-04-09 | Finished |  |  | 2020-04-10 | 2020-04-14 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | 2021-05-13 | 2020-11-09 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-11-09 | Finished |  |  | 100 | 2020-05-27 | Finished | CONSTRUCTION DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-01-18 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007686 | 2019-12-15 |  |  |  | HDME000768 | 2020-01-18 | QC Passed
TAC1572-TH | HET | 61000494 | HO | ส่งมอบแล้ว | - | TH199159 | Office Benz BKK | P3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SORAWIT WANITCHAPAK | 2019-02-11 | 2019-11-01 | 2020-02-28 | 2020-06-30 | VFI-1350-CO150,150S/12F | VFI-II | 1350 | 150 | 12 | 12 |  | 2373046 | Bangkok | เขตบางนา | 2020-02-28 | 2020-02-28 | Finished | [34 empty] | 2019-12-07 | 2020-01-18 | 2020-01-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-20 | 2020-03-20 | 2020-04-17 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-14 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | [41 empty] | 2020-05-20 | 2020-05-18 | 2020-05-18 | Finished |  |  | 2020-04-10 | 2020-05-25 | Finished |  |  | 2020-05-26 | Finished |  |  | 2020-05-28 | Finished |  |  | 100 | 2021-05-13 | 2020-10-05 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-10-05 | Finished |  |  | 100 | 2020-04-27 | Finished | CONSTRUCTION DELAY |  | 2020-07-15 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-01-18 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007686 | 2019-12-15 |  |  |  | HDME000768 | 2020-01-18 | QC Passed
TAJ0516-TH | HET | 61000500 | Install | ยังอยู่ในสัญญา HO | - | TH199162 | Sahathanee | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-04-01 | 2019-09-01 | 2019-12-01 | 2021-12-06 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1300050 | Bangkok | แขวงคันนายาว | 2020-04-01 | 2020-03-31 | Finished | [34 empty] | 2019-08-25 | 2019-10-02 | 2019-11-12 | Finished | STORE AREA | [13 empty] | 2020-03-31 | 2020-05-01 | 2020-03-31 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-05 | Finished |  |  | 100 | [41 empty] | 2020-06-05 | 1900-01-01 | 2020-06-05 | Waiting | POWER SUPPLY DELAY |  | 2021-11-17 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-04-24 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2019-11-12 | Finished |  |  | 2019-11-12 | Finished |  |  | 2019-11-12 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 24 | 16 | 122 | 78.75 | Green |  |  | 20006918 | 2019-08-25 |  |  |  | HDME000708 | 2019-11-12
TAJ0517-TH | HET | 61000500 | Install | ยังอยู่ในสัญญา HO | - | TH199162 | Sahathanee | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-04-01 | 2019-09-01 | 2019-12-01 | 2021-12-06 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1300050 | Bangkok | แขวงคันนายาว | 2020-04-01 | 2020-03-31 | Finished | [34 empty] | 2019-08-25 | 2019-10-02 | 2019-11-12 | Finished | STORE AREA | [13 empty] | 2020-03-31 | 2020-05-01 | 2020-03-31 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-05-24 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-04 | Finished |  |  | 2020-05-07 | Finished |  |  | 100 | [41 empty] | 2020-05-07 | 1900-01-01 | 2020-05-07 | Waiting | POWER SUPPLY DELAY |  | 2021-11-17 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-04-24 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2019-11-12 | Finished |  |  | 2019-11-12 | Finished |  |  | 2019-11-12 | Finished | [17 empty] | in process (defect) |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 24 | 16 | 122 | 78.75 | Green |  |  | 20006918 | 2019-08-25 |  |  |  | HDME000708 | 2019-11-12
TAJ0514-TH | HET | 61000502 | HO | ส่งมอบแล้ว | - | TH199166 | Khun Adirek Bangpakok | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Thamnul Kongsar | 2019-04-05 | 2019-07-20 | 2019-09-05 | 2021-01-06 | P-750-CO90,90S/8F | UAG-SN1 | 750 | 90 | 8 | 8 |  | 1070000 | Bangkok | อ.พระประแดง | 2019-08-02 | 2019-08-10 | Finished | [34 empty] | 2019-07-13 | 2019-11-02 | 2019-07-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-08-12 | 2019-09-05 | 2019-08-13 | Finished |  |  | 2019-08-15 | Finished |  |  | 2019-08-17 | Finished |  |  | 2019-08-19 | Finished |  |  | 2019-08-21 | Finished |  |  | 2019-08-23 | Finished |  |  | 2019-08-25 | Finished |  |  | 2019-08-27 | Finished |  |  | 2019-08-30 | Finished |  |  | 2019-09-05 | Finished |  |  | 100 | [41 empty] | 2019-09-05 | 2020-11-24 | 2020-11-24 | Finished |  |  | 2020-11-20 | 2020-11-24 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-01-06 | Finished |  |  | 100 | 2021-01-25 | 2021-06-04 | 2021-01-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-06-04 | Finished |  |  | 100 | 2021-02-13 | Finished | POWER SUPPLY DELAY |  | 2021-02-15 | Finished |  |  | 2019-05-03 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2019-07-23 | Finished |  |  | 2019-08-01 | Finished |  |  | 2019-08-01 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  | pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006917 | 2019-07-13 |  |  |  | HDME000603 | 2019-07-23 | QC Passed
TAJ0515-TH | HET | 61000502 | Install | ยังอยู่ในสัญญา HO | - | TH199166 | Khun Adirek Bangpakok | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Thamnul Kongsar | 2019-04-05 | 2019-07-20 | 2020-01-05 | 2021-10-30 | P-1000-CO90W2,90S/8F | UAG-SN1 | 1000 | 90 | 8 | 8 |  | 1230500 | Bangkok | อ.พระประแดง | 2021-05-01 | 2021-05-15 | Finished | [34 empty] | 2019-07-13 | 2019-12-14 | 2019-12-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-01 | 2021-05-15 | 2021-05-24 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-29 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-19 | Finished |  |  | 100 | [41 empty] | 2021-06-19 | 1900-01-01 | 2021-06-19 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2021-07-02 | 2000-01-01 | 2021-07-02 | Finished | [14 empty] | 25 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-05-03 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2019-10-08 | Finished |  |  | 2019-10-09 | Finished |  |  | 2019-10-15 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 0 | 84 | 6 | 16 | 106 | 84.06 | Green |  |  | 20006917 | 2019-07-13 |  |  |  | HDME000677 | 2019-10-08
TAJ0518-TH | HET | 61000503 | HO | ส่งมอบแล้ว | - | TH199167 | Office & Residences Khun Ubon Klinyoo | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-04-05 | 2019-11-05 | 2019-12-20 | 2021-08-23 | P-1600-CO60,60S/4F | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1444500 | Bangkok | แขวงดินแดง | 2020-03-15 | 2020-03-15 | Finished | [34 empty] | 2019-10-22 | 2019-11-20 | 2019-11-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-20 | 2019-12-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-11-18 | 2021-11-18 | Finished |  |  | 2021-11-17 | 1900-01-01 | Finished |  |  | 1900-01-02 | Finished |  |  | 1900-01-03 | Finished |  |  | 100 | 2020-06-19 | 2000-01-01 | 2020-06-19 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-02 | Finished | [6 empty] | 90 | 2021-09-23 | Finished | CONSTRUCTION DELAY |  | 2021-08-30 | Finished |  |  | 2019-04-26 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2019-11-19 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | no pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20006884 | 2019-10-22 |  |  |  | HDME000722 | 2019-11-19
TEB0107-TH | HET | 61000504 | HO | ส่งมอบแล้ว | - | TH199168 | Home Khun Phop | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | ANUSSARA POLDONGNOK | 2019-04-05 | 2019-08-05 | 2019-09-05 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 909500 | Bangkok | เขตสวนหลวง | 2019-11-30 | [36 empty] | 2019-07-21 | 2019-08-23 | 2019-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-09-20 | 2020-05-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-03-01 | 2020-03-01 | Finished |  |  | 2020-03-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-04-17 | 2021-02-17 | 2020-04-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2020-03-17 | Finished | POWER SUPPLY DELAY |  | 2020-04-07 | Finished |  |  | 2019-04-26 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2019-08-29 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-10-03 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass | 2020-04-24 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20006957 | 2019-07-21 |  |  |  | HDME000638 | 2019-08-29 | QC Passed
TAJ0519-TH | HET | 61000506 | HO | ส่งมอบแล้ว | - | TH199171 | Home Khun Natthakan | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2019-04-19 | 2019-09-19 | 2019-11-19 | 2021-07-18 | P-600-CO60W,60S/5F | UAG-SN1 | 600 | 60 | 5 | 5 |  | 1342850 | Chumphon | ต. ตากแดด | 2020-04-25 | 2020-06-09 | Finished | [34 empty] | 2019-09-12 | 2020-03-17 | 2020-05-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-09 | 2020-07-10 | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 100 | [41 empty] | 2020-06-09 | 2021-06-01 | 2021-06-01 | Finished |  |  | 2021-05-26 | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2020-08-18 | 2000-01-01 | 2020-08-18 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-07-05 | Finished | POWER SUPPLY DELAY |  | 2021-07-29 | Finished |  |  | 2019-05-15 | Finished | [10 empty] | 2021-07-05 | Finished | [6 empty] | 2020-05-02 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-07-29 | Finished | [13 empty] | no pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20007030 | 2019-09-12 |  |  |  | HDME000878 | 2020-05-02
TAJ0521-TH | HET | 61000508 | Test | ยังอยู่ในสัญญา HO | - | TH199172 | Town Home One | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Siraprapa Sihamart | 2019-04-04 | 2019-08-04 | 2019-10-04 | 2021-11-26 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1000000 | Bangkok | เขตวัฒนา | 2019-07-15 | 2019-11-13 | Finished | [34 empty] | 2019-07-28 | 2019-11-08 | 2019-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-14 | 2020-05-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-05 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-05-13 | Finished | [18 empty] | 2019-11-07 | Finished |  |  | 2019-12-02 | Finished |  |  | 2019-12-03 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 16 | 16 | 113 | 76.31 | Green |  |  | 20007101 | 2019-07-28 |  |  |  | HDME000700 | 2019-11-07
TAJ0522-TH | HET | 61000508 | Test | ยังอยู่ในสัญญา HO | - | TH199172 | Town Home One | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Siraprapa Sihamart | 2019-04-04 | 2019-08-04 | 2019-10-04 | 2021-11-26 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1000000 | Bangkok | เขตวัฒนา | 2019-08-05 | 2019-11-13 | Finished | [34 empty] | 2019-07-28 | 2019-11-08 | 2019-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-14 | 2020-05-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-05 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-05-13 | Finished | [18 empty] | 2019-11-07 | Finished |  |  | 2019-12-02 | Finished |  |  | 2019-12-03 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 16 | 16 | 113 | 76.31 | Green |  |  | 20007101 | 2019-07-28 |  |  |  | HDME000700 | 2019-11-07
TAJ0525-TH | HET | 61000511 | HO | ส่งมอบแล้ว | - | TH199177 | The SR Resident Chiang Mai | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-01-13 | 2020-07-13 | 2020-09-13 | 2021-05-16 | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1316100 | Chiang Mai | อ.เมืองเชียงใหม่ | 2020-07-13 | 2020-07-16 | Finished | [34 empty] | 2020-07-13 | 2020-07-16 | 2020-07-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-15 | 2020-07-30 | 2020-07-17 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-23 | Finished |  |  | 2020-07-23 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-24 | Finished |  |  | 100 | [41 empty] | 2020-07-24 | 2021-04-28 | 2021-04-28 | Finished |  |  | 2021-04-30 | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-05-01 | Finished |  |  | 100 | 2020-08-14 | 2021-05-17 | 2020-08-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished | [6 empty] | 90 | 2021-05-20 | Finished | POWER SUPPLY DELAY |  | 2021-05-28 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-05-28 | Finished | [6 empty] | 2020-07-16 | Finished |  |  | 2020-07-16 | Finished |  |  | 2020-07-20 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass | 2021-06-09 | Finished |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 1 | 1 | 99.84 | Blue |  |  | 20010672 | 2020-07-13 |  |  |  | HDME000925 | 2020-07-16 | QC Passed
TFA1269-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R1.4M,D30 | SX-EN |  |  |  |  | 1400 | 845300 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-02-19 | Finished | [14 empty] | 2019-10-16 | 2019-12-02 | 2019-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-19 | 2020-03-19 | [41 empty] | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-04-05 | Finished |  |  | 100 | 2020-04-05 | 2020-06-18 | 2020-06-18 | Finished |  |  | 2020-06-18 | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-06-26 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-12-02 | Finished |  |  | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 504 | 32 | 16 | 14 | 566 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000739 | 2019-12-02 | QC Passed
TFA1270-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R1.2M,D30 | SX-EN |  |  |  |  | 1200 | 834600 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-02-21 | Finished | [14 empty] | 2019-10-16 | 2019-12-02 | 2019-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-21 | 2020-03-22 | [41 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-04-18 | Finished |  |  | 100 | 2020-04-18 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 2020-08-03 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-07 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-12-02 | Finished |  |  | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 504 | 32 | 16 | 14 | 566 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000739 | 2019-12-02 | QC Passed
TFA1271-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R1.2M,D30 | SX-EN |  |  |  |  | 1200 | 834600 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-04-17 | Finished | [14 empty] | 2019-10-16 | 2019-12-02 | 2019-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-05-16 | [41 empty] | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-30 | Finished |  |  | 100 | 2020-04-30 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 2020-08-03 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-07 | Finished |  |  | 100 | 2021-05-13 | 2020-09-16 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-09-16 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-12-02 | Finished |  |  | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 504 | 32 | 16 | 14 | 566 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000739 | 2019-12-02 | QC Passed
TFA1272-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R1.1M,D30 | SX-EN |  |  |  |  | 1100 | 829250 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-02-28 | Finished | [14 empty] | 2019-10-16 | 2019-12-02 | 2019-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-28 | 2020-03-29 | [41 empty] | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-04-20 | Finished |  |  | 100 | 2020-04-20 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 2020-08-03 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-12-02 | Finished |  |  | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 504 | 32 | 16 | 14 | 566 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000739 | 2019-12-02 | QC Passed
TFA1273-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R1.1M,D30 | SX-EN |  |  |  |  | 1100 | 829250 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-04-17 | Finished | [14 empty] | 2019-10-16 | 2019-12-02 | 2019-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-05-16 | [41 empty] | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-05-04 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-05-05 | Finished |  |  | 100 | 2020-05-05 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-08-01 | 2020-08-03 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-12-02 | Finished |  |  | 2019-12-03 | Finished |  |  | 2019-12-06 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 504 | 32 | 16 | 14 | 566 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000739 | 2019-12-02 | QC Passed
TFA1274-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES6.1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.75M,D30 | SX-EN |  |  |  |  | 4750 | 963000 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-04-06 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-06 | 2020-04-15 | [41 empty] | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-06-02 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | 2020-06-04 | 2020-07-31 | 2020-07-31 | Finished |  |  | 2020-07-31 | 2020-08-01 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-25 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TFA1275-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES6.2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.75M,D30 | SX-EN |  |  |  |  | 4750 | 963000 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-04-06 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-06 | 2020-04-15 | [41 empty] | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-06-02 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | 2020-06-04 | 2020-07-31 | 2020-07-31 | Finished |  |  | 2020-07-31 | 2020-08-01 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-25 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TFA1276-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES6.3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.75M,D30 | SX-EN |  |  |  |  | 4750 | 963000 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-01-13 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-13 | 2020-02-13 | [41 empty] | 2020-01-16 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-20 | 2020-07-20 | Finished |  |  | 2020-07-20 | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TFA1277-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES6.4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.75M,D30 | SX-EN |  |  |  |  | 4750 | 963000 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-01-13 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-13 | 2020-02-13 | [41 empty] | 2020-01-16 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-20 | 2020-07-20 | Finished |  |  | 2020-07-20 | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | 2021-05-13 | 2021-07-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-23 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TFA1314-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R7.75M,D30 | SX-EN |  |  |  |  | 7750 | 2033000 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-03-23 | Finished | [14 empty] | 2020-02-15 | 2020-03-17 | 2020-03-17 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-03-24 | 2020-04-25 | [41 empty] | 2020-03-24 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-24 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 100 | 2020-05-30 | 2020-08-07 | 2020-08-07 | Finished |  |  | 2020-07-20 | 2020-08-07 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-25 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2020-03-17 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 756 | 42 | 24 | 21 | 843 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008952 | 2020-02-15 |  |  |  | HDME000821 | 2020-03-17 | QC Passed
TFA1279-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES8.1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-01-13 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-13 | 2020-02-13 | [41 empty] | 2020-01-16 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-20 | 2020-07-20 | Finished |  |  | 2020-07-20 | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TFA1280-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES8.2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-01-13 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-13 | 2020-02-13 | [41 empty] | 2020-01-16 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-15 | Finished |  |  | 100 | 2020-02-15 | 2020-07-20 | 2020-07-20 | Finished |  |  | 2020-07-20 | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TFA1281-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES8.3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-02-19 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-19 | 2020-03-19 | [41 empty] | 2020-02-20 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 100 | 2020-03-02 | 2020-07-31 | 2020-07-31 | Finished |  |  | 2020-07-31 | 2020-08-01 | Finished |  |  | 2020-08-12 | Finished |  |  | 2020-08-14 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TFA1282-TH | HET | 61000519 | HO | ส่งมอบแล้ว | - | TH199179 | Mun Mun Seacon Square | ES8.4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-05-07 | 2019-11-01 | 2020-03-01 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2019-11-01 | [20 empty] | 2020-02-19 | Finished | [14 empty] | 2019-10-16 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-19 | 2020-03-19 | [41 empty] | 2020-02-20 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 100 | 2020-03-02 | 2020-07-31 | 2020-07-31 | Finished |  |  | 2020-07-31 | 2020-08-01 | Finished |  |  | 2020-08-12 | Finished |  |  | 2020-08-14 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-07-13 | Finished | [18 empty] | 2019-11-14 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007814 | 2019-10-16 |  |  |  | HDME000715 | 2019-11-14 | QC Passed
TBL0202-TH | HET | 61000521 | HO | ส่งมอบแล้ว | - | TH199184 | วัดบรมราชากาญจนาภิเษกอนุสรณ์ | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2019-05-15 | 2019-11-15 | 2020-01-15 |  | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1500000 | Nonthaburi | เขตบางบัวทอง | 2020-08-30 | 2020-08-30 | Finished | [34 empty] | 2019-11-08 | 2019-11-18 | 2019-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-21 | 2019-12-18 | 2019-11-21 | Finished |  |  | 2019-11-22 | Finished |  |  | 2019-11-25 | Finished |  |  | 2019-11-27 | Finished |  |  | 2019-11-29 | Finished |  |  | 2019-12-01 | Finished |  |  | 2019-12-05 | Finished |  |  | 2019-12-07 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-18 | Finished |  |  | 100 | [41 empty] | 2019-12-18 | 2019-12-20 | 2019-12-20 | Finished |  |  | 2019-12-20 | 2019-12-20 | Finished |  |  | 2019-12-22 | Finished |  |  | 2019-12-30 | Finished |  |  | 100 | 2021-05-13 | 2020-03-23 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-03-23 | Finished |  |  | 100 | 2020-01-16 | Finished | CUSTOMER DECORATION DELAY |  | 2020-01-21 | Finished |  |  | 2019-06-10 | Finished | [18 empty] | 2019-11-18 | Finished |  |  | 2019-11-18 | Finished |  |  | 2019-11-20 | Finished |  |  | 2020-01-21 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass | 2020-04-24 | Finished |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007339 | 2019-11-20 |  |  |  | HDME000718 | 2019-11-18 | QC Passed
TAJ0532-TH | HET | 61000522 | HO | ยังอยู่ในสัญญา HO | - | TH209006 | Home 4 Fl (K.YI) | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-04-04 | 2020-02-04 | 2020-04-04 | 2022-01-30 | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1100000 | Bangkok | แขวงบางซื่อ | 2022-01-20 | [36 empty] | 2020-01-28 | 2020-02-21 | 2020-02-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2022-01-20 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-04-01 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-08-09 | Finished | [18 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-24 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20007344 | 2020-01-28 |  |  |  | HDME000801 | 2020-02-21
TFA1289-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | 1200TX-EN,R5.75M,D30 | TX-EN |  |  |  |  | 5750 | 1050000 | Songkhla | ตำบลพะวง | 2020-04-15 | [20 empty] | 2020-06-20 | Finished | [14 empty] | 2019-10-31 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | [41 empty] | 2020-05-26 | Finished |  |  | 2020-05-26 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-11 | Finished |  |  | 100 | 2020-11-11 | 1900-01-01 | 2020-11-11 | Waiting | POWER SUPPLY DELAY |  | 2021-10-17 | [12 empty] | 0 | 2020-11-30 | 2000-01-01 | 2020-11-30 | Finished | [14 empty] | 25 | 2021-12-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-13 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-15 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Red |  |  | 20007570 | 2019-10-31 |  |  |  | HDME000712 | 2019-11-13
TFA1290-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | 1200TX-EN,R5.75M,D30 | TX-EN |  |  |  |  | 5750 | 1050000 | Songkhla | ตำบลพะวง | 2020-04-15 | [20 empty] | 2020-06-20 | Finished | [14 empty] | 2019-10-31 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | [41 empty] | 2020-05-26 | Finished |  |  | 2020-05-26 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-11 | Finished |  |  | 100 | 2020-11-11 | 1900-01-01 | 2020-11-11 | Waiting | POWER SUPPLY DELAY |  | 2021-10-17 | [12 empty] | 0 | 2020-11-30 | 2000-01-01 | 2020-11-30 | Finished | [14 empty] | 25 | 2021-12-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-13 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-15 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Red |  |  | 20007570 | 2019-10-31 |  |  |  | HDME000712 | 2019-11-13
TAJ0534-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | PL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1050000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-08-03 | Finished | [34 empty] | 2019-11-08 | 2019-11-18 | 2019-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2020-08-25 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-24 | Finished |  |  | 100 | [41 empty] | 2020-12-24 | 2021-07-10 | 2021-07-10 | Finished |  |  | 2021-07-10 | 2021-07-15 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-11-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-18 | Finished |  |  | 2019-11-18 | Finished |  |  | 2019-11-20 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 16 | 16 | 97.21 | Red |  |  | 20007568 | 2019-11-08 |  |  |  | HDME000717 | 2019-11-18
TAJ0535-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | PL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1050000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-08-03 | Finished | [34 empty] | 2019-11-08 | 2019-11-18 | 2019-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2020-05-25 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-04-15 | Finished |  |  | 2021-04-25 | Finished |  |  | 2021-04-16 | Finished |  |  | 2021-04-16 | Finished |  |  | 100 | [41 empty] | 2021-04-16 | 2021-07-10 | 2021-07-10 | Finished |  |  | 2021-07-10 | 2021-07-15 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-11-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-18 | Finished |  |  | 2019-11-18 | Finished |  |  | 2019-11-20 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 16 | 16 | 97.21 | Red |  |  | 20007568 | 2019-11-08 |  |  |  | HDME000717 | 2019-11-18
TAJ0536-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | PL3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1050000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-07-15 | Finished | [34 empty] | 2019-11-08 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2020-07-30 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-28 | Finished |  |  | 100 | [41 empty] | 2020-12-28 | 2021-07-10 | 2021-07-10 | Finished |  |  | 2021-07-10 | 2021-07-15 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-11-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-13 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-15 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 16 | 16 | 97.21 | Red |  |  | 20007568 | 2019-11-08 |  |  |  | HDME000712 | 2019-11-13
TAJ0537-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | PL4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1050000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-07-15 | Finished | [34 empty] | 2019-11-08 | 2019-11-14 | 2019-11-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2020-07-30 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-09 | Finished |  |  | 100 | [41 empty] | 2021-03-09 | 2021-07-10 | 2021-07-10 | Finished |  |  | 2021-07-10 | 2021-07-15 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-11-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-13 | Finished |  |  | 2019-11-14 | Finished |  |  | 2019-11-15 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 16 | 16 | 97.21 | Red |  |  | 20007568 | 2019-11-08 |  |  |  | HDME000712 | 2019-11-13
TAJ0538-TH | HET | 61000524 | Test | ยังอยู่ในสัญญา HO | - | TH199185 | Laguna Grand Hotel | PL5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | P-1000-CO60W2,60S/6F | UAG-SN1 | 1000 | 60 | 6 | 6 |  | 1100000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-08-03 | Finished | [34 empty] | 2019-11-08 | 2019-11-28 | 2019-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2020-09-28 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-11 | Finished |  |  | 2020-10-25 | Finished |  |  | 100 | [41 empty] | 2020-10-25 | 2021-06-28 | 2021-06-28 | Finished |  |  | 2020-06-16 | 2021-06-28 | Finished |  |  | 2021-07-10 | Finished |  |  | 2021-07-10 | Finished |  |  | 100 | 2021-02-08 | 2021-09-13 | 2021-02-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-09-13 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-27 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-11-29 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20007568 | 2019-11-08 |  |  |  | HDME000731 | 2019-11-27 | QC Passed
TAJ0539-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | PL6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | P-1000-CO60W2,60S/6F | UAG-SN1 | 1000 | 60 | 6 | 6 |  | 1100000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-07-15 | Finished | [34 empty] | 2019-11-08 | 2019-11-28 | 2019-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2020-07-20 | Finished |  |  | 2020-07-28 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-26 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-08 | Finished |  |  | 2020-08-10 | Finished |  |  | 100 | [41 empty] | 2020-08-10 | 2021-07-10 | 2021-07-10 | Finished |  |  | 2021-10-17 | 2021-07-15 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-12-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-27 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-11-29 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 16 | 16 | 97.21 | Red |  |  | 20007568 | 2019-11-08 |  |  |  | HDME000731 | 2019-11-27
TAJ0540-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | PL7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1100000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-08-03 | Finished | [34 empty] | 2019-11-08 | 2019-11-28 | 2019-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2020-07-18 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-09 | Finished |  |  | 2021-01-09 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-23 | Finished |  |  | 100 | [41 empty] | 2021-01-23 | 2021-07-13 | 2021-07-13 | Finished |  |  | 2020-06-16 | 2021-07-16 | Finished |  |  | 2021-07-18 | Finished |  |  | 2021-07-24 | Finished |  |  | 100 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-09-13 | Finished | [6 empty] | 90 | 2021-12-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-27 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-11-29 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 1 | 1 | 99.83 | Red |  |  | 20007568 | 2019-11-08 |  |  |  | HDME000731 | 2019-11-27
TBL0203-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | SL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1450000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-08-03 | Finished | [34 empty] | 2019-11-15 | 2019-11-18 | 2019-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2019-10-19 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-07-20 | Finished |  |  | 100 | [41 empty] | 2020-07-20 | 2021-08-14 | 2021-08-14 | Finished |  |  | 2021-10-17 | 2021-08-16 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2020-09-08 | 2000-01-01 | 2020-09-08 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-11-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-18 | Finished |  |  | 2019-11-18 | Finished |  |  | 2019-11-20 | Finished | [17 empty] | in process (defect) |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 16 | 16 | 96.8 | Red |  |  | 20007568 | 2019-11-15 |  |  |  | HDME000717 | 2019-11-18
TBL0204-TH | HET | 61000524 | Test | เลยสัญญา HO | - | TH199185 | Laguna Grand Hotel | SL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2019-05-15 | 2019-11-15 | 2020-02-15 | 2021-09-15 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1450000 | Songkhla | ตำบลพะวง | 2020-04-15 | 2020-08-03 | Finished | [34 empty] | 2019-11-15 | 2019-11-18 | 2019-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-15 | 2020-06-15 | 2019-10-19 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-14 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | [41 empty] | 2020-07-15 | 2021-08-17 | 2021-08-17 | Finished |  |  | 2021-10-17 | 2021-08-20 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2020-09-08 | 2000-01-01 | 2020-09-08 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-11-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-15 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2019-11-18 | Finished |  |  | 2019-11-18 | Finished |  |  | 2019-11-20 | Finished | [17 empty] | in process (defect) |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 16 | 16 | 96.8 | Red |  |  | 20007568 | 2019-11-15 |  |  |  | HDME000717 | 2019-11-18
TAJ0548-TH | HET | 61000529 | HO | ส่งมอบแล้ว | - | TH199191 | La Citta Delre Thonglor 16 | A-E01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-11-04 | 2020-02-04 | 2020-05-04 | 2020-09-04 | P-1000-CO60W2,60S/9F | UAG-SN1 | 1000 | 60 | 9 | 9 |  | 1444500 | Bangkok | แขวงคลองตันเหนือ เขตวัฒนา | 2020-03-19 | 2020-03-19 | Finished | [34 empty] | 2020-02-04 | 2020-02-13 | 2020-02-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-04 | 2020-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | [41 empty] | 2020-06-21 | 2020-08-02 | 2020-08-02 | Finished |  |  | 2020-08-02 | 2020-08-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-01-29 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2020-09-01 | Finished | INSTALLATION DELAY |  | 2020-09-11 | Finished |  |  | 2019-11-28 | Finished | [18 empty] | 2020-02-04 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass | 2021-05-05 | Finished |  |  | 585 | 84 | 24 | 16 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009776 | 2020-02-04 |  |  |  | HDME000783 | 2020-02-04 | QC Passed
TBL0206-TH | HET | 61000529 | HO | ส่งมอบแล้ว | - | TH199191 | La Citta Delre Thonglor 16 | A-E02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-11-04 | 2020-02-04 | 2020-05-04 | 2020-09-04 | OUG-1000-CO60,60S/9F | OUG-ON1 | 1000 | 60 | 9 | 9 |  | 1498000 | Bangkok | แขวงคลองตันเหนือ เขตวัฒนา | 2020-03-19 | [36 empty] | 2020-02-04 | 2020-02-15 | 2020-02-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-04 | 2020-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | [41 empty] | 2020-06-21 | 2020-08-02 | 2020-08-02 | Finished |  |  | 2020-08-02 | 2020-08-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-11-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 100 | 2020-09-01 | Finished | INSTALLATION DELAY |  | 2020-09-11 | Finished |  |  | 2019-11-28 | Finished | [18 empty] | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass | 2021-05-05 | Finished |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009776 | 2020-02-04 |  |  |  | HDME000809 | 2020-02-28 | QC Passed
TAJ0549-TH | HET | 61000529 | HO | ส่งมอบแล้ว | - | TH199191 | La Citta Delre Thonglor 16 | A-E03 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-11-04 | 2020-02-04 | 2020-05-04 | 2020-09-04 | P-1000-CO60W2,60S/9F | UAG-SN1 | 1000 | 60 | 9 | 9 |  | 1444500 | Bangkok | แขวงคลองตันเหนือ เขตวัฒนา | 2020-03-19 | [36 empty] | 2020-02-04 | 2020-02-15 | 2020-02-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-04 | 2020-06-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | [41 empty] | 2020-06-21 | 2020-08-02 | 2020-08-02 | Finished |  |  | 2020-08-02 | 2020-08-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-06-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-02 | Finished |  |  | 100 | 2020-09-01 | Finished | INSTALLATION DELAY |  | 2020-09-11 | Finished |  |  | 2019-11-28 | Finished | [18 empty] | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 585 | 84 | 24 | 16 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009776 | 2020-02-04 |  |  |  | HDME000809 | 2020-02-28 | QC Passed
TAJ0550-TH | HET | 61000529 | HO | ส่งมอบแล้ว | - | TH199191 | La Citta Delre Thonglor 16 | B-E01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-11-04 | 2020-02-04 | 2020-05-04 | 2020-09-04 | P-1000-CO60W2,60S/12F | UAG-SN1 | 1000 | 60 | 12 | 12 |  | 1551500 | Bangkok | แขวงคลองตันเหนือ เขตวัฒนา | 2020-03-19 | [36 empty] | 2020-02-04 | 2020-02-13 | 2020-02-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-04 | 2020-07-01 | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | [41 empty] | 2020-06-21 | 2020-08-02 | 2020-08-02 | Finished |  |  | 2020-08-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-01 | Finished | INSTALLATION DELAY |  | 2020-10-30 | Finished |  |  | 2019-11-28 | Finished | [18 empty] | 2020-02-04 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 718 | 94 | 32 | 20 | 864 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009776 | 2020-02-04 |  |  |  | HDME000783 | 2020-02-04 | QC Passed
TAJ0551-TH | HET | 61000529 | HO | ส่งมอบแล้ว | - | TH199191 | La Citta Delre Thonglor 16 | B-E02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-11-04 | 2020-02-04 | 2020-05-04 | 2020-09-04 | P-1000-CO60W2,60S/12F | UAG-SN1 | 1000 | 60 | 12 | 12 |  | 1551500 | Bangkok | แขวงคลองตันเหนือ เขตวัฒนา | 2020-03-19 | [36 empty] | 2020-02-04 | 2020-02-13 | 2020-02-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-04 | 2020-07-01 | 1900-01-01 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | [41 empty] | 2020-06-21 | 2020-08-02 | 2020-08-02 | Finished |  |  | 2020-08-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-20 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2020-11-01 | Finished | INSTALLATION DELAY |  | 2021-02-15 | Finished |  |  | 2019-11-28 | Finished | [18 empty] | 2020-02-04 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-14 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 718 | 94 | 32 | 20 | 864 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009776 | 2020-02-04 |  |  |  | HDME000783 | 2020-02-04 | QC Passed
TAC1588-TH | HET | 61000534 | HO | ส่งมอบแล้ว | - | TH209009 | Lerdsin Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-02-04 | 2020-10-01 | 2020-12-25 | 2021-08-27 | VFI-1000-CO150,150S/27F | VFI-II | 1000 | 150 | 27 | 27 |  | 2963900 | Bangkok | เขตบางรัก | 2020-09-25 | 2020-09-01 | Finished | [34 empty] | 2020-10-01 | 2020-08-15 | 2020-08-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-02 | 2020-11-16 | 2020-09-04 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 100 | [41 empty] | 2020-10-20 | 2021-04-28 | 2021-04-28 | Finished |  |  | 2020-11-17 | 2021-04-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-12 | 2021-08-18 | 2021-02-12 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-08-18 | Finished | [6 empty] | 90 | 2021-08-20 | Finished | POWER SUPPLY DELAY |  | 2021-08-22 | Finished |  |  | 2020-04-20 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-08-15 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-26 | Finished |  |  | 2021-08-22 | Finished | [13 empty] | pass |  |  |  |  | 1743 | 119 | 56 | 24 | 1942 | 0 | 0 | 0 | 2 | 2 | 99.9 | Blue |  |  | 20011676 | 2020-08-14 |  |  |  | HDME000958 | 2020-08-15 | QC Passed
TAC1589-TH | HET | 61000534 | HO | ส่งมอบแล้ว | - | TH209009 | Lerdsin Hospital | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-02-04 | 2020-10-01 | 2020-12-25 | 2021-08-27 | VFI-1000-CO150,150S/27F | VFI-II | 1000 | 150 | 27 | 27 |  | 2963900 | Bangkok | เขตบางรัก | 2020-09-25 | 2020-09-01 | Finished | [34 empty] | 2020-10-01 | 2020-08-15 | 2020-08-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-02 | 2020-11-16 | 2020-09-04 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 100 | [41 empty] | 2020-10-20 | 2021-04-28 | 2021-04-28 | Finished |  |  | 2020-11-17 | 2021-04-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-12 | 2021-08-18 | 2021-02-12 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-08-18 | Finished | [6 empty] | 90 | 2021-08-20 | Finished | POWER SUPPLY DELAY |  | 2021-08-22 | Finished |  |  | 2020-04-20 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-08-15 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-26 | Finished |  |  | 2021-08-22 | Finished | [13 empty] | pass |  |  |  |  | 1743 | 119 | 56 | 24 | 1942 | 0 | 0 | 0 | 2 | 2 | 99.9 | Blue |  |  | 20011676 | 2020-08-14 |  |  |  | HDME000958 | 2020-08-15 | QC Passed
TAC1590-TH | HET | 61000534 | Install | ยังอยู่ในสัญญา HO | - | TH209009 | Lerdsin Hospital | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-02-04 | 2020-10-01 | 2020-12-25 | 2021-11-27 | VFI-1000-CO150,150S/28F | VFI-II | 1000 | 150 | 28 | 28 |  | 2953200 | Bangkok | เขตบางรัก | 2020-09-25 | 2020-09-01 | Finished | [34 empty] | 2020-10-01 | 2020-08-15 | 2020-08-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-02 | 2020-11-16 | 2020-09-04 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 100 | [41 empty] | 2020-10-20 | 2020-11-17 | 2020-11-17 | Finished |  |  | 2020-11-17 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-12 | 2000-01-01 | 2021-02-12 | Finished | [14 empty] | 25 | 2021-10-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-04-20 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-08-15 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-26 | Finished | [22 empty] | 1798 | 120 | 56 | 24 | 1998 | 0 | 0 | 14 | 24 | 38 | 98.1 | Green |  |  | 20011676 | 2020-08-14 |  |  |  | HDME000958 | 2020-08-15
TAC1592-TH | HET | 61000537 | HO | ส่งมอบแล้ว | - | TH199194 | Suan Mali Center | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2019-05-21 | 2019-09-21 | 2019-11-21 |  | VFI-600-CO60,60S/8F | VFI-II | 600 | 60 | 8 | 8 |  | 1284000 | Bangkok | เขตป้อมปราบศัตรูพ่าย | 2020-09-30 | 2020-09-30 | Finished | [34 empty] | 2019-09-14 | 2019-09-27 | 2019-09-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-12-10 | 2020-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 2020-10-11 | 2020-10-11 | 2020-10-11 | Finished |  |  | 2020-10-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-02-19 | 2000-01-01 | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 100 | 2020-11-21 | Finished | CONSTRUCTION DELAY |  | 2020-02-21 | Finished |  |  | 2020-03-17 | Finished | [18 empty] | 2019-09-28 | Finished |  |  | 2019-10-01 | Finished |  |  | 2019-10-03 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Working |  | pass (defect) |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007505 | 2019-09-14 |  |  |  | HDME000665 | 2019-09-28
TAJ0558-TH | HET | 61000538 | HO | ส่งมอบแล้ว | - | TH199196 | Apartment 7 Floors Ladkrabang | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-08-19 | 2020-04-17 | 2020-06-19 | 2021-08-30 | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1070000 | Bangkok | แขวงลาดกระบัง | 2020-04-17 | 2020-06-26 | Finished | [34 empty] | 2020-04-17 | 2020-04-27 | 2020-04-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-26 | 2021-04-18 | 2020-06-28 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 100 | [41 empty] | 2021-03-17 | 2021-08-09 | 2021-08-09 | Finished |  |  | 2021-08-09 | 2021-08-10 | Finished |  |  | 2021-08-13 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-08-20 | 2000-01-01 | 2021-08-20 | Finished |  |  | 2021-09-07 | Finished | [10 empty] | 50 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-26 | Finished |  |  | 2019-11-10 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-04-27 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-27 | Finished |  |  | 2021-08-26 | Finished | [18 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 16 | 16 | 97.42 | Blue |  |  | 20009550 | 2020-04-17 |  |  |  | HDME000862 | 2020-04-27
TAC1600-TH | HET | 61000550 | HO | ส่งมอบแล้ว | - | TH199204 | Lee Mart Super Wholesaler | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2019-06-07 | 2019-11-07 | 2020-01-07 | 2020-11-01 | VFI-750-CO60,60S/3F | VFI-II | 750 | 60 | 3 | 3 |  | 1070000 | Trang | อำเภอเมืองตรัง | 2019-11-01 | 2019-11-01 | Finished | [34 empty] | 2019-10-23 | 2019-11-08 | 2019-11-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-27 | 2020-02-16 | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-16 | Finished |  |  | 100 | [41 empty] | 2020-02-16 | 2020-10-11 | 2020-10-11 | Finished |  |  | 2020-10-20 | 2020-10-11 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2020-07-01 | 2021-01-21 | 2020-07-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-16 | Finished |  |  | 2021-01-21 | Finished |  |  | 100 | 2020-11-19 | Finished | CONSTRUCTION DELAY |  | 2020-11-18 | Finished |  |  | 2019-06-21 | Finished | [10 empty] | 2021-01-15 | Finished | [6 empty] | 2019-11-08 | Finished |  |  | 2019-11-27 | Finished |  |  | 2019-11-28 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 417 | 89 | 16 | 16 | 538 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007678 | 2019-10-23 | [5 empty] | QC Passed
TFA1294-TH | HET | 61000552 | HO | ส่งมอบแล้ว | - | TH199205 | J.C. NAWAMIN 70 | ESC-1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-06-13 | 2019-10-15 | 2019-12-15 | 2020-07-20 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตบึงกุ่ม | 2019-12-20 | [20 empty] | 2019-12-26 | Finished | [14 empty] | 2019-09-30 | 2019-09-27 | 2019-09-27 | Finished | [14 empty] | 2019-12-25 | 2020-01-21 | [41 empty] | 2019-12-26 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-08 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-13 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-21 | Finished |  |  | 100 | 2020-01-21 | 2020-02-18 | 2020-02-18 | Finished |  |  | 2020-02-17 | 2020-02-18 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-22 | Finished |  |  | 100 | 2020-06-12 | 2020-06-26 | 2020-06-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-26 | Finished |  |  | 100 | 2020-07-29 | Finished | CONSTRUCTION DELAY |  | 2020-07-30 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-09-30 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass | 2020-08-25 | Finished |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007846 | 2019-09-30 |  |  |  | HDME000662 | 2019-09-26 | QC Passed
TFA1295-TH | HET | 61000552 | HO | ส่งมอบแล้ว | - | TH199205 | J.C. NAWAMIN 70 | ESC-2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-06-13 | 2019-10-15 | 2019-12-15 | 2020-07-20 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1123500 | Bangkok | เขตบึงกุ่ม | 2019-12-20 | [20 empty] | 2019-12-26 | Finished | [14 empty] | 2019-09-30 | 2019-09-27 | 2019-09-27 | Finished | [14 empty] | 2019-12-25 | 2020-01-21 | [41 empty] | 2019-12-26 | Finished |  |  | 2019-12-29 | Finished |  |  | 2020-01-08 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-13 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-21 | Finished |  |  | 100 | 2020-01-21 | 2020-02-18 | 2020-02-18 | Finished |  |  | 2020-02-17 | 2020-02-18 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-22 | Finished |  |  | 100 | 2021-05-13 | 2020-08-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-17 | Finished |  |  | 100 | 2020-07-29 | Finished | CONSTRUCTION DELAY |  | 2020-07-30 | Finished |  |  | 2019-07-12 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2019-09-26 | Finished |  |  | 2019-09-27 | Finished |  |  | 2019-09-30 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass | 2020-08-25 | Finished |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007846 | 2019-09-30 |  |  |  | HDME000662 | 2019-09-26 | QC Passed
TAJ0570-TH | HET | 61000553 | HO | ส่งมอบแล้ว | - | TH199210 | Factory MNG | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-06-28 | 2019-11-28 | 2020-01-28 | 2021-08-30 | P-750-CO60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1070000 | Samut Prakan | ตำบลบางโฉลง | 2020-02-29 | 2020-04-10 | Finished | [34 empty] | 2019-11-21 | 2020-02-11 | 2019-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-13 | 2020-04-30 | 2020-04-13 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-30 | Finished |  |  | 100 | [41 empty] | 2020-04-30 | 2021-07-27 | 2021-07-27 | Finished |  |  | 2021-08-20 | 2021-07-29 | Finished |  |  | 2021-08-04 | Finished |  |  | 2021-08-06 | Finished |  |  | 100 | 2021-06-29 | 2021-08-12 | 2021-06-29 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 90 | 2021-08-18 | Finished | CONSTRUCTION DELAY |  | 2021-08-22 | Finished |  |  | 2019-07-15 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2019-12-10 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-13 | Finished |  |  | 2021-08-22 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 1 | 1 | 99.74 | Blue |  |  | 20007943 | 2019-11-21 |  |  |  | HDME000743 | 2019-12-04 | QC Passed
TAK0571-TH | HET | 61000554 | HO | ส่งมอบแล้ว | - | TH199212 | Navamin 9 Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2019-06-25 | 2019-12-25 | 2020-02-25 |  | B-1000-2S60,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1605000 | Bangkok | เขตมีนบุรี | 2019-12-06 | 2019-12-28 | Finished | [34 empty] | 2019-12-18 | 2019-12-04 | 2019-12-04 | Finished | [14 empty] | 2019-12-26 | 2020-01-29 | 2019-12-28 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-01-08 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-26 | Finished |  |  | 2020-01-29 | Finished |  |  | 100 | [41 empty] | 2020-01-29 | 2020-02-06 | 2020-02-06 | Finished |  |  | 2020-02-06 | 2020-02-06 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-10 | Finished |  |  | 100 | 2021-05-13 | 2020-11-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-11-19 | Finished |  |  | 100 | 2020-02-17 | Finished | POWER SUPPLY DELAY |  | 2020-02-27 | Finished |  |  | 2019-07-15 | Finished | [18 empty] | 2019-12-04 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-06 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  | pass | 2020-04-22 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20007960 | 2019-12-18 |  |  |  | HDME000744 | 2019-12-04 | QC Passed
TAJ0573-TH | HET | 61000556 | HO | ยังอยู่ในสัญญา HO | - | TH199215 | Pearl Resort And Hotel (Phase 2) | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-07-08 | 2019-11-08 | 2020-01-08 | 2021-08-20 | P-1000-CO60D,60S/6F | UAG-SN1 | 1000 | 60 | 6 | 6 |  | 1123500 | Nonthaburi | อำเภอปากเกร็ด | 2019-11-10 | 2020-02-26 | Finished | [34 empty] | 2019-11-01 | 2020-02-12 | 2020-02-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-26 | 2020-03-24 | 2020-02-27 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-24 | Finished |  |  | 100 | [41 empty] | 2020-03-24 | 2020-12-23 | 2020-12-23 | Finished |  |  | 2020-09-20 | 2020-12-24 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 100 | 2020-05-15 | 2021-01-29 | 2020-05-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2021-10-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-07-26 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-02-13 | Finished | [17 empty] | pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008055 | 2019-11-01 |  |  |  | HDME000786 | 2020-02-11 | QC Passed
TAJ0576-TH | HET | 61000559 | HO | ส่งมอบแล้ว | - | TH199218 | Harrow School New Teacher Apartment | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Somsak Sutthosri | 2019-07-20 | 2019-11-20 | 2020-01-20 |  | P-1600-CO60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1556850 | Bangkok | แขวงสีกัน เขตดอนเมือง | 2019-11-01 | 2019-11-01 | Finished | [34 empty] | 2019-11-13 | 2019-11-25 | 2019-11-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2019-11-20 | 2020-01-09 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 2019-12-20 | 2019-12-20 | 2019-12-20 | Finished |  |  | 2019-12-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-01-20 | Finished | DELIVERY DELAY |  | 2020-02-06 | Finished |  |  | 2020-02-24 | Finished | [18 empty] | 2019-11-25 | Finished |  |  | 2019-11-29 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-02-06 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-24 | Working |  | pass (defect) |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20008079 | 2019-11-13 |  |  |  | HDME000727 | 2019-11-25
TAD0412-TH | HET | 61000560 | HO | ส่งมอบแล้ว | - | TH199213 | Quarantine Center | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-07-04 | 2019-10-04 | 2020-01-04 |  | B-1000-2S60,60S/6F | B-II(VFI-II) | 1000 | 60 | 6 | 6 |  | 1284000 | Nonthaburi | ถนนติวานนท์ ตำบลตลาดขวัญ | 2020-02-20 | 2020-02-20 | Finished | [34 empty] | 2019-10-04 | 2019-10-21 | 2019-10-21 | Finished | PAYMENT DELAY | [13 empty] | 2019-09-30 | 2019-12-14 | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-22 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-08 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-22 | Finished |  |  | 100 | [41 empty] | 2019-12-22 | 2019-12-26 | 2019-12-26 | Finished |  |  | 2019-12-18 | 2020-01-10 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-12 | Finished |  |  | 100 | 2020-02-21 | 2000-01-01 | 2020-02-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-24 | Finished |  |  | 2021-09-09 | Finished |  |  | 100 | 2020-01-15 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-02-28 | Finished |  |  | 2019-08-27 | Finished | [18 empty] | 2019-10-18 | Finished |  |  | 2019-10-21 | Finished |  |  | 2019-10-24 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-16 | Working |  |  | 2020-06-16 | Working |  | pass (defect) |  |  |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008066 | 2019-10-29 |  |  |  | HDME000684 | 2019-10-16
TAD0413-TH | HET | 61000560 | HO | ส่งมอบแล้ว | - | TH199213 | Quarantine Center | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-07-04 | 2019-10-04 | 2020-01-04 |  | B-1000-2S90,90S/7F | B-II(VFI-II) | 1000 | 90 | 7 | 7 |  | 1433800 | Nonthaburi | ถนนติวานนท์ ตำบลตลาดขวัญ | 2020-02-20 | 2020-02-20 | Finished | [34 empty] | 2019-10-04 | 2019-10-21 | 2019-10-21 | Finished | PAYMENT DELAY | [13 empty] | 2019-09-30 | 2019-12-14 | 2019-10-30 | Finished |  |  | 2019-11-05 | Finished |  |  | 2019-11-10 | Finished |  |  | 2019-11-16 | Finished |  |  | 2019-11-22 | Finished |  |  | 2019-11-28 | Finished |  |  | 2019-12-04 | Finished |  |  | 2019-12-08 | Finished |  |  | 2019-12-14 | Finished |  |  | 2019-12-22 | Finished |  |  | 100 | [41 empty] | 2019-12-22 | 2019-12-26 | 2019-12-26 | Finished |  |  | 2019-12-18 | 2020-01-10 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-12 | Finished |  |  | 100 | 2020-02-21 | 2000-01-01 | 2020-02-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-02-24 | Finished |  |  | 2021-09-09 | Finished |  |  | 100 | 2020-01-15 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-02-28 | Finished |  |  | 2019-08-27 | Finished | [18 empty] | 2019-10-18 | Finished |  |  | 2019-10-21 | Finished |  |  | 2019-10-24 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-16 | Working |  |  | 2020-06-16 | Working |  | pass (defect) |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008066 | 2019-10-29 |  |  |  | HDME000684 | 2019-10-16
TBJ0017-TH | HET | 61000563 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | EL-HE-5 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2019-07-15 | 2020-02-01 | 2020-04-01 | 2021-04-23 | F-3000-3S45,45S/6F | F(H)-EL | 3000 | 45 | 5 | 6 |  | 7329500 | Samut Prakan | อำเภอบางพลี | 2020-02-02 | 2020-02-03 | Finished | [34 empty] | 2020-01-17 | 2020-01-27 | 2020-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-07 | 2020-06-15 | 2020-04-08 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-06-02 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-12 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-13 | Finished |  |  | 100 | [41 empty] | 2020-06-13 | 2020-06-28 | 2020-06-28 | Finished |  |  | 2020-06-20 | 2020-06-30 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-12 | Finished |  |  | 2021-07-05 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-28 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 719 | 111 | 72 | 20 | 922 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008093 | 2020-01-17 |  |  |  | HDME000804 | 2020-02-21
TBJ0015-TH | HET | 61000563 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | EL-HW-3 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2019-07-15 | 2020-02-01 | 2020-04-01 | 2021-04-23 | F-3000-3S60,60S/3F | F(H)-EL | 3000 | 60 | 2 | 3 |  | 2996000 | Samut Prakan | อำเภอบางพลี | 2020-02-02 | 2020-02-03 | Finished | [34 empty] | 2020-01-17 | 2020-01-27 | 2020-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-24 | 2020-03-28 | 2020-02-27 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-15 | Finished |  |  | 100 | [41 empty] | 2020-03-15 | 2020-06-28 | 2020-06-28 | Finished |  |  | 2020-05-28 | 2020-06-30 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-08-20 | Finished |  |  | 100 | 2021-05-13 | 2021-07-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-28 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass |  |  |  |  | 515 | 94 | 36 | 20 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008093 | 2020-01-17 |  |  |  | HDME000804 | 2020-02-21 | QC Passed
TBJ0016-TH | HET | 61000563 | HO | ส่งมอบแล้ว | - | TH199037 | Suvarnabhumi Airport Expansion Project (Fiscal Year 201 | EL-HW-6 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Phumiphat Siprajan | 2019-07-15 | 2020-02-01 | 2020-04-01 | 2021-04-23 | F-3000-3S45,45S/6F | F(H)-EL | 3000 | 45 | 5 | 6 |  | 7329500 | Samut Prakan | อำเภอบางพลี | 2020-02-02 | 2020-02-03 | Finished | [34 empty] | 2020-01-17 | 2020-01-27 | 2020-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-07 | 2020-06-15 | 2020-04-08 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-12 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | [41 empty] | 2020-05-29 | 2020-07-30 | 2020-07-30 | Finished |  |  | 2020-07-15 | 2020-08-01 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-20 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2019-01-12 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-28 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Working |  |  | 2021-06-09 | Working |  | no pass |  |  |  |  | 719 | 111 | 72 | 20 | 922 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008093 | 2020-01-17 |  |  |  | HDME000804 | 2020-02-21
TBL0208-TH | HET | 61000565 | Test | เลยสัญญา HO | - | TH199211 | Auditorium Mekong River Nakhon Phanom | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2019-07-05 | 2019-11-05 | 2020-01-05 | 2021-09-05 | OUG-1600-CO60,60S/4F | OUG-ON1 | 1600 | 60 | 4 | 4 |  | 1480000.46 | Nakhon Phanom | อำเภอเมือง | 2019-11-30 | 2019-11-30 | Finished | [34 empty] | 2019-10-28 | 2019-11-21 | 2019-11-21 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-01 | 2020-01-31 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2020-12-28 | 2000-01-01 | 2020-12-28 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-27 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2019-11-21 | Finished |  |  | 2019-11-21 | Finished |  |  | 2019-11-23 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 0 | 85 | 4 | 16 | 105 | 81.05 | Red |  |  | 20008146 | 2019-12-04 |  |  |  | HDME000723 | 2019-11-21
TAC1605-TH | HET | 61000570 | HO | ยังอยู่ในสัญญา HO | - | TH209011 | Metris Pattanakarn 12 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2019-06-01 | 2020-03-01 | 2020-12-31 | 2021-09-30 | VFI-1000-CO150,150S/29F | VFI-II | 1000 | 150 | 29 | 29 |  | 2750000 | Bangkok | แขวงสวนหลวง | 2020-02-23 | 2020-03-01 | Finished | [34 empty] | 2020-02-23 | 2020-02-25 | 2020-02-25 | Finished | STORE AREA | [13 empty] | 2020-02-24 | 2020-05-23 | 2020-03-05 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | [41 empty] | 2020-06-04 | 2020-06-05 | 2020-06-05 | Finished |  |  | 2020-06-01 | 2020-06-08 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-08 | Finished |  |  | 100 | 2020-12-25 | 2000-01-01 | 2020-12-25 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-08-11 | Finished | [6 empty] | 90 | 2021-08-30 | Working | OTHERS | [5 empty] | 2019-09-28 | Finished | [10 empty] | 2021-09-30 | Finished | [6 empty] | 2020-02-26 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-10 | Finished | [17 empty] | no pass |  |  |  |  | 1853 | 120 | 56 | 24 | 2053 | 0 | 0 | 0 | 2 | 2 | 99.9 | Green |  |  | 20008865 | 2020-02-21 |  |  |  | HDME000807 | 2020-02-26
TAC1606-TH | HET | 61000570 | HO | ยังอยู่ในสัญญา HO | - | TH209011 | Metris Pattanakarn 12 | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2019-06-01 | 2020-03-01 | 2020-12-31 | 2021-09-30 | VFI-1000-CO150,150S/29F | VFI-II | 1000 | 150 | 29 | 29 |  | 2750000 | Bangkok | แขวงสวนหลวง | 2020-02-23 | 2020-03-01 | Finished | [34 empty] | 2020-02-23 | 2020-02-25 | 2020-02-25 | Finished | STORE AREA | [13 empty] | 2020-02-24 | 2020-05-23 | 2020-03-05 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | [41 empty] | 2020-06-04 | 2020-06-05 | 2020-06-05 | Finished |  |  | 2020-06-01 | 2020-06-08 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-08-08 | Finished |  |  | 100 | 2021-04-30 | 2000-01-01 | 2021-04-30 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-08-11 | Finished | [6 empty] | 90 | 2021-08-30 | Working | OTHERS | [5 empty] | 2019-09-28 | Finished | [10 empty] | 2021-09-30 | Finished | [6 empty] | 2020-03-01 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-10 | Finished | [17 empty] | no pass |  |  |  |  | 1853 | 120 | 56 | 24 | 2053 | 0 | 0 | 0 | 2 | 2 | 99.9 | Green |  |  | 20008865 | 2020-02-21 |  |  |  | HDME000810 | 2020-03-01
TAC1607-TH | HET | 61000570 | HO | ยังอยู่ในสัญญา HO | - | TH209011 | Metris Pattanakarn 12 | SL/FL | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2019-06-01 | 2020-03-01 | 2020-12-31 | 2021-09-30 | VFI-1350-CO150,150S/29F | VFI-II | 1350 | 150 | 29 | 29 |  | 2750000 | Bangkok | แขวงสวนหลวง | 2020-02-23 | 2020-03-03 | Finished | [34 empty] | 2020-02-23 | 2020-02-25 | 2020-02-25 | Finished | STORE AREA | [13 empty] | 2020-02-24 | 2020-05-23 | 2020-03-07 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | [41 empty] | 2020-06-04 | 2020-06-05 | 2020-06-05 | Finished |  |  | 2020-06-01 | 2020-06-08 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-08-05 | Finished |  |  | 100 | 2021-04-30 | 2000-01-01 | 2021-04-30 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-08-11 | Finished | [6 empty] | 90 | 2021-08-30 | Working | OTHERS | [5 empty] | 2019-09-28 | Finished | [10 empty] | 2021-09-30 | Finished | [6 empty] | 2020-03-01 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-10 | Finished | [17 empty] | in process (defect) |  |  |  |  | 1853 | 120 | 56 | 24 | 2053 | 0 | 0 | 0 | 2 | 2 | 99.9 | Green |  |  | 20008865 | 2020-02-21 |  |  |  | HDME000810 | 2020-03-01
TAJ0582-TH | HET | 61000574 | HO | ส่งมอบแล้ว | - | TH199224 | ENVILAB | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | ANUSSARA POLDONGNOK | 2019-07-22 | 2019-12-22 | 2020-02-22 | 2020-03-09 | P-1000-CO60W1,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1123500 | Bangkok | เขตบางแค | 2019-12-18 | 2019-12-18 | Finished | [34 empty] | 2019-12-15 | 2019-12-18 | 2019-12-18 | Finished | [14 empty] | 2019-12-18 | 2020-02-07 | 2020-01-16 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-22 | Finished |  |  | 2020-01-16 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-02-06 | Finished |  |  | 2020-02-07 | Finished |  |  | 100 | [41 empty] | 2020-02-07 | 2020-02-29 | 2020-02-29 | Finished |  |  | 2020-02-24 | 2020-02-29 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-06 | Finished |  |  | 100 | 2020-03-09 | 2000-01-01 | 2020-03-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-09 | Finished |  |  | 100 | 2020-03-10 | Finished | POWER SUPPLY DELAY |  | 2020-03-18 | Finished |  |  | 2020-03-25 | Finished | [18 empty] | 2019-12-18 | Finished |  |  | 2019-12-18 | Finished |  |  | 2019-12-24 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-25 | Working |  | pass (defect) |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008228 | 2019-12-15
TAC1609-TH | HET | 61000576 | HO | ส่งมอบแล้ว | - | TH199229 | The Revenue Department Chonburi 2 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2019-07-26 | 2019-11-26 | 2020-01-26 | 2020-06-10 | VFI-750-CO60,60S/4F | VFI-II | 750 | 60 | 4 | 4 |  | 1070000 | Chon Buri | อำเภอศรีราชา | 2020-03-07 | 2020-03-07 | Finished | [34 empty] | 2019-11-19 | 2019-11-26 | 2019-11-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-14 | 2020-02-14 | 2020-01-20 | Finished |  |  | 2020-01-22 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-26 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-25 | Finished |  |  | 100 | [41 empty] | 2020-02-25 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 2020-04-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-27 | Finished |  |  | 100 | 2020-05-11 | 2021-06-14 | 2020-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-11 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2020-11-30 | Finished |  |  | 2019-08-23 | Finished | [18 empty] | 2019-11-26 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008297 | 2019-11-19 |  |  |  | HDME000728 | 2019-11-26 | QC Passed
TAC1610-TH | HET | 61000576 | HO | ส่งมอบแล้ว | - | TH199229 | The Revenue Department Chonburi 2 | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2019-07-26 | 2019-11-26 | 2020-01-26 | 2020-06-10 | VFI-750-CO60,60S/4F | VFI-II | 750 | 60 | 4 | 4 |  | 1070000 | Chon Buri | อำเภอศรีราชา | 2020-03-07 | 2020-03-07 | Finished | [34 empty] | 2019-11-19 | 2019-11-26 | 2019-11-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-14 | 2020-02-14 | 2020-01-20 | Finished |  |  | 2020-01-22 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-26 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-02-07 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-25 | Finished |  |  | 100 | [41 empty] | 2020-02-25 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 2020-04-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-04-27 | Finished |  |  | 100 | 2020-05-11 | 2021-06-14 | 2020-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-11 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2020-11-30 | Finished |  |  | 2019-08-23 | Finished | [18 empty] | 2019-11-26 | Finished |  |  | 2019-11-26 | Finished |  |  | 2019-11-29 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008297 | 2019-11-19 |  |  |  | HDME000728 | 2019-11-26 | QC Passed
TAJ0584-TH | HET | 61000579 | HO | ส่งมอบแล้ว | - | TH199232 | KALM Village | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-08-01 | 2019-12-01 | 2020-01-01 | 2020-11-20 | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1400000 | Chiang Mai | อำเภอเมืองเชียงใหม่ | 2019-10-04 | 2020-06-30 | Finished | [34 empty] | 2019-11-24 | 2019-12-01 | 2019-12-01 | Finished | PAYMENT DELAY | [13 empty] | 2019-12-05 | 2019-12-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-12-14 | 2020-12-14 | Finished |  |  | 2020-11-20 | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-20 | Finished |  |  | 100 | 2021-05-13 | 2020-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished | [6 empty] | 90 | 2020-12-23 | Finished | POWER SUPPLY DELAY |  | 2020-12-28 | Finished |  |  | 2019-08-26 | Finished | [10 empty] | 2021-01-15 | Finished | [6 empty] | 2019-12-01 | Finished |  |  | 2019-12-01 | Finished |  |  | 2019-12-03 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20008324 | 2019-11-24 |  |  |  | HDME000736 | 2019-12-01 | QC Passed
TEB0108-TH | HET | 61000580 | HO | ส่งมอบแล้ว | - | TH199233 | Home Khun Nalinrut Jiravanstit | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-07-31 | 2019-11-30 | 2019-12-31 | 2020-08-15 | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 4 | 4 |  | 1070000 | Bangkok | เขตราษฎร์บูรณะ | 2020-08-10 | 2020-08-11 | Finished | [34 empty] | 2019-11-15 | 2019-12-03 | 2019-12-03 | Finished | STORE AREA | [13 empty] | 2020-08-11 | 2020-08-30 | 2020-08-30 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-03 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-09-06 | Finished |  |  | 100 | [41 empty] | 2020-09-06 | 2021-01-04 | 2021-01-04 | Finished |  |  | 2020-09-01 | 2021-01-05 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-06 | Finished |  |  | 100 | 2021-01-19 | 2021-01-19 | 2021-01-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-19 | Finished | [6 empty] | 90 | 2021-01-15 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2019-08-15 | Finished | [18 empty] | 2019-12-02 | Finished |  |  | 2019-12-06 | Finished |  |  | 2019-12-10 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20008303 | 2019-11-15 |  |  |  | HDME000737 | 2019-12-02 | QC Passed
TAD0420-TH | HET | 61000581 | Test | ยังอยู่ในสัญญา HO | - | TH209012 | Community Health Center, Maharaj Hospital Nakorn Si Tha | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 242024 | 2020-01-20 | 2020-03-20 | 2021-10-28 | B-1000-2S60,60S/4F | B-II(VFI-II) | 1000 | 60 | 4 | 4 |  | 1551500 | Nakhon Si Thammarat | ตำบลปากนคร | 2019-08-23 | 2019-08-23 | Finished | [34 empty] | 2020-01-13 | 2020-01-30 | 2020-01-30 | Finished | OTHERS | [13 empty] | 2020-01-20 | 2020-03-25 | 2020-01-24 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-16 | Finished |  |  | 2020-02-16 | Finished |  |  | 2020-02-24 | Finished |  |  | 100 | [41 empty] | 2020-02-24 | 1900-01-01 | 2020-02-24 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2020-06-01 | 2000-01-01 | 2020-06-01 | Finished | [14 empty] | 25 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-08-28 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-01-28 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 0 | 90 | 4 | 16 | 110 | 81.48 | Green |  |  | 20008575 | 2020-01-13 |  |  |  | HDME000776 | 2020-01-28
TFA1300-TH | HET | 61000583 | HO | ส่งมอบแล้ว | - | TH199237 | Mun Mun Seacon Square (Addition) | ES6.5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-06-10 | 2019-12-15 | 2020-02-15 | 2020-08-30 | 1200SX-EN,R4.75M,D30 | SX-EN |  |  |  |  | 4750 | 963000 | Bangkok | เขตประเวศ | 2019-12-15 | [20 empty] | 2020-04-20 | Finished | [14 empty] | 2019-11-30 | 2019-12-10 | 2019-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-15 | [41 empty] | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | 2020-06-24 | 2020-08-07 | 2020-08-07 | Finished |  |  | 2020-07-20 | 2020-08-07 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-25 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-09-24 | Finished | [18 empty] | 2019-12-10 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-17 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008529 | 2019-11-30 |  |  |  | HDME000748 | 2019-12-10 | QC Passed
TFA1301-TH | HET | 61000583 | HO | ส่งมอบแล้ว | - | TH199237 | Mun Mun Seacon Square (Addition) | ES6.6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-06-10 | 2019-12-15 | 2020-02-15 | 2020-08-30 | 1200SX-EN,R4.75M,D30 | SX-EN |  |  |  |  | 4750 | 963000 | Bangkok | เขตประเวศ | 2019-12-15 | [20 empty] | 2020-04-20 | Finished | [14 empty] | 2019-11-30 | 2019-12-10 | 2019-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-15 | [41 empty] | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | 2020-06-24 | 2020-08-08 | 2020-08-08 | Finished |  |  | 2020-07-20 | 2020-08-08 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-15 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-09-24 | Finished | [18 empty] | 2019-12-10 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-17 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008529 | 2019-11-30 |  |  |  | HDME000748 | 2019-12-10 | QC Passed
TFA1302-TH | HET | 61000583 | HO | ส่งมอบแล้ว | - | TH199237 | Mun Mun Seacon Square (Addition) | ES8.5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-06-10 | 2019-12-15 | 2020-02-15 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2019-12-15 | [20 empty] | 2020-02-28 | Finished | [14 empty] | 2019-11-30 | 2019-12-10 | 2019-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-28 | 2020-03-28 | [41 empty] | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-01 | Finished |  |  | 2020-03-01 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-07 | Finished |  |  | 100 | 2020-03-07 | 2020-08-08 | 2020-08-08 | Finished |  |  | 2020-07-20 | 2020-08-08 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-15 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-28 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-09-24 | Finished | [18 empty] | 2019-12-10 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-17 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008529 | 2019-11-30 |  |  |  | HDME000748 | 2019-12-10 | QC Passed
TFA1303-TH | HET | 61000583 | HO | ส่งมอบแล้ว | - | TH199237 | Mun Mun Seacon Square (Addition) | ES8.6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-06-10 | 2019-12-15 | 2020-02-15 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2019-12-15 | [20 empty] | 2020-02-28 | Finished | [14 empty] | 2019-11-30 | 2019-12-10 | 2019-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-28 | 2020-03-28 | [41 empty] | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-01 | Finished |  |  | 2020-03-01 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-05 | Finished |  |  | 2020-03-07 | Finished |  |  | 100 | 2020-03-07 | 2020-08-08 | 2020-08-08 | Finished |  |  | 2020-07-20 | 2020-08-08 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-15 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-09-24 | Finished | [18 empty] | 2019-12-10 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-17 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008529 | 2019-11-30 |  |  |  | HDME000748 | 2019-12-10 | QC Passed
TAJ0585-TH | HET | 61000584 | HO | ส่งมอบแล้ว | - | TH209014 | Home Office Ekachai Bangbon 12 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-08-05 | 2020-01-05 | 2020-03-05 | 2020-09-08 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1251900 | Bangkok | เขตบางขุนเทียน | 2020-01-07 | 2020-01-14 | Finished | [34 empty] | 2020-01-05 | 2020-01-14 | 2020-01-14 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-01-07 | 2020-01-31 | 2020-01-15 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-31 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-22 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-01-30 | Finished |  |  | 100 | [41 empty] | 2020-01-30 | 2020-10-22 | 2020-10-22 | Finished |  |  | 2020-08-07 | 2020-10-22 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-24 | Finished |  |  | 100 | 2021-01-08 | 2021-06-18 | 2021-01-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-06-18 | Finished |  |  | 100 | 2021-05-25 | Finished | POWER SUPPLY DELAY |  | 2021-05-28 | Finished |  |  | 2019-08-27 | Finished | [10 empty] | 2021-05-28 | Finished | [6 empty] | 2020-01-14 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-01-17 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008436 | 2020-01-05 |  |  |  | HDME000767 | 2020-01-14 | QC Passed
TAJ0586-TH | HET | 61000585 | HO | ส่งมอบแล้ว | - | TH199234 | Home Khun Sunee | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-03 | 2019-12-03 | 2020-01-18 | 2020-07-18 | P-600-CO60D,60S/3F | UAG-SN1 | 600 | 60 | 3 | 3 |  | 1100000 | Tak | อำเภอเมืองตาก | 2019-11-10 | 2020-01-05 | Finished | [34 empty] | 2019-12-03 | 2020-01-07 | 2020-01-07 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-05 | 2020-01-15 | 1900-01-01 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-13 | Finished |  |  | 2019-12-14 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2019-12-16 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-18 | Finished |  |  | 2019-12-19 | Finished |  |  | 100 | [41 empty] | 2019-12-19 | 2020-07-30 | 2020-07-30 | Finished |  |  | 2020-07-20 | 2020-07-31 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-02 | Finished |  |  | 100 | 2021-05-13 | 2021-03-31 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-07 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | 2020-08-05 | Finished | POWER SUPPLY DELAY |  | 2020-08-18 | Finished |  |  | 2019-08-27 | Finished | [10 empty] | 2021-01-15 | Finished | [6 empty] | 2020-01-07 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-14 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass | 2020-08-25 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008437 | 2019-12-03 |  |  |  | HDME000759 | 2020-01-07 | QC Passed
TAJ0587-TH | HET | 61000586 | Test | ยังอยู่ในสัญญา HO | - | TH209015 | Betong Apartment | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2019-08-15 | 2020-01-15 | 2020-03-15 | 2021-09-30 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1819000 | Yala | ตำบลเบตง | 2020-06-30 | 2020-07-01 | Finished | [34 empty] | 2020-01-08 | 2020-01-22 | 2020-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-30 | 2020-07-20 | 2020-08-05 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-25 | Finished |  |  | 100 | [41 empty] | 2020-08-25 | 1900-01-01 | 2020-08-25 | Waiting | POWER SUPPLY DELAY |  | 2021-12-01 | [12 empty] | 0 | 2020-11-30 | 2000-01-01 | 2020-11-30 | Finished | [14 empty] | 25 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-15 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-01-22 | Finished |  |  | 2020-01-22 | Finished |  |  | 2020-01-27 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 6 | 16 | 104 | 81.88 | Orange |  |  | 20008928 | 2020-01-08 |  |  |  | HDME000769 | 2020-01-22
TAJ0588-TH | HET | 61000587 | Test | ยังอยู่ในสัญญา HO | - | TH209016 | Sakuldee Foundation | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-08-16 | 2020-02-16 | 2020-03-31 | 2021-10-19 | P-750-CO60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1070000 | Bangkok | แขวงคลองสองต้นนุ่น | 2020-04-01 | 2020-06-10 | Finished | [34 empty] | 2020-02-09 | 2020-02-21 | 2020-02-21 | Finished | STORE AREA | [13 empty] | 2020-04-01 | 2020-04-10 | 2020-06-11 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-20 | Finished |  |  | 100 | [41 empty] | 2020-06-20 | 1900-01-01 | 2020-06-20 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | 2020-07-13 | 2000-01-01 | 2020-07-13 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-08-28 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished | [22 empty] | 276 | 79 | 16 | 16 | 387 | 0 | 79 | 4 | 16 | 99 | 74.42 | Green |  |  | 20008498 | 2020-02-09 |  |  |  | HDME000799 | 2020-02-21
TBK0169-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-EL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO240,240S/30F | HVF-5 | 1600 | 240 | 30 | 30 |  | 7811000 | Bangkok | แขวงลาดยาว | 2020-05-09 | [36 empty] | 2020-02-25 | 2020-04-24 | 2020-04-25 | Finished | OTHERS | [13 empty] | 2020-06-08 | 2020-09-15 | 2020-06-27 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-05 | Finished |  |  | 100 | [41 empty] | 2020-08-05 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-10-16 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-11-05 | Finished |  |  | 100 | 2021-01-08 | 2000-01-01 | 2021-01-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-04-24 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-30 | Finished | [17 empty] | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000861 | 2020-04-24
TBK0160-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO180,180S/16F | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-25 | Finished | [34 empty] | 2020-02-25 | 2020-03-21 | 2020-03-21 | Finished | OTHERS | [13 empty] | 2020-05-09 | 2020-08-16 | 2020-04-27 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-23 | Finished |  |  | 100 | [41 empty] | 2020-05-23 | 2020-09-30 | 2020-09-30 | Finished |  |  | 2020-09-30 | 2020-10-02 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-11-09 | Finished |  |  | 100 | 2021-01-06 | 2021-03-12 | 2021-01-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-03-21 | Finished |  |  | 2020-03-21 | Finished |  |  | 2020-03-26 | Finished | [17 empty] | pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000827 | 2020-03-21 | QC Passed
TBK0161-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO180,180S/16F | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-25 | Finished | [34 empty] | 2020-02-25 | 2020-03-21 | 2020-03-21 | Finished | OTHERS | [13 empty] | 2020-05-09 | 2020-08-16 | 2020-04-27 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-23 | Finished |  |  | 100 | [41 empty] | 2020-05-23 | 2020-09-30 | 2020-09-30 | Finished |  |  | 2020-09-30 | 2020-10-02 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-11-12 | Finished |  |  | 100 | 2021-01-06 | 2021-03-12 | 2021-01-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-03-21 | Finished |  |  | 2020-03-21 | Finished |  |  | 2020-03-26 | Finished | [17 empty] | pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000827 | 2020-03-21 | QC Passed
TBK0162-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO180,180S/16F | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-25 | Finished | [34 empty] | 2020-02-25 | 2020-03-21 | 2020-03-21 | Finished | OTHERS | [13 empty] | 2020-05-09 | 2020-08-16 | 2020-04-27 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | [41 empty] | 2020-06-04 | 2020-10-07 | 2020-10-07 | Finished |  |  | 2020-09-30 | 2020-10-09 | Finished |  |  | 2020-10-12 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-06 | 2021-03-12 | 2021-01-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-03-21 | Finished |  |  | 2020-03-21 | Finished |  |  | 2020-03-26 | Finished | [17 empty] | pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000827 | 2020-03-21 | QC Passed
TBK0163-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO180,180S/16F | HVF-5 | 1600 | 180 | 16 | 16 |  | 6486875 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-25 | Finished | [34 empty] | 2020-02-25 | 2020-03-21 | 2020-03-21 | Finished | OTHERS | [13 empty] | 2020-05-09 | 2020-08-16 | 2020-04-27 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | [41 empty] | 2020-06-04 | 2020-10-07 | 2020-10-07 | Finished |  |  | 2020-09-30 | 2020-10-09 | Finished |  |  | 2020-10-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-06 | 2021-03-12 | 2021-01-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-03-21 | Finished |  |  | 2020-03-21 | Finished |  |  | 2020-03-26 | Finished | [17 empty] | pass |  |  |  |  | 1143 | 97 | 40 | 20 | 1300 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000827 | 2020-03-21 | QC Passed
TBK0164-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-05 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO240,240S/30F | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-06-05 | Finished | [34 empty] | 2020-02-25 | 2020-04-03 | 2020-04-03 | Finished | OTHERS | [13 empty] | 2020-06-08 | 2020-09-15 | 2020-06-24 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | [41 empty] | 2020-07-31 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-10-28 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-12-06 | Finished |  |  | 100 | 2021-03-23 | 2000-01-01 | 2021-03-23 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-04-03 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-21 | Finished | [17 empty] | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000840 | 2020-04-03
TBK0165-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-06 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO240,240S/30F | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-06-05 | Finished | [34 empty] | 2020-02-25 | 2020-04-03 | 2020-04-03 | Finished | OTHERS | [13 empty] | 2020-06-08 | 2020-09-15 | 2020-06-24 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | [41 empty] | 2020-07-31 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-11-05 | Finished |  |  | 2020-11-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-19 | 2000-01-01 | 2021-02-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-04-03 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-21 | Finished | [17 empty] | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000840 | 2020-04-03
TBK0166-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-07 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO240,240S/30F | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-06-05 | Finished | [34 empty] | 2020-02-25 | 2020-04-03 | 2020-04-03 | Finished | OTHERS | [13 empty] | 2020-06-08 | 2020-09-15 | 2020-06-24 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 100 | [41 empty] | 2020-07-31 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-11-07 | Finished |  |  | 2020-11-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-11 | 2000-01-01 | 2021-02-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-04-03 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-21 | Finished | [17 empty] | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000840 | 2020-04-03
TBK0167-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-08 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO240,240S/30F | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Bangkok | แขวงลาดยาว | 2020-05-09 | [36 empty] | 2020-02-25 | 2020-04-03 | 2020-04-03 | Finished | OTHERS | [13 empty] | 2020-06-08 | 2020-09-15 | 2020-06-27 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-04 | Finished |  |  | 100 | [41 empty] | 2020-08-04 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-11-09 | Finished |  |  | 2020-11-23 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-12 | 2000-01-01 | 2021-02-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-04-03 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-21 | Finished | [17 empty] | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000840 | 2020-04-03
TBK0168-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-PL-09 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | HVF-1600-CO240,240S/30F | HVF-5 | 1600 | 240 | 18 | 30 |  | 7243900 | Bangkok | แขวงลาดยาว | 2020-05-09 | [36 empty] | 2020-02-25 | 2020-04-24 | 2020-04-25 | Finished | OTHERS | [13 empty] | 2020-06-08 | 2020-09-15 | 2020-06-27 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-08-03 | Finished |  |  | 100 | [41 empty] | 2020-08-03 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-11-11 | Finished |  |  | 2020-11-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-04-24 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-30 | Finished | [17 empty] | no pass |  |  |  |  | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-03-30 |  |  |  | HDME000861 | 2020-04-24
TAC1636-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | VFI-1600-CO150,150S/16F | VFI-II | 1600 | 150 | 16 | 16 |  | 5564000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-25 | Finished | [34 empty] | 2020-02-24 | 2020-02-28 | 2020-02-28 | Finished | OTHERS | [13 empty] | 2020-05-09 | 2020-07-12 | 2020-04-27 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 100 | [41 empty] | 2020-06-04 | 2020-07-01 | 2020-07-01 | Finished |  |  | 2020-06-29 | 2020-07-01 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 100 | 2020-08-28 | 2021-03-12 | 2020-08-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-28 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished | [17 empty] | pass |  |  |  |  | 1135 | 109 | 40 | 20 | 1304 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2020-02-24 |  |  |  | HDME000808 | 2020-02-28 | QC Passed
TAC1637-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 1-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-08-15 |  | VFI-1600-CO150,150S/31F | VFI-II | 1600 | 150 | 31 | 31 |  | 5992000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-05-26 | Finished | [34 empty] | 2020-02-24 | 2020-02-28 | 2020-02-28 | Finished | OTHERS | [13 empty] | 2020-05-25 | 2020-08-25 | 2020-06-05 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-12 | Finished |  |  | 100 | [41 empty] | 2020-06-12 | 2020-07-15 | 2020-07-15 | Finished |  |  | 2020-07-14 | 2020-07-17 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-09-02 | Finished |  |  | 100 | 2021-03-26 | 2000-01-01 | 2021-03-26 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished | [17 empty] | no pass |  |  |  |  | 1964 | 122 | 64 | 32 | 2182 | 0 | 0 | 0 | 3 | 3 | 99.86 | Red |  |  | 20008628 | 2020-02-24 |  |  |  | HDME000808 | 2020-02-28
TAC1656-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 2-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-03-15 |  | VFI-1000-CO105,105S/7F | VFI-II | 1000 | 105 | 7 | 7 |  | 2675000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-05-29 | Finished | [34 empty] | 2020-01-26 | 2020-02-04 | 2020-02-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-29 | 2020-08-16 | 2020-06-19 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-23 | Finished |  |  | 2020-07-23 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-11 | Finished |  |  | 100 | [41 empty] | 2020-07-11 | 2020-08-17 | 2020-08-17 | Finished |  |  | 2020-08-17 | 2020-08-18 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | 2021-01-19 | 2021-03-23 | 2021-01-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-02-04 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-04 | Finished | [17 empty] | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000782 | 2020-02-04 | QC Passed
TAC1657-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 2-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-03-15 |  | VFI-1000-CO105,105S/7F | VFI-II | 1000 | 105 | 7 | 7 |  | 2675000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-05-29 | Finished | [34 empty] | 2020-01-26 | 2020-02-04 | 2020-02-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-29 | 2020-08-16 | 2020-06-19 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-23 | Finished |  |  | 2020-07-23 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-11 | Finished |  |  | 100 | [41 empty] | 2020-07-11 | 2020-08-17 | 2020-08-17 | Finished |  |  | 2020-08-17 | 2020-08-18 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | 2021-01-19 | 2021-03-23 | 2021-01-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-23 | Finished | [6 empty] | 90 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-02-04 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-04 | Finished | [17 empty] | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000782 | 2020-02-04 | QC Passed
TAC1638-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 5-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2019-12-27 | 2019-12-27 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | [41 empty] | 2020-02-13 | 2020-07-31 | 2020-07-31 | Finished |  |  | 2020-07-27 | 2020-07-31 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-28 | Finished |  |  | 100 | 2020-10-15 | 2021-05-17 | 2020-10-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2019-12-26 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-27 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000757 | 2019-12-26 | QC Passed
TAC1639-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 5-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2019-12-27 | 2019-12-27 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-13 | Finished |  |  | 100 | [41 empty] | 2020-02-13 | 2020-07-31 | 2020-07-31 | Finished |  |  | 2020-07-27 | 2020-07-31 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-28 | Finished |  |  | 100 | 2021-01-08 | 2021-05-17 | 2021-01-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2019-12-26 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-27 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000757 | 2019-12-26 | QC Passed
TAC1640-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 5-PL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-24 | Finished | [34 empty] | 2019-12-30 | 2019-12-27 | 2019-12-27 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-25 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 100 | [41 empty] | 2020-02-28 | 2020-04-28 | 2020-04-28 | Finished |  |  | 2020-04-27 | 2020-05-05 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2020-09-25 | 2021-05-17 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2019-12-26 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-27 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000757 | 2019-12-26 | QC Passed
TAC1641-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 5-PL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-24 | Finished | [34 empty] | 2019-12-30 | 2019-12-27 | 2019-12-27 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-25 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 100 | [41 empty] | 2020-02-28 | 2020-04-28 | 2020-04-28 | Finished |  |  | 2020-04-27 | 2020-05-05 | Finished |  |  | 2020-07-17 | Finished |  |  | 2020-07-24 | Finished |  |  | 100 | 2020-09-25 | 2021-05-17 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2019-12-26 | Finished |  |  | 2019-12-27 | Finished |  |  | 2019-12-27 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000757 | 2019-12-26 | QC Passed
TAC1642-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 5-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO105,105S/20F | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-07-31 | 2020-07-31 | Finished |  |  | 2020-07-27 | 2020-07-31 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-29 | Finished |  |  | 100 | 2020-09-25 | 2021-05-17 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08 | QC Passed
TAC1643-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 5-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO105,105S/20F | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-04-28 | 2020-04-28 | Finished |  |  | 2020-04-27 | 2020-05-05 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | 2020-10-15 | 2021-05-17 | 2020-10-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08 | QC Passed
TAC1644-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 6-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-08-13 | 2020-08-13 | Finished |  |  | 2020-08-10 | 2020-08-14 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-23 | Finished |  |  | 100 | 2020-10-27 | 2000-01-01 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-10 | Finished | [6 empty] | 90 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Red |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08
TAC1645-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 6-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-01-10 | Finished |  |  | 2020-01-15 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-01 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-08-13 | 2020-08-13 | Finished |  |  | 2020-08-10 | 2020-08-14 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-23 | Finished |  |  | 100 | 2020-10-27 | 2021-05-17 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08 | QC Passed
TAC1646-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 6-PL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-08 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-11 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-05-20 | 2020-06-11 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | 2020-09-25 | 2021-05-17 | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08 | QC Passed
TAC1647-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 6-PL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-08 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-11 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-06-10 | 2020-06-10 | Finished |  |  | 2020-05-20 | 2020-06-11 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | 2020-08-21 | 2021-05-17 | 2020-08-21 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08 | QC Passed
TAC1648-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 6-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO105,105S/20F | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-05-20 | 2020-09-11 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-10-08 | Finished |  |  | 100 | 2020-10-27 | 2021-05-17 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08 | QC Passed
TAC1649-TH | HET | 61000593 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 6-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-05-15 |  | VFI-1000-CO105,105S/20F | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-01-06 | Finished | [34 empty] | 2019-12-30 | 2020-01-09 | 2020-01-09 | Finished | OTHERS | [13 empty] | 2020-01-05 | 2020-03-27 | 2020-01-08 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-14 | Finished |  |  | 100 | [41 empty] | 2020-02-14 | 2020-05-29 | 2020-05-29 | Finished |  |  | 2020-05-20 | 2020-06-02 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-07-23 | Finished |  |  | 100 | 2020-08-21 | 2021-05-17 | 2020-08-21 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-08 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-14 | Finished | [17 empty] | pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008628 | 2019-12-30 |  |  |  | HDME000761 | 2020-01-08 | QC Passed
TAC1650-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 7-PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-06-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-02 | Finished | [34 empty] | 2020-01-26 | 2020-01-24 | 2020-01-24 | Finished | [14 empty] | 2020-03-30 | 2020-07-03 | 2020-04-04 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-06-02 | Finished |  |  | 100 | [41 empty] | 2020-06-02 | 2020-09-15 | 2020-09-15 | Finished |  |  | 2020-09-15 | 2020-12-02 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-06 | Finished |  |  | 100 | 2021-07-12 | 2000-01-01 | 2021-07-12 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 90 | 2021-10-25 | Working | OTHERS | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-23 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished | [17 empty] | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000771 | 2020-01-23
TAC1651-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 7-PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-06-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-02 | Finished | [34 empty] | 2020-01-26 | 2020-01-24 | 2020-01-24 | Finished | [14 empty] | 2020-03-30 | 2020-07-03 | 2020-04-04 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-06-02 | Finished |  |  | 100 | [41 empty] | 2020-06-02 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-15 | 2020-12-03 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-06 | Finished |  |  | 100 | 2021-07-12 | 2000-01-01 | 2021-07-12 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 90 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-23 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished | [17 empty] | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000771 | 2020-01-23
TAC1652-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 7-PL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-06-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-02 | Finished | [34 empty] | 2020-01-26 | 2020-01-24 | 2020-01-24 | Finished | [14 empty] | 2020-03-30 | 2020-07-03 | 2020-04-04 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-06-02 | Finished |  |  | 100 | [41 empty] | 2020-06-02 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-15 | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | 2021-07-12 | 2000-01-01 | 2021-07-12 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 90 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-23 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished | [17 empty] | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000771 | 2020-01-23
TAC1653-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 7-PL-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-06-15 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4815000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-04-02 | Finished | [34 empty] | 2020-01-26 | 2020-01-24 | 2020-01-24 | Finished | [14 empty] | 2020-03-30 | 2020-07-03 | 2020-04-04 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-06-02 | Finished |  |  | 100 | [41 empty] | 2020-06-02 | 2020-06-15 | 2020-06-15 | Finished |  |  | 2020-06-15 | 2020-12-05 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-24 | Finished |  |  | 100 | 2021-07-12 | 2000-01-01 | 2021-07-12 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 90 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-23 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished | [17 empty] | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000771 | 2020-01-23
TAC1654-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 7-SL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-06-15 |  | VFI-1000-CO105,105S/20F | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-05-10 | Finished | [34 empty] | 2020-01-26 | 2020-01-24 | 2020-01-24 | Finished | [14 empty] | 2020-03-30 | 2020-07-03 | 2020-05-13 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-13 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-20 | Finished |  |  | 100 | [41 empty] | 2020-06-20 | 2020-07-20 | 2020-07-20 | Finished |  |  | 2020-07-20 | 2020-12-06 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-20 | Finished |  |  | 100 | 2021-04-21 | 2000-01-01 | 2021-04-21 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 90 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-23 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished | [17 empty] | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000771 | 2020-01-23
TAC1655-TH | HET | 61000593 | Install | เลยสัญญา HO | - | TH209018 | Immigration Bureau | 7-SL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-01-06 | 2020-06-15 |  | VFI-1000-CO105,105S/20F | VFI-II | 1000 | 105 | 20 | 20 |  | 3745000 | Bangkok | แขวงลาดยาว | 2020-05-09 | 2020-03-26 | Finished | [34 empty] | 2020-01-26 | 2020-01-24 | 2020-01-24 | Finished | [14 empty] | 2020-03-30 | 2020-07-03 | 2020-03-30 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 100 | [41 empty] | 2020-05-07 | 2020-07-17 | 2020-07-17 | Finished |  |  | 2020-05-30 | 2020-07-17 | Finished |  |  | 2020-07-28 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | 2021-07-12 | 2000-01-01 | 2021-07-12 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 90 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-01-23 | Finished |  |  | 2020-01-24 | Finished |  |  | 2020-01-27 | Finished | [17 empty] | no pass |  |  |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Red |  |  | 20008628 | 2020-01-26 |  |  |  | HDME000771 | 2020-01-23
TAD0422-TH | HET | 61000594 | HO | ส่งมอบแล้ว | - | TH209017 | โรงพยาบาลพัทลุง [อ.พักคนไข้ 298 เตียง] | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2019-08-28 | 2020-01-28 | 2020-05-28 | 2020-10-28 | B-1000-2S90,90S/8F | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1712000 | Patthalung | อำเภอเมืองพัทลุง | 2020-04-06 | 2020-04-06 | Finished | [34 empty] | 2020-01-28 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-06 | 2020-05-20 | 2020-04-06 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-04-19 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-02-24 | Finished |  |  | 100 | [41 empty] | 2020-02-24 | 2020-07-06 | 2020-07-06 | Finished |  |  | 2020-06-25 | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2020-10-03 | Finished | POWER SUPPLY DELAY |  | 2020-08-18 | Finished |  |  | 2019-09-16 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-01-28 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008643 | 2020-01-28 |  |  |  | HDME000775 | 2020-01-28 | QC Passed
TAD0423-TH | HET | 61000594 | HO | ส่งมอบแล้ว | - | TH209017 | โรงพยาบาลพัทลุง [อ.พักคนไข้ 298 เตียง] | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2019-08-28 | 2020-01-28 | 2020-05-28 | 2020-09-28 | B-1000-2S90,90S/8F | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1712000 | Patthalung | อำเภอเมืองพัทลุง | 2020-04-06 | 2019-12-15 | Finished | [34 empty] | 2020-01-28 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-06 | 2020-05-20 | 2020-04-06 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-04-19 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-02-24 | Finished |  |  | 100 | [41 empty] | 2020-02-24 | 2020-07-06 | 2020-07-06 | Finished |  |  | 2020-06-25 | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2020-10-03 | Finished | POWER SUPPLY DELAY |  | 2020-08-18 | Finished |  |  | 2019-09-16 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-01-28 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008643 | 2020-01-28 |  |  |  | HDME000775 | 2020-01-28 | QC Passed
TAD0424-TH | HET | 61000594 | HO | ส่งมอบแล้ว | - | TH209017 | โรงพยาบาลพัทลุง [อ.พักคนไข้ 298 เตียง] | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2019-08-28 | 2020-01-28 | 2020-05-28 | 2020-09-28 | B-1000-2S90,90S/8F | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1712000 | Patthalung | อำเภอเมืองพัทลุง | 2020-04-06 | 2019-12-15 | Finished | [34 empty] | 2020-01-28 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-06 | 2020-05-20 | 2020-04-06 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-04-19 | Finished |  |  | 2020-04-14 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-02-24 | Finished |  |  | 100 | [41 empty] | 2020-02-24 | 2020-07-06 | 2020-07-06 | Finished |  |  | 2020-06-25 | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2020-10-03 | Finished | POWER SUPPLY DELAY |  | 2020-08-18 | Finished |  |  | 2019-09-16 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-01-28 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008643 | 2020-01-28 |  |  |  | HDME000775 | 2020-01-28 | QC Passed
TAD0425-TH | HET | 61000594 | HO | ส่งมอบแล้ว | - | TH209017 | โรงพยาบาลพัทลุง [อ.พักคนไข้ 298 เตียง] | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2019-08-28 | 2020-01-28 | 2020-05-28 | 2020-10-28 | B-1000-2S90,90S/8F | B-II(VFI-II) | 1000 | 90 | 8 | 8 |  | 1712000 | Patthalung | อำเภอเมืองพัทลุง | 2020-02-22 | 2019-12-29 | Finished | [34 empty] | 2020-01-28 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-28 | 2020-03-28 | 2019-12-29 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-26 | Finished |  |  | 100 | [41 empty] | 2020-02-26 | 2020-07-06 | 2020-07-06 | Finished |  |  | 2020-04-21 | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2020-04-07 | 2020-12-25 | 2020-04-07 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2020-10-03 | Finished | POWER SUPPLY DELAY |  | 2020-10-30 | Finished |  |  | 2019-09-16 | Finished | [10 empty] | 2020-11-30 | Finished | [6 empty] | 2020-01-28 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008643 | 2020-01-28 |  |  |  | HDME000775 | 2020-01-28 | QC Passed
TAC1658-TH | HET | 61000594 | HO | ส่งมอบแล้ว | - | TH209017 | โรงพยาบาลพัทลุง [อ.พักคนไข้ 298 เตียง] | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2019-08-28 | 2020-01-28 | 2020-05-28 | 2020-09-28 | VFI-750-CO90,90S/8F | VFI-II | 750 | 90 | 8 | 8 |  | 1391000 | Patthalung | อำเภอเมืองพัทลุง | 2020-02-22 | 2019-12-29 | Finished | [34 empty] | 2020-01-28 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-28 | 2020-03-28 | 2019-12-29 | Finished |  |  | 2020-02-02 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-26 | Finished |  |  | 100 | [41 empty] | 2020-02-26 | 2020-07-06 | 2020-07-06 | Finished |  |  | 2020-06-25 | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2021-05-13 | 2020-12-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2020-10-03 | Finished | POWER SUPPLY DELAY |  | 2020-08-18 | Finished |  |  | 2019-09-16 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-01-28 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008643 | 2020-01-28 |  |  |  | HDME000775 | 2020-01-28 | QC Passed
TEB0109-TH | HET | 61000595 | HO | เลยสัญญา HO | - | TH199154 | Townhome Khao-Yai Khun Pornchai | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Orawan Kwanpheng | 2019-08-27 | 2019-12-15 | 2020-01-30 | 2021-09-09 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 4 | 4 |  | 1262600 | Nakhon Ratchasima | ตำบลหมูสี | 2019-12-06 | 2019-12-06 | Finished | [34 empty] | 2019-12-15 | 2019-12-19 | 2019-12-19 | Finished | PAYMENT DELAY | [13 empty] | 2019-12-15 | 2020-01-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-09-11 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2019-12-19 | Finished |  |  | 2019-12-19 | Finished |  |  | 2019-12-20 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 16 | 16 | 87 | 66.15 | Red |  |  | 20008675 | 2019-12-15 |  |  |  | HDME000755 | 2019-12-19
TAC1659-TH | HET | 61000596 | HO | ส่งมอบแล้ว | - | TH199245 | Apartment Khun Damon Lee | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-08-30 | 2019-12-15 | 2020-03-16 | 2020-05-03 | VFI-700-CO60,60S/9F | VFI-II | 700 | 60 | 9 | 9 |  | 1080000 | Bangkok | แขวงบางนา | 2020-04-11 | 2020-02-06 | Finished | [34 empty] | 2019-12-15 | 2019-12-17 | 2019-12-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-06 | 2020-03-23 | 2020-02-10 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-19 | Finished |  |  | 100 | [41 empty] | 2020-03-19 | 2020-05-24 | 2020-05-24 | Finished |  |  | 2020-04-20 | 2020-05-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-14 | 2000-01-01 | 2020-07-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-26 | Finished |  |  | 100 | 2021-04-02 | Finished | CUSTOMER DECORATION DELAY |  | 2021-03-29 | Finished |  |  | 2019-09-24 | Finished | [10 empty] | 2021-03-29 | Finished | [6 empty] | 2019-12-16 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-18 | Finished |  |  | 2021-03-29 | Finished | [13 empty] | no pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008682 | 2019-12-15 |  |  |  | HDME000750 | 2019-12-16
TAC1660-TH | HET | 61000596 | HO | ส่งมอบแล้ว | - | TH199245 | Apartment Khun Damon Lee | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-08-30 | 2019-12-15 | 2020-03-16 | 2020-05-03 | VFI-700-CO60,60S/9F | VFI-II | 700 | 60 | 9 | 9 |  | 1080000 | Bangkok | แขวงบางนา | 2020-02-05 | 2020-02-06 | Finished | [34 empty] | 2019-12-15 | 2019-12-17 | 2019-12-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-06 | 2020-03-23 | 2020-02-10 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-19 | Finished |  |  | 100 | [41 empty] | 2020-03-19 | 2020-05-24 | 2020-05-24 | Finished |  |  | 2020-04-20 | 2020-05-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-14 | 2000-01-01 | 2020-07-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-26 | Finished |  |  | 100 | 2021-04-02 | Finished | CUSTOMER DECORATION DELAY |  | 2021-03-29 | Finished |  |  | 2019-09-24 | Finished | [10 empty] | 2021-03-29 | Finished | [6 empty] | 2019-12-16 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-18 | Finished |  |  | 2021-03-29 | Finished | [13 empty] | pass (defect) |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008682 | 2019-12-15 |  |  |  | HDME000750 | 2019-12-16
TAC1661-TH | HET | 61000596 | HO | ส่งมอบแล้ว | - | TH199245 | Apartment Khun Damon Lee | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-08-30 | 2019-12-15 | 2020-03-16 | 2020-05-03 | VFI-700-CO60,60S/9F | VFI-II | 700 | 60 | 9 | 9 |  | 1080000 | Bangkok | แขวงบางนา | 2020-01-10 | 2020-02-06 | Finished | [34 empty] | 2019-12-15 | 2019-12-17 | 2019-12-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-06 | 2020-03-23 | 2020-02-10 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-19 | Finished |  |  | 100 | [41 empty] | 2020-03-19 | 2020-05-24 | 2020-05-24 | Finished |  |  | 2020-04-20 | 2020-05-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-14 | 2000-01-01 | 2020-07-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-26 | Finished |  |  | 100 | 2021-04-02 | Finished | CUSTOMER DECORATION DELAY |  | 2021-03-29 | Finished |  |  | 2019-09-24 | Finished | [10 empty] | 2021-03-29 | Finished | [6 empty] | 2019-12-16 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-18 | Finished |  |  | 2021-03-29 | Finished | [13 empty] | no pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008682 | 2019-12-15 |  |  |  | HDME000750 | 2019-12-16
TAC1662-TH | HET | 61000596 | HO | ส่งมอบแล้ว | - | TH199245 | Apartment Khun Damon Lee | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-08-30 | 2019-12-15 | 2020-03-16 | 2020-05-03 | VFI-700-CO60,60S/9F | VFI-II | 700 | 60 | 9 | 9 |  | 1080000 | Bangkok | แขวงบางนา | 2019-12-15 | 2020-02-06 | Finished | [34 empty] | 2019-12-15 | 2019-12-17 | 2019-12-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-06 | 2020-03-23 | 2020-02-10 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-19 | Finished |  |  | 100 | [41 empty] | 2020-03-19 | 2020-05-24 | 2020-05-24 | Finished |  |  | 2020-04-20 | 2020-05-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-14 | 2000-01-01 | 2020-07-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-08-26 | Finished |  |  | 100 | 2021-04-02 | Finished | CUSTOMER DECORATION DELAY |  | 2021-03-29 | Finished |  |  | 2019-09-24 | Finished | [10 empty] | 2021-03-29 | Finished | [6 empty] | 2019-12-16 | Finished |  |  | 2019-12-17 | Finished |  |  | 2019-12-18 | Finished |  |  | 2021-03-29 | Finished | [13 empty] | no pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008682 | 2019-12-15 |  |  |  | HDME000750 | 2019-12-16
TFA1304-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | C-ESC-1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | 1200TX-EN,R6.4M,D30 | TX-EN |  |  |  |  | 6400 | 1316100 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | [20 empty] | 2020-11-20 | Finished | [14 empty] | 2020-01-20 | 2020-04-17 | 2020-04-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-20 | 2021-12-21 | [41 empty] | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-26 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-05 | Finished |  |  | 100 | 2021-02-05 | 1900-01-01 | 2021-02-05 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-17 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished | [22 empty] | 590 | 42 | 24 | 21 | 677 | 0 | 42 | 24 | 21 | 87 | 87.15 | Green |  |  | 20008684 | 2020-01-20 |  |  |  | HDME000849 | 2020-04-17
TFA1305-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | C-ESC-2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | 1200TX-EN,R6.4M,D30 | TX-EN |  |  |  |  | 6400 | 1316100 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | [20 empty] | 2020-11-20 | Finished | [14 empty] | 2020-01-20 | 2020-04-17 | 2020-04-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-20 | 2021-12-21 | [41 empty] | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-26 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-05 | Finished |  |  | 100 | 2021-02-05 | 1900-01-01 | 2021-02-05 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-17 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished | [22 empty] | 590 | 42 | 24 | 21 | 677 | 0 | 42 | 24 | 21 | 87 | 87.15 | Green |  |  | 20008684 | 2020-01-20 |  |  |  | HDME000849 | 2020-04-17
TFA1306-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | C-ESC-3 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | 1200TX-EN,R5.9M,D30 | TX-EN |  |  |  |  | 5900 | 1262600 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | [20 empty] | 2020-11-20 | Finished | [14 empty] | 2020-01-20 | 2020-04-17 | 2020-04-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-20 | 2021-12-21 | [41 empty] | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-26 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-05 | Finished |  |  | 100 | 2021-02-05 | 1900-01-01 | 2021-02-05 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-17 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 16 | 21 | 79 | 87.15 | Green |  |  | 20008684 | 2020-01-20 |  |  |  | HDME000849 | 2020-04-17
TFA1307-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | C-ESC-4 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | 1200TX-EN,R5.9M,D30 | TX-EN |  |  |  |  | 5900 | 1262600 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | [20 empty] | 2020-11-20 | Finished | [14 empty] | 2020-01-20 | 2020-04-17 | 2020-04-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-20 | 2021-12-21 | [41 empty] | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-26 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-05 | Finished |  |  | 100 | 2021-02-05 | 1900-01-01 | 2021-02-05 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-17 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 16 | 21 | 79 | 87.15 | Green |  |  | 20008684 | 2020-01-20 |  |  |  | HDME000849 | 2020-04-17
TFA1308-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | C-ESC-5 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | 1200TX-EN,R7.3M,D30 | TX-EN |  |  |  |  | 7300 | 1391000 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | [20 empty] | 2021-08-17 | Finished | [14 empty] | 2020-01-20 | 2020-04-17 | 2020-04-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-20 | 2021-11-21 | [41 empty] | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-26 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2021-08-17 | 1900-01-01 | 2021-08-17 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-17 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 0 | 42 | 24 | 21 | 87 | 88.08 | Green |  |  | 20008684 | 2020-01-20 |  |  |  | HDME000849 | 2020-04-17
TFA1309-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | C-ESC-6 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | 1200TX-EN,R7.3M,D30 | TX-EN |  |  |  |  | 7300 | 1391000 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | [20 empty] | 2021-08-17 | Finished | [14 empty] | 2020-01-20 | 2020-04-17 | 2020-04-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-20 | 2021-11-21 | [41 empty] | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-26 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 90 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-17 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 64 | 42 | 24 | 21 | 151 | 79.32 | Green |  |  | 20008684 | 2020-01-20 |  |  |  | HDME000849 | 2020-04-17
TBL0213-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CBL-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-CO105,105S/6F | OUG-ON1 | 1600 | 105 | 4 | 6 |  | 1444500 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2020-11-11 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 100 | [41 empty] | 2021-03-18 | 2021-03-24 | 2021-03-24 | Finished |  |  | 2020-12-25 | 2021-03-26 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-08 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2021-10-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 6 | 16 | 22 | 96.71 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0211-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CBL-2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-CO105,105S/6F | OUG-ON1 | 1600 | 105 | 6 | 6 |  | 1476600 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2020-11-11 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 100 | [41 empty] | 2021-03-18 | 2021-03-24 | 2021-03-24 | Finished |  |  | 2020-12-25 | 2021-03-26 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-08 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2021-10-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 6 | 16 | 22 | 96.71 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0212-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CBL-3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-CO105,105S/6F | OUG-ON1 | 1600 | 105 | 6 | 6 |  | 1476600 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2020-11-11 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 100 | [41 empty] | 2021-03-18 | 2021-03-24 | 2021-03-24 | Finished |  |  | 2020-12-25 | 2021-03-26 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-08 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2021-10-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 6 | 16 | 22 | 96.71 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0216-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CFL-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-2S105,105S/11F | OUG-ON1 | 1600 | 105 | 11 | 11 |  | 1797600 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2020-11-11 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | [41 empty] | 2021-03-26 | 2021-03-23 | 2021-03-23 | Finished |  |  | 2020-12-25 | 2021-03-31 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 808 | 98 | 32 | 20 | 958 | 0 | 0 | 32 | 20 | 52 | 94.57 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0217-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CFL-2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-2S105,105S/11F | OUG-ON1 | 1600 | 105 | 11 | 11 |  | 1797600 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2020-11-11 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | [41 empty] | 2021-03-26 | 2021-03-23 | 2021-03-23 | Finished |  |  | 2020-12-25 | 2021-03-31 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 808 | 98 | 32 | 20 | 958 | 0 | 0 | 32 | 20 | 52 | 94.57 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0209-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CHL-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-CO105,105S/11F | OUG-ON1 | 1600 | 105 | 9 | 11 |  | 1744100 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2021-02-24 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-04-25 | Finished |  |  | 100 | [41 empty] | 2021-04-25 | 2021-04-26 | 2021-04-26 | Finished |  |  | 2020-12-25 | 2021-04-30 | Finished |  |  | 2021-05-03 | Finished |  |  | 2021-05-08 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 808 | 98 | 32 | 20 | 958 | 0 | 0 | 8 | 20 | 28 | 97.08 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0210-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CHL-2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-CO105,105S/11F | OUG-ON1 | 1600 | 105 | 11 | 11 |  | 1840400 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2021-02-24 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-04-25 | Finished |  |  | 100 | [41 empty] | 2021-04-25 | 2021-04-26 | 2021-04-26 | Finished |  |  | 2020-12-25 | 2021-04-30 | Finished |  |  | 2021-05-03 | Finished |  |  | 2021-05-08 | Finished |  |  | 100 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 808 | 98 | 32 | 20 | 958 | 0 | 0 | 8 | 20 | 28 | 97.08 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0214-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CSL-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-2S60,60S/10F | OUG-ON1 | 1600 | 60 | 9 | 10 |  | 1744100 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2020-11-11 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-19 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | [41 empty] | 2021-01-29 | 2021-03-11 | 2021-03-11 | Finished |  |  | 2020-12-25 | 2021-03-12 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-05 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 755 | 89 | 24 | 16 | 884 | 0 | 0 | 24 | 16 | 40 | 95.48 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TBL0215-TH | HET | 61000597 | HO | ยังอยู่ในสัญญา HO | - | TH199241 | Asawin Convention Hotel | CSL-2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-08-20 | 2020-01-20 | 2020-05-20 | 2021-12-01 | OUG-1600-2S60,60S/10F | OUG-ON1 | 1600 | 60 | 9 | 10 |  | 1744100 | Bangkok | แขวงตลาดบางเขน | 2020-08-16 | 2020-08-17 | Finished | [34 empty] | 2020-01-20 | 2020-04-21 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-20 | 2020-12-21 | 2020-11-11 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-19 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | [41 empty] | 2021-01-29 | 2021-03-11 | 2021-03-11 | Finished |  |  | 2020-12-25 | 2021-03-12 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-05 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-05-12 | Finished |  |  | 2020-05-19 | Finished | [22 empty] | 755 | 89 | 24 | 16 | 884 | 0 | 0 | 24 | 16 | 40 | 95.48 | Green |  |  | 20008683 | 2020-01-22 |  |  |  | HDME000851 | 2020-04-21
TFA1310-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | 1200TX-EN,R5.2M,D35 | TX-EN |  |  |  |  | 5200 | 1177000 | Nonthaburi | อำเภอเมือง | 2020-01-16 | [20 empty] | 2020-01-16 | Finished | [14 empty] | 2019-12-08 | 2019-12-20 | 2019-12-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-15 | 2020-05-15 | [41 empty] | 2020-05-14 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-14 | Finished |  |  | 2020-05-18 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-21 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-09-13 | Finished |  |  | 100 | 2020-09-13 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-09-12 | Finished |  |  | 2020-09-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 100 | 2021-05-13 | 2021-04-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-28 | Finished |  |  | 100 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2019-12-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008692 | 2019-12-08 | [5 empty] | QC Passed
TFA1311-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | 1200TX-EN,R5.2M,D35 | TX-EN |  |  |  |  | 5200 | 1177000 | Nonthaburi | อำเภอเมือง | 2020-01-16 | [20 empty] | 2020-01-16 | Finished | [14 empty] | 2019-12-08 | 2019-12-20 | 2019-12-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-15 | 2020-05-15 | [41 empty] | 2020-05-14 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-14 | Finished |  |  | 2020-05-18 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-21 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-09-13 | Finished |  |  | 100 | 2020-09-13 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-09-12 | Finished |  |  | 2020-09-13 | Finished |  |  | 2020-10-02 | Finished |  |  | 100 | 2021-05-13 | 2021-04-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-09 | Finished |  |  | 2021-04-28 | Finished |  |  | 100 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2019-12-19 | Finished |  |  | 2019-12-25 | Finished |  |  | 2019-12-25 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008692 | 2019-12-08 | [5 empty] | QC Passed
TEC0139-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | DF1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | DF-100S-B30,30S/6F | DF | 100 | 30 | 6 | 6 |  | 288900 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-03-20 | 2020-03-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2020-02-18 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-15 | Finished |  |  | 100 | [41 empty] | 2020-03-15 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-09-03 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-23 | Finished |  |  | 100 | 2020-08-31 | 2000-01-01 | 2020-08-31 | Finished | [14 empty] | 25 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-03-19 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | dumb |  |  |  |  | 283 | 0 | 24 | 0 | 307 | 0 | 0 | 6 | 0 | 6 | 98.05 | Blue |  |  | 20008689 | 2019-12-08 |  |  |  | HDME000824 | 2020-03-19
TEC0140-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | DF2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | DF-100S-B30,30S/6F | DF | 100 | 30 | 6 | 6 |  | 288900 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-03-20 | 2020-03-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2020-02-18 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-03-02 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-15 | Finished |  |  | 100 | [41 empty] | 2020-03-15 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-09-03 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-23 | Finished |  |  | 100 | 2020-08-31 | 2000-01-01 | 2020-08-31 | Finished | [14 empty] | 25 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-03-19 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | dumb |  |  |  |  | 283 | 0 | 24 | 0 | 307 | 0 | 0 | 6 | 0 | 6 | 98.05 | Blue |  |  | 20008689 | 2019-12-08 |  |  |  | HDME000824 | 2020-03-19
TAC1663-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | PL1 (Bldg.1) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | VFI-1600-CO90,90S/4F | VFI-II | 1600 | 90 | 4 | 4 |  | 1514050 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-01-20 | 2020-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2019-11-30 | Finished |  |  | 2019-12-05 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-16 | Finished |  |  | 2019-12-22 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-04-05 | Finished |  |  | 100 | [41 empty] | 2020-04-05 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-07-10 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | 2020-05-22 | 2020-08-31 | 2020-05-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-31 | Finished | [6 empty] | 90 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-01-11 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20008690 | 2019-12-16 |  |  |  | HDME000764 | 2020-01-11 | QC Passed
TAC1667-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | PL1 (Bldg.B3,B4,B5) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | VFI-1000-CO90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1391000 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-01-20 | 2020-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2020-01-30 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-05-06 | Finished |  |  | 100 | [41 empty] | 2020-05-06 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-07-07 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2020-06-19 | 2021-05-18 | 2020-06-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-18 | Finished |  |  | 100 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-01-11 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008690 | 2019-12-16 |  |  |  | HDME000764 | 2020-01-11 | QC Passed
TAC1668-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | PL2 (Bldg.B3,B4,B5) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | VFI-1000-CO90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1391000 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-01-20 | 2020-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2020-01-30 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-05-06 | Finished |  |  | 100 | [41 empty] | 2020-05-06 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-07-08 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2020-06-19 | 2021-05-18 | 2020-06-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-05-18 | Finished |  |  | 100 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-01-11 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008690 | 2019-12-16 |  |  |  | HDME000764 | 2020-01-11 | QC Passed
TAC1664-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | PL2(Bldg.1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | VFI-1600-CO90,90S/4F | VFI-II | 1600 | 90 | 4 | 4 |  | 1514050 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-01-20 | 2020-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2019-11-30 | Finished |  |  | 2019-12-05 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-16 | Finished |  |  | 2019-12-22 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-04-05 | Finished |  |  | 100 | [41 empty] | 2020-04-05 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-07-10 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | 2020-08-31 | 2020-08-31 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-31 | Finished | [6 empty] | 90 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-01-11 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20008690 | 2019-12-16 |  |  |  | HDME000764 | 2020-01-11 | QC Passed
TAC1665-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | PL3 (Bldg.1) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | VFI-1600-CO90,90S/4F | VFI-II | 1600 | 90 | 4 | 4 |  | 1514050 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-01-20 | 2020-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2019-11-30 | Finished |  |  | 2019-12-05 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-16 | Finished |  |  | 2019-12-22 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-04-05 | Finished |  |  | 100 | [41 empty] | 2020-04-05 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-07-10 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | 2020-08-31 | 2021-03-31 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-01-11 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008690 | 2019-12-16 |  |  |  | HDME000764 | 2020-01-11 | QC Passed
TAC1666-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | SL1 (Bldg.1) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | VFI-1600-2S90,90S/5F | VFI-II | 1600 | 90 | 5 | 5 |  | 1567550 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-01-20 | 2020-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2019-11-30 | Finished |  |  | 2019-12-05 | Finished |  |  | 2019-12-10 | Finished |  |  | 2019-12-16 | Finished |  |  | 2019-12-22 | Finished |  |  | 2019-12-28 | Finished |  |  | 2020-01-18 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-04-05 | Finished |  |  | 100 | [41 empty] | 2020-04-05 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-07-06 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-29 | Finished |  |  | 100 | 2020-08-31 | 2020-08-31 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-31 | Finished | [6 empty] | 90 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-01-11 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20008690 | 2019-12-16 |  |  |  | HDME000764 | 2020-01-11 | QC Passed
TAC1669-TH | HET | 61000598 | HO | ส่งมอบแล้ว | - | TH199240 | Tax Collection Training Institute | SL1 (Bldg.B3,B4,B5) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-08-08 | 2019-12-08 | 2020-04-08 | 2020-10-30 | VFI-1000-CO90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1391000 | Nonthaburi | อำเภอเมือง | 2020-01-16 | 2020-01-16 | Finished | [34 empty] | 2019-12-08 | 2020-01-20 | 2020-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-03-15 | 2020-01-30 | Finished |  |  | 2020-01-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-05-06 | Finished |  |  | 100 | [41 empty] | 2020-05-06 | 2020-07-02 | 2020-07-02 | Finished |  |  | 2020-06-05 | 2020-07-09 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2020-06-19 | 2020-09-25 | 2020-06-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished | [6 empty] | 90 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-10-30 | Finished |  |  | 2019-10-01 | Finished | [18 empty] | 2020-01-11 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20008690 | 2019-12-16 |  |  |  | HDME000764 | 2020-01-11 | QC Passed
TFA1312-TH | HET | 61000599 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-ES-01 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-03-02 | 2020-08-15 |  | 1200SX-EN,R4.5M,D35 | SX-EN |  |  |  |  | 4500 | 2033000 | Bangkok | แขวงลาดยาว | 2020-05-09 | [20 empty] | 2020-04-10 | Finished | [14 empty] | 2020-03-02 | 2020-03-19 | 2020-03-19 | Finished | OTHERS | [13 empty] | 2020-04-03 | 2020-05-02 | [41 empty] | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-26 | Finished |  |  | 100 | 2020-04-26 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-29 | 2020-05-05 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-12 | Finished |  |  | 100 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-03-19 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-03-26 | Finished | [17 empty] | no pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008761 | 2020-02-17 |  |  |  | HDME000823 | 2020-03-19
TFA1313-TH | HET | 61000599 | Install | ยังอยู่ในสัญญา HO | - | TH209018 | Immigration Bureau | 1-ES-02 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 |  | SIRIRAT YUANGNGAM | 2019-08-15 | 2020-03-02 | 2020-08-15 |  | 1200SX-EN,R4.5M,D35 | SX-EN |  |  |  |  | 4500 | 2033000 | Bangkok | แขวงลาดยาว | 2020-05-09 | [20 empty] | 2020-04-10 | Finished | [14 empty] | 2020-03-02 | 2020-03-19 | 2020-03-19 | Finished | OTHERS | [13 empty] | 2020-02-06 | 2020-05-02 | [41 empty] | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-26 | Finished |  |  | 100 | 2020-04-26 | 2020-04-30 | 2020-04-30 | Finished |  |  | 2020-04-29 | 2020-05-02 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-08 | Finished |  |  | 100 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-17 | Finished | [18 empty] | 2020-03-19 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-03-26 | Finished | [17 empty] | no pass |  |  |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20008761 | 2020-02-17 |  |  |  | HDME000823 | 2020-03-19
TAJ0592-TH | HET | 61000602 | HO | ส่งมอบแล้ว | - | TH199247 | Saint Gabriel¦s College | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2019-09-06 | 2019-12-20 | 2020-02-05 |  | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1444500 | Bangkok | เขตดุสิต | 2020-02-05 | 2020-02-05 | Finished | [34 empty] | 2019-12-20 | 2019-12-22 | 2019-12-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-02-06 | 2020-03-07 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 2020-03-08 | 2020-03-08 | 2020-03-08 | Finished |  |  | 2020-03-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-02-27 | 2000-01-01 | 2020-02-27 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-02-27 | Finished |  |  | 100 | 2020-03-26 | Finished | CONSTRUCTION DELAY |  | 2020-02-12 | Finished |  |  | 2020-03-17 | Finished | [18 empty] | 2019-12-22 | Finished |  |  | 2019-12-22 | Finished |  |  | 2019-12-24 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Working |  | pass (defect) |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008811 | 2019-12-20 |  |  |  | HDME000756 | 2019-12-22
TAJ0593-TH | HET | 61000604 | HO | ส่งมอบแล้ว | - | TH209020 | Radar Station Doi Inthanon | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2019-09-03 | 2020-02-03 | 2020-04-03 | 2021-04-11 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 3 | 5 |  | 1519400 | Chiang Mai | อำเภอจอมทอง | 2020-12-20 | 2020-12-21 | Finished | [34 empty] | 2020-02-03 | 2020-01-30 | 2020-05-28 | Finished | PAYMENT DELAY | [13 empty] | 2020-02-05 | 2021-03-05 | 2020-02-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-03-23 | 2021-03-23 | Finished |  |  | 2021-03-22 | 2021-03-23 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | 2021-02-22 | 2021-04-28 | 2021-02-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-28 | Finished |  |  | 100 | 2021-04-30 | Finished | CUSTOMER PAYMENT DELAY |  | 2021-04-30 | Finished |  |  | 2019-09-24 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-05-20 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-05-29 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20008807 | 2020-05-07 |  |  |  | HDME000895 | 2020-05-20 | QC Passed
TAJ0594-TH | HET | 61000605 | HO | ส่งมอบแล้ว | - | TH199249 | Myst Srinakarin | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2020-02-06 | 2021-06-01 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2019-12-15 | 2020-03-24 | Finished | [34 empty] | 2019-12-06 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-25 | 2020-06-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-17 | 2000-01-01 | 2020-07-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished | [6 empty] | 90 | 2021-04-23 | Finished | CONSTRUCTION DELAY |  | 2021-04-23 | Finished |  |  | 2019-09-24 | Finished | [10 empty] | 2021-04-23 | Finished | [6 empty] | 2020-02-11 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2021-04-23 | Finished | [13 empty] | no pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20008868 | 2019-12-06 |  |  |  | HDME000788 | 2020-02-11
TAJ0595-TH | HET | 61000605 | Test | เลยสัญญา HO | - | TH199249 | Myst Srinakarin | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2020-02-06 | 2021-08-30 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2019-12-15 | 2020-03-24 | Finished | [34 empty] | 2019-12-06 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-25 | 2020-06-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-17 | 2000-01-01 | 2020-07-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-12 | Finished | [6 empty] | 90 | 2021-09-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-24 | Finished | [10 empty] | 2021-07-15 | Finished | [6 empty] | 2020-02-11 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished | [17 empty] | no pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Red |  |  | 20008868 | 2019-12-06 |  |  |  | HDME000788 | 2020-02-11
TAJ0596-TH | HET | 61000605 | HO | ส่งมอบแล้ว | - | TH199249 | Myst Srinakarin | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2020-02-06 | 2021-06-01 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2019-12-15 | 2020-03-24 | Finished | [34 empty] | 2019-12-06 | 2020-02-11 | 2020-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-25 | 2020-06-28 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-07-17 | 2000-01-01 | 2020-07-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished | [6 empty] | 90 | 2021-04-23 | Finished | CONSTRUCTION DELAY |  | 2021-04-23 | Finished |  |  | 2019-09-24 | Finished | [10 empty] | 2021-04-23 | Finished | [6 empty] | 2020-02-11 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2021-04-23 | Finished | [13 empty] | no pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20008868 | 2019-12-06 |  |  |  | HDME000788 | 2020-02-11
TAJ0597-TH | HET | 61000605 |  | ยังอยู่ในสัญญา HO | - | TH199249 | Myst Srinakarin | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2021-01-02 | 2022-08-30 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2022-11-01 | [36 empty] | 2020-10-01 | 2020-03-02 |  |  | PAYMENT DELAY | [13 empty] | 2022-11-02 | 2022-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-24 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20008868 | 2020-10-01
TAJ0598-TH | HET | 61000605 |  | ยังอยู่ในสัญญา HO | - | TH199249 | Myst Srinakarin | L5 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2021-01-02 | 2022-08-30 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2022-11-01 | [36 empty] | 2020-10-01 | 2020-01-07 |  |  | PAYMENT DELAY | [13 empty] | 2022-11-02 | 2022-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-24 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20008868 | 2020-10-01
TAJ0599-TH | HET | 61000605 |  | ยังอยู่ในสัญญา HO | - | TH199249 | Myst Srinakarin | L6 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2021-01-02 | 2022-08-30 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2022-11-01 | [36 empty] | 2020-10-01 | 2020-01-07 |  |  | PAYMENT DELAY | [13 empty] | 2022-11-02 | 2022-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-24 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20008868 | 2020-10-01
TAJ0600-TH | HET | 61000605 |  | ยังอยู่ในสัญญา HO | - | TH199249 | Myst Srinakarin | L7 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2021-01-02 | 2022-08-30 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2022-11-01 | [36 empty] | 2020-10-01 | 2020-04-08 |  |  | PAYMENT DELAY | [13 empty] | 2022-11-02 | 2022-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-24 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20008868 | 2020-10-01
TAJ0601-TH | HET | 61000605 |  | ยังอยู่ในสัญญา HO | - | TH199249 | Myst Srinakarin | L8 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2021-01-02 | 2022-08-30 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2022-11-01 | [36 empty] | 2020-10-01 | 2020-04-10 |  |  | PAYMENT DELAY | [13 empty] | 2022-11-02 | 2022-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-24 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20008868 | 2020-10-01
TAJ0602-TH | HET | 61000605 |  | ยังอยู่ในสัญญา HO | - | TH199249 | Myst Srinakarin | L9 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2019-09-06 | 2019-12-06 | 2021-01-02 | 2022-08-30 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 994444.45 | Bangkok | แขวงสวนหลวง | 2022-11-01 | [36 empty] | 2020-10-01 | 2020-04-10 |  |  | PAYMENT DELAY | [13 empty] | 2022-11-02 | 2022-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-12-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-12-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-09-24 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20008868 | 2020-10-01
TAJ0604-TH | HET | 61000607 | HO | ส่งมอบแล้ว | - | TH199251 | Chachoengsao Provincial Court | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-07-17 | 2020-02-11 | 2020-04-11 | 2020-06-15 | P-1000-CO60W1,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1519400 | Chachoengsao | อำเภอเมืองฉะเชิงเทรา | 2020-06-30 | 2020-06-30 | Finished | [34 empty] | 2020-02-11 | 2020-02-21 | 2020-02-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-15 | 2020-06-10 | 2020-06-05 | Finished |  |  | 2020-06-07 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | [41 empty] | 2020-06-24 | 2020-07-04 | 2020-07-04 | Finished |  |  | 2020-04-22 | 2020-07-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-01-05 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2019-09-25 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20008869 | 2020-02-11 |  |  |  | HDME000800 | 2020-02-21 | QC Passed
TEB0112-TH | HET | 61000608 | HO | เลยสัญญา HO | - | TH199252 | Home Thanayathorn | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-09-06 | 2020-04-13 | 2020-04-29 | 2020-08-05 | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 3 | 3 |  | 800000 | Bangkok | แขวงแสมดำ | 2020-08-17 | 2020-11-13 | Finished | [34 empty] | 2020-03-24 | 2020-04-16 | 2020-04-16 | Finished | STORE AREA | [13 empty] | 2020-08-18 | 2020-08-28 | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 100 | [41 empty] | 2020-11-15 | 1900-01-01 | 2020-11-15 | Waiting | POWER SUPPLY DELAY |  | 2021-09-14 | [12 empty] | 0 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished | [14 empty] | 25 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-31 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-04-16 | Finished |  |  | 2020-04-17 | Finished |  |  | 2020-04-21 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 4 | 16 | 75 | 70.82 | Red |  |  | 20010850 | 2020-03-27 |  |  |  | HDME000848 | 2020-04-16
TAJ0605-TH | HET | 61000610 | HO | ส่งมอบแล้ว | - | TH199254 | ALT Silom | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-02-16 | 2020-06-16 | 2021-02-18 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 920000 | Bangkok | เขตบางรัก | 2020-01-31 | 2020-03-04 | Finished | [34 empty] | 2020-02-16 | 2020-02-26 | 2020-02-26 | Finished | STORE AREA | [13 empty] | 2020-03-03 | 2020-03-20 | 2020-03-04 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-03-20 | Finished |  |  | 100 | [41 empty] | 2020-03-20 | 2020-07-22 | 2020-07-22 | Finished |  |  | 2020-07-23 | 2020-07-24 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | 2021-05-13 | 2021-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-04 | Finished | [6 empty] | 90 | 2020-11-21 | Finished | CONSTRUCTION DELAY |  | 2020-12-28 | Finished |  |  | 2019-10-08 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20008896 | 2020-02-16 |  |  |  | HDME000792 | 2020-02-18 | QC Passed
TAJ0606-TH | HET | 61000610 | HO | ส่งมอบแล้ว | - | TH199254 | ALT Silom | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-02-16 | 2020-06-16 | 2021-02-18 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 920000 | Bangkok | เขตบางรัก | 2020-01-31 | 2020-03-04 | Finished | [34 empty] | 2020-02-16 | 2020-02-26 | 2020-02-26 | Finished | STORE AREA | [13 empty] | 2020-03-03 | 2020-03-20 | 2020-03-04 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-03-20 | Finished |  |  | 100 | [41 empty] | 2020-03-20 | 2020-07-22 | 2020-07-22 | Finished |  |  | 2020-07-23 | 2020-07-24 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | 2021-05-13 | 2021-01-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-04 | Finished | [6 empty] | 90 | 2020-11-21 | Finished | CONSTRUCTION DELAY |  | 2020-12-28 | Finished |  |  | 2019-10-08 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20008896 | 2020-02-16 |  |  |  | HDME000792 | 2020-02-18 | QC Passed
TAJ0607-TH | HET | 61000610 | HO | ส่งมอบแล้ว | - | TH199254 | ALT Silom | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-02-16 | 2020-06-16 | 2020-12-18 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 920000 | Bangkok | เขตบางรัก | 2020-03-25 | [36 empty] | 2020-02-16 | 2020-02-26 | 2020-02-26 | Finished | STORE AREA | [13 empty] | 2020-03-27 | 2020-04-05 | 2020-05-17 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 100 | [41 empty] | 2020-05-27 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-07-30 | 2020-08-03 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-09 | Finished |  |  | 100 | 2021-05-13 | 2021-01-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-25 | Finished | [6 empty] | 90 | 2020-11-21 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2019-10-08 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  | pass | 2021-02-16 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20008896 | 2020-02-16 |  |  |  | HDME000792 | 2020-02-18 | QC Passed
TAJ0608-TH | HET | 61000610 | HO | ส่งมอบแล้ว | - | TH199254 | ALT Silom | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-02-16 | 2020-06-16 | 2020-12-18 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 920000 | Bangkok | เขตบางรัก | 2020-03-25 | [36 empty] | 2020-02-16 | 2020-02-26 | 2020-02-26 | Finished | STORE AREA | [13 empty] | 2020-03-27 | 2020-04-05 | 2020-05-17 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 100 | [41 empty] | 2020-05-27 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-07-30 | 2020-08-03 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-09 | Finished |  |  | 100 | 2021-05-13 | 2021-01-25 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-25 | Finished | [6 empty] | 90 | 2020-11-21 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2019-10-08 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  | pass | 2021-02-16 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20008896 | 2020-02-16 |  |  |  | HDME000792 | 2020-02-18 | QC Passed
TAJ0609-TH | HET | 61000610 | HO | ส่งมอบแล้ว | - | TH199254 | ALT Silom | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-02-16 | 2020-06-16 | 2021-02-18 | P-750-CO105,105S/7F | UAG-SN1 | 750 | 105 | 7 | 7 |  | 980000 | Bangkok | เขตบางรัก | 2020-01-31 | 2020-03-23 | Finished | [34 empty] | 2020-02-16 | 2020-03-15 | 2020-03-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-22 | 2020-04-11 | 2020-03-24 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-07 | Finished |  |  | 100 | [41 empty] | 2020-04-07 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-07-28 | 2020-08-05 | Finished |  |  | 2020-08-09 | Finished |  |  | 2020-08-11 | Finished |  |  | 100 | 2021-05-13 | 2021-02-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished | [6 empty] | 90 | 2020-11-21 | Finished | CONSTRUCTION DELAY |  | 2021-01-27 | Finished |  |  | 2019-10-08 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  | pass | 2021-02-16 | Finished |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 1 | 1 | 99.84 | Blue |  |  | 20008896 | 2020-03-16 |  |  |  | HDME000820 | 2020-03-16 | QC Passed
TAJ0610-TH | HET | 61000610 | HO | ส่งมอบแล้ว | - | TH199254 | ALT Silom | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-02-16 | 2020-06-16 | 2021-02-18 | P-750-CO105,105S/7F | UAG-SN1 | 750 | 105 | 7 | 7 |  | 980000 | Bangkok | เขตบางรัก | 2020-01-31 | 2020-03-23 | Finished | [34 empty] | 2020-02-16 | 2020-03-15 | 2020-03-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-22 | 2020-04-11 | 2020-03-24 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-07 | Finished |  |  | 100 | [41 empty] | 2020-04-07 | 2020-08-01 | 2020-08-01 | Finished |  |  | 2020-07-28 | 2020-08-05 | Finished |  |  | 2020-08-09 | Finished |  |  | 2020-08-11 | Finished |  |  | 100 | 2021-05-13 | 2021-02-03 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished | [6 empty] | 90 | 2020-11-21 | Finished | CONSTRUCTION DELAY |  | 2021-01-27 | Finished |  |  | 2019-10-08 | Finished | [10 empty] | 2021-02-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-26 | Finished |  |  | 2020-02-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  | pass | 2021-02-16 | Finished |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 1 | 1 | 99.84 | Blue |  |  | 20008896 | 2020-03-16 |  |  |  | HDME000820 | 2020-03-16 | QC Passed
TBL0218-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | CP1 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | OUG-1000-CO105,105S/9F | OUG-ON1 | 1000 | 105 | 9 | 9 |  | 1605000 | Bangkok | ถนนเพลินจิต | 2020-04-30 | 2020-07-22 | Finished | [34 empty] | 2020-03-04 | 2020-03-15 | 2020-03-15 | Finished | OTHERS | [13 empty] | 2020-05-25 | 2020-10-01 | 2020-08-01 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-11-13 | Finished |  |  | 100 | [41 empty] | 2020-11-13 | 2020-11-12 | 2020-11-12 | Finished |  |  | 2020-10-30 | 2020-11-12 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-17 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-14 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-26 | Finished | [22 empty] | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 6 | 16 | 22 | 97.35 | Green |  |  | 20009019 | 2020-03-04 |  |  |  | HDME000818 | 2020-03-14
TBL0219-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | CP2 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | OUG-1000-CO105,105S/9F | OUG-ON1 | 1000 | 105 | 9 | 9 |  | 1605000 | Bangkok | ถนนเพลินจิต | 2020-04-30 | 2020-07-22 | Finished | [34 empty] | 2020-03-04 | 2020-03-15 | 2020-03-15 | Finished | OTHERS | [13 empty] | 2020-05-25 | 2020-10-01 | 2020-08-01 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-11-13 | Finished |  |  | 100 | [41 empty] | 2020-11-13 | 2020-11-13 | 2020-11-13 | Finished |  |  | 2020-10-30 | 2020-11-13 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-19 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-14 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-26 | Finished | [22 empty] | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 6 | 16 | 22 | 97.35 | Green |  |  | 20009019 | 2020-03-04 |  |  |  | HDME000818 | 2020-03-14
TAC1677-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | FL (Building A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 3049500 | Bangkok | ถนนเพลินจิต | 2020-06-10 | 2020-08-20 | Finished | [34 empty] | 2020-03-04 | 2020-03-14 | 2020-03-14 | Finished | OTHERS | [13 empty] | 2020-05-25 | 2020-10-20 | 2020-08-04 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-11-13 | Finished |  |  | 100 | [41 empty] | 2020-11-13 | 2020-11-11 | 2020-11-11 | Finished |  |  | 2020-10-30 | 2020-11-11 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-20 | Finished |  |  | 100 | 2021-01-21 | 2000-01-01 | 2021-01-21 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-14 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-26 | Finished | [22 empty] | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 10 | 24 | 34 | 97.78 | Green |  |  | 20009019 | 2020-03-04 |  |  |  | HDME000818 | 2020-03-14
TBK0176-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | FL (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | HVF-1600-CO180,180S/31F | HVF-5 | 1600 | 180 | 31 | 31 |  | 5617500 | Bangkok | ถนนเพลินจิต | 2020-10-10 | 2020-10-28 | Finished | [34 empty] | 2020-07-25 | 2020-03-10 | 2020-10-24 | Finished | STORE AREA | [13 empty] | 2020-10-01 | 2020-12-01 | 2020-11-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-19 | Finished |  |  | 2021-01-15 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-27 | Finished |  |  | 2020-12-27 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-30 | Finished |  |  | 100 | [41 empty] | 2020-12-30 | 2020-12-21 | 2020-12-21 | Finished |  |  | 2021-03-27 | 2020-12-30 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-15 | Finished |  |  | 100 | 2020-02-04 | 2000-01-01 | 2020-02-04 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-12-19 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-22 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 16 | 32 | 48 | 97.7 | Green |  |  | 20009019 | 2020-07-25 |  |  |  | HDME001073 | 2020-12-19
TBK0173-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | H1 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | HVF-1600-CO240,240S/24F | HVF-5 | 1600 | 240 | 12 | 24 |  | 5470642.33 | Bangkok | ถนนเพลินจิต | 2020-10-30 | 2021-02-13 | Finished | [34 empty] | 2020-07-25 | 2020-03-10 | 2020-11-15 | Finished | STORE AREA | [13 empty] | 2020-10-15 | 2020-12-20 | 2021-02-15 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 2021-04-21 | 2021-04-21 | Finished |  |  | 2021-03-27 | 2021-05-07 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-11-17 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-22 | Finished | [22 empty] | 1535 | 111 | 48 | 24 | 1718 | 0 | 0 | 12 | 24 | 36 | 97.9 | Green |  |  | 20009019 | 2020-07-25 |  |  |  | HDME001036 | 2020-11-17
TBK0174-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | H2 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | HVF-1600-CO240,240S/24F | HVF-5 | 1600 | 240 | 12 | 24 |  | 5470642.33 | Bangkok | ถนนเพลินจิต | 2020-10-30 | 2021-02-13 | Finished | [34 empty] | 2020-07-25 | 2020-03-10 | 2020-11-15 | Finished | STORE AREA | [13 empty] | 2020-10-15 | 2020-12-20 | 2021-02-15 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 2021-04-21 | 2021-04-21 | Finished |  |  | 2021-03-27 | 2021-05-07 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-06-04 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-11-17 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-22 | Finished | [22 empty] | 1535 | 111 | 48 | 24 | 1718 | 0 | 0 | 12 | 24 | 36 | 97.9 | Green |  |  | 20009019 | 2020-07-25 |  |  |  | HDME001036 | 2020-11-17
TBK0175-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | H3 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | HVF-1600-CO240,240S/24F | HVF-5 | 1600 | 240 | 12 | 24 |  | 5470642.33 | Bangkok | ถนนเพลินจิต | 2020-10-30 | 2020-12-04 | Finished | [34 empty] | 2020-07-25 | 2020-03-10 | 2020-11-15 | Finished | STORE AREA | [13 empty] | 2020-10-15 | 2020-12-20 | 2021-01-05 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | [41 empty] | 2021-02-04 | 2021-03-01 | 2021-03-01 | Finished |  |  | 2021-03-27 | 2021-03-05 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-11-17 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-22 | Finished | [22 empty] | 1535 | 111 | 48 | 24 | 1718 | 0 | 0 | 12 | 24 | 36 | 97.9 | Green |  |  | 20009019 | 2020-07-25 |  |  |  | HDME001036 | 2020-11-17
TAC1675-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | L1 (Building A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | VFI-1000-CO150,150S/14F | VFI-II | 1000 | 150 | 14 | 14 |  | 2889000 | Bangkok | ถนนเพลินจิต | 2020-04-30 | 2020-07-22 | Finished | [34 empty] | 2020-03-04 | 2020-03-14 | 2020-03-14 | Finished | OTHERS | [13 empty] | 2020-05-25 | 2020-10-01 | 2020-08-04 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 100 | [41 empty] | 2020-11-14 | 2020-11-09 | 2020-11-09 | Finished |  |  | 2020-10-30 | 2020-11-09 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-16 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-14 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-26 | Finished | [22 empty] | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 8 | 20 | 28 | 97.64 | Green |  |  | 20009019 | 2020-03-04 |  |  |  | HDME000818 | 2020-03-14
TBK0170-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | L1(Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | HVF-1600-CO240,240S/17F | HVF-5 | 1600 | 240 | 15 | 17 |  | 5513442.67 | Bangkok | ถนนเพลินจิต | 2020-08-15 | 2020-09-08 | Finished | [34 empty] | 2020-06-07 | 2020-02-23 | 2020-09-10 | Finished | STORE AREA | [13 empty] | 2020-08-16 | 2020-10-16 | 2020-09-23 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | [41 empty] | 2020-11-08 | 2020-10-25 | 2020-10-25 | Finished |  |  | 2020-12-10 | 2020-10-25 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-09 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-10-01 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished | [22 empty] | 1192 | 98 | 40 | 20 | 1350 | 0 | 0 | 10 | 20 | 30 | 97.78 | Green |  |  | 20009019 | 2020-07-07 |  |  |  | HDME000997 | 2020-10-01
TAC1676-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | L2 (Building A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | VFI-1000-CO150,150S/14F | VFI-II | 1000 | 150 | 14 | 14 |  | 2889000 | Bangkok | ถนนเพลินจิต | 2020-04-30 | 2020-07-22 | Finished | [34 empty] | 2020-03-04 | 2020-03-14 | 2020-03-14 | Finished | OTHERS | [13 empty] | 2020-05-25 | 2020-10-01 | 2020-08-04 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 100 | [41 empty] | 2020-11-14 | 2020-11-10 | 2020-11-10 | Finished |  |  | 2020-10-30 | 2020-11-10 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-18 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-03-14 | Finished |  |  | 2020-03-23 | Finished |  |  | 2020-03-26 | Finished | [22 empty] | 1025 | 108 | 32 | 20 | 1185 | 0 | 0 | 32 | 20 | 52 | 95.61 | Green |  |  | 20009019 | 2020-03-04 |  |  |  | HDME000818 | 2020-03-14
TBK0171-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | L2 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | HVF-1600-CO240,240S/17F | HVF-5 | 1600 | 240 | 15 | 17 |  | 5513442.67 | Bangkok | ถนนเพลินจิต | 2020-08-15 | 2020-09-08 | Finished | [34 empty] | 2020-06-07 | 2020-02-23 | 2020-09-10 | Finished | STORE AREA | [13 empty] | 2020-08-16 | 2020-10-16 | 2020-09-23 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | [41 empty] | 2020-11-08 | 2020-10-26 | 2020-10-26 | Finished |  |  | 2020-12-10 | 2020-11-26 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-09 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-10-01 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished | [22 empty] | 1192 | 98 | 40 | 20 | 1350 | 0 | 0 | 10 | 20 | 30 | 97.78 | Green |  |  | 20009019 | 2020-07-07 |  |  |  | HDME000997 | 2020-10-01
TBK0172-TH | HET | 61000612 | Test | ยังอยู่ในสัญญา HO | - | TH209013 | Vanissa Building | L3 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | SORAWIT WANITCHAPAK | 2019-08-08 | 2020-03-04 | 2020-11-15 | 2021-11-30 | HVF-1600-CO240,240S/17F | HVF-5 | 1600 | 240 | 15 | 17 |  | 5513442.67 | Bangkok | ถนนเพลินจิต | 2020-08-15 | 2020-09-08 | Finished | [34 empty] | 2020-06-07 | 2020-03-20 | 2020-09-10 | Finished | STORE AREA | [13 empty] | 2020-08-16 | 2020-10-16 | 2020-09-23 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | [41 empty] | 2020-11-08 | 2020-11-27 | 2020-11-27 | Finished |  |  | 2020-12-10 | 2020-11-27 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-11 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-11-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-12 | Finished | [18 empty] | 2020-10-01 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished | [22 empty] | 1192 | 98 | 40 | 20 | 1350 | 0 | 0 | 10 | 20 | 30 | 97.78 | Green |  |  | 20009019 | 2020-07-07 |  |  |  | HDME000997 | 2020-10-01
TAJ0611-TH | HET | 61000613 | HO | ส่งมอบแล้ว | - | TH199250 | องค์การพิพิธภัณฑ์วิทยาศาสตร์แห่งชาติ (อพวช.) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | CHALERMKHUAN KERDPOOM | 2019-09-09 | 2019-12-24 | 2020-04-24 | 2020-07-06 | P-1600-CO60,60S/2F | UAG-SN1 | 1600 | 60 | 2 | 2 |  | 2390000 | Pathum Thani | อำเภอคลองหลวง | 2020-01-10 | 2020-01-10 | Finished | [34 empty] | 2019-12-24 | 2019-12-18 | 2019-12-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-14 | 2020-03-10 | 2019-12-27 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-13 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-19 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-08 | Finished |  |  | 100 | [41 empty] | 2020-02-08 | 2020-04-15 | 2020-04-15 | Finished |  |  | 2020-04-15 | 2020-04-23 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-07-10 | 2020-11-27 | 2020-07-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-11-27 | Finished |  |  | 100 | 2020-09-14 | Finished | CUSTOMER DECORATION DELAY |  | 2020-09-29 | Finished |  |  | 2019-10-15 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2019-12-18 | Finished |  |  | 2019-12-18 | Finished |  |  | 2019-12-18 | Finished |  |  | 2020-09-29 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009020 | 2019-12-24 | [5 empty] | QC Passed
TAJ0612-TH | HET | 61000613 | HO | ส่งมอบแล้ว | - | TH199250 | องค์การพิพิธภัณฑ์วิทยาศาสตร์แห่งชาติ (อพวช.) | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | CHALERMKHUAN KERDPOOM | 2019-09-09 | 2019-12-24 | 2020-04-24 | 2020-07-06 | P-1600-CO60,60S/2F | UAG-SN1 | 1600 | 60 | 2 | 2 |  | 2390000 | Pathum Thani | อำเภอคลองหลวง | 2020-01-10 | 2020-01-10 | Finished | [34 empty] | 2019-12-24 | 2019-12-18 | 2019-12-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-14 | 2020-03-10 | 2019-12-27 | Finished |  |  | 2020-01-09 | Finished |  |  | 2020-01-13 | Finished |  |  | 2020-01-17 | Finished |  |  | 2020-01-19 | Finished |  |  | 2020-01-23 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-01-27 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-08 | Finished |  |  | 100 | [41 empty] | 2020-02-08 | 2020-04-15 | 2020-04-15 | Finished |  |  | 2020-04-15 | 2020-04-23 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-07-10 | 2020-11-27 | 2020-07-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-11-27 | Finished |  |  | 100 | 2020-09-14 | Finished | CUSTOMER DECORATION DELAY |  | 2020-09-29 | Finished |  |  | 2019-10-15 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2019-12-18 | Finished |  |  | 2019-12-18 | Finished |  |  | 2019-12-18 | Finished |  |  | 2020-09-29 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009020 | 2019-12-24 | [5 empty] | QC Passed
TBL0220-TH | HET | 61000613 | HO | ส่งมอบแล้ว | - | TH199250 | องค์การพิพิธภัณฑ์วิทยาศาสตร์แห่งชาติ (อพวช.) | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | CHALERMKHUAN KERDPOOM | 2019-09-09 | 2019-12-24 | 2020-04-24 | 2020-07-06 | OUG-1600-CO60,60S/2F | OUG-ON1 | 1600 | 60 | 2 | 2 |  | 2390000 | Pathum Thani | อำเภอคลองหลวง | 2020-01-10 | 2020-01-10 | Finished | [34 empty] | 2019-12-24 | 2020-02-03 | 2020-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-04-10 | 2020-01-28 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-17 | Finished |  |  | 100 | [41 empty] | 2020-03-17 | 2020-04-15 | 2020-04-15 | Finished |  |  | 2020-04-15 | 2020-04-23 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-30 | Finished | [6 empty] | 90 | 2020-09-14 | Finished | CUSTOMER DECORATION DELAY |  | 2020-09-29 | Finished |  |  | 2019-10-15 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2020-02-03 | Finished |  |  | 2020-02-03 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-09-29 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 1 | 1 | 99.78 | Blue |  |  | 20009020 | 2020-02-14 |  |  |  | HDME000781 | 2020-02-03 | QC Passed
TBL0221-TH | HET | 61000613 | HO | ส่งมอบแล้ว | - | TH199250 | องค์การพิพิธภัณฑ์วิทยาศาสตร์แห่งชาติ (อพวช.) | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | CHALERMKHUAN KERDPOOM | 2019-09-09 | 2019-12-24 | 2020-04-24 | 2020-07-06 | OUG-1600-CO60,60S/2F | OUG-ON1 | 1600 | 60 | 2 | 2 |  | 2390000 | Pathum Thani | อำเภอคลองหลวง | 2020-01-10 | 2020-01-10 | Finished | [34 empty] | 2019-12-24 | 2020-02-03 | 2020-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-15 | 2020-04-10 | 2020-01-28 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-09 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-27 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-17 | Finished |  |  | 100 | [41 empty] | 2020-03-17 | 2020-04-15 | 2020-04-15 | Finished |  |  | 2020-04-15 | 2020-04-23 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-29 | Finished |  |  | 100 | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-30 | Finished | [6 empty] | 90 | 2020-09-14 | Finished | CUSTOMER DECORATION DELAY |  | 2020-09-29 | Finished |  |  | 2019-10-15 | Finished | [10 empty] | 2020-07-30 | Finished | [6 empty] | 2020-02-03 | Finished |  |  | 2020-02-03 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-09-29 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 1 | 1 | 99.78 | Blue |  |  | 20009020 | 2020-02-14 |  |  |  | HDME000781 | 2020-02-03 | QC Passed
TEB0113-TH | HET | 61000614 | HO | ส่งมอบแล้ว | - | TH199255 | Home Khun Kritsada | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-09-23 | 2019-12-23 | 2020-02-07 | 2020-06-10 | P3-200-2S20 (SED200S),RM,D | P3 |  |  | 2 | 2 |  | 900000 | Bangkok | แขวงบางกะปิ เขตห้วยขวาง | 2020-02-15 | 2020-02-15 | Finished | [34 empty] | 2019-12-23 | 2020-01-28 | 2020-01-28 | Finished | PAYMENT DELAY | [13 empty] | 2020-02-15 | 2020-02-25 | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-21 | Finished |  |  | 100 | [41 empty] | 2020-02-21 | 2020-06-17 | 2020-06-17 | Finished |  |  | 2020-06-20 | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-17 | Finished |  |  | 100 | 2020-06-26 | 2021-06-01 | 2020-06-26 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-01 | Finished | [6 empty] | 90 | 2020-11-15 | Finished | POWER SUPPLY DELAY |  | 2021-06-10 | Finished |  |  | 2019-10-08 | Finished | [10 empty] | 2021-06-10 | Finished | [6 empty] | 2020-01-28 | Finished |  |  | 2020-01-28 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  | pass | 2021-07-08 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20009018 | 2019-12-23 |  |  |  | HDME000777 | 2020-01-28 | QC Passed
TAC1678-TH | HET | 61000616 | HO | ส่งมอบแล้ว | - | TH199256 | Samsen Wittayalai School | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-01-31 | 2020-03-31 | 2020-09-30 | VFI-1000-CO60,60S/6F | VFI-II | 1000 | 60 | 6 | 6 |  | 1100000 | Bangkok | เขตพญาไท | 2020-05-20 | 2020-05-20 | Finished | [34 empty] | 2020-01-31 | 2020-04-23 | 2020-04-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-21 | 2020-06-10 | 2020-05-22 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-02 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-10 | Finished |  |  | 100 | [41 empty] | 2020-06-10 | 2020-08-14 | 2020-08-14 | Finished |  |  | 2020-08-14 | 2020-08-15 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-17 | Finished |  |  | 100 | 2020-09-15 | 2020-09-15 | 2020-09-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-15 | Finished | [6 empty] | 90 | 2020-08-20 | Finished | POWER SUPPLY DELAY |  | 2020-09-03 | Finished |  |  | 2019-10-15 | Finished | [10 empty] | 2021-03-15 | Finished | [6 empty] | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-09-03 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 1 | 1 | 99.86 | Blue |  |  | 20009089 | 2020-03-31 |  |  |  | HDME000859 | 2020-04-23 | QC Passed
TAC1679-TH | HET | 61000616 | HO | ส่งมอบแล้ว | - | TH199256 | Samsen Wittayalai School | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-09-16 | 2020-01-31 | 2020-03-31 | 2020-09-30 | VFI-1000-CO60,60S/6F | VFI-II | 1000 | 60 | 6 | 6 |  | 1100000 | Bangkok | เขตพญาไท | 2020-05-20 | 2020-05-20 | Finished | [34 empty] | 2020-01-31 | 2020-04-23 | 2020-04-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-21 | 2020-06-10 | 2020-05-22 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-02 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-10 | Finished |  |  | 100 | [41 empty] | 2020-06-10 | 2020-08-14 | 2020-08-14 | Finished |  |  | 2020-08-14 | 2020-08-15 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-17 | Finished |  |  | 100 | 2020-09-15 | 2021-01-25 | 2020-09-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-15 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | 2020-08-20 | Finished | POWER SUPPLY DELAY |  | 2020-09-03 | Finished |  |  | 2019-10-15 | Finished | [10 empty] | 2021-03-15 | Finished | [6 empty] | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-09-03 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009089 | 2020-03-31 |  |  |  | HDME000859 | 2020-04-23 | QC Passed
TFA1315-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | 1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 6 |  | 1 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | 1200TX-EN,R3.6M,D35 | TX-EN |  |  |  |  | 3600 | 963000 | Bangkok | เขตบางกะปิ | 2020-02-01 | [20 empty] | 2020-03-05 | Finished | [14 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-30 | 2020-05-28 | [41 empty] | 2020-03-05 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | 2020-07-09 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-09 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | CONTRACT CANCELLATION |  | 2021-04-30 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no pass |  |  |  |  | 482 | 32 | 16 | 14 | 544 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20009091 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30
TFA1316-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | 2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 6 |  | 1 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | 1200TX-EN,R3.6M,D35 | TX-EN |  |  |  |  | 3600 | 963000 | Bangkok | เขตบางกะปิ | 2020-02-01 | [20 empty] | 2020-03-05 | Finished | [14 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-30 | 2020-05-28 | [41 empty] | 2020-03-05 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | 2020-07-09 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-09 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | OTHERS |  | 2021-04-30 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no pass |  |  |  |  | 482 | 32 | 16 | 14 | 544 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20009091 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30
TFA1317-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | 3 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 6 |  | 1 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | 1200TX-EN,R3.6M,D35 | TX-EN |  |  |  |  | 3600 | 963000 | Bangkok | เขตบางกะปิ | 2020-04-20 | [20 empty] | 2020-04-15 | Finished | [14 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-28 | [41 empty] | 2020-04-20 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | 2020-07-09 | 2020-05-10 | 2020-05-10 | Finished |  |  | 2020-05-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-09 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no pass |  |  |  |  | 482 | 32 | 16 | 14 | 544 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20009091 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30
TFA1318-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | 4 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 6 |  | 1 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | 1200TX-EN,R3.6M,D35 | TX-EN |  |  |  |  | 3600 | 963000 | Bangkok | เขตบางกะปิ | 2020-04-20 | [20 empty] | 2020-04-15 | Finished | [14 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-28 | [41 empty] | 2020-04-20 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | 2020-07-09 | 2020-05-10 | 2020-05-10 | Finished |  |  | 2020-05-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-09 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no pass |  |  |  |  | 482 | 32 | 16 | 14 | 544 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20009091 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30
TFA1319-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | 5 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 6 |  | 1 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | 1200TX-EN,R4.25M,D35 | TX-EN |  |  |  |  | 4250 | 995100 | Bangkok | เขตบางกะปิ | 2020-02-01 | [20 empty] | 2020-03-05 | Finished | [14 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-30 | 2020-05-28 | [41 empty] | 2020-03-06 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-15 | Finished |  |  | 2020-03-17 | Finished |  |  | 100 | 2020-03-17 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-09 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no pass |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20009091 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30
TFA1320-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | 6 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 6 |  | 1 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | 1200TX-EN,R4.25M,D35 | TX-EN |  |  |  |  | 4250 | 995100 | Bangkok | เขตบางกะปิ | 2020-02-01 | [20 empty] | 2020-03-05 | Finished | [14 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-30 | 2020-05-28 | [41 empty] | 2020-03-06 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-15 | Finished |  |  | 2020-03-17 | Finished |  |  | 100 | 2020-03-17 | 2020-04-20 | 2020-04-20 | Finished |  |  | 2020-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-09 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no pass |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20009091 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30
TAK0614-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | E01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | B-1000-2S60,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1284000 | Bangkok | เขตบางกะปิ | 2020-03-31 | 2020-04-03 | Finished | [34 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-15 | 2020-04-20 | 2020-04-14 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-09 | Finished |  |  | 100 | [41 empty] | 2020-05-09 | 2020-07-17 | 2020-07-17 | Finished |  |  | 2020-05-15 | 2020-07-19 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-26 | Finished |  |  | 100 | 2021-02-01 | 2021-01-29 | 2021-02-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2021-12-28 | Finished | CONSTRUCTION DELAY |  | 2021-02-05 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-02-05 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009869 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30 | QC Passed
TAK0615-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | E02 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | B-1000-2S60,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1284000 | Bangkok | เขตบางกะปิ | 2020-03-31 | 2020-04-03 | Finished | [34 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-15 | 2020-04-20 | 2020-04-14 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-18 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-09 | Finished |  |  | 100 | [41 empty] | 2020-05-09 | 2020-07-17 | 2020-07-17 | Finished |  |  | 2020-05-15 | 2020-07-19 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-26 | Finished |  |  | 100 | 2021-02-01 | 2021-01-29 | 2021-02-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2021-12-28 | Finished | CONSTRUCTION DELAY |  | 2021-02-05 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-02-05 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009869 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30 | QC Passed
TAK0616-TH | HET | 61000619 | HO | ส่งมอบแล้ว | - | TH199259 | King of Bone | E03 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-09-30 | 2020-01-30 | 2020-04-30 | 2020-09-02 | B-750-2S60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1219800 | Bangkok | เขตบางกะปิ | 2020-05-12 | [36 empty] | 2020-01-30 | 2020-01-30 | 2020-01-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-15 | 2020-04-20 | 2020-06-02 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-26 | Finished |  |  | 100 | [41 empty] | 2020-06-26 | 2020-05-15 | 2020-05-15 | Finished |  |  | 2020-05-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-01 | 2021-02-01 | 2021-02-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-02-01 | Finished |  |  | 100 | 2021-01-20 | Finished | CONSTRUCTION DELAY |  | 2021-02-05 | Finished |  |  | 2019-10-22 | Finished | [10 empty] | 2021-02-05 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009869 | 2020-01-30 |  |  |  | HDME000778 | 2020-01-30 | QC Passed
TAJ0619-TH | HET | 61000623 | HO | ยังอยู่ในสัญญา HO | - | TH209024 | Home Khun Nattawut | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-10-15 | 2020-02-15 | 2020-04-15 | 2021-10-01 | P-600-CO60D,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 1250000 | Si Sa Ket | อำเภอราษีไศล | 2020-09-15 | 2020-04-15 | Finished | [34 empty] | 2020-02-15 | 2020-02-19 | 2020-02-19 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-15 | 2020-10-15 | 2021-04-30 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-24 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-02-19 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-21 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 4 | 16 | 101 | 78.83 | Orange |  |  | 20009315 | 2020-02-15 |  |  |  | HDME000795 | 2020-02-19
TAJ0620-TH | HET | 61000624 |  | ยังอยู่ในสัญญา HO | - | TH219001 | Wat Saen Suk @Min Buri | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | APHIRADA BUNKUEA | 2019-10-01 | 2021-05-01 | 2021-06-01 | 2021-10-10 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 1241200 | Bangkok | แขวงมีนบุรี | 2021-10-30 | [36 empty] | 2021-04-30 | 2021-10-10 | 2021-05-05 | Finished | STORE AREA | [13 empty] | 2021-10-30 | 2021-11-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-24 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-08 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Orange |  |  | 20009216 | 2021-04-30 |  |  |  | HDME001205 | 2021-05-05
TFA1321-TH | HET | 61000625 | Test | เลยสัญญา HO | - | TH209023 | Vajira Hospital (Academic Building) | ESC1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-03-01 | 2020-07-30 | 2021-08-30 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 1016500 | Bangkok | แขวงวชิรพยาบาล | 2020-07-29 | [20 empty] | 2020-04-01 | Finished | [14 empty] | 2020-02-28 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-01 | 2020-09-02 | [41 empty] | 2020-04-01 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-13 | Finished |  |  | 2020-09-14 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-21 | Finished |  |  | 100 | 2020-09-21 | 1900-01-01 | 2020-09-21 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | 2020-10-27 | 2000-01-01 | 2020-10-27 | Finished | [14 empty] | 25 | 2021-11-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-30 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-03-24 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Red |  |  | 20009214 | 2020-02-28 |  |  |  | HDME000829 | 2020-03-24
TFA1322-TH | HET | 61000625 | Test | เลยสัญญา HO | - | TH209023 | Vajira Hospital (Academic Building) | ESC2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-03-01 | 2020-07-30 | 2021-08-30 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 1016500 | Bangkok | แขวงวชิรพยาบาล | 2020-07-29 | [20 empty] | 2020-04-01 | Finished | [14 empty] | 2020-02-28 | 2020-03-31 | 2020-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-01 | 2020-09-02 | [41 empty] | 2020-04-01 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-13 | Finished |  |  | 2020-09-14 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-21 | Finished |  |  | 100 | 2020-09-21 | 1900-01-01 | 2020-09-21 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | 2020-10-27 | 2000-01-01 | 2020-10-27 | Finished | [14 empty] | 25 | 2021-11-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-10-30 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-03-24 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Red |  |  | 20009214 | 2020-02-28 |  |  |  | HDME000829 | 2020-03-24
TBL0222-TH | HET | 61000625 | HO | ส่งมอบแล้ว | - | TH209023 | Vajira Hospital (Academic Building) | A-PL-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-03-01 | 2020-07-30 | 2021-08-30 | OUG-1600-2S105,105S/10F | OUG-ON1 | 1600 | 105 | 10 | 10 |  | 2140000 | Bangkok | แขวงวชิรพยาบาล | 2020-08-29 | 2020-12-11 | Finished | [34 empty] | 2020-02-28 | 2020-03-02 | 2020-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-11 | 2021-01-15 | 2020-12-13 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-01-01 | Finished |  |  | 2021-01-02 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 100 | [41 empty] | 2021-01-15 | 2021-05-21 | 2021-05-21 | Finished |  |  | 2021-05-21 | 2021-05-22 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-19 | Finished |  |  | 100 | 2020-09-11 | 2000-01-01 | 2020-09-11 | Finished |  |  | 2021-06-21 | Finished | [10 empty] | 50 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-26 | Finished |  |  | 2019-10-30 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-03-02 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-08-26 | Finished | [13 empty] | in process (defect) |  |  |  |  | 755 | 89 | 24 | 16 | 884 | 0 | 0 | 0 | 16 | 16 | 98.19 | Blue |  |  | 20009212 | 2020-02-28 |  |  |  | HDME000813 | 2020-03-02
TBL0223-TH | HET | 61000625 | HO | ส่งมอบแล้ว | - | TH209023 | Vajira Hospital (Academic Building) | A-PL-02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-03-01 | 2020-07-30 | 2021-08-30 | OUG-1600-2S105,105S/10F | OUG-ON1 | 1600 | 105 | 10 | 10 |  | 2140000 | Bangkok | แขวงวชิรพยาบาล | 2020-08-29 | 2020-12-11 | Finished | [34 empty] | 2020-02-28 | 2020-03-02 | 2020-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-11 | 2021-01-15 | 2020-12-13 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-01-01 | Finished |  |  | 2021-01-02 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 100 | [41 empty] | 2021-01-15 | 2021-05-21 | 2021-05-21 | Finished |  |  | 2021-05-21 | 2021-05-22 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-19 | Finished |  |  | 100 | 2020-09-11 | 2000-01-01 | 2020-09-11 | Finished |  |  | 2021-06-21 | Finished | [10 empty] | 50 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-26 | Finished |  |  | 2019-10-30 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-03-02 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-08-26 | Finished | [13 empty] | in process (defect) |  |  |  |  | 755 | 89 | 24 | 16 | 884 | 0 | 0 | 0 | 16 | 16 | 98.19 | Blue |  |  | 20009212 | 2020-02-28 |  |  |  | HDME000813 | 2020-03-02
TAC1684-TH | HET | 61000625 | HO | ส่งมอบแล้ว | - | TH209023 | Vajira Hospital (Academic Building) | B-PL-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-03-01 | 2020-07-30 | 2021-04-30 | VFI-1600-2S105,105S/11F | VFI-II | 1600 | 105 | 11 | 11 |  | 2300500 | Bangkok | แขวงวชิรพยาบาล | 2020-06-25 | 2020-06-25 | Finished | [34 empty] | 2020-02-28 | 2020-03-02 | 2020-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-25 | 2020-09-02 | 2020-06-30 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-28 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | [41 empty] | 2020-09-25 | 2020-10-27 | 2020-10-27 | Finished |  |  | 2020-09-03 | 2020-10-27 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-05 | Finished |  |  | 100 | 2021-02-12 | 2000-01-01 | 2021-02-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-12-28 | Finished |  |  | 2019-10-30 | Finished | [18 empty] | 2020-03-02 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-12-28 | Finished | [13 empty] | no pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 2 | 2 | 99.8 | Blue |  |  | 20009212 | 2020-02-28 |  |  |  | HDME000813 | 2020-03-02
TAC1685-TH | HET | 61000625 | HO | ส่งมอบแล้ว | - | TH209023 | Vajira Hospital (Academic Building) | B-PL-02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-03-01 | 2020-07-30 | 2021-04-30 | VFI-1600-2S105,105S/11F | VFI-II | 1600 | 105 | 11 | 11 |  | 2300500 | Bangkok | แขวงวชิรพยาบาล | 2020-06-25 | 2020-06-25 | Finished | [34 empty] | 2020-02-28 | 2020-03-02 | 2020-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-25 | 2020-09-02 | 2020-06-30 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-28 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | [41 empty] | 2020-09-25 | 2020-10-28 | 2020-10-28 | Finished |  |  | 2020-09-03 | 2020-10-28 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | 2021-02-12 | 2000-01-01 | 2021-02-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2020-12-28 | Finished |  |  | 2019-10-30 | Finished | [18 empty] | 2020-03-02 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-12-28 | Finished | [13 empty] | pass (defect) |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 2 | 2 | 99.8 | Blue |  |  | 20009212 | 2020-02-28 |  |  |  | HDME000813 | 2020-03-02
TAC1686-TH | HET | 61000629 | HO | เลยสัญญา HO | - | TH209028 | Office Khun Pitch | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-10-14 | 2020-02-14 | 2020-05-14 | 2020-08-15 | VFI-750-CO60,60S/5F | VFI-II | 750 | 60 | 5 | 5 |  | 1428450 | Bangkok | แขวงบางมด | 2020-02-16 | 2020-02-20 | Finished | [34 empty] | 2020-02-14 | 2020-02-18 | 2020-02-18 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-02-17 | 2020-04-11 | 2020-02-26 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-28 | Finished |  |  | 100 | [41 empty] | 2020-04-28 | 1900-01-01 | 2020-04-28 | Waiting | POWER SUPPLY DELAY |  | 2021-07-15 | [12 empty] | 0 | 2021-02-17 | 2000-01-01 | 2021-02-17 | Finished | [14 empty] | 25 | 2021-08-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-24 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-21 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Red |  |  | 20009314 | 2020-02-14 |  |  |  | HDME000791 | 2020-02-18
TAC1687-TH | HET | 61000629 | HO | เลยสัญญา HO | - | TH209028 | Office Khun Pitch | 2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-10-14 | 2020-02-14 | 2020-05-14 | 2020-08-15 | VFI-750-CO60,60S/5F | VFI-II | 750 | 60 | 5 | 5 |  | 1428450 | Bangkok | แขวงบางมด | 2020-02-16 | 2020-02-20 | Finished | [34 empty] | 2020-02-14 | 2020-02-18 | 2020-02-18 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-02-17 | 2020-04-11 | 2020-02-26 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-26 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-28 | Finished |  |  | 100 | [41 empty] | 2020-04-28 | 1900-01-01 | 2020-04-28 | Waiting | POWER SUPPLY DELAY |  | 2021-07-15 | [12 empty] | 0 | 2021-02-17 | 2000-01-01 | 2021-02-17 | Finished | [14 empty] | 25 | 2021-08-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-10-24 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-21 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Red |  |  | 20009314 | 2020-02-14 |  |  |  | HDME000791 | 2020-02-18
TFA1323-TH | HET | 61000631 | HO | ส่งมอบแล้ว | - | TH209029 | Lasalle¦s Avenue Phase 2 | ES1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Chonticha Angsuwichitkun | 2019-10-17 | 2020-01-31 | 2020-03-31 | 2020-10-31 | 1200SX-EN,R5.5M,D35 | SX-EN |  |  |  |  | 5500 | 1093540 | Bangkok | แขวงบางนาใต้ เขตบางนา | 2020-05-20 | [20 empty] | 2020-06-21 | Finished | [14 empty] | 2020-01-31 | 2020-03-03 | 2020-03-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-01 | 2020-06-20 | [41 empty] | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-28 | Finished |  |  | 2020-06-29 | Finished |  |  | 100 | 2020-06-29 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-29 | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | 2020-08-28 | 2021-08-03 | 2020-08-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-19 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2020-10-08 | Finished | CONSTRUCTION DELAY |  | 2020-11-23 | Finished |  |  | 2019-10-29 | Finished | [18 empty] | 2020-03-02 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  | pass | 2021-06-08 | Finished |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009356 | 2020-01-31 |  |  |  | HDME000812 | 2020-03-02 | QC Passed
TFA1324-TH | HET | 61000631 | HO | ส่งมอบแล้ว | - | TH209029 | Lasalle¦s Avenue Phase 2 | ES2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Chonticha Angsuwichitkun | 2019-10-17 | 2020-01-31 | 2020-03-31 | 2020-10-31 | 1200SX-EN,R5.5M,D35 | SX-EN |  |  |  |  | 5500 | 1093540 | Bangkok | แขวงบางนาใต้ เขตบางนา | 2020-05-20 | [20 empty] | 2020-06-21 | Finished | [14 empty] | 2020-01-31 | 2020-03-03 | 2020-03-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-01 | 2020-06-20 | [41 empty] | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-28 | Finished |  |  | 2020-06-29 | Finished |  |  | 100 | 2020-06-29 | 2020-06-30 | 2020-06-30 | Finished |  |  | 2020-06-29 | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-07-01 | Finished |  |  | 100 | 2020-08-28 | 2021-01-19 | 2020-08-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-19 | Finished | [6 empty] | 90 | 2020-10-08 | Finished | CONSTRUCTION DELAY |  | 2020-11-23 | Finished |  |  | 2019-10-29 | Finished | [18 empty] | 2020-03-02 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  | pass | 2021-06-08 | Finished |  |  | 630 | 42 | 16 | 21 | 709 | 0 | 0 | 0 | 2 | 2 | 99.72 | Blue |  |  | 20009356 | 2020-01-31 |  |  |  | HDME000812 | 2020-03-02 | QC Passed
TAJ0625-TH | HET | 61000631 | HO | ส่งมอบแล้ว | - | TH209029 | Lasalle¦s Avenue Phase 2 | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Chonticha Angsuwichitkun | 2019-10-17 | 2020-01-31 | 2020-03-31 | 2020-10-31 | P-1600-CO60,60S/2F | UAG-SN1 | 1600 | 60 | 2 | 2 |  | 1391000 | Bangkok | แขวงบางนาใต้ เขตบางนา | 2020-05-20 | 2020-06-08 | Finished | [34 empty] | 2020-01-31 | 2020-03-02 | 2020-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-01 | 2020-06-08 | 2020-06-08 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-29 | Finished |  |  | 100 | [41 empty] | 2020-06-29 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-07-10 | 2020-07-28 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-13 | Finished |  |  | 100 | 2021-05-13 | 2021-03-08 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-19 | Finished |  |  | 2021-03-08 | Finished |  |  | 100 | 2020-11-06 | Finished | CONSTRUCTION DELAY |  | 2020-11-23 | Finished |  |  | 2019-10-29 | Finished | [18 empty] | 2020-03-02 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  | pass | 2021-06-08 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009354 | 2020-01-31 |  |  |  | HDME000812 | 2020-03-02 | QC Passed
TAC1688-TH | HET | 61000633 | HO | ส่งมอบแล้ว | - | TH209030 | Criminal Court | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | CHALERMKHUAN KERDPOOM | 2019-09-25 | 2020-01-24 | 2020-03-22 | 2020-04-30 | VFI-1000-CO105,105S/13F | VFI-II | 1000 | 105 | 13 | 13 |  | 3000000 | Bangkok | เขตจตุจักร | 2020-01-27 | 2020-02-16 | Finished | [34 empty] | 2020-01-24 | 2020-01-26 | 2020-01-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-01-24 | 2020-02-28 | 2020-02-17 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-02-28 | Finished |  |  | 100 | [41 empty] | 2020-02-28 | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-03-02 | 2020-03-02 | Finished |  |  | 2020-03-03 | Finished |  |  | 2020-03-16 | Finished |  |  | 100 | 2021-05-13 | 2021-08-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-20 | Finished |  |  | 2021-08-04 | Finished |  |  | 100 | 2020-10-15 | Finished | H/O DOCUMENT DELAY |  | 2021-07-16 | Finished |  |  | 2019-10-31 | Finished | [10 empty] | 2021-07-15 | Finished | [6 empty] | 2020-04-15 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009433 | 2020-02-03 |  |  |  | HDME000774 | 2020-01-26 | QC Passed
TAJ0626-TH | HET | 61000634 | HO | ยังอยู่ในสัญญา HO | - | TH209033 | Office 5 Floor Khun EDDY | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | APHIRADA BUNKUEA | 2019-10-22 | 2020-07-22 | 2020-08-22 | 2022-01-01 | P-600-CO60W,60S/5F | UAG-SN1 | 600 | 60 | 5 | 5 |  | 1000000 | Nonthaburi | อำเภอปากเกร็ด | 2021-11-30 | [36 empty] | 2020-07-22 | 2020-07-22 | 2020-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-26 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2019-11-07 | Finished | [10 empty] | 2021-11-22 | Finished | [6 empty] | 2020-07-22 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-24 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Green |  |  | 20009434 | 2020-07-22 |  |  |  | HDME000927 | 2020-07-22
TAJ0627-TH | HET | 61000636 | HO | ส่งมอบแล้ว | - | TH209031 | Larissa Condominium Lot.1/1 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-11-15 | 2020-07-15 | 2020-09-15 | 2021-02-28 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1100000 | Samut Prakan | อ.เมืองสมุทรปราการ | 2020-08-31 | 2020-08-31 | Finished | [34 empty] | 2020-07-15 | 2020-07-29 | 2020-07-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-16 | 2020-07-30 | 2020-09-12 | Finished |  |  | 2020-09-14 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 100 | [41 empty] | 2020-10-08 | 2020-11-27 | 2020-11-27 | Finished |  |  | 2020-11-20 | 2020-11-30 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | 2020-12-17 | 2021-05-21 | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2021-03-10 | Finished | CONSTRUCTION DELAY |  | 2021-03-17 | Finished |  |  | 2019-12-12 | Finished | [10 empty] | 2021-03-17 | Finished | [6 empty] | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  | pass | 2021-06-11 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009814 | 2020-07-15 |  |  |  | HDME000933 | 2020-07-29 | QC Passed
TAJ0628-TH | HET | 61000637 | HO | ส่งมอบแล้ว | - | TH209032 | Larissa Condominium Lot.1/2 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-11-15 | 2020-07-15 | 2020-09-15 | 2021-04-30 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1100000 | Samut Prakan | อำเภอเมืองสมุทรปราการ | 2020-08-15 | 2020-08-15 | Finished | [34 empty] | 2020-07-15 | 2020-07-29 | 2020-07-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-16 | 2020-07-30 | 2020-08-15 | Finished |  |  | 2020-08-17 | Finished |  |  | 2020-08-19 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-03 | Finished |  |  | 100 | [41 empty] | 2020-08-03 | 2021-01-22 | 2021-01-22 | Finished |  |  | 2020-11-11 | 2021-01-22 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | 2021-03-01 | 2021-07-15 | 2021-03-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-07-15 | Finished |  |  | 100 | 2021-05-02 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2019-11-27 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009786 | 2020-07-15 |  |  |  | HDME000934 | 2020-07-29 | QC Passed
TAD0430-TH | HET | 61000638 | HO | ส่งมอบแล้ว | - | TH209035 | Thepmitr School Surat | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | ANUSSARA POLDONGNOK | 2019-10-25 | 2020-03-25 | 2020-05-25 | 2020-07-26 | B-1000-2S60,60S/4F | B-II(VFI-II) | 1000 | 60 | 4 | 4 |  | 1396350 | Surat Thani | อำเภอเมืองสุราษฎร์ธานี | 2020-03-30 | 2020-03-27 | Finished | [34 empty] | 2020-03-25 | 2020-03-28 | 2020-03-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-27 | 2020-04-25 | 2020-03-27 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-03-29 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | [41 empty] | 2020-04-24 | 2020-06-20 | 2020-06-20 | Finished |  |  | 2020-05-15 | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-22 | Finished |  |  | 100 | 2020-06-01 | 2020-01-04 | 2020-06-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished | [6 empty] | 90 | 2020-06-30 | Finished | POWER SUPPLY DELAY |  | 2020-06-30 | Finished |  |  | 2019-11-13 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2020-03-27 | Finished |  |  | 2020-03-28 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-06-30 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20009527 | 2020-03-25 |  |  |  | HDME000833 | 2020-03-27 | QC Passed
TAJ0629-TH | HET | 61000640 | HO | ส่งมอบแล้ว | - | TH209039 | Apartment 5 Fl. Soi Ratchawithi 2 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2019-10-28 | 2020-03-30 | 2020-05-28 | 2020-08-30 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1070000 | Bangkok | เขตราชเทวี | 2020-03-01 | 2021-03-01 | Finished | [34 empty] | 2020-03-30 | 2020-04-08 | 2020-04-08 | Finished | PAYMENT DELAY | [13 empty] | 2020-04-01 | 2020-04-30 | 2020-01-27 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-10 | Finished |  |  | 100 | [41 empty] | 2020-05-10 | 2020-07-29 | 2020-07-29 | Finished |  |  | 2020-07-30 | 2020-07-29 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-08-14 | 2021-08-10 | 2020-08-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-08-10 | Finished |  |  | 100 | 2020-08-08 | Finished | POWER SUPPLY DELAY |  | 2020-08-18 | Finished |  |  | 2019-11-10 | Finished | [18 empty] | 2020-04-08 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-08-18 | Finished | [13 empty] | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009549 | 2020-03-30 |  |  |  | HDME000843 | 2020-04-08 | QC Passed
TAJ0631-TH | HET | 61000642 | HO | ส่งมอบแล้ว | - | TH209040 | Condominium Thadawaree | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2019-10-31 | 2020-02-28 | 2020-04-30 | 2021-02-28 | P-600-CO60W,60S/8F | UAG-SN1 | 600 | 60 | 8 | 8 |  | 1000000 | Nakhon Pathom | อำเภอกำแพงแสน | 2020-03-30 | 2020-03-30 | Finished | [34 empty] | 2020-02-28 | 2020-03-07 | 2020-03-07 | Finished | STORE AREA | [13 empty] | 2020-04-01 | 2020-04-30 | 2020-04-01 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-10 | Finished |  |  | 100 | [41 empty] | 2020-05-10 | 2021-01-13 | 2021-01-13 | Finished |  |  | 2020-11-10 | 2021-01-14 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-20 | Finished |  |  | 100 | 2021-02-12 | 2021-05-31 | 2021-02-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-05-31 | Finished |  |  | 100 | 2021-02-05 | Finished | POWER SUPPLY DELAY |  | 2021-02-08 | Finished |  |  | 2019-11-20 | Finished | [10 empty] | 2021-02-08 | Finished | [6 empty] | 2020-03-07 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-10 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass | 2021-06-09 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009712 | 2020-02-28 |  |  |  | HDME000816 | 2020-03-07 | QC Passed
TAJ0632-TH | HET | 61000642 | HO | ส่งมอบแล้ว | - | TH209040 | Condominium Thadawaree | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2019-10-31 | 2020-02-28 | 2020-04-30 | 2021-02-28 | P-600-CO60W,60S/8F | UAG-SN1 | 600 | 60 | 8 | 8 |  | 1000000 | Nakhon Pathom | อำเภอกำแพงแสน | 2020-03-30 | 2020-03-30 | Finished | [34 empty] | 2020-02-28 | 2020-03-07 | 2020-03-07 | Finished | STORE AREA | [13 empty] | 2020-04-01 | 2020-04-30 | 2020-04-01 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-07 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-09 | Finished |  |  | 2020-05-10 | Finished |  |  | 100 | [41 empty] | 2020-05-10 | 2021-01-13 | 2021-01-13 | Finished |  |  | 2020-11-10 | 2021-01-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-22 | Finished |  |  | 100 | 2021-02-12 | 2021-02-03 | 2021-02-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-03 | Finished | [6 empty] | 90 | 2021-02-05 | Finished | POWER SUPPLY DELAY |  | 2021-02-08 | Finished |  |  | 2019-11-20 | Finished | [10 empty] | 2021-02-08 | Finished | [6 empty] | 2020-03-07 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-10 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  | pass | 2021-06-09 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20009712 | 2020-02-28 |  |  |  | HDME000816 | 2020-03-07 | QC Passed
TAJ0633-TH | HET | 61000643 | HO | ส่งมอบแล้ว | - | TH209042 | Office Khun Vikrom | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | ANUSSARA POLDONGNOK | 2019-11-01 | 2020-01-31 | 2020-03-16 | 2021-10-10 | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1177000 | Bangkok | แขวงสามเสนนอก | 2020-10-30 | 2020-10-30 | Finished | [34 empty] | 2020-01-31 | 2020-01-21 | 2020-01-21 | Finished | STORE AREA | [13 empty] | 2020-02-02 | 2020-04-20 | 2020-02-02 | Finished |  |  | 2020-02-04 | Finished |  |  | 2020-02-08 | Finished |  |  | 2020-02-08 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-16 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-02-23 | Finished |  |  | 100 | [41 empty] | 2020-02-23 | 2020-12-10 | 2020-12-10 | Finished |  |  | 2020-08-30 | 2020-12-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-06-26 | 2021-06-11 | 2020-06-26 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-06-11 | Finished |  |  | 100 | 2021-03-08 | Finished | POWER SUPPLY DELAY |  | 2021-03-10 | Finished |  |  | 2019-11-14 | Finished | [10 empty] | 2021-03-10 | Finished | [6 empty] | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2020-01-30 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009613 | 2020-01-31 |  |  |  | HDME000780 | 2020-01-30 | QC Passed
TFA1325-TH | HET | 61000645 | HO | ส่งมอบแล้ว | - | TH209045 | Bus Gate 2 (Pier 5) | 1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 6 |  | 1 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2019-11-06 | 2020-02-21 | 2020-04-21 | 2020-07-15 | 1200TX-EN,R5.5M,D35 | TX-EN |  |  |  |  | 5500 | 1712000 | Bangkok | เขตดอนเมือง | 2020-03-19 | [20 empty] | 2020-06-20 | Finished | [14 empty] | 2020-02-21 | 2020-05-26 | 2020-05-27 | Finished | PAYMENT DELAY | [13 empty] | 2020-06-04 | 2020-06-20 | [41 empty] | 2020-06-04 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | 2020-06-19 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2020-06-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-06-19 | 2021-01-26 | 2020-06-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-10 | Finished |  |  | 2021-01-26 | Finished |  |  | 100 | 2020-07-30 | Finished | CUSTOMER PAYMENT DELAY |  | 2020-08-04 | Finished |  |  | 2019-11-29 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2020-05-27 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-29 | Finished |  |  | 2020-08-04 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-25 | Finished |  | pass | 2020-08-25 | Finished |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009731 | 2020-02-06 |  |  |  | HDME000898 | 2020-05-27 | QC Passed
TAJ0634-TH | HET | 61000646 | HO | ส่งมอบแล้ว | - | TH209036 | Magnix Ramintra 21 | EC-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2019-10-15 | 2020-04-15 | 2020-06-15 | 2020-09-30 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1000000 | Bangkok | เขตคันนายาว | 2020-07-30 | 2020-07-30 | Finished | [34 empty] | 2020-04-15 | 2020-04-29 | 2020-04-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-04-15 | 2020-05-28 | 2020-06-02 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-04 | Finished |  |  | 100 | [41 empty] | 2020-07-04 | 2020-06-05 | 2020-06-05 | Finished |  |  | 2020-06-05 | 2020-07-05 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2021-05-13 | 2020-08-07 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-07 | Finished | [6 empty] | 90 | 2020-07-25 | Finished | CONSTRUCTION DELAY |  | 2020-07-21 | Finished |  |  | 2019-12-06 | Finished | [10 empty] | 2020-08-30 | Finished | [6 empty] | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-07-21 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  | pass | 2020-10-14 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20009973 | 2020-04-10 |  |  |  | HDME000865 | 2020-04-29 | QC Passed
TAD0433-TH | HET | 61000647 | HO | ส่งมอบแล้ว | - | TH209046 | Outpatient Building@Phang Khon Hospital | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2019-11-07 | 2020-02-21 | 2020-03-22 | 2020-11-15 | B-1000-2S60,60S/2F | B-II(VFI-II) | 1000 | 60 | 2 | 2 |  | 1350000 | Sakon Nakhon | อำเภอพังโคน | 2020-08-17 | [36 empty] | 2020-02-21 | 2020-08-01 | 2020-08-01 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-01 | 2020-10-01 | 2020-08-20 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-27 | Finished |  |  | 100 | [41 empty] | 2020-08-27 | 2020-10-22 | 2020-10-22 | Finished |  |  | 2020-09-21 | 2020-10-23 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-25 | Finished |  |  | 100 | 2020-10-09 | 2021-08-13 | 2020-10-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-09 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | 2020-11-01 | Finished | CONSTRUCTION DELAY |  | 2020-11-18 | Finished |  |  | 2019-11-23 | Finished | [18 empty] | 2020-08-01 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-04 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 362 | 88 | 16 | 16 | 482 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009713 | 2020-02-21 |  |  |  | HDME000947 | 2020-08-01 | QC Passed
TEB0115-TH | HET | 61000648 | HO | ส่งมอบแล้ว | - | TH209044 | Home Khun Chatchanit | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-10-29 | 2020-01-29 | 1900-01-01 | 2020-02-18 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 4 | 4 |  | 989750 | Bangkok | แขวงคลองตันเหนือ เขตวัฒนา | 1900-01-01 | 2020-02-11 | Finished | [34 empty] | 2020-01-29 | 2020-02-11 | 2020-02-11 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2020-02-18 | 2020-02-28 | 2020-02-18 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-22 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-02-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-02-28 | Finished |  |  | 2020-02-28 | Finished |  |  | 100 | [41 empty] | 2020-02-28 | 2020-03-06 | 2020-03-06 | Finished |  |  | 2020-03-06 | 2020-03-06 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-03-14 | Finished |  |  | 2021-03-05 | Finished |  |  | 100 | 2020-03-17 | Finished | CUSTOMER DECORATION DELAY |  | 2020-03-18 | Finished |  |  | 2019-11-28 | Finished | [18 empty] | 2020-02-07 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Working |  |  | 2020-04-24 | Working |  | pass (defect) |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009765 | 2019-12-22 |  |  |  | HDME000785 | 2020-02-07
TAJ0636-TH | HET | 61000650 | HO | ยังอยู่ในสัญญา HO | - | TH209049 | Nita Clinic | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-11-13 | 2020-02-28 | 2020-04-13 | 2021-10-10 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1070000 | Bangkok | แขวงอนุเสาวรีย์ | 2020-03-07 | 2020-03-07 | Finished | [34 empty] | 2020-08-28 | 2020-03-02 | 2020-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-07 | 2020-03-15 | 2020-03-07 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-01 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-15 | Finished |  |  | 2020-03-19 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-21 | Finished |  |  | 100 | [41 empty] | 2020-03-21 | 1900-01-01 | 2020-03-21 | Waiting | POWER SUPPLY DELAY |  | 2021-11-10 | [12 empty] | 0 | 2020-04-13 | 2000-01-01 | 2020-04-13 | Finished | [14 empty] | 25 | 2021-12-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-11-23 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-03-06 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-10 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 4 | 16 | 101 | 78.83 | Green |  |  | 20009774 | 2020-02-28 |  |  |  | HDME000815 | 2020-03-06
TAJ0637-TH | HET | 61000651 | HO | ส่งมอบแล้ว | - | TH209051 | Building 5 Floor@K.SANTHAI FOOD | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2019-11-18 | 2020-02-18 | 2020-05-03 | 2020-11-30 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1310000 | Nonthaburi | อ.บางใหญ่ | 2020-03-09 | 2020-03-09 | Finished | [34 empty] | 2020-02-18 | 2020-02-23 | 2020-02-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-09 | 2020-04-09 | 2020-03-10 | Finished |  |  | 2020-03-15 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-09 | Finished |  |  | 100 | [41 empty] | 2020-04-09 | 2020-07-10 | 2020-07-10 | Finished |  |  | 2020-07-10 | 2020-07-13 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-25 | Finished |  |  | 100 | 2020-05-20 | 2021-02-19 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-10 | Finished |  |  | 2021-02-19 | Finished |  |  | 100 | 2020-11-20 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-02-23 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009816 | 2020-02-18 |  |  |  | HDME000803 | 2020-02-23 | QC Passed
TAJ0638-TH | HET | 61000651 | HO | ส่งมอบแล้ว | - | TH209051 | Building 5 Floor@K.SANTHAI FOOD | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2019-11-18 | 2020-02-18 | 2020-05-03 | 2020-11-30 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1310000 | Nonthaburi | อ.บางใหญ่ | 2020-03-09 | 2020-03-09 | Finished | [34 empty] | 2020-02-18 | 2020-02-23 | 2020-02-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-09 | 2020-04-09 | 2020-03-10 | Finished |  |  | 2020-03-15 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-09 | Finished |  |  | 100 | [41 empty] | 2020-04-09 | 2020-07-10 | 2020-07-10 | Finished |  |  | 2020-07-10 | 2020-07-13 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-25 | Finished |  |  | 100 | 2020-05-20 | 2021-02-19 | 2020-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-10 | Finished |  |  | 2021-02-19 | Finished |  |  | 100 | 2020-11-20 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-02-23 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009816 | 2020-02-18 |  |  |  | HDME000803 | 2020-02-23 | QC Passed
TAJ0639-TH | HET | 61000651 | HO | ส่งมอบแล้ว | - | TH209051 | Building 5 Floor@K.SANTHAI FOOD | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2019-11-18 | 2020-02-18 | 2020-05-03 | 2020-11-30 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1310000 | Nonthaburi | อ.บางใหญ่ | 2020-03-09 | 2020-06-15 | Finished | [34 empty] | 2020-02-18 | 2020-02-23 | 2020-02-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-15 | 2020-07-09 | 2020-06-20 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-05 | Finished |  |  | 100 | [41 empty] | 2020-08-05 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-09-10 | 2020-09-11 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-08-10 | 2021-02-19 | 2020-08-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-09 | Finished |  |  | 2021-02-19 | Finished |  |  | 100 | 2020-11-20 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-02-23 | Finished |  |  | 2020-02-23 | Finished |  |  | 2020-02-24 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009816 | 2020-02-18 |  |  |  | HDME000803 | 2020-02-23 | QC Passed
TAJ0640-TH | HET | 61000652 | HO | ส่งมอบแล้ว | - | TH199181 | Sport Center Bangpu | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2019-09-16 | 2020-01-21 | 2020-02-26 | 2021-01-31 | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1326800 | Samut Prakan | จังหวัดสมุทรปราการ 10280 | 2020-04-20 | 2020-04-20 | Finished | [34 empty] | 2020-01-20 | 2020-04-02 | 2020-04-02 | Finished | PAYMENT DELAY | [13 empty] | 2020-04-25 | 2020-05-15 | 2020-04-02 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-04-12 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-03 | Finished |  |  | 2020-05-06 | Finished |  |  | 100 | [41 empty] | 2020-05-06 | 2020-07-28 | 2020-07-28 | Finished |  |  | 2020-05-15 | 2020-10-26 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-25 | Finished |  |  | 100 | 2020-12-07 | 2000-01-01 | 2020-12-07 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-04-05 | Finished |  |  | 100 | 2021-01-14 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2019-12-21 | Finished | [10 empty] | 2021-01-26 | Finished | [6 empty] | 2020-04-02 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-09 | Finished |  |  | 2021-01-26 | Finished | [13 empty] | pass (defect) |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009813 | 2020-03-31 |  |  |  | HDME000838 | 2020-04-02
TAC1692-TH | HET | 61000653 | HO | ส่งมอบแล้ว | - | TH209047 | Klong Rangsit Metropolitan Electricity | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2019-11-01 | 2020-04-01 | 2020-06-01 | 2020-10-30 | VFI-700-CO60,60S/4F | VFI-II | 700 | 60 | 4 | 4 |  | 1230500 | Pathum Thani | อำเภอเมืองปทุมธานี | 2020-03-15 | 2020-03-16 | Finished | [34 empty] | 2020-04-01 | 2020-03-16 | 2020-03-16 | Finished | OTHERS | [13 empty] | 2020-03-16 | 2020-04-26 | 2020-03-18 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-03-27 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-04-15 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-26 | Finished |  |  | 100 | [41 empty] | 2020-04-26 | 2020-05-15 | 2020-05-15 | Finished |  |  | 2020-05-15 | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 100 | 2020-05-29 | 2021-01-25 | 2020-05-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-05 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | 2020-12-20 | Finished | POWER SUPPLY DELAY |  | 2020-10-30 | Finished |  |  | 2019-12-11 | Finished | [10 empty] | 2020-07-15 | Finished | [6 empty] | 2020-03-16 | Finished |  |  | 2020-03-16 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  | pass | 2021-02-16 | Finished |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009867 | 2020-04-01 |  |  |  | HDME000819 | 2020-03-16 | QC Passed
TEC0141-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/19F | DF | 500 | 30 | 19 | 19 |  | 1070000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-03-10 | 2020-03-10 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-02-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-02-06 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-19 | Finished |  |  | 100 | [41 empty] | 2020-04-19 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-03-20 | 2020-06-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-15 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 642 | 0 | 40 | 0 | 682 | 0 | 0 | 40 | 0 | 40 | 94.13 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000817 | 2020-03-09
TEC0150-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D10 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/11F | DF | 500 | 30 | 11 | 11 |  | 909500 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-05 | 2020-04-05 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-03-02 | 2020-01-04 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-01-03 | Finished |  |  | 100 | [41 empty] | 2020-01-03 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-07-03 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-02 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-09 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 421 | 0 | 32 | 0 | 453 | 0 | 0 | 32 | 0 | 32 | 92.94 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000839 | 2020-04-02
TEC0151-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D11 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/4F | DF | 500 | 30 | 4 | 4 |  | 535000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-12 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-01 | Finished |  |  | 100 | [41 empty] | 2020-05-01 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0152-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D12 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/4F | DF | 500 | 30 | 4 | 4 |  | 535000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-12 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-01 | Finished |  |  | 100 | [41 empty] | 2020-05-01 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0153-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D13 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/4F | DF | 500 | 30 | 4 | 4 |  | 535000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-12 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-01 | Finished |  |  | 100 | [41 empty] | 2020-05-01 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0154-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D14 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/4F | DF | 500 | 30 | 4 | 4 |  | 535000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-12 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-21 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-27 | Finished |  |  | 2020-05-01 | Finished |  |  | 100 | [41 empty] | 2020-05-01 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0155-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D15 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/4F | DF | 500 | 30 | 4 | 4 |  | 535000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-05-04 | Finished |  |  | 100 | [41 empty] | 2020-05-04 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0156-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D16 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/4F | DF | 500 | 30 | 4 | 4 |  | 535000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-30 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-05-04 | Finished |  |  | 100 | [41 empty] | 2020-05-04 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0157-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D17 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/9F | DF | 500 | 30 | 9 | 9 |  | 642000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-05-04 | Finished |  |  | 100 | [41 empty] | 2020-05-04 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 366 | 0 | 24 | 0 | 390 | 0 | 0 | 24 | 0 | 24 | 93.85 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0158-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D18 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/9F | DF | 500 | 30 | 9 | 9 |  | 642000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-03-10 | Finished |  |  | 2020-04-02 | Finished |  |  | 2020-04-06 | Finished |  |  | 2020-04-04 | Finished |  |  | 2020-04-10 | Finished |  |  | 2020-04-16 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-05-04 | Finished |  |  | 100 | [41 empty] | 2020-05-04 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 366 | 0 | 24 | 0 | 390 | 0 | 0 | 24 | 0 | 24 | 93.85 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000858 | 2020-04-21
TEC0142-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/19F | DF | 500 | 30 | 19 | 19 |  | 1070000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-03-10 | 2020-03-10 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-02-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-02-06 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-19 | Finished |  |  | 100 | [41 empty] | 2020-04-19 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-03-20 | 2020-06-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-15 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 642 | 0 | 40 | 0 | 682 | 0 | 0 | 40 | 0 | 40 | 94.13 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000817 | 2020-03-09
TEC0159-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D21 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/3F | DF | 500 | 30 | 3 | 3 |  | 513600 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-03-22 | 2020-03-02 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-22 | Finished |  |  | 100 | [41 empty] | 2020-03-22 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000855 | 2020-04-21
TEC0160-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D22 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/3F | DF | 500 | 30 | 3 | 3 |  | 513600 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-03-22 | 2020-03-02 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-22 | Finished |  |  | 100 | [41 empty] | 2020-03-22 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000855 | 2020-04-21
TEC0161-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D23 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/3F | DF | 500 | 30 | 3 | 3 |  | 513600 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-03-22 | 2020-03-02 | Finished |  |  | 2020-03-04 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-14 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-22 | Finished |  |  | 100 | [41 empty] | 2020-03-22 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-08-20 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000855 | 2020-04-21
TEC0143-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/19F | DF | 500 | 30 | 19 | 19 |  | 1070000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-03-10 | 2020-03-10 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-02-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-02-06 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-19 | Finished |  |  | 100 | [41 empty] | 2020-04-19 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-03-20 | 2020-06-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-15 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 642 | 0 | 40 | 0 | 682 | 0 | 0 | 40 | 0 | 40 | 94.13 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000817 | 2020-03-09
TEC0144-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/19F | DF | 500 | 30 | 19 | 19 |  | 1070000 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-03-10 | 2020-03-10 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-02-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-02-06 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-19 | Finished |  |  | 2020-03-06 | Finished |  |  | 2020-03-17 | Finished |  |  | 2020-03-25 | Finished |  |  | 2020-04-03 | Finished |  |  | 2020-04-19 | Finished |  |  | 100 | [41 empty] | 2020-04-19 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-03-20 | 2020-06-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-15 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-03-09 | Finished |  |  | 2020-03-10 | Finished |  |  | 2020-03-26 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 642 | 0 | 40 | 0 | 682 | 0 | 0 | 40 | 0 | 40 | 94.13 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000817 | 2020-03-09
TEC0145-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D5 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/17F | DF | 500 | 30 | 17 | 17 |  | 1016500 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-04-20 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-07 | Finished |  |  | 2020-06-15 | Finished |  |  | 100 | [41 empty] | 2020-06-15 | 2020-06-25 | 2020-06-25 | Finished |  |  | 2020-04-20 | 2020-07-02 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-15 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 587 | 0 | 40 | 0 | 627 | 0 | 0 | 40 | 0 | 40 | 93.62 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000855 | 2020-04-21
TEC0146-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D6 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/17F | DF | 500 | 30 | 17 | 17 |  | 1016500 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-22 | 2020-04-22 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-01-04 | 2020-02-04 | 2020-04-20 | Finished |  |  | 2020-04-25 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-28 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-07 | Finished |  |  | 2020-06-15 | Finished |  |  | 100 | [41 empty] | 2020-06-15 | 2020-06-25 | 2020-06-25 | Finished |  |  | 2020-04-20 | 2020-07-02 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-15 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-21 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 587 | 0 | 40 | 0 | 627 | 0 | 0 | 40 | 0 | 40 | 93.62 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000855 | 2020-04-21
TEC0147-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D7 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/11F | DF | 500 | 30 | 11 | 11 |  | 909500 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-05 | 2020-04-05 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-03-02 | 2020-01-04 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-01-03 | Finished |  |  | 100 | [41 empty] | 2020-01-03 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-07-03 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-02 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-09 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 421 | 0 | 32 | 0 | 453 | 0 | 0 | 32 | 0 | 32 | 92.94 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000839 | 2020-04-02
TEC0148-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D8 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/11F | DF | 500 | 30 | 11 | 11 |  | 909500 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-05 | 2020-04-05 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-03-02 | 2020-01-04 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-01-03 | Finished |  |  | 100 | [41 empty] | 2020-01-03 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-07-03 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-02 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-09 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 421 | 0 | 32 | 0 | 453 | 0 | 0 | 32 | 0 | 32 | 92.94 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000839 | 2020-04-02
TEC0149-TH | HET | 61000655 | HO | ส่งมอบแล้ว | - | TH209052 | รพ.สมเด็จพระบรมราชเทวี ณ ศรีราชา | D9 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Chanyuth Soithong | 2019-09-16 | 2020-01-03 | 2020-03-31 | 2020-07-31 | DF-500S-B30,30S/11F | DF | 500 | 30 | 11 | 11 |  | 909500 | Chon Buri | อำเภอศรีราชา | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-01-03 | 2020-04-05 | 2020-04-05 | Finished | PAYMENT DELAY | [13 empty] | 2020-01-04 | 2020-03-02 | 2020-01-04 | Finished |  |  | 2020-01-07 | Finished |  |  | 2020-01-11 | Finished |  |  | 2020-01-20 | Finished |  |  | 2020-01-25 | Finished |  |  | 2020-02-05 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-25 | Finished |  |  | 2020-01-03 | Finished |  |  | 100 | [41 empty] | 2020-01-03 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-04-20 | 2020-07-03 | Finished |  |  | 2020-07-05 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | [18 empty] | 0 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2021-03-23 | Finished |  |  | 2019-12-12 | Finished | [18 empty] | 2020-04-02 | Finished |  |  | 2020-04-08 | Finished |  |  | 2020-04-09 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | dumb | 2021-08-18 | Finished |  |  | 421 | 0 | 32 | 0 | 453 | 0 | 0 | 32 | 0 | 32 | 92.94 | Blue |  |  | 20009859 | 2020-01-03 |  |  |  | HDME000839 | 2020-04-02
TAJ0642-TH | HET | 61000656 | HO | ส่งมอบแล้ว | - | TH209054 | Ploen Ploen Condominium, Tiwanon-Pak Kret 3 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2019-11-22 | 2020-02-20 | 2020-03-20 | 2020-04-20 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 941600 | Nonthaburi | ต.บ้านใหม่ อ.ปากเกร็ด | 1900-01-01 | 2020-04-25 | Finished | [34 empty] | 2020-02-20 | 2020-02-20 | 2020-02-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-03-05 | 2020-03-20 | 2020-03-06 | Finished |  |  | 2020-03-07 | Finished |  |  | 2020-03-08 | Finished |  |  | 2020-03-09 | Finished |  |  | 2020-03-11 | Finished |  |  | 2020-03-12 | Finished |  |  | 2020-03-13 | Finished |  |  | 2020-03-15 | Finished |  |  | 2020-03-20 | Finished |  |  | 2020-03-21 | Finished |  |  | 100 | [41 empty] | 2020-03-21 | 2020-03-25 | 2020-03-25 | Finished |  |  | 2020-03-25 | 2020-04-02 | Finished |  |  | 2020-04-05 | Finished |  |  | 2020-04-07 | Finished |  |  | 100 | 2020-04-30 | 2020-07-10 | 2020-04-30 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-07-10 | Finished |  |  | 100 | 2020-04-23 | Finished | CONSTRUCTION DELAY |  | 2020-06-12 | Finished |  |  | 2019-12-12 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2020-02-20 | Finished |  |  | 2020-02-20 | Finished |  |  | 2020-02-21 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-09 | Finished |  | pass | 2020-07-09 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009926 | 2020-02-20 |  |  |  | HDME000797 | 2020-02-20 | QC Passed
TEB0116-TH | HET | 61000657 | HO | ส่งมอบแล้ว | - | TH209053 | Home Khun Udom | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2019-11-20 | 2020-02-01 | 2020-03-01 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 800000 | Bangkok | อ.บางแก้ว | 2020-02-01 | 2020-02-01 | Finished | [34 empty] | 2020-02-01 | 2020-02-10 | 2020-02-10 | Finished | STORE AREA | [13 empty] | 2020-02-10 | 2020-02-20 | 2020-02-10 | Finished |  |  | 2020-02-11 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-02-13 | Finished |  |  | 2020-02-14 | Finished |  |  | 2020-02-15 | Finished |  |  | 2020-02-16 | Finished |  |  | 2020-02-17 | Finished |  |  | 2020-02-18 | Finished |  |  | 2020-02-19 | Finished |  |  | 100 | [41 empty] | 2020-02-19 | 2020-03-25 | 2020-03-25 | Finished |  |  | 2020-03-24 | 2020-03-26 | Finished |  |  | 2020-03-26 | Finished |  |  | 2020-03-27 | Finished |  |  | 100 | 2021-05-13 | 2021-03-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-03-10 | Finished |  |  | 100 | 2020-03-31 | Finished | CONSTRUCTION DELAY |  | 2020-04-07 | Finished |  |  | 2019-12-12 | Finished | [10 empty] | 2020-04-15 | Finished | [6 empty] | 2020-02-06 | Finished |  |  | 2020-02-10 | Finished |  |  | 2020-02-12 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  | pass | 2020-04-24 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20009916 | 2020-01-16 |  |  |  | HDME000784 | 2020-02-06 | QC Passed
TEB0117-TH | HET | 61000659 | HO | ยังอยู่ในสัญญา HO | - | TH209055 | HOME KHUN JIRAPORN PHAHOL 44 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Thamnul Kongsar | 2019-11-21 | 2020-07-21 | 2020-09-21 | 2022-02-20 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 2 | 2 |  | 1000000 | Bangkok | แขวงเสนานิคม | 2021-11-30 | [36 empty] | 2020-07-14 | 2020-07-29 | 2020-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-26 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-19 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-07-29 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20010546 | 2020-07-14 |  |  |  | HDME000936 | 2020-07-29
TAJ0643-TH | HET | 61000660 | HO | ยังอยู่ในสัญญา HO | - | TH209057 | 3 Storey Villa Khun Chaleow | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | KRITWARONG KHIENSUWAN | 2019-11-26 | 2020-05-26 | 2020-08-26 | 2021-10-29 | P-630-CO60D,60S/3F | UAG-SN1 | 630 | 60 | 3 | 3 |  | 1000000 | Chiang Mai | อำเภอเมือง | 2020-07-26 | 2020-07-27 | Finished | [34 empty] | 2020-05-26 | 2020-06-02 | 2020-06-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-27 | 2020-08-30 | 2020-07-27 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-02 | Finished |  |  | 2020-08-03 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-07 | Finished |  |  | 100 | [41 empty] | 2020-08-07 | 2020-10-19 | 2020-10-19 | Finished |  |  | 2020-10-20 | 2020-10-20 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-23 | Finished |  |  | 100 | 2020-08-31 | 2020-04-25 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-04-25 | Finished |  |  | 100 | 2021-10-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2019-12-12 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-06-03 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-04 | Finished | [17 empty] | pass |  |  |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20009974 | 2020-05-26 |  |  |  | HDME000900 | 2020-06-03 | QC Passed
TBL0225-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | CP1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2020-06-30 |  | OUG-1000-CO120,120S/9F | OUG-ON1 | 1000 | 120 | 9 | 9 |  | 1819000 | Bangkok | เขตบางรัก | 2020-12-25 | 2021-02-01 | Finished | [34 empty] | 2021-12-16 | 2021-03-23 | 2021-03-25 | Finished | STORE AREA | [13 empty] | 2020-12-25 | 2021-01-27 | 2021-02-04 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-24 | Finished |  |  | 100 | [41 empty] | 2021-03-24 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-01-28 | 2021-03-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | 2021-02-17 | 2021-06-10 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-06-28 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-03-17 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-10 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010145 | 2020-05-01 |  |  |  | HDME000884 | 2020-05-10 | QC Passed
TBL0226-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | CP2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2020-06-30 |  | OUG-1000-CO120,120S/9F | OUG-ON1 | 1000 | 120 | 9 | 9 |  | 1819000 | Bangkok | เขตบางรัก | 2020-12-25 | 2021-02-01 | Finished | [34 empty] | 2021-12-16 | 2021-03-23 | 2021-03-25 | Finished | STORE AREA | [13 empty] | 2020-12-25 | 2021-01-27 | 2021-02-04 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-24 | Finished |  |  | 100 | [41 empty] | 2021-03-24 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-01-28 | 2021-03-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | 2021-02-17 | 2021-06-10 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-06-28 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-03-17 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-10 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010145 | 2020-05-01 |  |  |  | HDME000884 | 2020-05-10 | QC Passed
TBL0227-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | CP3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2020-06-30 |  | OUG-1000-CO120,120S/9F | OUG-ON1 | 1000 | 120 | 9 | 9 |  | 1819000 | Bangkok | เขตบางรัก | 2020-12-10 | 2021-02-01 | Finished | [34 empty] | 2020-12-01 | 2020-11-13 | 2020-11-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-10 | 2021-01-12 | 2020-11-19 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-23 | Finished |  |  | 100 | [41 empty] | 2021-01-23 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-13 | 2021-01-31 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-02-13 | Finished |  |  | 100 | 2021-02-17 | 2021-06-10 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-06-28 | Finished | OTHERS |  | 2021-03-17 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-10 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 702 | 88 | 24 | 16 | 830 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010145 | 2020-05-01 |  |  |  | HDME000884 | 2020-05-10 | QC Passed
TBK0185-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | FL | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2021-02-15 |  | HVF-1600-CO180,180S/29F | HVF-5 | 1600 | 180 | 29 | 29 |  | 4815000 | Bangkok | เขตบางรัก | 2020-12-10 | 2020-12-10 | Finished | [34 empty] | 2020-12-01 | 2020-11-13 | 2020-11-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-10 | 2021-01-12 | 2020-11-19 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-23 | Finished |  |  | 100 | [41 empty] | 2021-01-23 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-13 | 2021-01-31 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-02-13 | Finished |  |  | 100 | 2021-02-17 | 2021-08-16 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | OTHERS |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2020-11-13 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1780 | 114 | 56 | 24 | 1974 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2020-12-01 |  |  |  | HDME001031 | 2020-11-13 | QC Passed
TBK0181-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | H1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2021-04-19 |  | HVF-1600-CO240,240S/28F | HVF-5 | 1600 | 240 | 10 | 28 |  | 5457000 | Bangkok | เขตบางรัก | 2020-10-10 | 2021-02-01 | Finished | [34 empty] | 2020-10-01 | 2020-10-02 | 2020-10-02 | Finished | OTHERS | [13 empty] | 2020-10-10 | 2020-11-11 | 2020-08-17 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-06 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-28 | Finished |  |  | 100 | [41 empty] | 2020-10-28 | 2020-10-24 | 2020-10-24 | Finished |  |  | 2021-11-12 | 2020-10-29 | Finished |  |  | 2020-10-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-04-09 | 2021-08-16 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | OTHERS |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-03-12 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1731 | 114 | 56 | 24 | 1925 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2021-02-01 |  |  |  | HDME001165 | 2021-03-12 | QC Passed
TBK0182-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | H2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2021-04-19 |  | HVF-1600-CO240,240S/28F | HVF-5 | 1600 | 240 | 10 | 28 |  | 5457000 | Bangkok | เขตบางรัก | 2020-12-10 | 2021-02-01 | Finished | [34 empty] | 2020-12-01 | 2020-11-13 | 2020-11-13 | Finished | STORE AREA | [13 empty] | 2020-12-10 | 2021-01-11 | 2020-11-20 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | [41 empty] | 2020-12-25 | 2020-12-23 | 2020-12-23 | Finished |  |  | 2021-01-12 | 2020-12-24 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-29 | Finished |  |  | 100 | 2021-04-09 | 2021-08-16 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-03-12 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1731 | 114 | 56 | 24 | 1925 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2021-02-01 |  |  |  | HDME001165 | 2021-03-12 | QC Passed
TBK0183-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | H3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2021-02-26 |  | HVF-1600-CO240,240S/28F | HVF-5 | 1600 | 240 | 10 | 28 |  | 5457000 | Bangkok | เขตบางรัก | 2021-02-10 | 2021-02-01 | Finished | [34 empty] | 2021-02-01 | 2021-03-12 | 2021-03-12 | Finished | STORE AREA | [13 empty] | 2021-02-10 | 2021-03-11 | 2021-02-04 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-04-03 | Finished |  |  | 100 | [41 empty] | 2021-04-03 | 2021-03-25 | 2021-03-25 | Finished |  |  | 2021-03-12 | 2021-04-03 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-04-18 | Finished |  |  | 100 | 2021-04-09 | 2021-08-16 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-03-23 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1731 | 114 | 56 | 24 | 1925 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2020-12-16 |  |  |  | HDME001174 | 2021-03-23 | QC Passed
TBK0184-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | H4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2021-02-26 |  | HVF-1600-CO240,240S/28F | HVF-5 | 1600 | 240 | 10 | 28 |  | 5457000 | Bangkok | เขตบางรัก | 2021-02-10 | 2021-02-01 | Finished | [34 empty] | 2021-02-01 | 2021-03-12 | 2021-03-12 | Finished | STORE AREA | [13 empty] | 2021-02-10 | 2021-03-11 | 2021-02-04 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-04-03 | Finished |  |  | 100 | [41 empty] | 2021-04-03 | 2021-03-25 | 2021-03-25 | Finished |  |  | 2021-03-12 | 2021-04-03 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-04-18 | Finished |  |  | 100 | 2021-04-09 | 2021-08-16 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-03-23 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1731 | 114 | 56 | 24 | 1925 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2020-12-16 |  |  |  | HDME001174 | 2021-03-23 | QC Passed
TBK0177-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2021-02-15 |  | HVF-1600-CO180,180S/20F | HVF-5 | 1600 | 180 | 12 | 20 |  | 4815000 | Bangkok | เขตบางรัก | 2020-05-01 | 2020-05-13 | Finished | [34 empty] | 2020-05-01 | 2020-05-10 | 2020-05-10 | Finished | STORE AREA | [13 empty] | 2020-05-01 | 2020-05-30 | 2020-05-24 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-08 | Finished |  |  | 100 | [41 empty] | 2020-06-08 | 2020-07-03 | 2020-07-03 | Finished |  |  | 2020-06-01 | 2020-07-04 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | 2021-02-22 | 2021-08-16 | 2021-02-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2020-11-13 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1339 | 108 | 40 | 24 | 1511 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2020-12-01 |  |  |  | HDME001031 | 2020-11-13 | QC Passed
TBK0178-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2021-02-15 |  | HVF-1600-CO180,180S/20F | HVF-5 | 1600 | 180 | 12 | 20 |  | 4815000 | Bangkok | เขตบางรัก | 2020-05-01 | 2020-05-13 | Finished | [34 empty] | 2020-05-01 | 2020-05-11 | 2020-05-10 | Finished | STORE AREA | [13 empty] | 2020-05-01 | 2020-05-30 | 2020-05-24 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-08 | Finished |  |  | 100 | [41 empty] | 2020-06-08 | 2020-07-03 | 2020-07-03 | Finished |  |  | 2020-06-01 | 2020-07-04 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | 2021-02-22 | 2021-08-16 | 2021-02-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2020-11-13 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1339 | 108 | 40 | 24 | 1511 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2020-12-01 |  |  |  | HDME001031 | 2020-11-13 | QC Passed
TBK0179-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2020-12-15 |  | HVF-1600-CO180,180S/20F | HVF-5 | 1600 | 180 | 12 | 20 |  | 4815000 | Bangkok | เขตบางรัก | 2020-05-01 | 2020-05-13 | Finished | [34 empty] | 2020-05-01 | 2020-05-12 | 2020-05-10 | Finished | STORE AREA | [13 empty] | 2020-05-01 | 2020-05-30 | 2020-05-24 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-01 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-22 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-06-08 | Finished |  |  | 100 | [41 empty] | 2020-06-08 | 2020-07-03 | 2020-07-03 | Finished |  |  | 2020-06-01 | 2020-07-04 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-09 | Finished |  |  | 100 | 2021-02-17 | 2021-08-16 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2020-10-02 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-08 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1339 | 108 | 40 | 24 | 1511 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2020-10-01 |  |  |  | HDME001001 | 2020-10-02 | QC Passed
TBK0180-TH | HET | 61000661 | HO | ส่งมอบแล้ว | - | TH209037 | Kronos Office Building, Sathorn | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-09-02 | 2020-05-01 | 2020-12-15 |  | HVF-1600-CO180,180S/20F | HVF-5 | 1600 | 180 | 12 | 20 |  | 4815000 | Bangkok | เขตบางรัก | 2020-10-10 | 2021-02-01 | Finished | [34 empty] | 2020-10-01 | 2020-10-02 | 2020-10-02 | Finished | OTHERS | [13 empty] | 2020-10-10 | 2020-11-11 | 2020-08-17 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-06 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-28 | Finished |  |  | 100 | [41 empty] | 2020-10-28 | 2020-10-24 | 2020-10-24 | Finished |  |  | 2021-11-12 | 2020-10-29 | Finished |  |  | 2020-10-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-17 | 2021-08-16 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-07-30 | Finished | OTHERS |  | 2021-07-30 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2020-10-02 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-08 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 1339 | 108 | 40 | 24 | 1511 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010050 | 2020-10-01 |  |  |  | HDME001001 | 2020-10-02 | QC Passed
TAC1694-TH | HET | 61000662 | HO | ส่งมอบแล้ว | - | TH209056 | Chewathai Kaset Nawamin | P1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Phumiphat Siprajan | 2019-11-25 | 2020-04-25 | 2020-06-25 | 2020-11-28 | VFI-1000-CO150,150S/25F | VFI-II | 1000 | 150 | 25 | 25 |  | 2150000 | Bangkok | แขวงเสนานิคม เขตจตุจักร | 2020-04-25 | 2020-04-25 | Finished | [34 empty] | 2020-04-25 | 2020-04-29 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-25 | 2020-06-25 | 2020-04-26 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-25 | Finished |  |  | 100 | [41 empty] | 2020-06-25 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2020-06-22 | 2020-07-10 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-25 | Finished |  |  | 100 | 2021-01-29 | 2021-06-18 | 2021-01-29 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-06-18 | Finished |  |  | 100 | 2021-01-20 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2019-12-24 | Finished | [18 empty] | 2020-04-28 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 1632 | 117 | 48 | 24 | 1821 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010083 | 2020-04-25 |  |  |  | HDME000864 | 2020-04-28 | QC Passed
TAC1695-TH | HET | 61000662 | HO | ส่งมอบแล้ว | - | TH209056 | Chewathai Kaset Nawamin | P2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Phumiphat Siprajan | 2019-11-25 | 2020-04-25 | 2020-06-25 | 2020-11-28 | VFI-1000-CO150,150S/25F | VFI-II | 1000 | 150 | 25 | 25 |  | 2150000 | Bangkok | แขวงเสนานิคม เขตจตุจักร | 2020-04-25 | 2020-04-25 | Finished | [34 empty] | 2020-04-25 | 2020-04-29 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-25 | 2020-06-25 | 2020-04-26 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-25 | Finished |  |  | 100 | [41 empty] | 2020-06-25 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2020-06-22 | 2020-07-10 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-25 | Finished |  |  | 100 | 2021-01-29 | 2021-06-18 | 2021-01-29 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-06-18 | Finished |  |  | 100 | 2021-01-20 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2019-12-24 | Finished | [18 empty] | 2020-04-28 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 1632 | 117 | 48 | 24 | 1821 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010083 | 2020-04-25 |  |  |  | HDME000864 | 2020-04-28 | QC Passed
TAC1696-TH | HET | 61000662 | HO | ส่งมอบแล้ว | - | TH209056 | Chewathai Kaset Nawamin | P3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Phumiphat Siprajan | 2019-11-25 | 2020-04-25 | 2020-06-25 | 2020-11-28 | VFI-1000-CO150,150S/25F | VFI-II | 1000 | 150 | 25 | 25 |  | 2150000 | Bangkok | แขวงเสนานิคม เขตจตุจักร | 2020-04-25 | 2020-04-25 | Finished | [34 empty] | 2020-04-25 | 2020-04-29 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-25 | 2020-06-25 | 2020-04-26 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-25 | Finished |  |  | 100 | [41 empty] | 2020-06-25 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2020-06-22 | 2020-07-10 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-01-29 | 2021-06-18 | 2021-01-29 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-06-18 | Finished |  |  | 100 | 2021-01-20 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2019-12-24 | Finished | [18 empty] | 2020-04-28 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 1632 | 117 | 48 | 24 | 1821 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010083 | 2020-04-25 |  |  |  | HDME000864 | 2020-04-28 | QC Passed
TAC1697-TH | HET | 61000662 | HO | ส่งมอบแล้ว | - | TH209056 | Chewathai Kaset Nawamin | S1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Phumiphat Siprajan | 2019-11-25 | 2020-04-25 | 2020-06-25 | 2020-11-28 | VFI-1600-CO150,150S/25F | VFI-II | 1600 | 150 | 25 | 25 |  | 2450000 | Bangkok | แขวงเสนานิคม เขตจตุจักร | 2020-04-25 | 2020-04-25 | Finished | [34 empty] | 2020-04-25 | 2020-04-29 | 2020-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-25 | 2020-06-25 | 2020-04-26 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-05-30 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-25 | Finished |  |  | 100 | [41 empty] | 2020-06-25 | 2020-06-22 | 2020-06-22 | Finished |  |  | 2020-06-22 | 2020-07-10 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2021-03-04 | 2021-06-18 | 2021-03-04 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-06-18 | Finished |  |  | 100 | 2021-01-20 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2019-12-24 | Finished | [18 empty] | 2020-04-28 | Finished |  |  | 2020-05-08 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 1632 | 117 | 48 | 24 | 1821 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010083 | 2020-04-25 |  |  |  | HDME000864 | 2020-04-28 | QC Passed
TFA1327-TH | HET | 61000663 | HO | ส่งมอบแล้ว | - | TH209059 | Mun Mun Seacon Square Srinakharin (ES9,ES10) | ES10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-11-13 | 2020-03-13 | 2020-04-10 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2020-05-07 | [20 empty] | 2020-06-01 | Finished | [14 empty] | 2020-03-13 | 2020-04-14 | 2020-05-07 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-06-03 | 2020-06-22 | [41 empty] | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-07 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-06 | Finished |  |  | 2020-06-10 | Finished |  |  | 100 | 2020-06-10 | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-07-20 | 2020-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-08-25 | Finished |  |  | 100 | 2021-05-13 | 2021-02-04 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-12-21 | Finished | [10 empty] | 2021-01-15 | Finished | [6 empty] | 2020-05-07 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010108 | 2020-03-13 |  |  |  | HDME000883 | 2020-05-07 | QC Passed
TFA1326-TH | HET | 61000663 | HO | ส่งมอบแล้ว | - | TH209059 | Mun Mun Seacon Square Srinakharin (ES9,ES10) | ES9 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Phumiphat Siprajan | 2019-11-13 | 2020-03-13 | 2020-04-10 | 2020-08-30 | 1200SX-EN,R4.35M,D30 | SX-EN |  |  |  |  | 4350 | 909500 | Bangkok | เขตประเวศ | 2020-05-07 | [20 empty] | 2020-06-01 | Finished | [14 empty] | 2020-03-13 | 2020-04-14 | 2020-05-07 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-06-03 | 2020-06-22 | [41 empty] | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-07 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-06 | Finished |  |  | 2020-06-10 | Finished |  |  | 100 | 2020-06-10 | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-07-20 | 2020-08-15 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-08-25 | Finished |  |  | 100 | 2021-05-13 | 2021-06-14 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-10-17 | Finished | CONSTRUCTION DELAY |  | 2020-10-06 | Finished |  |  | 2019-12-21 | Finished | [10 empty] | 2021-01-15 | Finished | [6 empty] | 2020-05-07 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-05-22 | Finished |  |  | 2020-10-06 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 567 | 42 | 16 | 21 | 646 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010108 | 2020-03-13 |  |  |  | HDME000883 | 2020-05-07 | QC Passed
TFA1328-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | ESC-1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 6 |  | 1 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | 1000TX-EN,R4.4M,D35 | TX-EN |  |  |  |  | 4400 | 952300 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | [20 empty] | 2020-05-30 | Finished | [14 empty] | 2020-04-30 | 2020-05-11 | 2020-05-11 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2020-05-06 | 2020-07-20 | [41 empty] | 2020-06-01 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-06-20 | Finished |  |  | 100 | 2020-06-20 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-16 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-21 | Finished |  |  | 100 | 2020-10-09 | 2021-06-10 | 2020-10-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-03-05 | Finished | POWER SUPPLY DELAY |  | 2021-02-17 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010247 | 2020-04-30 |  |  |  | HDME000886 | 2020-05-11 | QC Passed
TFA1329-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | ESC-2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 6 |  | 1 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | 1000TX-EN,R4.4M,D35 | TX-EN |  |  |  |  | 4400 | 952300 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | [20 empty] | 2020-05-30 | Finished | [14 empty] | 2020-04-30 | 2020-05-11 | 2020-05-11 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2020-05-06 | 2020-07-20 | [41 empty] | 2020-06-01 | Finished |  |  | 2020-06-02 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-07 | Finished |  |  | 2020-06-07 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-18 | Finished |  |  | 100 | 2020-06-18 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-16 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-20 | Finished |  |  | 100 | 2020-10-09 | 2021-06-10 | 2020-10-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-03-05 | Finished | POWER SUPPLY DELAY |  | 2021-02-17 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010247 | 2020-04-30 |  |  |  | HDME000886 | 2020-05-11 | QC Passed
TFA1330-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | ESC-3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 6 |  | 1 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | 1000TX-EN,R5.35M,D35 | TX-EN |  |  |  |  | 5350 | 1038970 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | [20 empty] | 2020-05-30 | Finished | [14 empty] | 2020-04-30 | 2020-05-11 | 2020-05-11 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2020-05-06 | 2020-07-20 | [41 empty] | 2020-06-01 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-06-20 | Finished |  |  | 100 | 2020-06-20 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-16 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-22 | Finished |  |  | 100 | 2020-10-09 | 2021-06-10 | 2020-10-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-03-05 | Finished | POWER SUPPLY DELAY |  | 2021-02-17 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010247 | 2020-04-30 |  |  |  | HDME000886 | 2020-05-11 | QC Passed
TFA1331-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | ESC-4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 6 |  | 1 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | 1000TX-EN,R5.35M,D35 | TX-EN |  |  |  |  | 5350 | 1038970 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | [20 empty] | 2020-05-30 | Finished | [14 empty] | 2020-04-30 | 2020-05-11 | 2020-05-11 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2020-05-06 | 2020-07-20 | [41 empty] | 2020-06-01 | Finished |  |  | 2020-06-02 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-18 | Finished |  |  | 100 | 2020-06-18 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-16 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-24 | Finished |  |  | 100 | 2020-10-09 | 2021-06-23 | 2020-10-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-23 | Finished |  |  | 100 | 2021-03-05 | Finished | POWER SUPPLY DELAY |  | 2021-02-17 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010247 | 2020-04-30 |  |  |  | HDME000886 | 2020-05-11 | QC Passed
TEC0162-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | D1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | DT-100S-B30,30S/8F | DT | 100 | 30 | 8 | 8 |  | 385200 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | 2020-05-29 | Finished | [34 empty] | 2020-04-30 | 2020-05-07 | 2020-05-07 | Finished | [14 empty] | 2020-05-06 | 2020-07-20 | 2020-06-01 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | [41 empty] | 2020-06-19 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-25 | Finished |  |  | 2020-09-27 | Finished |  |  | 2020-09-29 | Finished |  |  | 100 | [18 empty] | 0 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2021-02-28 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-28 | Finished | [13 empty] | dumb |  |  |  |  | 338 | 0 | 24 | 0 | 362 | 0 | 0 | 24 | 0 | 24 | 93.37 | Blue |  |  | 20010246 | 2020-04-30 |  |  |  | HDME000888 | 2020-05-14
TAD0434-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | LIFT-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | B-1000-2S105,105S/8F | B-II(VFI-II) | 1000 | 105 | 8 | 8 |  | 1540800 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | 2020-05-07 | Finished | [34 empty] | 2020-04-30 | 2020-05-04 | 2020-05-04 | Finished | [14 empty] | 2020-05-06 | 2020-07-20 | 2020-05-08 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-17 | Finished |  |  | 100 | [41 empty] | 2020-05-17 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-21 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-29 | Finished |  |  | 100 | 2020-07-03 | 2021-01-29 | 2020-07-03 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2021-02-28 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010245 | 2020-04-30 |  |  |  | HDME000881 | 2020-05-05 | QC Passed
TAD0435-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | LIFT-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | B-1000-2S105,105S/8F | B-II(VFI-II) | 1000 | 105 | 8 | 8 |  | 1540800 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | 2020-05-07 | Finished | [34 empty] | 2020-04-30 | 2020-05-04 | 2020-05-04 | Finished | [14 empty] | 2020-05-06 | 2020-07-20 | 2020-05-08 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-06-03 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-18 | Finished |  |  | 100 | [41 empty] | 2020-05-18 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-22 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-30 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2021-02-28 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20010245 | 2020-04-30 |  |  |  | HDME000881 | 2020-05-05 | QC Passed
TAD0436-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | LIFT-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | B-1000-2S105,105S/8F | B-II(VFI-II) | 1000 | 105 | 8 | 8 |  | 1540800 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | 2020-05-14 | Finished | [34 empty] | 2020-04-30 | 2020-05-04 | 2020-05-04 | Finished | [14 empty] | 2020-05-06 | 2020-07-20 | 2020-05-15 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-05-17 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-05-21 | Finished |  |  | 100 | [41 empty] | 2020-05-21 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-23 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-07-03 | 2021-06-14 | 2020-07-03 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2021-02-28 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010245 | 2020-04-30 |  |  |  | HDME000881 | 2020-05-05 | QC Passed
TAC1698-TH | HET | 61000665 | HO | ส่งมอบแล้ว | - | TH209061 | CGH Hospital Lamlukka | LIFT-4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-06 | 2020-04-30 | 2020-08-06 | 2021-03-05 | VFI-1150-CO105,105S/9F | VFI-II | 1150 | 105 | 9 | 9 |  | 1629610 | Pathum Thani | อำเภอลำลูกกา | 2020-05-05 | 2020-05-07 | Finished | [34 empty] | 2020-04-30 | 2020-05-04 | 2020-05-04 | Finished | [14 empty] | 2020-05-06 | 2020-07-20 | 2020-05-10 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-21 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-05-14 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-05-27 | Finished |  |  | 100 | [41 empty] | 2020-05-27 | 2020-09-14 | 2020-09-14 | Finished |  |  | 2020-09-10 | 2020-09-24 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-27 | Finished |  |  | 100 | 2020-10-09 | 2021-06-14 | 2020-10-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2021-02-28 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-05-25 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-28 | Finished |  |  | 2021-02-28 | Finished | [13 empty] | pass |  |  |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010245 | 2020-04-30 |  |  |  | HDME000881 | 2020-05-05 | QC Passed
TEC0163-TH | HET | 61000666 | HO | ยังอยู่ในสัญญา HO | - | TH209062 | Social Security and Mri Building, Vichaivej Internation | DW-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-12-09 | 2020-03-09 | 2020-05-09 | 2021-11-06 | DT-100T-B30,30S/5F | DT | 100 | 30 | 4 | 5 |  | 350000 | Samut Sakhon | ตำบลอ้อมน้อย | 2020-08-15 | 2020-08-15 | Finished | [34 empty] | 2020-03-09 | 2020-03-09 | 2020-03-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-15 | 2020-09-15 | 2020-08-20 | Finished |  |  | 2020-08-22 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-11 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-23 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-12 | Finished |  |  | 2021-06-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | [41 empty] | 2021-06-14 | 1900-01-01 | 2021-06-14 | Waiting | POWER SUPPLY DELAY |  | 2021-10-02 | [12 empty] | 0 | [18 empty] | 0 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-14 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-05-14 | Finished |  |  | 2020-05-29 | Finished |  |  | 2020-05-30 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Green |  |  | 20010191 | 2020-03-09 |  |  |  | HDME000887 | 2020-05-14
TAK0649-TH | HET | 61000666 | HO | ยังอยู่ในสัญญา HO | - | TH209062 | Social Security and Mri Building, Vichaivej Internation | PL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-12-09 | 2020-03-09 | 2020-05-09 | 2021-11-06 | B-1000-2S60,60S/5F | UAG-SN1 | 1000 | 60 | 4 | 5 |  | 1450000 | Samut Sakhon | ตำบลอ้อมน้อย | 2020-08-01 | 2020-08-01 | Finished | [34 empty] | 2020-03-09 | 2020-03-09 | 2020-03-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-01 | 2020-09-15 | 2020-08-03 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | [41 empty] | 2020-08-26 | 2021-08-02 | 2021-08-02 | Finished |  |  | 2021-08-02 | 2021-08-06 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-08-19 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-14 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 16 | 16 | 32 | 93.87 | Green |  |  | 20010190 | 2020-03-09 |  |  |  | HDME000822 | 2020-03-18
TAK0650-TH | HET | 61000666 | HO | ยังอยู่ในสัญญา HO | - | TH209062 | Social Security and Mri Building, Vichaivej Internation | PL-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-12-09 | 2020-03-09 | 2020-05-09 | 2021-11-06 | B-1000-2S60,60S/5F | UAG-SN1 | 1000 | 60 | 4 | 5 |  | 1450000 | Samut Sakhon | ตำบลอ้อมน้อย | 2020-08-01 | 2020-08-01 | Finished | [34 empty] | 2020-03-09 | 2020-03-09 | 2020-03-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-01 | 2020-09-15 | 2020-08-03 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | [41 empty] | 2020-08-26 | 2021-08-02 | 2021-08-02 | Finished |  |  | 2021-08-02 | 2021-08-06 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-08-19 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-14 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 16 | 16 | 32 | 93.87 | Green |  |  | 20010190 | 2020-03-09 |  |  |  | HDME000822 | 2020-03-18
TAK0651-TH | HET | 61000666 | HO | ยังอยู่ในสัญญา HO | - | TH209062 | Social Security and Mri Building, Vichaivej Internation | SL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2019-12-09 | 2020-03-09 | 2020-05-09 | 2021-11-06 | B-1000-2S60,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1425000 | Samut Sakhon | ตำบลอ้อมน้อย | 2020-08-15 | 2020-08-15 | Finished | [34 empty] | 2020-03-09 | 2020-03-09 | 2020-03-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-15 | 2020-09-15 | 2020-08-20 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-08-30 | Finished |  |  | 2020-08-04 | Finished |  |  | 2020-08-05 | Finished |  |  | 100 | [41 empty] | 2020-08-05 | 2021-08-02 | 2021-08-02 | Finished |  |  | 2021-08-02 | 2021-08-06 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-08-19 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-14 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished |  |  | 2020-03-18 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 16 | 16 | 32 | 93.87 | Green |  |  | 20010190 | 2020-03-09 |  |  |  | HDME000822 | 2020-03-18
TBL0229-TH | HET | 61000667 | HO | ส่งมอบแล้ว | - | TH209064 | NARA 15 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2019-12-13 | 2020-10-12 | 2020-12-13 | 2021-05-30 | OUG-600-CO60,60S/8F | OUG-ON1 | 600 | 60 | 8 | 8 |  | 1439100 | Bangkok | แขวงทุ่งมหาเมฆ เขตสาทร | 2020-09-30 | 2020-10-19 | Finished | [34 empty] | 2020-10-12 | 2020-10-21 | 2020-10-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-13 | 2020-11-01 | 2020-10-21 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-29 | Finished |  |  | 2020-10-29 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-11-02 | Finished |  |  | 100 | [41 empty] | 2020-11-02 | 2021-05-05 | 2021-05-05 | Finished |  |  | 2020-11-02 | 2021-05-06 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 100 | 2021-01-11 | 2021-05-24 | 2021-01-11 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-05-24 | Finished | [6 empty] | 90 | 2021-05-19 | Finished | POWER SUPPLY DELAY |  | 2021-05-21 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-05-21 | Finished | [6 empty] | 2020-10-17 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-22 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  | pass | 2021-07-08 | Finished |  |  | 649 | 88 | 24 | 16 | 777 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20010360 | 2020-10-12 |  |  |  | HDME001011 | 2020-10-17 | QC Passed
TAJ0652-TH | HET | 61000668 | HO | ส่งมอบแล้ว | - | TH209065 | The Charotte Hotel | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2019-12-17 | 2020-04-17 | 2020-06-17 | 2020-11-23 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 963000 | Lop Buri | อำเภอเมืองลพบุรี | 2020-04-17 | 2020-04-23 | Finished | [34 empty] | 2020-04-17 | 2020-04-21 | 2020-04-21 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-04-17 | 2020-05-17 | 2020-05-05 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-13 | Finished |  |  | 2020-05-14 | Finished |  |  | 100 | [41 empty] | 2020-05-14 | 2020-09-09 | 2020-09-09 | Finished |  |  | 2020-09-09 | 2020-09-11 | Finished |  |  | 2020-09-13 | Finished |  |  | 2020-09-14 | Finished |  |  | 100 | 2020-09-15 | 2021-03-22 | 2020-09-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-24 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | 2020-10-20 | Finished | POWER SUPPLY DELAY |  | 2020-11-10 | Finished |  |  | 2020-01-16 | Finished | [10 empty] | 2021-03-15 | Finished | [6 empty] | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-04-22 | Finished |  |  | 2020-11-10 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass | 2021-03-17 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010389 | 2020-04-17 |  |  |  | HDME000852 | 2020-04-22 | QC Passed
TBF0029-TH | HET | 61000669 | HO | ส่งมอบแล้ว | - | TH209063 | ATTA Donmueng Airport | FL01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-17 | 2020-04-30 | 2020-05-30 | 2020-07-31 | F-2000-2S60,60S/3F | F-EL | 2000 | 60 | 2 | 3 |  | 3210000 | Bangkok | เขตดอนเมือง | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-04-30 | 2020-06-18 | 2020-06-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-30 | 2020-06-15 | 2020-04-30 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | [41 empty] | 2020-06-24 | 2020-06-24 | 2020-06-24 | Finished |  |  | 2020-06-24 | 2020-06-24 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2020-07-10 | 2021-02-10 | 2020-07-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-17 | Finished |  |  | 2021-02-10 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-18 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2020-06-18 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 515 | 94 | 36 | 20 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010381 | 2020-04-30 |  |  |  | HDME000906 | 2020-06-18 | QC Passed
TBF0030-TH | HET | 61000669 | HO | ส่งมอบแล้ว | - | TH209063 | ATTA Donmueng Airport | FL02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-17 | 2020-04-30 | 2020-05-30 | 2020-07-31 | F-2000-2S60,60S/3F | F-EL | 2000 | 60 | 2 | 3 |  | 3210000 | Bangkok | เขตดอนเมือง | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-04-30 | 2020-06-18 | 2020-06-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-30 | 2020-06-15 | 2020-04-30 | Finished |  |  | 2020-05-10 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | [41 empty] | 2020-06-24 | 2020-06-24 | 2020-06-24 | Finished |  |  | 2020-06-24 | 2020-06-24 | Finished |  |  | 2020-06-25 | Finished |  |  | 2020-06-27 | Finished |  |  | 100 | 2020-07-10 | 2021-01-25 | 2020-07-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-17 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-18 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2020-06-18 | Finished |  |  | 2020-06-22 | Finished |  |  | 2020-06-23 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 515 | 94 | 36 | 20 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010381 | 2020-04-30 |  |  |  | HDME000906 | 2020-06-18 | QC Passed
TAC1699-TH | HET | 61000669 | HO | ส่งมอบแล้ว | - | TH209063 | ATTA Donmueng Airport | PL01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2019-12-17 | 2020-04-30 | 2020-05-30 | 2020-07-31 | VFI-750-CO60,60S/3F | VFI-II | 750 | 60 | 2 | 3 |  | 963000 | Bangkok | เขตดอนเมือง | 2020-04-30 | 2020-04-30 | Finished | [34 empty] | 2020-04-30 | 2020-03-31 | 2020-03-31 | Finished | [14 empty] | 2020-04-30 | 2020-05-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-24 | Finished |  |  | 100 | [41 empty] | 2020-06-24 | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-05-01 | 2020-05-01 | Finished |  |  | 2020-05-04 | Finished |  |  | 2020-05-08 | Finished |  |  | 100 | 2020-03-23 | 2021-08-03 | 2020-03-23 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-07-17 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2020-08-30 | Finished | CONSTRUCTION DELAY |  | 2020-08-18 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2020-03-28 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-03-31 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 417 | 89 | 16 | 16 | 538 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010426 | 2020-04-30 |  |  |  | HDME000837 | 2020-03-28 | QC Passed
TAC1700-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1600-2S105,105S/8F | VFI-II | 1600 | 105 | 8 | 8 |  | 2000000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-31 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-22 | 2000-01-01 | 2021-02-22 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 6 | 16 | 22 | 97.34 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1709-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 10 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1000-CO105,105S/8F | VFI-II | 1000 | 105 | 8 | 8 |  | 1475000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-11 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 74 | 6 | 16 | 96 | 88.38 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1710-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 11 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1000-CO105,105S/8F | VFI-II | 1000 | 105 | 8 | 8 |  | 1475000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-11 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 74 | 6 | 16 | 96 | 88.38 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1701-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1600-2S105,105S/8F | VFI-II | 1600 | 105 | 8 | 8 |  | 2000000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-31 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-22 | 2000-01-01 | 2021-02-22 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 6 | 16 | 22 | 97.34 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1702-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1600-2S105,105S/8F | VFI-II | 1600 | 105 | 8 | 8 |  | 2000000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-31 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-22 | 2000-01-01 | 2021-02-22 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 6 | 16 | 22 | 97.34 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1703-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1600-2S105,105S/8F | VFI-II | 1600 | 105 | 8 | 8 |  | 2000000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-31 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-22 | 2000-01-01 | 2021-02-22 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 6 | 16 | 22 | 97.34 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1704-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1600-2S105,105S/8F | VFI-II | 1600 | 105 | 8 | 8 |  | 2000000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-31 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-22 | 2000-01-01 | 2021-02-22 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 6 | 16 | 22 | 97.34 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1705-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1600-2S105,105S/9F | VFI-II | 1600 | 105 | 9 | 9 |  | 2050000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-03-11 | 2000-01-01 | 2021-03-11 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 748 | 94 | 24 | 16 | 882 | 0 | 75 | 6 | 16 | 97 | 89 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1706-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1600-2S105,105S/9F | VFI-II | 1600 | 105 | 9 | 9 |  | 2050000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-03-11 | 2000-01-01 | 2021-03-11 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 748 | 94 | 24 | 16 | 882 | 0 | 75 | 6 | 16 | 97 | 89 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1707-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1000-CO105,105S/8F | VFI-II | 1000 | 105 | 8 | 8 |  | 1475000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-04 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-03-11 | 2000-01-01 | 2021-03-11 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 74 | 6 | 16 | 96 | 88.38 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAC1708-TH | HET | 61000670 | Test | เลยสัญญา HO | - | TH199091 | Maharaj Nakhonratchasima Hospital (IPD 496 beds buildin | 9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-03-01 | 2020-09-07 | 2020-12-20 | 2021-09-25 | VFI-1000-CO105,105S/8F | VFI-II | 1000 | 105 | 8 | 8 |  | 1475000 | Nakhon Ratchasima | ต.ในเมือง | 2020-08-15 | 2020-09-07 | Finished | [34 empty] | 2020-09-07 | 2020-08-29 | 2020-08-29 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-07 | 2020-10-07 | 2020-09-09 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-04 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-19 | 2021-08-19 | Finished |  |  | 2021-11-01 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-03-11 | 2000-01-01 | 2021-03-11 | Finished | [14 empty] | 25 | 2021-11-26 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 74 | 6 | 16 | 96 | 88.38 | Red |  |  | 20011300 | 2020-08-03 |  |  |  | HDME000964 | 2020-08-29
TAD0437-TH | HET | 61000672 | HO | ส่งมอบแล้ว | - | TH209068 | Inpatient Building, Phra Phrom Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2019-12-24 | 2020-04-24 | 2020-06-24 | 2020-08-20 | B-1000-2S60,60S/3F | B-II(VFI-II) | 1000 | 60 | 3 | 3 |  | 1350000 | Nakhon Si Thammarat | อำเภอพระพรหม | 2020-04-24 | 2020-04-20 | Finished | [34 empty] | 2020-04-24 | 2020-04-19 | 2020-04-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-24 | 2020-05-24 | 2020-04-02 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 2020-04-24 | Finished |  |  | 100 | [41 empty] | 2020-04-24 | 2020-08-20 | 2020-08-20 | Finished |  |  | 2020-07-24 | 2020-08-20 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-08-20 | Finished |  |  | 100 | 2020-06-01 | 2000-01-01 | 2020-06-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-10-02 | Finished |  |  | 100 | 2020-10-03 | Finished | POWER SUPPLY DELAY |  | 2020-09-09 | Finished |  |  | 2020-01-19 | Finished | [18 empty] | 2020-04-18 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-04-29 | Finished |  |  | 2020-09-09 | Finished | [13 empty] | pass (defect) |  |  |  |  | 417 | 89 | 16 | 16 | 538 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010427 | 2020-04-24 |  |  |  | HDME000850 | 2020-04-18
TBL0237-TH | HET | 61000673 | HO | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-CP-01 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 6 | 6 |  | 2800000 | Samut Prakan | อำเภอบางพลี | 2020-11-15 | 2020-11-01 | Finished | [34 empty] | 2020-05-20 | 2020-05-20 | 2020-06-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-15 | 2020-12-08 | 2020-11-04 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-12 | Finished |  |  | 100 | [41 empty] | 2020-12-12 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2021-07-31 | 2020-11-15 | Finished |  |  | 2020-11-21 | Finished | [6 empty] | 80 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2021-05-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 17 | 6 | 16 | 39 | 94.17 | Red |  |  | 20010425 | 2020-05-20 |  |  |  | HDME000914 | 2020-06-30
TBL0238-TH | HET | 61000673 | HO | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-CP-02 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-2000-CO60,60S/6F | OUG-ON1 | 2000 | 60 | 6 | 6 |  | 2800000 | Samut Prakan | อำเภอบางพลี | 2020-11-15 | 2020-11-01 | Finished | [34 empty] | 2020-05-20 | 2020-05-20 | 2020-06-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-15 | 2020-12-08 | 2020-11-04 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-12 | Finished |  |  | 100 | [41 empty] | 2020-12-12 | 2020-11-02 | 2020-11-02 | Finished |  |  | 2021-07-31 | 2020-11-15 | Finished |  |  | 2020-11-21 | Finished | [6 empty] | 80 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2021-05-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished |  |  | 2020-06-30 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 17 | 6 | 16 | 39 | 94.17 | Red |  |  | 20010425 | 2020-05-20 |  |  |  | HDME000914 | 2020-06-30
TBL0230-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-01 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-1600-CO60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 2000000 | Samut Prakan | อำเภอบางพลี | 2021-04-20 | 2021-05-05 | Finished | [34 empty] | 2020-08-15 | 2020-08-15 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-20 | 2021-05-21 | 2021-05-06 | Finished | [14 empty] | 2021-05-08 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 80 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-22 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 108 | 86 | 24 | 16 | 234 | 65.02 | Red |  |  | 20010425 | 2020-08-24 |  |  |  | HDME000995 | 2020-10-01
TBL0231-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-02 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-1600-CO60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 2000000 | Samut Prakan | อำเภอบางพลี | 2021-04-20 | 2021-05-05 | Finished | [34 empty] | 2020-08-15 | 2020-08-15 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-20 | 2021-05-21 | 2021-05-06 | Finished | [14 empty] | 2021-05-08 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 80 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-22 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 108 | 86 | 24 | 16 | 234 | 65.02 | Red |  |  | 20010425 | 2020-08-24 |  |  |  | HDME000995 | 2020-10-01
TBL0232-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-03 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-1600-CO60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 2000000 | Samut Prakan | อำเภอบางพลี | 2021-04-20 | 2021-05-05 | Finished | [34 empty] | 2020-08-15 | 2020-08-15 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-20 | 2021-05-21 | 2021-05-06 | Finished | [14 empty] | 2021-05-08 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 80 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-22 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 108 | 86 | 24 | 16 | 234 | 65.02 | Red |  |  | 20010425 | 2020-08-24 |  |  |  | HDME000995 | 2020-10-01
TBL0233-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-04 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-1600-CO60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 2000000 | Samut Prakan | อำเภอบางพลี | 2021-04-20 | 2021-05-05 | Finished | [34 empty] | 2020-08-15 | 2020-08-15 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-20 | 2021-05-21 | 2021-05-06 | Finished | [14 empty] | 2021-05-08 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 80 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-22 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 108 | 86 | 24 | 16 | 234 | 65.02 | Red |  |  | 20010425 | 2020-08-24 |  |  |  | HDME000995 | 2020-10-01
TBL0234-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-05 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-1600-CO60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 2000000 | Samut Prakan | อำเภอบางพลี | 2021-04-20 | 2021-05-05 | Finished | [34 empty] | 2020-08-15 | 2020-08-15 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-20 | 2021-05-21 | 2021-05-06 | Finished | [14 empty] | 2021-05-08 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 80 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-22 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 108 | 86 | 24 | 16 | 234 | 65.02 | Red |  |  | 20010425 | 2020-08-24 |  |  |  | HDME000995 | 2020-10-01
TBL0235-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-06 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-1600-CO60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 2000000 | Samut Prakan | อำเภอบางพลี | 2021-04-20 | 2021-05-05 | Finished | [34 empty] | 2020-08-15 | 2020-08-15 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-20 | 2021-05-21 | 2021-05-06 | Finished | [14 empty] | 2021-05-08 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 80 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-22 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 108 | 86 | 24 | 16 | 234 | 65.02 | Red |  |  | 20010425 | 2020-08-24 |  |  |  | HDME000995 | 2020-10-01
TBL0236-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-07 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-2000-2S60,60S/7F | OUG-ON1 | 2000 | 60 | 7 | 7 |  | 2250000 | Samut Prakan | อำเภอบางพลี | 2021-03-15 | 2021-04-05 | Finished | [34 empty] | 2020-07-01 | 2020-07-01 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-05 | 2021-05-06 | 2021-04-05 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-11 | Finished |  |  | 2021-04-15 | Finished |  |  | 2021-04-21 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-04-29 | Finished |  |  | 2021-05-02 | Finished |  |  | 2021-05-03 | Finished |  |  | 2021-05-05 | Finished |  |  | 100 | [41 empty] | 2021-05-05 | 2021-05-15 | 2021-05-15 | Finished |  |  | 2021-05-07 | 2021-05-15 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-07-09 | Finished |  |  | 100 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-07-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 24 | 16 | 40 | 94.47 | Red |  |  | 20010425 | 2020-07-01 |  |  |  | HDME000995 | 2020-10-01
TBL0239-TH | HET | 61000673 | Install | เลยสัญญา HO | - | TH209069 | Suvarnabhumi Airport Expansion Project | EL-OFF-08 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | SORAWIT WANITCHAPAK | 2019-12-27 | 2020-05-20 | 2020-10-27 |  | OUG-2000-2S60,60S/6F | OUG-ON1 | 2000 | 60 | 6 | 6 |  | 2150000 | Samut Prakan | อำเภอบางพลี | 2020-11-15 | 2021-01-07 | Finished | [34 empty] | 2020-07-01 | 2020-07-01 | 2020-10-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-15 | 2020-12-08 | 2021-01-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-31 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | [41 empty] | 2021-02-16 | 2021-01-08 | 2021-01-08 | Finished |  |  | 2020-12-09 | 2021-01-15 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-06-18 | Finished |  |  | 100 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-22 | Finished | [6 empty] | 90 | 2021-05-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-25 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 1 | 1 | 99.85 | Red |  |  | 20010425 | 2020-07-01 |  |  |  | HDME000995 | 2020-10-01
TAK0654-TH | HET | 61000674 | HO | เลยสัญญา HO | - | TH209067 | Bangpakok 1 Hospital | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-12-17 | 2020-06-17 | 2020-09-17 |  | B-1000-2S105,105S/6F | UAG-SN1 | 1000 | 105 | 6 | 6 |  | 1326800 | Bangkok | แขวงบางปะกอก | 2020-08-17 | 2021-02-18 | Finished | [34 empty] | 2020-06-17 | 2020-06-19 | 2020-06-19 | Finished | STORE AREA | [13 empty] | 2020-08-18 | 2020-10-01 | 2021-02-19 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-06 | Finished |  |  | 100 | [41 empty] | 2021-03-06 | 1900-01-01 | 2021-03-06 | Waiting | POWER SUPPLY DELAY |  | 2021-09-08 | [12 empty] | 0 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-10-17 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-28 | Finished | [18 empty] | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 6 | 16 | 104 | 81.88 | Red |  |  | 20010428 | 2020-06-17 |  |  |  | HDME000907 | 2020-06-19
TAK0655-TH | HET | 61000674 | HO | เลยสัญญา HO | - | TH209067 | Bangpakok 1 Hospital | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-12-17 | 2020-06-17 | 2020-09-17 |  | B-1000-2S105,105S/6F | UAG-SN1 | 1000 | 105 | 6 | 6 |  | 1326800 | Bangkok | แขวงบางปะกอก | 2020-08-17 | 2021-02-18 | Finished | [34 empty] | 2020-06-17 | 2020-06-19 | 2020-06-19 | Finished | STORE AREA | [13 empty] | 2020-08-18 | 2020-10-01 | 2021-02-19 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-06 | Finished |  |  | 100 | [41 empty] | 2021-03-06 | 1900-01-01 | 2021-03-06 | Waiting | POWER SUPPLY DELAY |  | 2021-09-08 | [12 empty] | 0 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2021-10-17 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-28 | Finished | [18 empty] | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 6 | 16 | 104 | 81.88 | Red |  |  | 20010428 | 2020-06-17 |  |  |  | HDME000907 | 2020-06-19
TAJ0656-TH | HET | 61000674 | HO | เลยสัญญา HO | - | TH209067 | Bangpakok 1 Hospital | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-12-17 | 2020-06-17 | 2020-09-17 |  | P-750-CO105,105S/6F | UAG-SN1 | 750 | 105 | 6 | 6 |  | 1102100 | Bangkok | แขวงบางปะกอก | 2020-08-17 | 2020-07-31 | Finished | [34 empty] | 2020-06-17 | 2020-06-19 | 2020-06-19 | Finished | STORE AREA | [13 empty] | 2020-08-18 | 2020-10-01 | 2020-09-03 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-27 | Finished |  |  | 100 | [41 empty] | 2020-09-27 | 1900-01-01 | 2020-09-27 | Waiting | POWER SUPPLY DELAY |  | 2021-09-08 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-17 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-28 | Finished | [18 empty] | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 24 | 16 | 122 | 78.75 | Red |  |  | 20010428 | 2020-06-17 |  |  |  | HDME000907 | 2020-06-19
TAJ0657-TH | HET | 61000674 | HO | เลยสัญญา HO | - | TH209067 | Bangpakok 1 Hospital | L4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-12-17 | 2020-06-17 | 2020-09-17 |  | P-750-CO105,105S/6F | UAG-SN1 | 750 | 105 | 6 | 6 |  | 1102100 | Bangkok | แขวงบางปะกอก | 2020-08-17 | 2020-07-31 | Finished | [34 empty] | 2020-06-17 | 2020-06-19 | 2020-06-19 | Finished | STORE AREA | [13 empty] | 2020-08-18 | 2020-10-01 | 2020-09-08 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-09-13 | Finished |  |  | 2020-09-13 | Finished |  |  | 2020-09-30 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-10-04 | Finished |  |  | 100 | [41 empty] | 2020-10-04 | 1900-01-01 | 2020-10-04 | Waiting | POWER SUPPLY DELAY |  | 2021-09-08 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-17 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-28 | Finished | [18 empty] | 2020-06-19 | Finished |  |  | 2020-06-19 | Finished |  |  | 2020-06-23 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 24 | 16 | 122 | 78.75 | Red |  |  | 20010428 | 2020-06-17 |  |  |  | HDME000907 | 2020-06-19
TEC0164-TH | HET | 61000674 | HO | เลยสัญญา HO | - | TH209067 | Bangpakok 1 Hospital | L5 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | CHALERMKHUAN KERDPOOM | 2019-12-17 | 2020-06-17 | 2020-09-17 |  | DT-50S-B30,30S/6F | DT | 50 | 30 | 6 | 6 |  | 385200 | Bangkok | แขวงบางปะกอก | 2020-08-17 | 2020-11-02 | Finished | [34 empty] | 2020-06-17 | 2020-09-23 | 2020-09-23 | Finished | OTHERS | [13 empty] | 2020-08-18 | 2020-10-01 | 2020-11-02 | Finished |  |  | 2020-11-03 | Finished |  |  | 2020-11-03 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-12 | Finished |  |  | 100 | [41 empty] | 2020-11-12 | 1900-01-01 | 2020-11-12 | Waiting | POWER SUPPLY DELAY |  | 2021-09-08 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-17 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-28 | Finished | [18 empty] | 2020-09-21 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-24 | Finished | [22 empty] | 283 | 0 | 24 | 0 | 307 | 0 | 0 | 24 | 0 | 24 | 92.18 | Red |  |  | 20010429 | 2020-06-17 |  |  |  | HDME000981 | 2020-09-21
TBL0240-TH | HET | 61000675 | Install | ยังอยู่ในสัญญา HO | - | TH219002 | Home Khun Voraphot Phornprapha | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2020-01-03 | 2021-01-03 | 2021-03-03 | 2021-10-20 | OUG-1500-CO60,60S/7F | OUG-ON1 | 1500 | 60 | 7 | 7 |  | 2942500 | Bangkok | แขวงบางกะปิ | 2021-03-28 | 2021-03-28 | Finished | [34 empty] | 2021-01-03 | 2021-03-08 | 2021-03-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-28 | 2021-05-13 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-10-04 | [12 empty] | 0 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2021-10-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-15 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-03-08 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 596 | 87 | 24 | 16 | 723 | 0 | 87 | 6 | 16 | 109 | 84.92 | Green |  |  | 20010432 | 2021-01-03 |  |  |  | HDME001155 | 2021-03-08
TAJ0658-TH | HET | 61000676 | HO | เลยสัญญา HO | - | TH209070 | Pradipat 7 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2019-12-26 | 2020-12-26 | 2021-03-26 | 2021-04-27 | P-1000-CO60W2,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1139550 | Bangkok | แขวงสามเสนใน | 2020-12-26 | 2021-02-03 | Finished | [34 empty] | 2020-12-26 | 2020-12-26 | 2021-01-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-04 | 2021-02-26 | 2021-02-06 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-14 | Finished |  |  | 2021-02-14 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-03 | Finished |  |  | 100 | [41 empty] | 2021-03-03 | 2021-04-20 | 2021-04-20 | Finished |  |  | 2021-01-27 | 2021-04-24 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-06-24 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-14 | Finished | [6 empty] | 90 | 2021-11-29 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-19 | Finished | [10 empty] | 2022-08-15 | Finished | [6 empty] | 2021-01-14 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 1 | 1 | 99.84 | Red |  |  | 20010431 | 2020-12-26 |  |  |  | HDME001092 | 2021-01-14
TAJ0659-TH | HET | 61000676 | HO | เลยสัญญา HO | - | TH209070 | Pradipat 7 | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2019-12-26 | 2020-12-26 | 2021-03-26 | 2021-04-27 | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1139550 | Bangkok | แขวงสามเสนใน | 2020-12-26 | 2021-02-03 | Finished | [34 empty] | 2020-12-26 | 2020-12-26 | 2021-01-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-04 | 2021-02-26 | 2021-02-06 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-03-07 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-03-04 | Finished |  |  | 100 | [41 empty] | 2021-03-04 | 2021-04-20 | 2021-04-20 | Finished |  |  | 2021-01-27 | 2021-04-24 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-06-24 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-14 | Finished | [6 empty] | 90 | 2021-11-29 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-01-19 | Finished | [10 empty] | 2022-08-15 | Finished | [6 empty] | 2021-01-14 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 1 | 1 | 99.84 | Red |  |  | 20010431 | 2020-12-26 |  |  |  | HDME001092 | 2021-01-14
TAK0660-TH | HET | 61000677 | HO | ส่งมอบแล้ว | - | TH209071 | Vichaivej Hospital Nongkheam | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-12-06 | 2020-03-21 | 2020-05-31 | 2020-10-30 | B-1000-2S60,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1450000 | Bangkok | เขตหนองแขม | 2020-04-20 | 2020-05-01 | Finished | [34 empty] | 2020-03-21 | 2020-04-07 | 2020-04-07 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-05-01 | 2020-05-20 | 2020-05-05 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 100 | [41 empty] | 2020-07-02 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-07-13 | 2020-07-28 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2020-08-21 | 2000-01-01 | 2020-08-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-11 | Finished | [6 empty] | 90 | 2020-09-14 | Finished | POWER SUPPLY DELAY |  | 2020-09-21 | Finished |  |  | 2020-01-23 | Finished | [10 empty] | 2020-09-15 | Finished | [6 empty] | 2020-04-07 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-09-21 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Working |  |  | 2021-03-17 | Working |  | pass (defect) |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20010433 | 2020-03-21 |  |  |  | HDME000842 | 2020-04-07
TAK0661-TH | HET | 61000677 | HO | ส่งมอบแล้ว | - | TH209071 | Vichaivej Hospital Nongkheam | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2019-12-06 | 2020-03-21 | 2020-05-31 | 2020-10-30 | B-1000-2S60,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1450000 | Bangkok | เขตหนองแขม | 2020-04-20 | 2020-05-01 | Finished | [34 empty] | 2020-03-21 | 2020-04-07 | 2020-04-07 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-05-01 | 2020-05-20 | 2020-05-05 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-11 | Finished |  |  | 100 | [41 empty] | 2020-07-11 | 2020-07-27 | 2020-07-27 | Finished |  |  | 2020-07-13 | 2020-07-28 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 100 | 2020-08-21 | 2020-12-25 | 2020-08-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2020-09-14 | Finished | POWER SUPPLY DELAY |  | 2020-09-21 | Finished |  |  | 2020-01-23 | Finished | [10 empty] | 2020-09-15 | Finished | [6 empty] | 2020-04-07 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-09-21 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010433 | 2020-03-21 |  |  |  | HDME000842 | 2020-04-07 | QC Passed
TAJ0662-TH | HET | 61000678 | HO | ส่งมอบแล้ว | - | TH209073 | Ketwadee Beauty School | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | ANUSSARA POLDONGNOK | 2020-01-06 | 2020-04-03 | 2020-05-21 | 2020-06-21 | P-600-CO60W,60S/6F | UAG-SN1 | 600 | 60 | 5 | 6 |  | 1102100 | Bangkok | เขตราชเทวี | 2020-04-30 | 2020-05-08 | Finished | [34 empty] | 2020-04-03 | 2020-04-23 | 2020-04-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-10 | 2020-05-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-06-16 | 2020-06-16 | Finished |  |  | 2020-06-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-06-26 | 2020-09-25 | 2020-06-26 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-09-25 | Finished |  |  | 100 | 2020-06-30 | Finished | CUSTOMER DECORATION DELAY |  | 2020-06-16 | Finished |  |  | 2020-01-19 | Finished | [10 empty] | 2020-06-15 | Finished | [6 empty] | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-04-23 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  | pass | 2020-08-13 | Finished |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010539 | 2020-04-03 |  |  |  | HDME000860 | 2020-04-23 | QC Passed
TAJ0663-TH | HET | 61000679 | HO | ส่งมอบแล้ว | - | TH209072 | Ton Palm Residence | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2020-01-03 | 2020-04-03 | 2020-06-03 | 2021-01-03 | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 1000000 | Bangkok | เขตลาดกระบัง | 2020-04-20 | 2020-04-20 | Finished | [34 empty] | 2020-04-03 | 2020-04-07 | 2020-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-20 | 2020-05-16 | 2020-04-21 | Finished |  |  | 2020-05-04 | Finished |  |  | 2020-05-04 | Finished |  |  | 2020-05-04 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-30 | Finished |  |  | 2020-05-05 | Finished |  |  | 2020-05-06 | Finished |  |  | 2020-05-08 | Finished |  |  | 100 | [41 empty] | 2020-05-08 | 2020-11-18 | 2020-11-18 | Finished |  |  | 2020-08-17 | 2020-11-18 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-25 | Finished |  |  | 100 | 2020-06-08 | 2021-02-04 | 2020-06-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-02 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-16 | Finished |  |  | 2020-01-16 | Finished | [18 empty] | 2020-04-07 | Finished |  |  | 2020-04-07 | Finished |  |  | 2020-04-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010547 | 2020-04-03 |  |  |  | HDME000841 | 2020-04-07 | QC Passed
TAC1711-TH | HET | 61000680 | HO | ส่งมอบแล้ว | - | TH209074 | Vajira Hospital (Dormitory Physician and Nurse Building | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-08-25 | 2020-12-28 | 2021-08-31 | VFI-1000-CO90,90S/8F | VFI-II | 1000 | 90 | 8 | 8 |  | 1444500 | Bangkok | แขวงวชิรพยาบาล | 2020-08-26 | 2020-08-26 | Finished | [34 empty] | 2020-08-25 | 2020-08-29 | 2020-09-02 | Finished | STORE AREA | [13 empty] | 2020-08-26 | 2020-11-26 | 2020-08-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-11-01 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-26 | Finished |  |  | 100 | [41 empty] | 2020-11-26 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-11-30 | 2021-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-03-01 | Finished |  |  | 100 | 2021-03-26 | 2000-01-01 | 2021-03-26 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 50 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 16 | 16 | 98.06 | Blue |  |  | 20010608 | 2020-08-25 |  |  |  | HDME000963 | 2020-08-29
TAC1712-TH | HET | 61000680 | HO | ส่งมอบแล้ว | - | TH209074 | Vajira Hospital (Dormitory Physician and Nurse Building | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-08-25 | 2020-12-28 | 2021-08-31 | VFI-1000-CO90,90S/8F | VFI-II | 1000 | 90 | 8 | 8 |  | 1444500 | Bangkok | แขวงวชิรพยาบาล | 2020-08-26 | 2020-08-26 | Finished | [34 empty] | 2020-08-25 | 2020-08-29 | 2020-09-02 | Finished | CONSTRUCTION STOP | [13 empty] | 2020-08-26 | 2020-11-26 | 2020-08-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-11-01 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-26 | Finished |  |  | 100 | [41 empty] | 2020-11-26 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-11-30 | 2021-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-03-01 | Finished |  |  | 100 | 2021-03-26 | 2000-01-01 | 2021-03-26 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 50 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 16 | 16 | 98.06 | Blue |  |  | 20010608 | 2020-08-25 |  |  |  | HDME000963 | 2020-08-29
TAC1713-TH | HET | 61000680 | HO | ส่งมอบแล้ว | - | TH209074 | Vajira Hospital (Dormitory Physician and Nurse Building | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-08-25 | 2020-12-28 | 2021-08-31 | VFI-1000-CO90,90S/8F | VFI-II | 1000 | 90 | 8 | 8 |  | 1444500 | Bangkok | แขวงวชิรพยาบาล | 2020-08-26 | 2020-08-26 | Finished | [34 empty] | 2020-08-25 | 2020-08-29 | 2020-09-02 | Finished | PAYMENT DELAY | [13 empty] | 2020-08-26 | 2020-11-26 | 2020-08-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-11-01 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-26 | Finished |  |  | 100 | [41 empty] | 2020-11-26 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-11-30 | 2021-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-03-01 | Finished |  |  | 100 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 50 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 16 | 16 | 98.06 | Blue |  |  | 20010608 | 2020-08-25 |  |  |  | HDME000963 | 2020-08-29
TAC1714-TH | HET | 61000680 | HO | ส่งมอบแล้ว | - | TH209074 | Vajira Hospital (Dormitory Physician and Nurse Building | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2019-05-24 | 2020-08-25 | 2020-12-28 | 2021-08-31 | VFI-1000-CO90,90S/8F | VFI-II | 1000 | 90 | 8 | 8 |  | 1444500 | Bangkok | แขวงวชิรพยาบาล | 2020-08-26 | 2020-08-26 | Finished | [34 empty] | 2020-08-25 | 2020-08-29 | 2020-09-02 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-08-26 | 2020-11-26 | 2020-08-27 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-11-01 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-26 | Finished |  |  | 100 | [41 empty] | 2020-11-26 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-11-30 | 2021-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-03-01 | Finished |  |  | 100 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 50 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 16 | 16 | 98.06 | Blue |  |  | 20010608 | 2020-08-25 |  |  |  | HDME000963 | 2020-08-29
TAJ0664-TH | HET | 61000681 | HO | เลยสัญญา HO | - | TH209075 | Tripper Hotel | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-01-08 | 2020-04-23 | 2020-05-23 | 2021-09-15 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1070000 | Ubon Ratchathani | อำเภอเมืองอุบลราชธานี | 2020-04-23 | 2020-08-15 | Finished | [34 empty] | 2020-04-23 | 2020-06-30 | 2020-06-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-23 | 2020-09-22 | 2020-10-18 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-20 | Finished |  |  | 100 | [41 empty] | 2020-10-20 | 1900-01-01 | 2020-10-20 | Waiting | POWER SUPPLY DELAY |  | 2021-09-20 | [12 empty] | 0 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished | [14 empty] | 25 | 2021-10-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-01-23 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-06-30 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-13 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 6 | 16 | 104 | 81.88 | Red |  |  | 20010595 | 2020-04-23 |  |  |  | HDME000913 | 2020-06-30
TAC1717-TH | HET | 61000684 | HO | ส่งมอบแล้ว | - | TH199125 | Langsuan Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-01-09 | 2020-04-25 | 2020-07-09 | 2021-02-28 | VFI-1600-2S90,90S/7F | VFI-II | 1600 | 90 | 7 | 7 |  | 1920000 | Chumphon | อำเภอหลังสวน | 2020-04-24 | 2020-05-07 | Finished | [34 empty] | 2020-04-24 | 2020-04-28 | 2020-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-24 | 2020-07-25 | 2020-05-07 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-10-29 | Finished |  |  | 100 | 2020-11-13 | 2021-05-13 | 2020-11-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-01-10 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2020-02-11 | Finished | [18 empty] | 2020-04-28 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20010702 | 2020-04-28 |  |  |  | HDME000863 | 2020-04-28 | QC Passed
TAC1718-TH | HET | 61000684 | HO | ส่งมอบแล้ว | - | TH199125 | Langsuan Hospital | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-01-09 | 2020-04-25 | 2020-07-09 | 2021-02-28 | VFI-1600-2S90,90S/7F | VFI-II | 1600 | 90 | 7 | 7 |  | 1920000 | Chumphon | อำเภอหลังสวน | 2020-04-24 | 2020-05-07 | Finished | [34 empty] | 2020-04-24 | 2020-04-28 | 2020-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-24 | 2020-07-25 | 2020-05-07 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-10-29 | Finished |  |  | 100 | 2020-07-01 | 2021-02-15 | 2020-07-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-02-15 | Finished |  |  | 100 | 2021-01-10 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2020-02-11 | Finished | [18 empty] | 2020-04-28 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010702 | 2020-04-28 |  |  |  | HDME000863 | 2020-04-28 | QC Passed
TAC1719-TH | HET | 61000684 | HO | ส่งมอบแล้ว | - | TH199125 | Langsuan Hospital | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-01-09 | 2020-04-25 | 2020-07-09 | 2021-02-28 | VFI-1600-2S90,90S/7F | VFI-II | 1600 | 90 | 7 | 7 |  | 1920000 | Chumphon | อำเภอหลังสวน | 2020-04-24 | 2020-05-07 | Finished | [34 empty] | 2020-04-24 | 2020-04-28 | 2020-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-24 | 2020-07-25 | 2020-05-07 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-10-29 | Finished |  |  | 100 | 2020-06-01 | 2021-02-17 | 2020-06-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-01-10 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2020-02-11 | Finished | [18 empty] | 2020-04-28 | Finished |  |  | 2020-04-28 | Finished |  |  | 2020-04-29 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010702 | 2020-04-28 |  |  |  | HDME000863 | 2020-04-28 | QC Passed
TBL0241-TH | HET | 61000684 | HO | ส่งมอบแล้ว | - | TH199125 | Langsuan Hospital | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-01-09 | 2020-04-25 | 2020-07-09 | 2021-02-28 | OUG-2000-CO90,90S/8F | OUG-ON1 | 2000 | 90 | 8 | 8 |  | 2045000 | Chumphon | อำเภอหลังสวน | 2020-04-24 | 2020-05-07 | Finished | [34 empty] | 2020-04-24 | 2020-05-02 | 2020-05-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-24 | 2020-07-25 | 2020-05-07 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-10-29 | Finished |  |  | 100 | 2020-07-01 | 2021-02-17 | 2020-07-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-01-10 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2020-02-11 | Finished | [18 empty] | 2020-05-02 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 649 | 88 | 24 | 16 | 777 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010702 | 2020-06-08 |  |  |  | HDME000879 | 2020-05-02 | QC Passed
TBL0242-TH | HET | 61000684 | HO | ส่งมอบแล้ว | - | TH199125 | Langsuan Hospital | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-01-09 | 2020-04-25 | 2020-07-09 | 2021-02-28 | OUG-2000-CO90,90S/7F | OUG-ON1 | 2000 | 90 | 7 | 7 |  | 1995000 | Chumphon | อำเภอหลังสวน | 2020-04-24 | 2020-06-20 | Finished | [34 empty] | 2020-04-24 | 2020-05-02 | 2020-05-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-24 | 2020-07-25 | 2020-06-10 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-06 | Finished |  |  | 2020-07-07 | Finished |  |  | 100 | [41 empty] | 2020-07-07 | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-08-15 | 2020-08-15 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-10-29 | Finished |  |  | 100 | 2021-05-13 | 2021-07-19 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-19 | Finished |  |  | 100 | 2021-01-10 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2020-02-11 | Finished | [18 empty] | 2020-05-02 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-05-05 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010702 | 2020-06-08 |  |  |  | HDME000879 | 2020-05-02 | QC Passed
TAJ0665-TH | HET | 61000686 | HO | ส่งมอบแล้ว | - | TH209077 | Office Racha Matalsheet | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-01-06 | 2020-05-07 | 2020-07-07 | 2020-11-30 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1100000 | Samut Prakan | อ.เมืองสมุทรปราการ | 2020-05-07 | 2020-06-04 | Finished | [34 empty] | 2020-05-07 | 2020-05-19 | 2020-05-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-08 | 2020-06-20 | 2020-06-06 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-08 | Finished |  |  | 2020-06-14 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-16 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-21 | Finished |  |  | 100 | [41 empty] | 2020-06-21 | 2020-10-16 | 2020-10-16 | Finished |  |  | 2020-10-15 | 2020-10-17 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-22 | Finished |  |  | 100 | 2020-10-27 | 2020-10-27 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-11 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | 2020-10-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-03-15 | Finished | [6 empty] | 2020-05-19 | Finished |  |  | 2020-05-19 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010699 | 2020-05-07 |  |  |  | HDME000892 | 2020-05-19 | QC Passed
TAJ0666-TH | HET | 61000687 | HO | ยังอยู่ในสัญญา HO | - | TH209078 | House Khun Sakanan | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-01-10 | 2020-04-10 | 2020-05-10 | 2021-11-29 | P-750-CO60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1070000 | Bangkok | ถนนเกษตร-นวมินทร์ | 2020-04-30 | 2020-05-11 | Finished | [34 empty] | 2020-04-10 | 2020-05-11 | 2020-05-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-05-11 | 2020-05-25 | 2020-05-13 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-23 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-16 | Finished |  |  | 2020-05-21 | Finished |  |  | 2020-05-21 | Finished |  |  | 2020-05-18 | Finished |  |  | 2020-05-20 | Finished |  |  | 100 | [41 empty] | 2020-05-20 | 2020-11-05 | 2020-11-05 | Finished |  |  | 2020-10-30 | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-10 | Finished |  |  | 100 | 2020-09-25 | 2000-01-01 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished | [10 empty] | 50 | 2021-11-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-02-11 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-05-11 | Finished |  |  | 2020-05-14 | Finished |  |  | 2020-05-20 | Finished | [22 empty] | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 16 | 16 | 95.87 | Green |  |  | 20010755 | 2020-04-10 |  |  |  | HDME000885 | 2020-05-11
TEB0119-TH | HET | 61000688 | HO | ยังอยู่ในสัญญา HO | - | TH209081 | Home KhunSukich Charanvas | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-01-14 | 2020-04-14 | 2020-05-14 | 2021-10-29 | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 2 | 2 |  | 1016500 | Bangkok | ถนนรามคำแหง แขวงพลับพลา | 2021-03-08 | 2021-03-07 | Finished | [34 empty] | 2020-04-01 | 2020-06-18 | 2020-06-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-07 | 2021-05-12 | 2021-03-07 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-14 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-20 | Finished |  |  | 100 | [41 empty] | 2021-03-20 | 1900-01-01 | 2021-03-20 | Waiting | POWER SUPPLY DELAY |  | 2021-10-10 | [12 empty] | 0 | 2021-03-26 | 2000-01-01 | 2021-03-26 | Finished | [14 empty] | 25 | 2021-10-29 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-02-11 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-06-18 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-20 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 4 | 16 | 75 | 70.82 | Green |  |  | 20010754 | 2020-04-01 |  |  |  | HDME000905 | 2020-06-18
TAJ0667-TH | HET | 61000689 | HO | ส่งมอบแล้ว | - | TH209082 | The Quart Ruamrudee | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-01-02 | 2020-06-02 | 2020-09-02 | 2021-09-05 | P-1000-CO105W2,105S/8F | UAG-SN1 | 1000 | 105 | 8 | 8 |  | 1037500 | Bangkok | เขตปทุมวัน | 2020-08-25 | 2020-10-12 | Finished | [34 empty] | 2020-06-02 | 2020-07-15 | 2020-07-15 | Finished | STORE AREA | [13 empty] | 2020-08-30 | 2020-10-30 | 2020-09-09 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-17 | Finished |  |  | 100 | [41 empty] | 2020-10-17 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2020-10-01 | 2021-03-17 | Finished |  |  | 2021-08-14 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-19 | Finished | [6 empty] | 90 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-20 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20010840 | 2020-06-02 |  |  |  | HDME000922 | 2020-07-15
TAJ0668-TH | HET | 61000689 | HO | ส่งมอบแล้ว | - | TH209082 | The Quart Ruamrudee | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-01-02 | 2020-06-02 | 2020-09-02 | 2021-09-05 | P-1000-CO105W2,105S/8F | UAG-SN1 | 1000 | 105 | 8 | 8 |  | 1037500 | Bangkok | เขตปทุมวัน | 2020-08-25 | 2020-10-12 | Finished | [34 empty] | 2020-06-02 | 2020-07-15 | 2020-07-15 | Finished | STORE AREA | [13 empty] | 2020-08-30 | 2020-10-30 | 2020-09-09 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-17 | Finished |  |  | 100 | [41 empty] | 2020-10-17 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2020-10-01 | 2021-03-17 | Finished |  |  | 2021-08-14 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-20 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | in process (defect) |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 6 | 16 | 22 | 96.69 | Blue |  |  | 20010840 | 2020-06-02 |  |  |  | HDME000922 | 2020-07-15
TAJ0669-TH | HET | 61000689 | HO | ส่งมอบแล้ว | - | TH209082 | The Quart Ruamrudee | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-01-02 | 2020-06-02 | 2020-09-02 | 2021-09-05 | P-1000-CO105W2,105S/8F | UAG-SN1 | 1000 | 105 | 8 | 8 |  | 1037500 | Bangkok | เขตปทุมวัน | 2020-08-25 | 2020-10-30 | Finished | [34 empty] | 2020-06-02 | 2020-07-15 | 2020-07-15 | Finished | STORE AREA | [13 empty] | 2020-08-30 | 2020-10-30 | 2020-11-02 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-19 | Finished |  |  | 100 | [41 empty] | 2020-11-19 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2020-10-01 | 2021-03-17 | Finished |  |  | 2021-08-14 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-04-09 | 2021-08-30 | 2021-04-09 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-08-30 | Finished |  |  | 2021-08-30 | Finished |  |  | 100 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-20 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010840 | 2020-06-02 |  |  |  | HDME000922 | 2020-07-15 | QC Passed
TAJ0670-TH | HET | 61000689 | HO | ส่งมอบแล้ว | - | TH209082 | The Quart Ruamrudee | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-01-02 | 2020-06-02 | 2020-09-02 | 2021-09-05 | P-1000-CO105W2,105S/8F | UAG-SN1 | 1000 | 105 | 8 | 8 |  | 1037500 | Bangkok | เขตปทุมวัน | 2020-08-25 | 2020-10-30 | Finished | [34 empty] | 2020-06-02 | 2020-07-15 | 2020-07-15 | Finished | STORE AREA | [13 empty] | 2020-08-30 | 2020-10-30 | 2020-11-02 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-19 | Finished |  |  | 100 | [41 empty] | 2020-11-19 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2020-10-01 | 2021-03-17 | Finished |  |  | 2021-08-14 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-08-30 | Finished | [6 empty] | 90 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-27 | Finished |  |  | 2020-02-11 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-20 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20010840 | 2020-06-02 |  |  |  | HDME000922 | 2020-07-15
TAC1721-TH | HET | 61000690 | HO | ส่งมอบแล้ว | - | TH209083 | โรงพยาบาลพระนั่งเกล้า | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2019-12-09 | 2020-04-30 | 2020-07-05 |  | VFI-1600-2S120,120S/18F | VFI-II | 1600 | 120 | 18 | 18 |  | 4440500 | Nonthaburi | จังหวัดนนทบุรี | 2020-03-28 | [36 empty] | 2020-04-30 | 2020-05-05 | 2020-05-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-04-01 | 2020-06-21 | 2020-04-05 | Finished |  |  | 2020-04-20 | Finished |  |  | 2020-05-01 | Finished |  |  | 2020-05-15 | Finished |  |  | 2020-05-20 | Finished |  |  | 2020-05-25 | Finished |  |  | 2020-06-05 | Finished |  |  | 2020-06-10 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-20 | Finished |  |  | 100 | [41 empty] | 2020-06-20 | 2020-06-24 | 2020-06-24 | Finished |  |  | 2020-06-24 | 2020-07-05 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-15 | Finished |  |  | 100 | 2020-08-31 | 2021-07-09 | 2020-08-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-07-09 | Finished |  |  | 100 | 2020-08-26 | Finished | POWER SUPPLY DELAY |  | 2020-09-03 | Finished |  |  | 2020-02-19 | Finished | [18 empty] | 2020-05-05 | Finished |  |  | 2020-05-06 | Finished |  |  | 2020-05-11 | Finished |  |  | 2020-09-03 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 1246 | 111 | 40 | 20 | 1417 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20010851 | 2020-04-30 |  |  |  | HDME000880 | 2020-05-05 | QC Passed
TAC1722-TH | HET | 61000691 | HO | ส่งมอบแล้ว | - | TH209084 | EMBLAZON C/1 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | ANUSSARA POLDONGNOK | 2020-02-02 | 2020-05-18 | 2020-07-02 | 2020-07-30 | VFI-550-CO60,60S/5F | VFI-II | 550 | 60 | 5 | 5 |  | 1016500 | Bangkok | แขวงคลองกุ่ม เขตบึงกุ่ม | 2020-06-20 | 2020-06-20 | Finished | [34 empty] | 2020-05-18 | 2020-05-27 | 2020-05-27 | Finished | STORE AREA | [13 empty] | 2020-05-19 | 2020-07-02 | 2020-06-20 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-07-03 | Finished |  |  | 2020-06-24 | Finished |  |  | 2020-06-04 | Finished |  |  | 2020-06-27 | Finished |  |  | 2020-06-25 | Finished |  |  | 100 | [41 empty] | 2020-06-25 | 2020-07-23 | 2020-07-23 | Finished |  |  | 2020-07-20 | 2020-07-23 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-08-07 | Finished |  |  | 100 | 2020-06-15 | 2020-08-28 | 2020-06-15 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-28 | Finished | [6 empty] | 90 | 2020-09-10 | Finished | POWER SUPPLY DELAY |  | 2020-08-18 | Finished |  |  | 2020-02-13 | Finished | [10 empty] | 2020-08-15 | Finished | [6 empty] | 2020-05-27 | Finished |  |  | 2020-05-27 | Finished |  |  | 2020-05-29 | Finished |  |  | 2020-08-18 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20010918 | 2020-05-18 |  |  |  | HDME000897 | 2020-05-27 | QC Passed
TAC1723-TH | HET | 61000692 | HO | ส่งมอบแล้ว | - | TH209086 | Vocational College Nakornratchasima Building | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-02-03 | 2020-06-18 | 2020-08-18 | 2021-02-07 | VFI-750-CO60,60S/7F | VFI-II | 750 | 60 | 7 | 7 |  | 1145000 | Nakhon Ratchasima | อำเภอเมือง | 2020-06-04 | [36 empty] | 2020-06-18 | 2020-06-20 | 2020-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-18 | 2020-09-17 | 2020-09-02 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-14 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-29 | Finished |  |  | 100 | [41 empty] | 2020-09-29 | 2020-09-27 | 2020-09-27 | Finished |  |  | 2020-09-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-04-01 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2020-02-26 | Finished | [10 empty] | 2021-01-26 | Finished | [6 empty] | 2020-06-20 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011042 | 2020-06-18 |  |  |  | HDME000908 | 2020-06-20 | QC Passed
TAC1724-TH | HET | 61000692 | HO | ส่งมอบแล้ว | - | TH209086 | Vocational College Nakornratchasima Building | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-02-03 | 2020-06-18 | 2020-08-18 | 2021-02-07 | VFI-750-CO60,60S/7F | VFI-II | 750 | 60 | 7 | 7 |  | 1145000 | Nakhon Ratchasima | อำเภอเมือง | 2020-06-04 | [36 empty] | 2020-06-18 | 2020-06-20 | 2020-06-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-18 | 2020-09-17 | 2020-09-02 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-14 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-29 | Finished |  |  | 100 | [41 empty] | 2020-09-29 | 2020-09-27 | 2020-09-27 | Finished |  |  | 2020-09-27 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-07-02 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-04-01 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2020-02-26 | Finished | [10 empty] | 2021-01-26 | Finished | [6 empty] | 2020-06-20 | Finished |  |  | 2020-06-20 | Finished |  |  | 2020-06-23 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011042 | 2020-06-18 |  |  |  | HDME000908 | 2020-06-20 | QC Passed
TAJ0675-TH | HET | 61000695 |  | เลยสัญญา HO | - | TH209085 | Apartment 8 Fl. Sukhumvit 31 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Phumiphat Siprajan | 2020-01-31 | 2020-08-15 | 2020-10-15 |  | P-750-CO90,90S/8F | UAG-SN1 | 750 | 90 | 8 | 8 |  | 1100000 | Bangkok | เขตวัฒนา | 2021-11-15 | 2021-07-19 | Finished | [34 empty] | 2020-08-15 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2021-08-15 | 2021-10-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-01 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-13 | Finished | [10 empty] | 2022-02-15 | Finished | [38 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Red |  |  | 20011225 | 2020-08-14
TEB0120-TH | HET | 61000698 | HO | เลยสัญญา HO | - | TH209092 | Nantawan Village 13/257 Soi 10/2 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | ANUSSARA POLDONGNOK | 2020-02-15 | 2020-10-15 | 2020-11-30 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 2 | 2 |  | 802500 | Bangkok | ถนนกาญจนาภิเษก | 2020-10-16 | 2020-11-26 | Finished | [34 empty] | 2020-09-30 | 2020-12-01 | 2020-12-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-16 | 2020-11-15 | 2020-11-28 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 100 | [41 empty] | 2020-12-02 | 1900-01-01 | 2020-12-02 | Waiting | POWER SUPPLY DELAY |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-02-25 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-11-27 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 16 | 16 | 87 | 66.15 | Red |  |  | 20011122 | 2020-11-09 |  |  |  | HDME001051 | 2020-11-27
TBL0246-TH | HET | 61000699 | Install | ยังอยู่ในสัญญา HO | - | TH209091 | Track Doubling Project For Northeast line | L1(New Muak Lek Station) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Orawan Kwanpheng | 2020-02-11 | 2020-06-25 | 2020-09-25 | 2021-12-25 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1134200 | Nakhon Ratchasima | อำเภอปากช่อง | 2020-06-20 | 2020-12-16 | Finished | [34 empty] | 2020-07-03 | 2020-11-18 | 2020-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-16 | 2021-01-15 | 2021-05-01 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-08 | Finished |  |  | 100 | [41 empty] | 2021-05-08 | 2020-08-02 | 2020-08-02 | Finished |  |  | 2020-08-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-15 | 2000-01-01 | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-04 | Finished | [6 empty] | 90 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-17 | Finished | [18 empty] | 2020-11-18 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-15 | Finished | [22 empty] | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 1 | 1 | 99.78 | Green |  |  | 20011125 | 2020-07-03 |  |  |  | HDME001037 | 2020-11-18
TBL0243-TH | HET | 61000699 | Install | ยังอยู่ในสัญญา HO | - | TH209091 | Track Doubling Project For Northeast line | L1(Pak Chong Station) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Orawan Kwanpheng | 2020-02-11 | 2020-06-25 | 2020-09-25 | 2021-12-25 | OUG-1000-CO60,60S/3F | OUG-ON1 | 1000 | 60 | 3 | 3 |  | 1241200 | Nakhon Ratchasima | อำเภอปากช่อง | 2020-06-20 | 2020-07-03 | Finished | [34 empty] | 2020-07-03 | 2020-06-26 | 2020-06-26 | Finished | [14 empty] | 2020-07-03 | 2020-08-02 | 2020-07-04 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-08-10 | Finished |  |  | 2020-07-07 | Finished |  |  | 1900-01-03 | Finished |  |  | 2020-08-11 | Finished |  |  | 2020-08-12 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 100 | [41 empty] | 2020-08-14 | 2020-10-23 | 2020-10-23 | Finished |  |  | 2020-10-20 | 2020-10-25 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-28 | Finished |  |  | 100 | 2020-10-27 | 2000-01-01 | 2020-10-27 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-10-27 | Finished | [6 empty] | 90 | 2022-01-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-03-17 | Finished | [18 empty] | 2020-06-26 | Finished |  |  | 2020-06-26 | Finished |  |  | 2020-06-30 | Finished | [17 empty] | pass (defect) |  |  |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 1 | 1 | 99.8 | Green |  |  | 20011125 | 2020-07-03 |  |  |  | HDME000910 | 2020-06-26
TBL0247-TH | HET | 61000699 | Install | ยังอยู่ในสัญญา HO | - | TH209091 | Track Doubling Project For Northeast line | L2(New Muak Lek Station) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Orawan Kwanpheng | 2020-02-11 | 2020-06-25 | 2020-09-25 | 2021-12-25 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1134200 | Nakhon Ratchasima | อำเภอปากช่อง | 2021-11-15 | 2021-07-02 | Finished | [34 empty] | 2020-07-03 | 2020-08-29 | 2020-08-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-03 | 2021-08-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-08-02 | 2020-08-02 | Finished |  |  | 2020-08-02 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-15 | 2000-01-01 | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-04 | Finished | [6 empty] | 90 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-17 | Finished | [50 empty] | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 1 | 1 | 99.78 | Green |  |  | 20011125 | 2020-07-03
TBL0244-TH | HET | 61000699 | Install | ยังอยู่ในสัญญา HO | - | TH209091 | Track Doubling Project For Northeast line | L2(Pak Chong Station) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Orawan Kwanpheng | 2020-02-11 | 2020-06-25 | 2020-09-25 | 2021-12-25 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1134200 | Nakhon Ratchasima | อำเภอปากช่อง | 2021-11-15 | [36 empty] | 2020-07-03 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-26 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-17 | Finished | [50 empty] | 331 | 83 | 16 | 16 | 446 | 331 | 83 | 16 | 16 | 446 | 0 | Green |  |  | 20011125 | 2020-07-03
TBL0245-TH | HET | 61000699 | Install | ยังอยู่ในสัญญา HO | - | TH209091 | Track Doubling Project For Northeast line | L3(Pak Chong Station) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Orawan Kwanpheng | 2020-02-11 | 2020-06-25 | 2020-09-25 | 2021-12-25 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1134200 | Nakhon Ratchasima | อำเภอปากช่อง | 2021-12-30 | [36 empty] | 2020-07-03 | 2020-11-18 | 2020-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-26 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-17 | Finished | [18 empty] | 2020-11-18 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-15 | Finished | [22 empty] | 331 | 83 | 16 | 16 | 446 | 331 | 83 | 16 | 16 | 446 | 0 | Green |  |  | 20011125 | 2020-07-03 |  |  |  | HDME001037 | 2020-11-18
TFA1332-TH | HET | 61000700 | Test | ยังอยู่ในสัญญา HO | - | TH209095 | Academy of Dermatology (Substitute) | ES8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-02-21 | 2020-07-21 | 2020-09-21 | 2021-12-30 | 1200SX-EN,R3.9M,D35 | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงทุ่งพญาไท | 2020-07-15 | [20 empty] | 2020-07-15 | Finished | [14 empty] | 2020-07-06 | 2020-07-25 | 2020-07-25 | Finished | STORE AREA | [13 empty] | 2020-07-21 | 2020-08-10 | [41 empty] | 2020-07-29 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-08-05 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-08-06 | Finished |  |  | 100 | 2020-08-06 | 1900-01-01 | 2020-08-06 | Waiting | POWER SUPPLY DELAY |  | 2021-11-21 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-03-17 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2020-07-25 | Finished |  |  | 2020-07-25 | Finished |  |  | 2020-07-29 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 16 | 14 | 62 | 90.14 | Green |  |  | 20011222 | 2020-07-06 |  |  |  | HDME000932 | 2020-07-25
TBL0248-TH | HET | 61000701 | HO | ส่งมอบแล้ว | - | TH209090 | Wat Amarintraram School | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-02-12 | 2020-05-27 | 2020-07-27 |  | OUG-1000-CO60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1337500 | Bangkok | เขตบางกอกน้อย | 2020-05-27 | [36 empty] | 2020-05-27 | 2020-05-27 | 2020-08-18 | Finished | PAYMENT DELAY | [13 empty] | 2020-05-28 | 2020-07-11 | 2020-08-27 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-12 | Finished |  |  | 100 | [41 empty] | 2020-09-12 | 2020-06-26 | 2020-06-26 | Finished |  |  | 2020-06-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-02-19 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-06 | Finished |  |  | 2021-02-19 | Finished |  |  | 100 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2020-11-04 | Finished |  |  | 2020-03-13 | Finished | [10 empty] | 2020-10-15 | Finished | [6 empty] | 2020-08-18 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-11-04 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011189 | 2020-07-06 |  |  |  | HDME000959 | 2020-08-18 | QC Passed
TBL0249-TH | HET | 61000701 | HO | ส่งมอบแล้ว | - | TH209090 | Wat Amarintraram School | 2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-02-12 | 2020-05-27 | 2020-07-27 |  | OUG-1000-CO60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1337500 | Bangkok | เขตบางกอกน้อย | 2020-05-27 | [36 empty] | 2020-05-27 | 2020-05-27 | 2020-08-18 | Finished | PAYMENT DELAY | [13 empty] | 2020-05-28 | 2020-07-11 | 2020-08-27 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-12 | Finished |  |  | 100 | [41 empty] | 2020-09-12 | 2020-06-26 | 2020-06-26 | Finished |  |  | 2020-06-26 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2020-11-04 | Finished |  |  | 2020-03-13 | Finished | [10 empty] | 2020-10-15 | Finished | [6 empty] | 2020-08-18 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-08-20 | Finished |  |  | 2020-11-04 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 1 | 1 | 99.84 | Blue |  |  | 20011189 | 2020-07-06 |  |  |  | HDME000959 | 2020-08-18 | QC Passed
TFA1335-TH | HET | 61000703 | Install | ยังอยู่ในสัญญา HO | - | TH209094 | TGE Office Building | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 6 |  | 1 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-02-14 | 2020-07-14 | 2020-09-14 | 2021-10-28 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1070000 | Surat Thani | อำเภอท่าฉาง | 2020-07-14 | [20 empty] | 2020-07-31 | Finished | [14 empty] | 2020-07-14 | 2020-07-15 | 2020-07-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-14 | 2020-08-31 | [41 empty] | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 100 | 2020-09-02 | 1900-01-01 | 2020-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-03-13 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011262 | 2020-06-29 |  |  |  | HDME000923 | 2020-07-15
TFA1336-TH | HET | 61000703 | Install | ยังอยู่ในสัญญา HO | - | TH209094 | TGE Office Building | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 6 |  | 1 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-02-14 | 2020-07-14 | 2020-09-14 | 2021-10-28 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1070000 | Surat Thani | อำเภอท่าฉาง | 2020-07-14 | [20 empty] | 2020-07-31 | Finished | [14 empty] | 2020-07-14 | 2020-07-15 | 2020-07-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-14 | 2020-08-31 | [41 empty] | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-07-31 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 100 | 2020-09-02 | 1900-01-01 | 2020-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-03-13 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011262 | 2020-06-29 |  |  |  | HDME000923 | 2020-07-15
TBL0250-TH | HET | 61000703 | Install | ยังอยู่ในสัญญา HO | - | TH209094 | TGE Office Building | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-02-14 | 2020-07-14 | 2020-09-14 | 2021-10-28 | OUG-750-CO60,60S/4F | OUG-ON1 | 750 | 60 | 4 | 4 |  | 1267950 | Surat Thani | อำเภอท่าฉาง | 2020-07-14 | 2020-08-16 | Finished | [34 empty] | 2020-07-14 | 2020-07-15 | 2020-07-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-14 | 2020-08-16 | 2020-08-16 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 100 | [41 empty] | 2020-09-02 | 1900-01-01 | 2020-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2020-10-02 | 2000-01-01 | 2020-10-02 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-03-13 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 0 | 85 | 4 | 16 | 105 | 81.05 | Green |  |  | 20011263 | 2020-07-14 |  |  |  | HDME000923 | 2020-07-15
TBL0251-TH | HET | 61000705 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-08-20 | 2021-01-31 | 2022-01-30 | OUG-1200-CO90,90S/14F | OUG-ON1 | 1200 | 90 | 14 | 14 |  | 1605000 | Bangkok | แขวงคลองต้นไทร | 2021-11-30 | [36 empty] | 2020-08-20 | 2021-01-14 | 2021-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-14 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 967 | 100 | 32 | 20 | 1119 | 967 | 100 | 32 | 20 | 1119 | 0 | Green |  |  | 20011545 | 2020-08-20 |  |  |  | HDME001094 | 2021-01-14
TBL0253-TH | HET | 61000705 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | L10 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-08-20 | 2021-01-31 | 2022-01-30 | OUG-1200-CO90,90S/16F | OUG-ON1 | 1200 | 90 | 16 | 16 |  | 1605000 | Bangkok | แขวงคลองต้นไทร | 2021-06-01 | 2021-06-05 | Finished | [34 empty] | 2020-08-20 | 2021-01-14 | 2021-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-05 | 2021-07-30 | 2021-06-06 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-20 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-07-05 | Finished |  |  | 2021-07-10 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-25 | Finished |  |  | 2021-07-30 | Finished |  |  | 100 | [41 empty] | 2021-07-30 | 1900-01-01 | 2021-07-30 | Waiting | POWER SUPPLY DELAY |  | 2021-09-01 | [12 empty] | 0 | 2021-08-30 | 2000-01-01 | 2021-08-30 | Finished | [14 empty] | 25 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-14 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 1073 | 101 | 40 | 20 | 1234 | 0 | 101 | 10 | 20 | 131 | 89.38 | Green |  |  | 20011545 | 2020-08-20 |  |  |  | HDME001094 | 2021-01-14
TBL0252-TH | HET | 61000705 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-08-20 | 2021-01-31 | 2022-01-30 | OUG-1200-CO90,90S/14F | OUG-ON1 | 1200 | 90 | 14 | 14 |  | 1605000 | Bangkok | แขวงคลองต้นไทร | 2021-11-30 | [36 empty] | 2020-08-20 | 2021-01-14 | 2021-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-14 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 967 | 100 | 32 | 20 | 1119 | 967 | 100 | 32 | 20 | 1119 | 0 | Green |  |  | 20011545 | 2020-08-20 |  |  |  | HDME001094 | 2021-01-14
TBL0254-TH | HET | 61000705 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | L8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-08-20 | 2021-01-31 | 2022-01-30 | OUG-1200-CO90,90S/14F | OUG-ON1 | 1200 | 90 | 14 | 14 |  | 1605000 | Bangkok | แขวงคลองต้นไทร | 2021-11-30 | [36 empty] | 2020-08-20 | 2021-01-14 | 2021-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-14 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 967 | 100 | 32 | 20 | 1119 | 967 | 100 | 32 | 20 | 1119 | 0 | Green |  |  | 20011545 | 2020-08-20 |  |  |  | HDME001094 | 2021-01-14
TFA1337-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | ES-A-01 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-09-30 | 2021-03-14 | 1200TX-EN,R6M,D35 | TX-EN |  |  |  |  | 6000 | 909500 | Bangkok | เขตดอนเมือง | 2020-08-20 | [20 empty] | 2020-08-21 | Finished | [14 empty] | 2020-07-01 | 2020-07-01 | 2020-07-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2020-10-14 | [41 empty] | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 100 | 2020-12-10 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-06-23 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-06-23 | Finished |  |  | 100 | 2021-03-11 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-08-01 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 590 | 42 | 24 | 21 | 677 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011364 | 2020-07-01 |  |  |  | HDME000948 | 2020-08-01 | QC Passed
TFA1338-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | ES-A-02 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-09-30 | 2021-03-14 | 1200TX-EN,R6M,D35 | TX-EN |  |  |  |  | 6000 | 909500 | Bangkok | เขตดอนเมือง | 2020-08-20 | [20 empty] | 2020-08-21 | Finished | [14 empty] | 2020-07-01 | 2020-07-01 | 2020-07-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2020-10-14 | [41 empty] | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 100 | 2020-12-10 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-04-12 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-04-12 | Finished |  |  | 100 | 2021-03-11 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-08-01 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 590 | 42 | 24 | 21 | 677 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011364 | 2020-07-01 |  |  |  | HDME000948 | 2020-08-01 | QC Passed
TFA1339-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | ES-A-03 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-09-30 | 2021-03-14 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 802500 | Bangkok | เขตดอนเมือง | 2020-08-20 | [20 empty] | 2020-08-21 | Finished | [14 empty] | 2020-07-01 | 2020-07-01 | 2020-07-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2020-10-14 | [41 empty] | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 100 | 2020-12-10 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-04-12 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-04-12 | Finished |  |  | 100 | 2021-03-11 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-08-01 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011364 | 2020-07-01 |  |  |  | HDME000948 | 2020-08-01 | QC Passed
TFA1340-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | ES-A-04 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-09-30 | 2021-03-14 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 802500 | Bangkok | เขตดอนเมือง | 2020-08-20 | [20 empty] | 2020-08-21 | Finished | [14 empty] | 2020-07-01 | 2020-07-01 | 2020-07-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2020-10-14 | [41 empty] | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 100 | 2020-12-10 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-09-25 | 2021-04-12 | 2020-09-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-04-12 | Finished |  |  | 100 | 2021-03-11 | Finished | CONSTRUCTION DELAY |  | 2021-03-23 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-08-01 | Finished |  |  | 2020-08-06 | Finished |  |  | 2020-08-11 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011364 | 2020-07-01 |  |  |  | HDME000948 | 2020-08-01 | QC Passed
TBL0255-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | LFP-A-L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-09-30 | 2021-03-14 | OUG-1000-2S60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1337500 | Bangkok | เขตดอนเมือง | 2020-08-15 | 2020-08-16 | Finished | [34 empty] | 2020-07-20 | 2020-07-02 | 2020-07-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2020-10-14 | 2020-11-10 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 100 | [41 empty] | 2020-12-05 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-01 | 2021-07-02 | 2021-02-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-03-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-29 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-06 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011367 | 2020-07-20 |  |  |  | HDME000916 | 2020-07-02 | QC Passed
TBL0256-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | LFP-A-L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-09-30 | 2021-03-14 | OUG-1000-2S60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1337500 | Bangkok | เขตดอนเมือง | 2020-08-15 | 2020-08-16 | Finished | [34 empty] | 2020-07-20 | 2020-07-02 | 2020-07-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2020-10-14 | 2020-11-10 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 100 | [41 empty] | 2020-12-05 | 2020-10-22 | 2020-10-22 | Finished |  |  | 2020-10-15 | 2020-10-22 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | 2020-12-25 | 2021-06-25 | 2020-12-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-06-25 | Finished |  |  | 100 | 2021-03-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-29 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-06 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011367 | 2020-07-20 |  |  |  | HDME000916 | 2020-07-02 | QC Passed
TBL0257-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | LFS-A-L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-09-30 | 2021-03-14 | OUG-1000-2S60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1391000 | Bangkok | เขตดอนเมือง | 2020-08-15 | 2020-08-16 | Finished | [34 empty] | 2020-07-20 | 2020-07-02 | 2020-07-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-20 | 2020-10-14 | 2020-11-10 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 100 | [41 empty] | 2020-12-05 | 2020-12-06 | 2020-12-06 | Finished |  |  | 2020-10-15 | 2020-12-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-25 | 2021-06-18 | 2020-12-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-06-18 | Finished |  |  | 100 | 2021-03-25 | Finished | CONSTRUCTION DELAY |  | 2021-03-29 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-06 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011367 | 2020-07-20 |  |  |  | HDME000916 | 2020-07-02 | QC Passed
TBL0258-TH | HET | 61000706 | HO | ส่งมอบแล้ว | - | TH209093 | Air Asia Academy | LFS-E-L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-02-06 | 2020-05-30 | 2020-06-30 | 2021-03-14 | OUG-1000-2S60,60S/4F | OUG-ON1 | 1000 | 60 | 4 | 4 |  | 1070000 | Bangkok | เขตดอนเมือง | 2020-07-01 | 2020-07-02 | Finished | [34 empty] | 2020-07-20 | 2020-07-02 | 2020-07-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-02 | 2020-08-14 | 2020-07-02 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-04 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | [41 empty] | 2020-07-30 | 2020-12-07 | 2020-12-07 | Finished |  |  | 2020-10-15 | 2020-12-07 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-03-09 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-09 | Finished | [6 empty] | 90 | 2020-12-15 | Finished | DELIVERY DELAY |  | 2021-02-02 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-07-02 | Finished |  |  | 2020-07-02 | Finished |  |  | 2020-07-06 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20011367 | 2020-07-20 |  |  |  | HDME000916 | 2020-07-02 | QC Passed
TEB0121-TH | HET | 61000707 | HO | ส่งมอบแล้ว | - | TH209102 | Villazzo 11 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-03-03 | 2020-06-03 | 2020-07-18 | 2021-07-20 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 5 | 5 |  | 909500 | Bangkok | แขวงพญาไท | 2020-09-25 | 2020-06-08 | Finished | [34 empty] | 2020-05-19 | 2020-06-09 | 2020-06-09 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-06-08 | 2020-07-15 | 2020-06-08 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | [41 empty] | 2020-06-19 | 2020-11-30 | 2020-11-30 | Finished |  |  | 2020-08-30 | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 100 | 2020-07-24 | 2021-06-21 | 2020-07-24 | Finished |  |  | 2020-12-16 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-06-20 | Finished | POWER SUPPLY DELAY |  | 2021-08-01 | Finished |  |  | 2020-03-31 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-15 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 170 | 27 | 16 | 16 | 229 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011391 | 2020-05-19 |  |  |  | HDME000901 | 2020-06-09 | QC Passed
TEB0122-TH | HET | 61000707 | HO | ส่งมอบแล้ว | - | TH209102 | Villazzo 11 | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-03-03 | 2020-06-03 | 2020-07-18 | 2021-07-20 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 5 | 5 |  | 909500 | Bangkok | แขวงพญาไท | 2020-09-25 | 2021-06-08 | Finished | [34 empty] | 2020-05-19 | 2020-06-09 | 2020-06-09 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-06-08 | 2020-07-15 | 2020-06-08 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | [41 empty] | 2020-06-19 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-08-30 | 1900-01-01 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 100 | 2020-07-24 | 2021-06-21 | 2020-07-24 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-06-20 | Finished | POWER SUPPLY DELAY |  | 2021-08-01 | Finished |  |  | 2020-03-31 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-15 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 170 | 27 | 16 | 16 | 229 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011391 | 2020-05-19 |  |  |  | HDME000901 | 2020-06-09 | QC Passed
TEB0123-TH | HET | 61000707 | HO | ส่งมอบแล้ว | - | TH209102 | Villazzo 11 | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-03-03 | 2020-06-03 | 2020-08-03 | 2021-07-20 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 5 | 5 |  | 909500 | Bangkok | แขวงพญาไท | 2020-09-25 | 2020-07-10 | Finished | [34 empty] | 2020-05-19 | 2020-07-08 | 2020-07-08 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-07-10 | 2020-07-15 | 2020-07-10 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-15 | Finished |  |  | 2020-07-16 | Finished |  |  | 100 | [41 empty] | 2020-07-16 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-08-30 | 1900-01-01 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 100 | 2020-07-24 | 2021-09-03 | 2020-07-24 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-09-03 | Finished |  |  | 100 | 2021-06-20 | Finished | POWER SUPPLY DELAY |  | 2021-08-01 | Finished |  |  | 2020-03-31 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-07-08 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-15 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 170 | 27 | 16 | 16 | 229 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011391 | 2020-06-18 |  |  |  | HDME000918 | 2020-07-08 | QC Passed
TEB0124-TH | HET | 61000707 | HO | ส่งมอบแล้ว | - | TH209102 | Villazzo 11 | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-03-03 | 2020-06-03 | 2020-07-18 | 2021-07-20 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 5 | 5 |  | 909500 | Bangkok | แขวงพญาไท | 2020-09-25 | 2020-06-08 | Finished | [34 empty] | 2020-05-19 | 2020-06-09 | 2020-06-09 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-06-08 | 2020-07-15 | 2020-06-08 | Finished |  |  | 2020-06-11 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-12 | Finished |  |  | 2020-06-15 | Finished |  |  | 2020-06-17 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-18 | Finished |  |  | 2020-06-19 | Finished |  |  | 100 | [41 empty] | 2020-06-19 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-08-30 | 1900-01-01 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-06 | Finished |  |  | 100 | 2020-07-24 | 2021-06-21 | 2020-07-24 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-21 | Finished | [6 empty] | 90 | 2021-06-20 | Finished | POWER SUPPLY DELAY |  | 2021-08-01 | Finished |  |  | 2020-03-31 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-06-09 | Finished |  |  | 2020-06-09 | Finished |  |  | 2020-06-15 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 170 | 27 | 16 | 16 | 229 | 0 | 0 | 0 | 1 | 1 | 99.56 | Blue |  |  | 20011391 | 2020-05-19 |  |  |  | HDME000901 | 2020-06-09 | QC Passed
TFB0086-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | TR-1 |  |  | 1 | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200EXS-N,R3M,D12 | EXS-N |  |  |  |  | 3000 | 1498000 | Bangkok | แขวงคลองต้นไทร | 2020-10-12 | [20 empty] | 2020-10-12 | Finished | [14 empty] | 2020-07-16 | 2020-08-08 | 2020-08-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-12 | 2021-04-20 | [41 empty] | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-15 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-08-08 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-08-28 | Finished | [22 empty] | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 4 | 0 | 4 | 75 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME000953 | 2020-08-08
TFB0087-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | TR-2 |  |  | 1 | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200EXS-N,R3M,D12 | EXS-N |  |  |  |  | 3000 | 1498000 | Bangkok | แขวงคลองต้นไทร | 2020-10-12 | [20 empty] | 2020-10-12 | Finished | [14 empty] | 2020-07-16 | 2020-08-08 | 2020-08-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-12 | 2021-04-20 | [41 empty] | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-15 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2020-11-27 | 2000-01-01 | 2020-11-27 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-08-08 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-08-28 | Finished | [22 empty] | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 4 | 0 | 4 | 75 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME000953 | 2020-08-08
TFB0088-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | TR-3 |  |  | 1 | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200EXS-N,R5.25M,D12 | EXS-N |  |  |  |  | 5250 | 1819000 | Bangkok | แขวงคลองต้นไทร | 2021-01-30 | [20 empty] | 2020-10-12 | Finished | [14 empty] | 2020-07-16 | 2020-08-08 | 2020-08-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-30 | 2021-04-20 | [41 empty] | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-15 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-08-08 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-08-28 | Finished | [22 empty] | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 4 | 0 | 4 | 75 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME000953 | 2020-08-08
TFB0089-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | TR-4 |  |  | 1 | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200EXS-N,R5.25M,D12 | EXS-N |  |  |  |  | 5250 | 1819000 | Bangkok | แขวงคลองต้นไทร | 2021-01-30 | [20 empty] | 2020-10-12 | Finished | [14 empty] | 2020-07-16 | 2020-08-08 | 2020-08-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-30 | 2021-04-20 | [41 empty] | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-15 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-08-08 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-08-28 | Finished | [22 empty] | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 4 | 0 | 4 | 75 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME000953 | 2020-08-08
TFA1352-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R9M,D30 | TX-L |  |  |  |  | 9000 | 1819000 | Bangkok | แขวงคลองต้นไทร | 2020-12-08 | [20 empty] | 2020-12-08 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-10 | 2021-04-20 | [41 empty] | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-20 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-08 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 750 | 42 | 24 | 28 | 844 | 187 | 42 | 6 | 28 | 263 | 68.84 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001064 | 2020-12-08
TFA1349-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-08 | [20 empty] | 2020-12-08 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-10 | 2021-04-12 | [41 empty] | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-08 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 4 | 21 | 201 | 67.32 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001064 | 2020-12-08
TFA1350-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-11 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R6.4M,D30 | TX-L |  |  |  |  | 6400 | 1080700 | Bangkok | แขวงคลองต้นไทร | 2021-11-30 | [36 empty] | 2020-07-16 | 2020-12-08 | 2021-03-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-04-01 | Finished | [22 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001168 | 2021-03-16
TFA1351-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-12 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R6.4M,D30 | TX-L |  |  |  |  | 6400 | 1080700 | Bangkok | แขวงคลองต้นไทร | 2021-11-30 | [36 empty] | 2020-07-16 | 2020-12-08 | 2021-03-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2022-01-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-04-01 | Finished | [22 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001168 | 2021-03-16
TFA1353-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R9M,D30 | TX-L |  |  |  |  | 9000 | 1819000 | Bangkok | แขวงคลองต้นไทร | 2020-12-25 | [20 empty] | 2020-12-08 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-10 | 2021-04-20 | [41 empty] | 2021-01-05 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-30 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 750 | 42 | 24 | 28 | 844 | 187 | 42 | 6 | 28 | 263 | 68.84 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001075 | 2020-12-21
TFA1342-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-22 | [20 empty] | 2020-12-22 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-22 | 2021-04-12 | [41 empty] | 2020-12-24 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 16 | 21 | 213 | 65.37 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001075 | 2020-12-21
TFA1343-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-22 | [20 empty] | 2020-12-22 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-22 | 2021-04-12 | [41 empty] | 2020-12-24 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 4 | 21 | 201 | 67.32 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001075 | 2020-12-21
TFA1344-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-22 | [20 empty] | 2020-12-22 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-22 | 2021-04-12 | [41 empty] | 2020-12-24 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 16 | 21 | 213 | 65.37 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001075 | 2020-12-21
TFA1345-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-22 | [20 empty] | 2020-12-22 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-24 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-22 | 2021-04-12 | [41 empty] | 2020-12-24 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 4 | 21 | 201 | 67.32 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001075 | 2020-12-21
TFA1346-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-08 | [20 empty] | 2020-12-08 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-10 | 2021-04-12 | [41 empty] | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2020-12-25 | 2000-01-01 | 2020-12-25 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-08 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 4 | 21 | 201 | 67.32 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001064 | 2020-12-08
TFA1347-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-08 | [20 empty] | 2020-12-08 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-10 | 2021-04-12 | [41 empty] | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-08 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 4 | 21 | 201 | 67.32 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001064 | 2020-12-08
TFA1348-TH | HET | 61000710 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | ESC-9 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-07-31 | 2020-12-30 | 2022-01-30 | 1200TX-L,R5.4M,D30 | TX-L |  |  |  |  | 5400 | 866700.01 | Bangkok | แขวงคลองต้นไทร | 2020-12-08 | [20 empty] | 2020-12-08 | Finished | [14 empty] | 2020-07-16 | 2020-12-08 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-10 | 2021-04-12 | [41 empty] | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-25 | Finished | [14 empty] | 75 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | 2020-12-25 | 2000-01-01 | 2020-12-25 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-12-08 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 134 | 42 | 4 | 21 | 201 | 67.32 | Green |  |  | 20011548 | 2020-07-16 |  |  |  | HDME001064 | 2020-12-08
TAJ0679-TH | HET | 61000711 | HO | ยังอยู่ในสัญญา HO | - | TH209101 | Lucky Tower | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-03-03 | 2020-05-18 | 2020-07-18 | 2022-01-15 | P-600-CO60D,60S/7F | UAG-SN1 | 600 | 60 | 7 | 7 |  | 950000 | Bangkok | กรุงเทพมหานคร 10140 | 2020-07-18 | 2020-07-18 | Finished | [34 empty] | 2020-05-18 | 2020-07-18 | 2020-07-18 | Finished | PAYMENT DELAY | [13 empty] | 2020-07-18 | 2020-07-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2022-04-10 | [12 empty] | 0 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished | [14 empty] | 25 | 2022-04-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-31 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-07-10 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-15 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 83 | 6 | 16 | 105 | 83.06 | Green |  |  | 20011437 | 2020-06-12 |  |  |  | HDME000921 | 2020-07-10
TAJ0680-TH | HET | 61000711 | HO | ยังอยู่ในสัญญา HO | - | TH209101 | Lucky Tower | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-03-03 | 2020-05-18 | 2020-07-18 | 2022-01-15 | P-600-CO60D,60S/7F | UAG-SN1 | 600 | 60 | 7 | 7 |  | 950000 | Bangkok | กรุงเทพมหานคร 10140 | 2020-07-18 | 2020-07-18 | Finished | [34 empty] | 2020-05-18 | 2020-07-18 | 2020-07-18 | Finished | PAYMENT DELAY | [13 empty] | 2020-07-18 | 2020-07-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2022-04-10 | [12 empty] | 0 | 2020-08-28 | 2000-01-01 | 2020-08-28 | Finished | [14 empty] | 25 | 2022-04-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-03-31 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-07-10 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-15 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 83 | 6 | 16 | 105 | 83.06 | Green |  |  | 20011437 | 2020-06-12 |  |  |  | HDME000921 | 2020-07-10
TAJ0681-TH | HET | 61000712 | HO | ส่งมอบแล้ว | - | TH209105 | Hotel Khun Kajohndet | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-03-10 | 2020-09-10 | 2020-11-10 | 2021-03-30 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 980000 | Chiang Mai | ถ.เจริญประเทศ อ.เมืองเชียงใหม่ | 2020-12-15 | 2020-12-15 | Finished | [34 empty] | 2020-09-10 | 2020-12-23 | 2020-12-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-15 | 2021-01-15 | 2020-12-24 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-27 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-29 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-07 | Finished |  |  | 100 | [41 empty] | 2021-01-07 | 2020-11-11 | 2020-11-11 | Finished |  |  | 2020-11-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-29 | 2020-11-03 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-23 | Finished |  |  | 2020-11-03 | Finished |  |  | 100 | 2021-03-30 | Finished | CONSTRUCTION DELAY |  | 2021-03-31 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-12-23 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass | 2021-05-05 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011551 | 2020-09-10 |  |  |  | HDME001076 | 2020-12-23 | QC Passed
TAJ0682-TH | HET | 61000713 | HO | ยังอยู่ในสัญญา HO | - | TH209106 | Hotel @Borwin | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | 2020-03-10 | 2020-12-10 | 2021-02-10 | 2021-12-30 | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1000000 | Chon Buri | อำเภอศรีราชา | 2021-11-01 | [36 empty] | 2020-12-10 | 2020-12-10 | 2021-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-01 | 2021-11-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-31 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-02 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Green |  |  | 20011593 | 2020-12-10 |  |  |  | HDME001146 | 2021-03-02
TAJ0683-TH | HET | 61000713 | HO | ยังอยู่ในสัญญา HO | - | TH209106 | Hotel @Borwin | EL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | 2020-03-10 | 2020-12-10 | 2021-02-10 | 2021-12-30 | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1000000 | Chon Buri | อำเภอศรีราชา | 2021-11-01 | [36 empty] | 2020-12-10 | 2020-12-10 | 2021-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-01 | 2021-11-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-03-31 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-02 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Green |  |  | 20011593 | 2020-12-10 |  |  |  | HDME001146 | 2021-03-02
TFA1355-TH | HET | 61000714 | HO | ส่งมอบแล้ว | - | TH209107 | SME Bank | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Somsak Denpraphat | Thamnul Kongsar | 2020-02-20 | 2020-07-31 | 2020-12-20 |  | 1200TX-EN,R4.3M,D35 | TX-EN |  |  |  |  | 4300 | 1599250 | Bangkok | เขตพญาไท | 2020-06-30 | [20 empty] | 2020-07-25 | Finished | [14 empty] | 2020-07-16 | 2020-08-01 | 2020-07-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-25 | 2020-10-01 | [41 empty] | 2020-08-30 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-09-28 | Finished |  |  | 100 | 2020-09-28 | 2020-10-16 | 2020-10-16 | Finished |  |  | 2020-10-14 | 2020-10-16 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2020-12-19 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished | [18 empty] | 2020-07-31 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Working |  | pass (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011552 | 2020-07-16 |  |  |  | HDME000941 | 2020-07-31
TFA1356-TH | HET | 61000714 | HO | ส่งมอบแล้ว | - | TH209107 | SME Bank | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Somsak Denpraphat | Thamnul Kongsar | 2020-02-20 | 2020-07-31 | 2020-12-20 |  | 1200TX-EN,R4.3M,D35 | TX-EN |  |  |  |  | 4300 | 1599250 | Bangkok | เขตพญาไท | 2020-06-30 | [20 empty] | 2020-07-25 | Finished | [14 empty] | 2020-07-16 | 2020-08-01 | 2020-07-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-25 | 2020-10-01 | [41 empty] | 2020-08-30 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-09-28 | Finished |  |  | 100 | 2020-09-28 | 2020-10-16 | 2020-10-16 | Finished |  |  | 2020-10-14 | 2020-10-16 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2020-10-09 | 2000-01-01 | 2020-10-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-02-10 | Finished |  |  | 100 | 2020-12-19 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished | [18 empty] | 2020-07-31 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Working |  | pass (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011552 | 2020-08-05 |  |  |  | HDME000941 | 2020-07-31
TFA1359-TH | HET | 61000714 | HO | ส่งมอบแล้ว | - | TH209107 | SME Bank | ES6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Somsak Denpraphat | Thamnul Kongsar | 2020-02-20 | 2020-07-31 | 2020-12-20 |  | 1200TX-EN,R4.3M,D35 | TX-EN |  |  |  |  | 4300 | 1599250 | Bangkok | เขตพญาไท | 2020-06-30 | [20 empty] | 2020-07-25 | Finished | [14 empty] | 2020-07-16 | 2020-09-03 | 2020-07-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-25 | 2020-10-01 | [41 empty] | 2020-09-05 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-10-03 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-05 | Finished |  |  | 100 | 2020-10-05 | 2020-10-16 | 2020-10-16 | Finished |  |  | 2020-10-14 | 2020-10-16 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-26 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2020-12-19 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished | [18 empty] | 2020-09-02 | Finished |  |  | 2020-09-03 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Working |  | pass (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011552 | 2020-08-05 |  |  |  | HDME000970 | 2020-09-02
TAJ0688-TH | HET | 61000716 | HO | ส่งมอบแล้ว | - | TH209109 | Kensington Rayong 2 | L1-(Bldg. C) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-02-12 | 2020-06-01 | 2020-09-01 | 2012-11-30 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 856000 | Rayong | อำเภอเมืองระยอง | 2020-09-01 | 2020-09-01 | Finished | [34 empty] | 2020-06-08 | 2020-06-04 | 2020-06-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-06 | 2020-09-01 | 2020-06-28 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-16 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-26 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | [41 empty] | 2020-07-30 | 2020-08-10 | 2020-08-10 | Finished |  |  | 2020-08-20 | 2020-07-04 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 100 | 2020-10-27 | 2020-10-27 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished | [6 empty] | 90 | 2021-04-17 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2020-04-09 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-06-10 | Finished |  |  | 2020-06-29 | Finished |  |  | 2020-06-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20011550 | 2020-06-08 |  |  |  | HDME000903 | 2020-06-10 | QC Passed
TAJ0689-TH | HET | 61000716 | HO | ส่งมอบแล้ว | - | TH209109 | Kensington Rayong 2 | L2 (Bldg. C) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-02-12 | 2020-06-01 | 2020-09-01 | 2012-11-30 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 856000 | Rayong | อำเภอเมืองระยอง | 2020-09-01 | 2020-09-01 | Finished | [34 empty] | 2020-06-08 | 2020-06-04 | 2020-06-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-06 | 2020-09-01 | 2020-06-28 | Finished |  |  | 2020-07-01 | Finished |  |  | 2020-07-07 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-16 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-26 | Finished |  |  | 2020-07-30 | Finished |  |  | 100 | [41 empty] | 2020-07-30 | 2020-08-10 | 2020-08-10 | Finished |  |  | 2020-08-20 | 2020-07-05 | Finished |  |  | 2020-07-11 | Finished |  |  | 2020-11-14 | Finished |  |  | 100 | 2020-10-27 | 2020-10-27 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished | [6 empty] | 90 | 2021-04-17 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2020-04-09 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-06-10 | Finished |  |  | 2020-06-29 | Finished |  |  | 2020-06-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20011550 | 2020-06-08 |  |  |  | HDME000903 | 2020-06-10 | QC Passed
TAJ0690-TH | HET | 61000716 | HO | ส่งมอบแล้ว | - | TH209109 | Kensington Rayong 2 | L3(Bldg. D) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-02-12 | 2020-06-01 | 2020-09-01 | 2012-11-30 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 856000 | Rayong | อำเภอเมืองระยอง | 2020-09-01 | 2020-09-01 | Finished | [34 empty] | 2020-06-08 | 2020-06-04 | 2020-06-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-06 | 2020-09-01 | 2020-09-01 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-07 | Finished |  |  | 100 | [41 empty] | 2020-10-07 | 2020-08-10 | 2020-08-10 | Finished |  |  | 2020-08-20 | 2020-09-20 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-24 | Finished |  |  | 100 | 2020-10-27 | 2020-10-27 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished | [6 empty] | 90 | 2021-04-17 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2020-04-09 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-06-10 | Finished |  |  | 2020-06-29 | Finished |  |  | 2020-06-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20011550 | 2020-06-08 |  |  |  | HDME000903 | 2020-06-10 | QC Passed
TAJ0691-TH | HET | 61000716 | HO | ส่งมอบแล้ว | - | TH209109 | Kensington Rayong 2 | L4 (Bldg. D) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-02-12 | 2020-06-01 | 2020-09-01 | 2012-11-30 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 856000 | Rayong | อำเภอเมืองระยอง | 2020-09-01 | 2020-09-01 | Finished | [34 empty] | 2020-06-08 | 2020-06-04 | 2020-06-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-06-06 | 2020-09-01 | 2020-09-01 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-07 | Finished |  |  | 100 | [41 empty] | 2020-10-07 | 2020-08-10 | 2020-08-10 | Finished |  |  | 2020-08-20 | 2020-09-20 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-26 | Finished |  |  | 100 | 2020-10-27 | 2020-10-27 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-27 | Finished | [6 empty] | 90 | 2021-04-17 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2020-04-09 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-06-10 | Finished |  |  | 2020-06-29 | Finished |  |  | 2020-06-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20011550 | 2020-06-08 |  |  |  | HDME000903 | 2020-06-10 | QC Passed
TAK0692-TH | HET | 61000717 | HO | ส่งมอบแล้ว | - | TH209110 | Bangkok Hospital Ratchasima | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2020-03-03 | 2020-07-30 | 2020-10-31 | 2021-12-15 | B-1000-2S105,105S/12F | UAG-SN1 | 1000 | 105 | 12 | 12 |  | 2200000 | Nakhon Ratchasima | ตำบลในเมือง | 2020-08-15 | 2020-07-30 | Finished | [34 empty] | 2020-07-30 | 2020-08-01 | 2020-08-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-30 | 2020-08-29 | 2020-08-01 | Finished |  |  | 2020-08-09 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-30 | Finished |  |  | 100 | [41 empty] | 2020-09-30 | 2020-10-01 | 2020-10-01 | Finished |  |  | 2020-09-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-28 | 2021-02-15 | 2020-12-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-02-15 | Finished |  |  | 100 | 2021-03-30 | Finished | CONSTRUCTION DELAY |  | 2021-03-17 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-08-01 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-04 | Finished |  |  | 2021-03-17 | Finished | [13 empty] | pass |  |  |  |  | 718 | 94 | 32 | 20 | 864 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011665 | 2020-07-30 |  |  |  | HDME000946 | 2020-08-01 | QC Passed
TAK0693-TH | HET | 61000717 | HO | ส่งมอบแล้ว | - | TH209110 | Bangkok Hospital Ratchasima | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2020-03-03 | 2020-07-30 | 2020-10-31 | 2021-12-15 | B-1000-2S105,105S/12F | UAG-SN1 | 1000 | 105 | 12 | 12 |  | 2200000 | Nakhon Ratchasima | ตำบลในเมือง | 2020-08-15 | 2020-07-30 | Finished | [34 empty] | 2020-07-30 | 2020-08-01 | 2020-08-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-30 | 2020-08-29 | 2020-08-01 | Finished |  |  | 2020-08-09 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-30 | Finished |  |  | 100 | [41 empty] | 2020-09-30 | 2020-10-01 | 2020-10-01 | Finished |  |  | 2020-09-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-28 | 2020-12-28 | 2020-12-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-28 | Finished | [6 empty] | 90 | 2021-03-30 | Finished | CONSTRUCTION DELAY |  | 2021-03-17 | Finished |  |  | 2020-03-31 | Finished | [18 empty] | 2020-08-01 | Finished |  |  | 2020-08-01 | Finished |  |  | 2020-08-04 | Finished |  |  | 2021-03-17 | Finished | [13 empty] | pass |  |  |  |  | 718 | 94 | 32 | 20 | 864 | 0 | 0 | 0 | 2 | 2 | 99.77 | Blue |  |  | 20011665 | 2020-07-30 |  |  |  | HDME000946 | 2020-08-01 | QC Passed
TBK0186-TH | HET | 61000718 | Install | เลยสัญญา HO | - | TH209112 | Strand Thonglor | P-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-03-01 | 2020-06-29 | 2020-12-31 | 2021-07-31 | HVF-1350-CO180,180S/27F | HVF-5 | 1350 | 180 | 25 | 27 |  | 4066000 | Bangkok | เขตวัฒนา | 2020-12-13 | 2021-01-18 | Finished | [34 empty] | 2020-10-26 | 2021-03-10 | 2021-03-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-15 | 2021-02-25 | 2021-01-20 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-08-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | [41 empty] | 2021-03-31 | 2021-03-31 | 2021-03-31 | Finished |  |  | 2021-03-31 | 2021-04-01 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | 2021-08-30 | 2000-01-01 | 2021-08-30 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 50 | 2021-10-15 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-04-17 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-03-10 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 1682 | 113 | 56 | 24 | 1875 | 0 | 0 | 0 | 24 | 24 | 98.72 | Red |  |  | 20011775 | 2020-12-01 |  |  |  | HDME001159 | 2021-03-10
TBK0187-TH | HET | 61000718 | Install | เลยสัญญา HO | - | TH209112 | Strand Thonglor | P-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-03-01 | 2020-06-29 | 2020-12-31 | 2021-07-31 | HVF-1350-CO180,180S/30F | HVF-5 | 1350 | 180 | 28 | 30 |  | 4226500 | Bangkok | เขตวัฒนา | 2020-12-13 | 2021-01-18 | Finished | [34 empty] | 2020-10-26 | 2021-03-10 | 2021-03-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-15 | 2021-02-25 | 2021-01-20 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-08-30 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | [41 empty] | 2021-03-31 | 2021-04-08 | 2021-04-08 | Finished |  |  | 2021-04-27 | 2021-04-10 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-07 | Finished |  |  | 100 | 2021-08-30 | 2000-01-01 | 2021-08-30 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 50 | 2021-10-15 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-04-17 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-03-10 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 1829 | 115 | 56 | 32 | 2032 | 0 | 0 | 0 | 32 | 32 | 98.43 | Red |  |  | 20011775 | 2020-12-01 |  |  |  | HDME001159 | 2021-03-10
TBK0188-TH | HET | 61000718 | Install | เลยสัญญา HO | - | TH209112 | Strand Thonglor | P-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-03-01 | 2020-06-29 | 2020-12-31 | 2021-07-31 | HVF-1350-CO180,180S/31F | HVF-5 | 1350 | 180 | 29 | 31 |  | 4280000 | Bangkok | เขตวัฒนา | 2020-12-13 | 2021-01-18 | Finished | [34 empty] | 2020-10-26 | 2021-03-10 | 2021-03-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-15 | 2021-02-25 | 2021-01-20 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-08-30 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | [41 empty] | 2021-03-31 | 2021-04-08 | 2021-04-08 | Finished |  |  | 2021-04-27 | 2021-04-10 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-05 | Finished |  |  | 100 | 2021-08-30 | 2000-01-01 | 2021-08-30 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 50 | 2021-10-15 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-04-17 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-03-10 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 1878 | 116 | 64 | 32 | 2090 | 0 | 0 | 0 | 32 | 32 | 98.47 | Red |  |  | 20011775 | 2020-12-01 |  |  |  | HDME001159 | 2021-03-10
TBL0259-TH | HET | 61000718 | Install | เลยสัญญา HO | - | TH209112 | Strand Thonglor | P-04 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-03-01 | 2020-06-29 | 2020-12-31 | 2021-07-31 | OUG-900-CO60,60S/4F | OUG-ON1 | 900 | 60 | 4 | 4 |  | 1712000 | Bangkok | เขตวัฒนา | 2020-08-16 | 2020-10-20 | Finished | [34 empty] | 2020-08-10 | 2020-10-14 | 2020-10-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-16 | 2020-10-26 | 2020-10-21 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 100 | [41 empty] | 2020-10-30 | 2021-05-05 | 2021-05-05 | Finished |  |  | 2021-04-21 | 2021-05-07 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | 2021-03-04 | 2000-01-01 | 2021-03-04 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-10-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-04-17 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-09-25 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-14 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 16 | 16 | 97.11 | Red |  |  | 20011775 | 2020-09-19 |  |  |  | HDME000986 | 2020-09-25
TAC1725-TH | HET | 61000718 | Install | เลยสัญญา HO | - | TH209112 | Strand Thonglor | S-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2019-03-01 | 2020-06-29 | 2020-12-31 | 2021-07-31 | VFI-1350-CO120,120S/31F | VFI-II | 1350 | 120 | 29 | 31 |  | 2942500 | Bangkok | เขตวัฒนา | 2020-11-16 | 2020-11-02 | Finished | [34 empty] | 2020-07-01 | 2020-11-28 | 2020-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-04 | 2020-12-28 | 2020-12-07 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | [41 empty] | 2021-01-25 | 2021-01-11 | 2021-01-11 | Finished |  |  | 2021-01-07 | 2021-01-12 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-02-01 | Finished |  |  | 100 | 2021-01-21 | 2000-01-01 | 2021-01-21 | Finished | [14 empty] | 25 | 2021-10-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-04-17 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-11-28 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished | [22 empty] | 1964 | 122 | 64 | 32 | 2182 | 0 | 0 | 16 | 32 | 48 | 97.8 | Red |  |  | 20011775 | 2020-07-01 |  |  |  | HDME001053 | 2020-11-28
TAJ0694-TH | HET | 61000719 | HO | เลยสัญญา HO | - | TH209113 | Home Khun Boon | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | ANUSSARA POLDONGNOK | 2020-03-21 | 2020-08-21 | 2020-10-21 |  | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1000000 | Bangkok | แขวงดาวคะนอง | 2021-10-17 | [36 empty] | 2020-08-21 | 2020-09-02 | 2020-09-02 | Finished | STORE AREA | [13 empty] | 2021-10-18 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-17 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-03 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-03 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Red |  |  | 20011768 | 2020-08-21 |  |  |  | HDME000967 | 2020-09-02
TBF0031-TH | HET | 61000720 | Install | ยังอยู่ในสัญญา HO | - | TH209096 | RTWO | L9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-11-20 | 2020-08-20 | 2021-01-31 | 2022-01-30 | F-2000-2S60,60S/16F | F-EL | 2000 | 60 | 16 | 16 |  | 3638000 | Bangkok | แขวงคลองต้นไทร | 2021-09-02 | 2021-09-02 | Finished | [34 empty] | 2020-10-26 | 2021-01-14 | 2021-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-03 | 2022-10-30 | 2021-09-04 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-14 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 1402 | 120 | 192 | 20 | 1734 | 1331 | 120 | 192 | 20 | 1663 | 4.09 | Green |  |  | 20011754 | 2020-10-26 |  |  |  | HDME001093 | 2021-01-14
TFA1362-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 1100000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-05 | 2020-12-16 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | [6 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001069 | 2020-12-16
TFA1363-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 1100000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-05 | 2020-12-16 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | [6 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001069 | 2020-12-16
TFA1364-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1000000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-24 | 2020-12-09 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001068 | 2020-12-09
TFA1365-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1000000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-05 | 2020-12-09 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001068 | 2020-12-09
TFA1366-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1000000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-05 | 2020-12-09 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001068 | 2020-12-09
TFA1367-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1000000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-05 | 2020-12-09 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001068 | 2020-12-09
TFA1368-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1000000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-05 | 2020-12-16 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001069 | 2020-12-16
TFA1369-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | ESC8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 6 |  | 1 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1000000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | [20 empty] | 2021-01-05 | Finished | [14 empty] | 2020-08-05 | 2020-12-16 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-02-04 | [41 empty] | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20011755 | 2020-08-24 |  |  |  | HDME001069 | 2020-12-16
TAJ0695-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | P-1600-2S60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1400000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | 2020-12-23 | Finished | [34 empty] | 2020-08-20 | 2020-12-09 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2020-12-23 | 2021-01-22 | 2021-05-01 | Finished |  |  | 2021-05-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Green |  |  | 20011770 | 2020-08-20 |  |  |  | HDME001068 | 2020-12-09
TAJ0696-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | P-1600-2S60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1400000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | 2020-12-23 | Finished | [34 empty] | 2020-08-20 | 2020-12-09 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2020-12-23 | 2021-01-22 | 2021-05-01 | Finished |  |  | 2021-05-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Green |  |  | 20011770 | 2020-08-20 |  |  |  | HDME001068 | 2020-12-09
TAJ0697-TH | HET | 61000721 | Install | ยังอยู่ในสัญญา HO | - | TH209114 | SUT (Tecnology Digital Building) | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Phumiphat Siprajan | 2019-12-22 | 2020-08-20 | 2020-11-30 | 2021-10-15 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1000000 | Nakhon Ratchasima | อำเภอนครราชสีมา | 2020-07-15 | 2020-12-23 | Finished | [34 empty] | 2020-08-20 | 2020-12-09 | 2020-12-16 | Finished | PAYMENT DELAY | [13 empty] | 2020-12-23 | 2021-01-22 | 2021-05-01 | Finished |  |  | 2021-05-05 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-10 | Finished |  |  | 2020-12-20 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished | [14 empty] | 25 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-04-17 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 4 | 16 | 101 | 78.83 | Green |  |  | 20011770 | 2020-08-20 |  |  |  | HDME001068 | 2020-12-09
TAC1726-TH | HET | 61000722 | HO | ส่งมอบแล้ว | - | TH209115 | V Win Apartment | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-03-23 | 2020-07-08 | 2020-08-23 | 2020-09-30 | VFI-600-CO60,60S/6F | VFI-II | 600 | 60 | 6 | 6 |  | 1123500 | Bangkok | แขวงบางนา เขตบางนา | 2020-07-08 | 2020-07-08 | Finished | [34 empty] | 2020-07-08 | 2020-07-09 | 2020-07-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-08 | 2020-07-10 | 2020-07-10 | Finished |  |  | 2020-07-12 | Finished |  |  | 2020-07-14 | Finished |  |  | 2020-07-16 | Finished |  |  | 2020-07-18 | Finished |  |  | 2020-07-20 | Finished |  |  | 2020-07-22 | Finished |  |  | 2020-07-24 | Finished |  |  | 2020-07-26 | Finished |  |  | 2020-07-28 | Finished |  |  | 100 | [41 empty] | 2020-07-28 | 2020-09-11 | 2020-09-11 | Finished |  |  | 2020-09-11 | 2020-09-11 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-22 | Finished |  |  | 100 | 2020-08-24 | 2020-10-02 | 2020-08-24 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-02 | Finished | [6 empty] | 90 | 2020-10-03 | Finished | CONSTRUCTION DELAY |  | 2020-10-27 | Finished |  |  | 2020-04-17 | Finished | [10 empty] | 2020-09-15 | Finished | [6 empty] | 2020-07-09 | Finished |  |  | 2020-07-09 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-10-27 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 1 | 1 | 99.86 | Blue |  |  | 20011743 | 2020-07-08 |  |  |  | HDME000919 | 2020-07-09 | QC Passed
TFA1370-TH | HET | 61000723 |  | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | ES-A1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-11-30 | 2021-04-30 | 2021-08-01 | 1200TX-EN,R6.65M,D30 | TX-EN |  |  |  |  | 6650 | 1391000 | Nonthaburi | ตำบลบางกระสอ | 1900-01-01 | [36 empty] | 2020-11-30 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-25 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [50 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20011781 | 2020-11-16
TFA1371-TH | HET | 61000723 |  | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | ES-A2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-11-30 | 2021-04-30 | 2021-08-01 | 1200TX-EN,R6.65M,D30 | TX-EN |  |  |  |  | 6650 | 1391000 | Nonthaburi | ตำบลบางกระสอ | 1900-01-01 | [36 empty] | 2020-11-30 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-25 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [50 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20011781 | 2020-11-16
TFA1372-TH | HET | 61000723 |  | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | ES-A3 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-11-30 | 2021-04-30 | 2021-08-01 | 1200TX-EN,R4.85M,D35 | TX-EN |  |  |  |  | 4850 | 1070000 | Nonthaburi | ตำบลบางกระสอ | 1900-01-01 | [36 empty] | 2020-11-30 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-25 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20011781 | 2020-11-16
TFA1373-TH | HET | 61000723 |  | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | ES-A4 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-11-30 | 2021-04-30 | 2021-08-01 | 1200TX-EN,R4.85M,D35 | TX-EN |  |  |  |  | 4850 | 1070000 | Nonthaburi | ตำบลบางกระสอ | 1900-01-01 | [36 empty] | 2020-11-30 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-25 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20011781 | 2020-11-16
TFA1374-TH | HET | 61000723 |  | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | ES-A5 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-11-30 | 2021-04-30 | 2021-08-01 | 1200TX-EN,R4.7M,D35 | TX-EN |  |  |  |  | 4700 | 1070000 | Nonthaburi | ตำบลบางกระสอ | 1900-01-01 | [36 empty] | 2020-11-30 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-25 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20011781 | 2020-11-16
TFA1375-TH | HET | 61000723 |  | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | ES-A6 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 6 |  | 1 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-11-30 | 2021-04-30 | 2021-08-01 | 1200TX-EN,R4.7M,D35 | TX-EN |  |  |  |  | 4700 | 1070000 | Nonthaburi | ตำบลบางกระสอ | 1900-01-01 | [36 empty] | 2020-11-30 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-25 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20011781 | 2020-11-16
TAC1730-TH | HET | 61000724 | HO | ส่งมอบแล้ว | - | TH209116 | Joon Chee Factory | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-03-26 | 2020-07-26 | 2020-09-26 | 2021-08-30 | VFI-1000-CO105,105S/5F | VFI-II | 1000 | 105 | 5 | 5 |  | 1500000 | Chon Buri | อำเภอศรีราชา | 2020-09-26 | 2020-12-17 | Finished | [34 empty] | 2020-07-26 | 2020-07-26 | 2020-08-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-27 | 2020-08-27 | 2021-03-02 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 100 | [41 empty] | 2021-03-18 | 1900-01-01 | 1900-01-01 | Finished |  |  | 2020-08-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-09-01 | 2000-01-01 | 2021-09-01 | Finished |  |  | 2021-09-01 | Finished |  |  | 2021-09-01 | Finished | [6 empty] | 90 | 2021-08-27 | Finished | CONSTRUCTION DELAY |  | 2021-08-27 | Finished |  |  | 2020-04-17 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-08-11 | Finished |  |  | 2020-08-11 | Finished |  |  | 2020-08-13 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | no pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20011835 | 2020-07-26 |  |  |  | HDME000955 | 2020-08-11
TBK0193-TH | HET | 61000726 | Install | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | OF1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-12-01 | 2021-04-30 | 2021-08-01 | HVF-1600-CO240,240S/20F | HVF-5 | 1600 | 240 | 11 | 20 |  | 4387000 | Nonthaburi | ตำบลบางกระสอ | 2021-04-30 | [36 empty] | 2020-12-01 | 2021-02-22 | 2021-01-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-30 | 2021-09-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [18 empty] | 2020-12-24 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 1339 | 108 | 40 | 24 | 1511 | 1339 | 108 | 40 | 24 | 1511 | 0 | Red |  |  | 20011899 | 2020-12-01 |  |  |  | HDME001079 | 2020-12-24
TBK0194-TH | HET | 61000726 | Install | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | OF2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-12-01 | 2021-04-30 | 2021-08-01 | HVF-1600-CO240,240S/20F | HVF-5 | 1600 | 240 | 11 | 20 |  | 4387000 | Nonthaburi | ตำบลบางกระสอ | 2021-04-30 | [36 empty] | 2020-12-01 | 2021-02-22 | 2021-01-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-30 | 2021-09-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [18 empty] | 2020-12-24 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 1339 | 108 | 40 | 24 | 1511 | 1339 | 108 | 40 | 24 | 1511 | 0 | Red |  |  | 20011899 | 2020-12-01 |  |  |  | HDME001079 | 2020-12-24
TBK0195-TH | HET | 61000726 | Install | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | OF3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-12-01 | 2021-04-30 | 2021-08-01 | HVF-1600-CO240,240S/20F | HVF-5 | 1600 | 240 | 11 | 20 |  | 4387000 | Nonthaburi | ตำบลบางกระสอ | 2021-04-30 | [36 empty] | 2020-12-01 | 2021-02-22 | 2021-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-30 | 2021-09-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [18 empty] | 2021-01-22 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 1339 | 108 | 40 | 24 | 1511 | 1339 | 108 | 40 | 24 | 1511 | 0 | Red |  |  | 20011899 | 2020-12-01 |  |  |  | HDME001101 | 2021-01-22
TBK0196-TH | HET | 61000726 | Install | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | OF4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-12-01 | 2021-04-30 | 2021-08-01 | HVF-1600-CO240,240S/20F | HVF-5 | 1600 | 240 | 11 | 20 |  | 4387000 | Nonthaburi | ตำบลบางกระสอ | 2021-04-30 | [36 empty] | 2020-12-01 | 2021-02-22 | 2021-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-30 | 2021-09-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [18 empty] | 2021-02-03 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 1339 | 108 | 40 | 24 | 1511 | 1339 | 108 | 40 | 24 | 1511 | 0 | Red |  |  | 20011899 | 2020-12-01 |  |  |  | HDME001117 | 2021-02-03
TBL0260-TH | HET | 61000726 | Install | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | PL1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-12-01 | 2021-04-30 | 2021-08-01 | OUG-1000-CO105,105S/11F | OUG-ON1 | 1000 | 105 | 11 | 11 |  | 1284000 | Nonthaburi | ตำบลบางกระสอ | 2021-01-18 | 2021-03-15 | Finished | [34 empty] | 2020-12-01 | 2021-01-18 | 2020-12-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-15 | 2021-05-10 | 2021-03-18 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-21 | Finished |  |  | 2021-04-27 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-10 | Finished |  |  | 100 | [41 empty] | 2021-05-10 | 1900-01-01 | 2021-05-10 | Waiting | POWER SUPPLY DELAY |  | 2021-09-25 | [12 empty] | 0 | 2021-06-21 | 2000-01-01 | 2021-06-21 | Finished | [14 empty] | 25 | 2021-09-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [18 empty] | 2020-12-16 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 808 | 98 | 32 | 20 | 958 | 0 | 98 | 8 | 20 | 126 | 86.85 | Red |  |  | 20011899 | 2020-08-28 |  |  |  | HDME001070 | 2020-12-16
TBL0261-TH | HET | 61000726 | Install | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | PL2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2020-12-01 | 2021-04-30 | 2021-08-01 | OUG-1000-CO105,105S/11F | OUG-ON1 | 1000 | 105 | 11 | 11 |  | 1284000 | Nonthaburi | ตำบลบางกระสอ | 2021-01-18 | 2021-03-15 | Finished | [34 empty] | 2020-12-01 | 2021-01-18 | 2020-12-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-15 | 2021-05-10 | 2021-03-18 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-21 | Finished |  |  | 2021-04-27 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-10 | Finished |  |  | 100 | [41 empty] | 2021-05-10 | 1900-01-01 | 2021-05-10 | Waiting | POWER SUPPLY DELAY |  | 2021-09-25 | [12 empty] | 0 | 2021-06-21 | 2000-01-01 | 2021-06-21 | Finished | [14 empty] | 25 | 2021-09-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [18 empty] | 2020-12-16 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 808 | 98 | 32 | 20 | 958 | 0 | 98 | 8 | 20 | 126 | 86.85 | Red |  |  | 20011899 | 2020-08-28 |  |  |  | HDME001070 | 2020-12-16
TAC1731-TH | HET | 61000727 | HO | ส่งมอบแล้ว | - | TH209119 | Substitution Buildings at Soi Charoen Nakorn 53 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-03-28 | 2020-07-28 | 2020-09-28 | 2020-11-29 | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 829250 | Bangkok | เขตคลองสาน | 2020-07-20 | 2020-08-01 | Finished | [34 empty] | 2020-07-28 | 2020-08-02 | 2020-08-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-05 | 2020-09-14 | 2020-08-11 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | [41 empty] | 2020-08-26 | 2020-10-07 | 2020-10-07 | Finished |  |  | 2020-09-15 | 2020-10-08 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-13 | Finished |  |  | 100 | 2021-03-12 | 2020-09-16 | 2021-03-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-11 | Finished |  |  | 2020-09-16 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-11-30 | Finished |  |  | 2020-04-27 | Finished | [18 empty] | 2020-08-02 | Finished |  |  | 2020-08-02 | Finished |  |  | 2020-08-04 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011841 | 2020-07-28 |  |  |  | HDME000949 | 2020-08-02 | QC Passed
TAC1732-TH | HET | 61000727 | HO | ส่งมอบแล้ว | - | TH209119 | Substitution Buildings at Soi Charoen Nakorn 53 | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-03-28 | 2020-07-28 | 2020-09-28 | 2020-11-29 | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 829250 | Bangkok | เขตคลองสาน | 2020-07-20 | 2020-08-01 | Finished | [34 empty] | 2020-07-28 | 2020-08-02 | 2020-08-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-05 | 2020-09-14 | 2020-08-11 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | [41 empty] | 2020-08-26 | 2020-10-07 | 2020-10-07 | Finished |  |  | 2020-09-15 | 2020-10-08 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-15 | Finished |  |  | 100 | 2021-01-11 | 2021-03-19 | 2021-01-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-11-30 | Finished |  |  | 2020-04-27 | Finished | [18 empty] | 2020-08-02 | Finished |  |  | 2020-08-02 | Finished |  |  | 2020-08-04 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20011841 | 2020-07-28 |  |  |  | HDME000949 | 2020-08-02 | QC Passed
TAC1733-TH | HET | 61000728 | HO | ส่งมอบแล้ว | - | TH209120 | Substitution Buildings at Krungthep Bridge | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-03-28 | 2020-07-28 | 2020-09-28 | 2020-11-29 | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 829250 | Bangkok | เขตบางคอแหลม | 2020-07-20 | [36 empty] | 2020-07-28 | 2020-07-29 | 2020-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-05 | 2020-09-14 | 2020-08-11 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | [41 empty] | 2020-08-26 | 2020-09-30 | 2020-09-30 | Finished |  |  | 2020-09-30 | 2020-10-02 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-08 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-11-30 | Finished |  |  | 2020-04-23 | Finished | [10 empty] | 2021-03-15 | Finished | [6 empty] | 2020-07-29 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20011842 | 2020-07-28 |  |  |  | HDME000935 | 2020-07-29 | QC Passed
TAC1734-TH | HET | 61000728 | HO | ส่งมอบแล้ว | - | TH209120 | Substitution Buildings at Krungthep Bridge | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-03-28 | 2020-07-28 | 2020-09-28 | 2020-11-29 | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 829250 | Bangkok | เขตบางคอแหลม | 2020-07-20 | [36 empty] | 2020-07-28 | 2020-07-29 | 2020-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-05 | 2020-09-14 | 2020-08-11 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-21 | Finished |  |  | 2020-08-16 | Finished |  |  | 2020-08-23 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-26 | Finished |  |  | 100 | [41 empty] | 2020-08-26 | 2020-09-30 | 2020-09-30 | Finished |  |  | 2020-09-30 | 2020-10-02 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-10 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-11-30 | Finished |  |  | 2020-04-23 | Finished | [10 empty] | 2021-03-15 | Finished | [6 empty] | 2020-07-29 | Finished |  |  | 2020-07-29 | Finished |  |  | 2020-07-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 693 | 93 | 24 | 16 | 826 | 0 | 0 | 0 | 1 | 1 | 99.88 | Blue |  |  | 20011842 | 2020-07-28 |  |  |  | HDME000935 | 2020-07-29 | QC Passed
TEB0125-TH | HET | 61000729 | HO | ส่งมอบแล้ว | - | TH209121 | Home Khun Surin | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-03-31 | 2020-06-15 | 2020-07-15 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 4 | 4 |  | 800000 | Bangkok | แขวงสวนหลวง เขตสวนหลวง | 2020-08-19 | [36 empty] | 2020-06-08 | 2020-06-23 | 2020-06-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-19 | 2020-09-25 | 2020-08-21 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-22 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-25 | Finished |  |  | 2020-08-26 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-09-01 | Finished |  |  | 100 | [41 empty] | 2020-09-01 | 2020-09-07 | 2020-09-07 | Finished |  |  | 2020-09-15 | 2020-09-08 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-11 | Finished |  |  | 100 | 2020-09-25 | 2021-06-11 | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 2021-06-11 | Finished | [6 empty] | 90 | 2021-05-20 | Finished | CONSTRUCTION DELAY |  | 2021-05-17 | Finished |  |  | 2020-04-17 | Finished | [10 empty] | 2021-05-17 | Finished | [6 empty] | 2020-06-23 | Finished |  |  | 2020-07-08 | Finished |  |  | 2020-07-10 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  | pass | 2021-07-08 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20011890 | 2020-06-08 |  |  |  | HDME000909 | 2020-06-23 | QC Passed
TBL0262-TH | HET | 61000731 | HO | ส่งมอบแล้ว | - | TH209123 | Home Khun Chaisak Chumprom | EL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-04-01 | 2020-11-01 | 2021-01-01 | 2021-07-01 | OUG-630-CO60,60S/4F | OUG-ON1 | 630 | 60 | 4 | 4 |  | 1551500 | Bangkok | เขตวังทองหลาง | 2020-12-25 | 2020-11-27 | Finished | [34 empty] | 2020-10-30 | 2020-11-04 | 2020-11-04 | Finished | STORE AREA | [13 empty] | 2020-10-30 | 2020-11-25 | 2020-11-29 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-13 | Finished |  |  | 2020-12-17 | Finished |  |  | 100 | [41 empty] | 2020-12-17 | 1900-01-01 | 2020-12-17 | Waiting | POWER SUPPLY DELAY |  | 2020-11-10 | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-26 | Finished |  |  | 100 | 2021-04-02 | 2021-07-10 | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-07-10 | Finished | [6 empty] | 90 | 2021-05-25 | Finished | POWER SUPPLY DELAY |  | 2021-06-22 | Finished |  |  | 2020-05-14 | Finished | [10 empty] | 2021-06-22 | Finished | [6 empty] | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20011925 | 2020-10-30 |  |  |  | HDME001026 | 2020-11-04 | QC Passed
TFA1376-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | 1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | 1200TX-EN,R4.1M,D30 | TX-EN |  |  |  |  | 4100 | 1016500 | Bangkok | แขวงพระโขนง | 2021-01-15 | [20 empty] | 2020-01-20 | Finished | [14 empty] | 2020-09-20 | 2020-09-20 | 2020-10-08 | Finished | STORE AREA | [13 empty] | 2021-01-22 | 2021-02-15 | [41 empty] | 2021-01-22 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-01-31 | Finished |  |  | 2021-02-02 | Finished |  |  | 100 | 2021-02-02 | 1900-01-01 | 2021-02-02 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | 2021-02-10 | 2000-01-01 | 2021-02-10 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-10-06 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Red |  |  | 20011953 | 2020-09-20 |  |  |  | HDME001003 | 2020-10-08
TFA1377-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | 2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | 1200TX-EN,R4.1M,D30 | TX-EN |  |  |  |  | 4100 | 1016500 | Bangkok | แขวงพระโขนง | 2021-01-15 | [20 empty] | 2020-01-20 | Finished | [14 empty] | 2020-09-20 | 2020-09-20 | 2020-10-08 | Finished | STORE AREA | [13 empty] | 2021-01-22 | 2021-02-15 | [41 empty] | 2021-01-22 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-01-31 | Finished |  |  | 2021-02-02 | Finished |  |  | 100 | 2021-02-02 | 1900-01-01 | 2021-02-02 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | 2021-02-10 | 2000-01-01 | 2021-02-10 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-10-06 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Red |  |  | 20011953 | 2020-09-20 |  |  |  | HDME001003 | 2020-10-08
TEC0165-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | DW01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | DT-50S-B30,30S/2F | DT | 50 | 30 | 2 | 2 |  | 214000 | Bangkok | แขวงพระโขนง | 2021-10-30 | [36 empty] | 2020-10-05 | 2020-10-05 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-09-06 | 2021-09-26 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2021-01-14 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20011955 | 2020-10-05 |  |  |  | HDME001095 | 2021-01-14
TAJ0700-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | P1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | P-1600-CO105,105S/8F | UAG-SN1 | 1600 | 105 | 8 | 8 |  | 1498000 | Bangkok | แขวงพระโขนง | 2021-03-26 | 2021-03-26 | Finished | [34 empty] | 2020-10-05 | 2020-10-05 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-03-22 | 2021-04-30 | 2021-04-01 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-20 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-22 | Finished |  |  | 2021-04-29 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-05 | Finished |  |  | 100 | [41 empty] | 2021-05-05 | 1900-01-01 | 2021-05-05 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 0 | 84 | 24 | 16 | 124 | 81.35 | Red |  |  | 20011954 | 2020-10-05 |  |  |  | HDME001007 | 2020-10-15
TAJ0701-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | P2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | P-1600-CO105,105S/8F | UAG-SN1 | 1600 | 105 | 8 | 8 |  | 1498000 | Bangkok | แขวงพระโขนง | 2021-03-26 | 2021-03-26 | Finished | [34 empty] | 2020-10-05 | 2020-10-05 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-03-22 | 2021-04-30 | 2021-04-01 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-20 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-22 | Finished |  |  | 2021-04-29 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-05 | Finished |  |  | 100 | [41 empty] | 2021-05-05 | 1900-01-01 | 2021-05-05 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 0 | 84 | 24 | 16 | 124 | 81.35 | Red |  |  | 20011954 | 2020-10-05 |  |  |  | HDME001007 | 2020-10-15
TAJ0702-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | P3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | P-1600-CO105,105S/8F | UAG-SN1 | 1600 | 105 | 8 | 8 |  | 1498000 | Bangkok | แขวงพระโขนง | 2021-04-30 | 2021-05-17 | Finished | [34 empty] | 2020-10-05 | 2020-10-05 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-05-17 | 2021-08-15 | 2021-05-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-12 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-06-23 | Finished |  |  | 2021-06-26 | Finished |  |  | 2021-06-30 | Finished |  |  | 100 | [41 empty] | 2021-06-30 | 1900-01-01 | 2021-06-30 | Waiting | POWER SUPPLY DELAY |  | 2021-10-30 | [12 empty] | 0 | 2021-07-02 | 2000-01-01 | 2021-07-02 | Finished | [14 empty] | 25 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 0 | 84 | 6 | 16 | 106 | 84.06 | Red |  |  | 20011954 | 2020-10-05 |  |  |  | HDME001007 | 2020-10-15
TAJ0703-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | P4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | P-1000-CO105D,105S/10F | UAG-SN1 | 1000 | 105 | 10 | 10 |  | 1177000 | Bangkok | แขวงพระโขนง | 2021-08-06 | 2021-08-06 | Finished | [34 empty] | 2020-09-02 | 2020-09-02 | 2020-09-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-06 | 2021-09-10 | 2021-08-07 | Finished |  |  | 2021-08-24 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-31 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-09-03 | Finished | [14 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-09-12 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-15 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 157 | 85 | 24 | 16 | 282 | 62.6 | Red |  |  | 20011954 | 2020-09-02 |  |  |  | HDME000977 | 2020-09-12
TAJ0704-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | P5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | P-1000-CO105D,105S/10F | UAG-SN1 | 1000 | 105 | 10 | 10 |  | 1177000 | Bangkok | แขวงพระโขนง | 2021-08-06 | 2021-08-06 | Finished | [34 empty] | 2020-09-02 | 2020-09-02 | 2020-09-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-06 | 2021-09-10 | 2021-08-07 | Finished |  |  | 2021-08-24 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-31 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-09-03 | Finished | [14 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-09-12 | Finished |  |  | 2020-09-12 | Finished |  |  | 2020-09-15 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 157 | 85 | 24 | 16 | 282 | 62.6 | Red |  |  | 20011954 | 2020-09-02 |  |  |  | HDME000977 | 2020-09-12
TBL0263-TH | HET | 61000733 | Install | เลยสัญญา HO | - | TH209125 | Berli Jucker Building (A,B & C) | S1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-17 | 2020-09-02 | 2021-03-31 | 2021-07-31 | OUG-1600-CO105,105S/9F | OUG-ON1 | 1600 | 105 | 9 | 9 |  | 2247000 | Bangkok | แขวงพระโขนง | 2021-04-30 | 2021-05-17 | Finished | [34 empty] | 2020-10-05 | 2020-10-05 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-05-17 | 2021-08-15 | 2021-05-22 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-12 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-21 | Finished | [14 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | 2021-07-02 | 2000-01-01 | 2021-07-02 | Finished | [14 empty] | 25 | 2021-12-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-05-01 | Finished | [18 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 702 | 88 | 24 | 16 | 830 | 175 | 88 | 6 | 16 | 285 | 65.66 | Red |  |  | 20011954 | 2020-10-05 |  |  |  | HDME001007 | 2020-10-15
TAD0444-TH | HET | 61000736 | Test | ยังอยู่ในสัญญา HO | - | TH209126 | In-patient 5 fl. bldg., Chaibadan Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-04-10 | 2020-07-25 | 2020-09-25 | 2021-11-01 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1600000 | Lop Buri | อำเภอชัยบาดาล | 2020-07-25 | 2020-07-25 | Finished | [34 empty] | 2020-07-24 | 2020-08-07 | 2020-08-07 | Finished | CONSTRUCTION STOP | [13 empty] | 2020-07-25 | 2020-08-25 | 2020-08-09 | Finished |  |  | 2020-08-13 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-17 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-16 | Finished |  |  | 100 | [41 empty] | 2020-08-16 | 1900-01-01 | 2020-08-16 | Waiting | POWER SUPPLY DELAY |  | 2021-10-25 | [12 empty] | 0 | 2021-04-12 | 2000-01-01 | 2021-04-12 | Finished | [14 empty] | 25 | 2021-12-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-05-14 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-08-07 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-11 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Green |  |  | 20012007 | 2020-07-24 |  |  |  | HDME000952 | 2020-08-07
TAD0445-TH | HET | 61000736 | Test | ยังอยู่ในสัญญา HO | - | TH209126 | In-patient 5 fl. bldg., Chaibadan Hospital | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-04-10 | 2020-07-25 | 2020-09-25 | 2021-11-01 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1600000 | Lop Buri | อำเภอชัยบาดาล | 2020-07-25 | 2020-07-25 | Finished | [34 empty] | 2020-07-24 | 2020-08-07 | 2020-08-07 | Finished | PAYMENT DELAY | [13 empty] | 2020-07-25 | 2020-08-25 | 2020-08-09 | Finished |  |  | 2020-08-13 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-17 | Finished |  |  | 2020-08-15 | Finished |  |  | 2020-08-16 | Finished |  |  | 100 | [41 empty] | 2020-08-16 | 1900-01-01 | 2020-08-16 | Waiting | POWER SUPPLY DELAY |  | 2021-10-25 | [12 empty] | 0 | 2021-04-12 | 2000-01-01 | 2021-04-12 | Finished | [14 empty] | 25 | 2021-12-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-05-14 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-08-07 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-11 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Green |  |  | 20012007 | 2020-07-24 |  |  |  | HDME000952 | 2020-08-07
TAJ0706-TH | HET | 61000736 | Test | ยังอยู่ในสัญญา HO | - | TH209126 | In-patient 5 fl. bldg., Chaibadan Hospital | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-04-10 | 2020-07-25 | 2020-09-25 | 2021-11-01 | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1300000 | Lop Buri | อำเภอชัยบาดาล | 2020-07-25 | 2020-07-25 | Finished | [34 empty] | 2020-07-24 | 2020-08-07 | 2020-08-07 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-07-25 | 2020-08-25 | 2020-08-10 | Finished |  |  | 2020-08-30 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-08-31 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-08-30 | Finished |  |  | 100 | [41 empty] | 2020-08-30 | 1900-01-01 | 2020-08-30 | Waiting | POWER SUPPLY DELAY |  | 2021-10-25 | [12 empty] | 0 | 2021-04-12 | 2000-01-01 | 2021-04-12 | Finished | [14 empty] | 25 | 2021-12-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-05-14 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-08-07 | Finished |  |  | 2020-08-07 | Finished |  |  | 2020-08-11 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Green |  |  | 20012007 | 2020-07-24 |  |  |  | HDME000952 | 2020-08-07
TAD0446-TH | HET | 61000737 | HO | ส่งมอบแล้ว | - | TH209130 | Building 114 Bed Suwannaphum Roi Et Hospital | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-01-28 | 2020-11-28 | 2021-02-28 | 2021-06-15 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1300000 | Roi Et | อำเภอเมืองสุวรรณภูมิ | 2020-12-11 | 2020-12-09 | Finished | [34 empty] | 2020-11-27 | 2020-12-01 | 2020-12-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-28 | 2020-12-28 | 2020-12-09 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-12-13 | Finished |  |  | 2021-12-15 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-09 | Finished |  |  | 100 | [41 empty] | 2021-01-09 | 2021-01-18 | 2021-01-18 | Finished |  |  | 2020-12-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished |  |  | 2021-06-01 | Finished | [10 empty] | 50 | 2021-02-28 | Finished | CUSTOMER PAYMENT DELAY |  | 2021-05-31 | Finished |  |  | 2020-05-14 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-12-01 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2021-05-31 | Finished | [13 empty] | in process (defect) |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 16 | 16 | 97.54 | Blue |  |  | 20012235 | 2020-11-27 |  |  |  | HDME001054 | 2020-12-01
TAD0447-TH | HET | 61000737 | HO | ส่งมอบแล้ว | - | TH209130 | Building 114 Bed Suwannaphum Roi Et Hospital | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-01-28 | 2020-11-28 | 2021-02-28 | 2021-06-15 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1300000 | Roi Et | อำเภอเมืองสุวรรณภูมิ | 2020-12-11 | 2020-12-09 | Finished | [34 empty] | 2020-11-27 | 2020-12-01 | 2020-12-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-28 | 2020-12-28 | 2020-12-09 | Finished |  |  | 2020-12-12 | Finished |  |  | 2021-12-13 | Finished |  |  | 2021-12-15 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-09 | Finished |  |  | 100 | [41 empty] | 2021-01-09 | 2021-01-18 | 2021-01-18 | Finished |  |  | 2020-12-18 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished |  |  | 2021-06-01 | Finished | [10 empty] | 50 | 2021-02-28 | Finished | CUSTOMER PAYMENT DELAY |  | 2021-05-31 | Finished |  |  | 2020-05-14 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-12-01 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2021-05-31 | Finished | [13 empty] | in process (defect) |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 16 | 16 | 97.54 | Blue |  |  | 20012235 | 2020-11-27 |  |  |  | HDME001054 | 2020-12-01
TAJ0711-TH | HET | 61000739 | HO | ส่งมอบแล้ว | - | TH209131 | Link Car Park Donmueng Airport | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-02-17 | 2020-07-10 | 2020-08-30 | 2020-11-30 | P-1000-CO60W1,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 1070000 | Bangkok | เขตดอนเมือง | 2020-07-10 | [36 empty] | 2020-07-10 | 2020-07-10 | 2020-07-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-07-10 | 2020-08-30 | 2020-07-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-07-25 | 2020-07-25 | Finished |  |  | 2020-07-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-08-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-08-28 | Finished | [6 empty] | 90 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2020-10-20 | Finished |  |  | 2020-04-30 | Finished | [10 empty] | 2020-08-30 | Finished | [6 empty] | 2020-07-10 | Finished |  |  | 2020-07-10 | Finished |  |  | 2020-07-13 | Finished |  |  | 2020-10-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 1 | 1 | 99.74 | Blue |  |  | 20012096 | 2020-07-10 |  |  |  | HDME000920 | 2020-07-10 | QC Passed
TAC1739-TH | HET | 61000740 | HO | ส่งมอบแล้ว | - | TH219004 | Apartment Triple T | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-04-17 | 2021-01-08 | 2021-03-08 | 2021-06-30 | VFI-600-CO60,60S/6F | VFI-II | 600 | 60 | 6 | 6 |  | 1070000 | Khon Kaen | อำเภอเมืองขอนแก่น | 2021-01-22 | [36 empty] | 2020-01-08 | 2021-01-19 | 2021-01-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-09 | 2021-02-08 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-05-21 | 2021-05-21 | Finished |  |  | 2021-05-21 | 2021-05-23 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-15 | 2021-07-21 | 2021-02-15 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-08 | Finished | CUSTOMER PAYMENT DELAY |  | 2021-06-24 | Finished |  |  | 2020-05-11 | Finished | [10 empty] | 2021-06-24 | Finished | [6 empty] | 2021-01-19 | Finished |  |  | 2021-01-19 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-06-24 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012122 | 2021-01-08 |  |  |  | HDME001099 | 2021-01-19 | QC Passed
TAK0712-TH | HET | 61000742 | HO | ส่งมอบแล้ว | - | TH209132 | Rungrueng Phan | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-04-20 | 2020-10-20 | 2020-12-20 | 2021-05-14 | B-1000-2S60,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1400000 | Surat Thani | อำเภอท่าฉาง | 2020-11-03 | 2020-11-13 | Finished | [34 empty] | 2020-10-20 | 2020-11-03 | 2020-11-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-13 | 2020-11-23 | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-16 | Finished |  |  | 100 | [41 empty] | 2020-12-16 | 2021-05-16 | 2021-05-16 | Finished |  |  | 2021-05-16 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-22 | 2000-01-01 | 2020-12-22 | Finished |  |  | 2021-09-08 | Finished | [10 empty] | 50 | 2021-05-30 | Finished | POWER SUPPLY DELAY |  | 2021-04-30 | Finished |  |  | 2020-05-11 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-11-03 | Finished |  |  | 2020-11-03 | Finished |  |  | 2020-11-04 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no qc |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 16 | 16 | 96.93 | Blue |  |  | 20012189 | 2020-10-20 |  |  |  | HDME001023 | 2020-11-03
TAJ0713-TH | HET | 61000743 | HO | ยังอยู่ในสัญญา HO | - | TH209133 | Yong Xing Steel Factory | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-04-13 | 2020-07-13 | 2020-08-13 | 2021-10-30 | P-1000-CO60W2,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1430000 | Phrachin Buri | อำเภอศรีมหาโพธิ | 2020-08-13 | 2020-09-10 | Finished | [34 empty] | 2020-07-30 | 2020-08-13 | 2020-08-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-10 | 2020-11-30 | 2020-09-14 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-09-27 | Finished |  |  | 100 | [41 empty] | 2020-09-27 | 2020-11-30 | 2020-11-30 | Finished |  |  | 2020-11-30 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-28 | 2000-01-01 | 2020-12-28 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished | [6 empty] | 90 | 2021-10-17 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-05-12 | Finished | [10 empty] | 2021-07-15 | Finished | [6 empty] | 2020-08-13 | Finished |  |  | 2020-08-13 | Finished |  |  | 2020-08-18 | Finished | [17 empty] | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Green |  |  | 20012207 | 2020-07-30 |  |  |  | HDME000956 | 2020-08-13
TBK0197-TH | HET | 61000744 | Install | เลยสัญญา HO | - | TH209098 | CY+FF Rattanathibet | HS3-F | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2019-08-01 | 2021-06-01 | 2021-09-01 | 2021-08-01 | HVF-1600-CO210,210S/22F | HVF-5 | 1600 | 210 | 22 | 22 |  | 5724500 | Nonthaburi | ตำบลบางกระสอ | 2021-08-30 | [36 empty] | 2020-11-11 | 2021-08-26 | 2021-08-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-30 | 2021-10-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-26 | Finished |  |  | 2021-08-31 | Finished |  |  | 2021-08-31 | Finished | [22 empty] | 1437 | 109 | 48 | 24 | 1618 | 1437 | 109 | 48 | 24 | 1618 | 0 | Red |  |  | 20014310 | 2021-07-06
TAC1741-TH | HET | 61000745 | HO | ส่งมอบแล้ว | - | TH209135 | รพ.พหลพลพยุหเสนา อ.ที่พักเจ้าหน้าที่ | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2020-04-28 | 2020-08-13 | 2020-10-13 |  | VFI-750-CO90,90S/7F | VFI-II | 750 | 90 | 7 | 7 |  | 1284000 | Kanchanaburi | อำเภอเมือง | 2020-08-13 | [36 empty] | 2020-08-13 | 2020-08-13 | 2020-08-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-14 | 2020-09-04 | 2020-08-22 | Finished |  |  | 2020-08-24 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-29 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-12 | Finished |  |  | 100 | [41 empty] | 2020-09-12 | 2020-10-20 | 2020-10-20 | Finished |  |  | 2020-08-23 | 2020-10-20 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-24 | Finished |  |  | 100 | 2020-10-30 | 2021-01-29 | 2020-10-30 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2020-12-08 | Finished |  |  | 2020-05-14 | Finished | [18 empty] | 2020-08-13 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-18 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  | pass | 2021-04-09 | Finished |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012236 | 2020-08-13 |  |  |  | HDME000957 | 2020-08-13 | QC Passed
TFA1378-TH | HET | 61000746 | HO | ส่งมอบแล้ว | - | TH209137 | Asia Hospital | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2020-04-30 | 2020-08-31 | 2020-10-30 | 2021-04-28 | 1200TX-EN,R4.2M,D35 | TX-EN |  |  |  |  | 4200 | 1000000 | Phra Nakhon Si Ayutthaya | อำเภออุทัย | 2020-09-01 | [20 empty] | 2020-09-01 | Finished | [14 empty] | 2020-08-31 | 2020-09-02 | 2020-09-21 | Finished | OTHERS | [13 empty] | 2020-10-20 | 2020-11-25 | [41 empty] | 2020-10-23 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-31 | Finished |  |  | 100 | 2020-10-31 | 2021-03-31 | 2021-03-31 | Finished |  |  | 2021-04-20 | 2021-03-31 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2021-04-12 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-12 | Finished | [6 empty] | 90 | 2021-04-20 | Finished | POWER SUPPLY DELAY |  | 2021-04-16 | Finished |  |  | 2020-05-11 | Finished | [10 empty] | 2021-04-16 | Finished | [6 empty] | 2020-09-02 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-21 | Finished |  |  | 2021-04-16 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass | 2021-05-05 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20012211 | 2020-08-13 |  |  |  | HDME000969 | 2020-09-02 | QC Passed
TFA1379-TH | HET | 61000746 | HO | ส่งมอบแล้ว | - | TH209137 | Asia Hospital | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2020-04-30 | 2020-08-31 | 2020-10-30 | 2021-04-28 | 1200TX-EN,R4.2M,D35 | TX-EN |  |  |  |  | 4200 | 1000000 | Phra Nakhon Si Ayutthaya | อำเภออุทัย | 2020-09-01 | [20 empty] | 2020-09-01 | Finished | [14 empty] | 2020-08-31 | 2020-09-03 | 2020-09-21 | Finished | OTHERS | [13 empty] | 2020-10-20 | 2020-11-25 | [41 empty] | 2020-10-23 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-11-01 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-03 | Finished |  |  | 100 | 2020-11-03 | 2021-03-31 | 2021-03-31 | Finished |  |  | 2021-04-20 | 2021-03-31 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2021-04-12 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-12 | Finished | [6 empty] | 90 | 2021-04-20 | Finished | POWER SUPPLY DELAY |  | 2021-04-16 | Finished |  |  | 2020-05-11 | Finished | [10 empty] | 2021-04-16 | Finished | [6 empty] | 2020-09-02 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-21 | Finished |  |  | 2021-04-16 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass | 2021-05-05 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20012211 | 2020-08-13 |  |  |  | HDME000969 | 2020-09-02 | QC Passed
TAC1742-TH | HET | 61000747 | HO | ส่งมอบแล้ว | - | TH209136 | Boonyawittaya Foundation | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-04-16 | 2020-08-16 | 2020-10-16 | 2021-06-08 | VFI-900-CO60,60S/2F | VFI-II | 900 | 60 | 2 | 2 |  | 1000000 | Chon Buri | จังหวัดชลบุรี | 2020-10-16 | 2021-01-07 | Finished | [34 empty] | 2020-08-14 | 2020-08-14 | 2020-08-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-15 | 2020-09-15 | 2020-09-08 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-30 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-06 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-09 | Finished |  |  | 100 | [41 empty] | 2020-10-09 | 2021-05-14 | 2021-05-14 | Finished |  |  | 2020-09-14 | 2021-05-15 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-17 | Finished |  |  | 100 | 2020-12-14 | 2021-06-28 | 2020-12-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2021-04-25 | Finished | CONSTRUCTION DELAY |  | 2021-06-22 | Finished |  |  | 2020-05-14 | Finished | [10 empty] | 2021-06-22 | Finished | [6 empty] | 2020-08-25 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  | pass | 2021-07-08 | Finished |  |  | 362 | 88 | 16 | 16 | 482 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012205 | 2020-08-14 |  |  |  | HDME000960 | 2020-08-25 | QC Passed
TBL0305-TH | HET | 61000748 | HO | ส่งมอบแล้ว | - | TH209134 | MBK Center (Add Sky Walk) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-03-17 | 2020-08-31 | 2020-10-31 | 2021-01-15 | OUG-1600-CO90,90S/6F | OUG-ON1 | 1600 | 90 | 6 | 6 |  | 2350000 | Bangkok | เขตปทุมวัน | 2020-11-09 | 2020-11-10 | Finished | [34 empty] | 2020-09-21 | 2020-09-10 | 2020-09-08 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-11 | 2020-11-30 | 2020-11-11 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-26 | Finished |  |  | 100 | [41 empty] | 2020-12-26 | 2020-12-23 | 2020-12-23 | Finished |  |  | 2020-11-15 | 2020-12-23 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | 2021-05-13 | 2021-03-26 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | 2021-03-23 | Finished | H/O DOCUMENT DELAY |  | 2021-04-12 | Finished |  |  | 2020-05-18 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2020-09-08 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-09-30 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012297 | 2020-09-21 |  |  |  | HDME000972 | 2020-09-08 | QC Passed
TAJ0733-TH | HET | 61000755 | HO | ส่งมอบแล้ว | - | TH209144 | Sena Medictrade Wanghin 87 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-05-25 | 2020-09-25 | 2020-11-25 | 2021-01-25 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1070000 | Bangkok | แขวงลาดพร้าว เขตลาดพร้าว | 2020-10-20 | 2020-11-27 | Finished | [34 empty] | 2020-09-25 | 2020-09-30 | 2020-09-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-25 | 2020-10-20 | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | [41 empty] | 2020-12-18 | 2020-10-10 | 2020-10-10 | Finished |  |  | 2020-10-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-19 | 2021-03-05 | 2021-02-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-05 | Finished | [6 empty] | 90 | 2021-02-15 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2020-06-24 | Finished | [10 empty] | 2020-11-30 | Finished | [6 empty] | 2020-09-30 | Finished |  |  | 2020-09-30 | Finished |  |  | 2020-09-30 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass | 2021-03-17 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20012560 | 2020-09-25 |  |  |  | HDME000993 | 2020-09-30 | QC Passed
TFA1380-TH | HET | 61000757 | HO | ส่งมอบแล้ว | - | TH209146 | MBK Center (Add FL.6-FL.7) | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 6 |  | 1 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-04-15 | 2020-08-31 | 2020-10-31 | 2020-11-25 | 1200TX-EN,R4.85M,D30 | TX-EN |  |  |  |  | 4850 | 1400000 | Bangkok | เขตปทุมวัน | 2020-08-31 | [20 empty] | 2020-09-01 | Finished | [14 empty] | 2020-09-10 | 2020-09-10 | 2020-09-08 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-09-28 | 2020-10-31 | [41 empty] | 2020-09-28 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-11 | Finished |  |  | 2020-10-12 | Finished |  |  | 2020-10-13 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-15 | Finished |  |  | 100 | 2020-10-15 | 2020-11-04 | 2020-11-04 | Finished |  |  | 2020-11-04 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-01-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-18 | Finished | [6 empty] | 90 | 2021-03-23 | Finished | CONSTRUCTION DELAY |  | 2021-04-12 | Finished |  |  | 2020-05-18 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2020-09-08 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-09-30 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | pass | 2021-04-19 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20012298 | 2020-09-10 |  |  |  | HDME000973 | 2020-09-08 | QC Passed
TFA1381-TH | HET | 61000757 | HO | ส่งมอบแล้ว | - | TH209146 | MBK Center (Add FL.6-FL.7) | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 6 |  | 1 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-04-15 | 2020-08-31 | 2020-10-31 | 2020-11-25 | 1200TX-EN,R4.8M,D30 | TX-EN |  |  |  |  | 4800 | 1400000 | Bangkok | เขตปทุมวัน | 2020-08-31 | [20 empty] | 2020-09-01 | Finished | [14 empty] | 2020-09-10 | 2020-09-10 | 2020-09-08 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-09-28 | 2020-10-31 | [41 empty] | 2020-09-28 | Finished |  |  | 2020-10-17 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-25 | Finished |  |  | 100 | 2020-10-25 | 2020-11-04 | 2020-11-04 | Finished |  |  | 2020-11-04 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-01-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-18 | Finished | [6 empty] | 90 | 2021-03-23 | Finished | CONSTRUCTION DELAY |  | 2021-04-12 | Finished |  |  | 2020-05-18 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2020-09-08 | Finished |  |  | 2020-09-29 | Finished |  |  | 2020-09-30 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | pass | 2021-04-19 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20012298 | 2020-09-10 |  |  |  | HDME000973 | 2020-09-08 | QC Passed
TAC1745-TH | HET | 61000758 | HO | ส่งมอบแล้ว | - | TH209139 | Police College@Rayal Thai Police | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | APHIRADA BUNKUEA | 2020-04-23 | 2020-08-23 | 2020-11-23 |  | VFI-1000-CO90,90S/13F | VFI-II | 1000 | 90 | 13 | 13 |  | 2863575 | Bangkok | เขตจตุจักร | 2020-08-19 | 2020-08-24 | Finished | [34 empty] | 2020-08-25 | 2020-08-29 | 2020-08-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-24 | 2020-09-24 | 2020-09-02 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-10-03 | Finished |  |  | 2020-09-27 | Finished |  |  | 2020-09-24 | Finished |  |  | 100 | [41 empty] | 2020-09-24 | 2020-11-15 | 2020-11-15 | Finished |  |  | 2020-11-04 | 2020-11-15 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-19 | Finished |  |  | 100 | 2020-10-27 | 2021-02-10 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-02-10 | Finished |  |  | 100 | 2020-12-16 | Finished | CONSTRUCTION DELAY |  | 2020-12-28 | Finished |  |  | 2020-05-30 | Finished | [10 empty] | 2020-12-30 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-03 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012458 | 2020-08-25 |  |  |  | HDME000965 | 2020-08-29 | QC Passed
TAC1746-TH | HET | 61000758 | HO | ส่งมอบแล้ว | - | TH209139 | Police College@Rayal Thai Police | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | APHIRADA BUNKUEA | 2020-04-23 | 2020-08-23 | 2020-11-23 |  | VFI-1000-CO90,90S/13F | VFI-II | 1000 | 90 | 13 | 13 |  | 2863575 | Bangkok | เขตจตุจักร | 2020-08-19 | 2020-08-24 | Finished | [34 empty] | 2020-08-25 | 2020-08-29 | 2020-08-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-24 | 2020-09-24 | 2020-09-02 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-21 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-10-03 | Finished |  |  | 2020-09-27 | Finished |  |  | 2020-09-24 | Finished |  |  | 100 | [41 empty] | 2020-09-24 | 2020-11-15 | 2020-11-15 | Finished |  |  | 2020-11-04 | 2020-11-15 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-19 | Finished |  |  | 100 | 2021-05-13 | 2021-02-10 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-27 | Finished |  |  | 2021-02-10 | Finished |  |  | 100 | 2020-12-16 | Finished | CONSTRUCTION DELAY |  | 2020-12-28 | Finished |  |  | 2020-05-30 | Finished | [10 empty] | 2020-12-30 | Finished | [6 empty] | 2020-08-29 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-03 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-24 | Finished |  | pass | 2021-02-24 | Finished |  |  | 969 | 107 | 32 | 20 | 1128 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012458 | 2020-08-25 |  |  |  | HDME000965 | 2020-08-29 | QC Passed
TAJ0735-TH | HET | 61000759 | Test | ยังอยู่ในสัญญา HO | - | TH209147 | Condo 7 Floors Sukhumvit 70 (Sattha Architect) | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-05-08 | 2020-09-08 | 2020-12-08 | 2021-09-30 | P-600-CO60W,60S/7F | UAG-SN1 | 600 | 60 | 7 | 7 |  | 960000 | Bangkok | แขวงบางนา | 2020-09-09 | 2020-11-05 | Finished | [34 empty] | 2020-09-08 | 2020-09-28 | 2020-09-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-09 | 2020-10-09 | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-20 | Finished |  |  | 100 | [41 empty] | 2020-12-20 | 1900-01-01 | 2020-12-20 | Waiting | POWER SUPPLY DELAY |  | 2021-10-15 | [12 empty] | 0 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2021-10-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-05-30 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-09-28 | Finished |  |  | 2020-09-28 | Finished |  |  | 2020-09-30 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 83 | 6 | 16 | 105 | 83.06 | Orange |  |  | 20012459 | 2020-09-08 |  |  |  | HDME000988 | 2020-09-28
TEB0126-TH | HET | 61000761 | Test | ยังอยู่ในสัญญา HO | - | TH209149 | Chanan Chai Gold | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Thamnul Kongsar | 2020-03-30 | 2021-01-30 | 2021-03-30 | 2021-11-30 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 4 | 4 |  | 1000000 | Samut Sakhon | ตำบลมหาชัย | 2021-11-30 | [36 empty] | 2021-01-15 | 2021-01-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-11-30 | 2021-12-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | OTHERS | [5 empty] | 2020-06-11 | Finished |  |  | 2021-10-11 | Finished | [6 empty] | 2021-11-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20012677 | 2021-09-30
TAC1749-TH | HET | 61000762 | HO | ส่งมอบแล้ว | - | TH209150 | Bumrung Witthaya School | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-05-15 | 2020-08-31 | 2020-10-30 | 2021-07-30 | VFI-750-CO60,60S/4F | VFI-II | 750 | 60 | 4 | 4 |  | 1144900 | Buri Ram | ตำบลลำปลายมาศ | 2020-08-16 | 2020-09-28 | Finished | [34 empty] | 2020-08-31 | 2020-09-10 | 2020-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-28 | 2020-11-30 | 2020-09-30 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-18 | Finished |  |  | 100 | [41 empty] | 2020-10-18 | 2021-06-09 | 2021-06-09 | Finished |  |  | 2020-11-30 | 2021-06-12 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-12-28 | 2000-01-01 | 2020-12-28 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 90 | 2021-05-04 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-05-30 | Finished | [10 empty] | 2021-07-15 | Finished | [6 empty] | 2020-09-10 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-07-30 | Finished | [13 empty] | no pass |  |  |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20012479 | 2020-08-31 |  |  |  | HDME000975 | 2020-09-10
TAC1750-TH | HET | 61000762 | HO | ส่งมอบแล้ว | - | TH209150 | Bumrung Witthaya School | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-05-15 | 2020-08-31 | 2020-10-30 | 2021-07-30 | VFI-750-CO60,60S/4F | VFI-II | 750 | 60 | 4 | 4 |  | 1144900 | Buri Ram | ตำบลลำปลายมาศ | 2020-08-16 | 2020-09-28 | Finished | [34 empty] | 2020-08-31 | 2020-09-10 | 2020-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-28 | 2020-11-30 | 2020-09-30 | Finished |  |  | 2020-10-02 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-04 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-07 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-18 | Finished |  |  | 100 | [41 empty] | 2020-10-18 | 2021-06-09 | 2021-06-09 | Finished |  |  | 2020-11-30 | 2021-06-12 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-12-28 | 2000-01-01 | 2020-12-28 | Finished |  |  | 2021-07-12 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 90 | 2021-05-04 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-05-30 | Finished | [10 empty] | 2021-07-15 | Finished | [6 empty] | 2020-09-10 | Finished |  |  | 2020-09-10 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-07-30 | Finished | [13 empty] | no pass |  |  |  |  | 472 | 90 | 16 | 16 | 594 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20012479 | 2020-08-31 |  |  |  | HDME000975 | 2020-09-10
TAJ0736-TH | HET | 61000763 | HO | ส่งมอบแล้ว | - | TH209151 | Office of The National Anti-Corruption Commission Phits | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-05-18 | 2020-09-18 | 2021-01-18 | 2021-10-25 | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1123500 | Phitsanulok | ตำบลมะขามสูง | 2020-09-19 | 2020-09-19 | Finished | [34 empty] | 2020-09-18 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-30 | 2021-01-18 | 2020-11-05 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-16 | Finished |  |  | 100 | [41 empty] | 2020-11-16 | 2021-04-11 | 2021-04-11 | Finished |  |  | 2021-04-05 | 2021-04-12 | Finished |  |  | 2021-04-24 | Finished |  |  | 2021-04-29 | Finished |  |  | 100 | 2020-12-10 | 2021-05-25 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-25 | Finished | [6 empty] | 90 | 2021-09-30 | Finished | CONSTRUCTION DELAY |  | 2021-09-15 | Finished |  |  | 2020-05-31 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-09-15 | Finished | [13 empty] | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20012486 | 2020-09-18 |  |  |  | HDME001019 | 2020-10-28 | QC Passed
TAJ0737-TH | HET | 61000763 | HO | ส่งมอบแล้ว | - | TH209151 | Office of The National Anti-Corruption Commission Phits | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-05-18 | 2020-09-18 | 2021-01-18 | 2021-10-25 | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1123500 | Phitsanulok | ตำบลมะขามสูง | 2020-09-19 | 2020-09-19 | Finished | [34 empty] | 2020-09-18 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-30 | 2021-01-18 | 2020-11-06 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-22 | Finished |  |  | 100 | [41 empty] | 2020-11-22 | 2021-04-25 | 2021-04-25 | Finished |  |  | 2021-04-05 | 2021-04-26 | Finished |  |  | 2021-04-27 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2020-12-10 | 2021-05-25 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-25 | Finished | [6 empty] | 90 | 2021-09-30 | Finished | CONSTRUCTION DELAY |  | 2021-09-15 | Finished |  |  | 2020-05-31 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-09-15 | Finished | [13 empty] | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20012486 | 2020-09-18 |  |  |  | HDME001019 | 2020-10-28 | QC Passed
TAJ0738-TH | HET | 61000763 | HO | ส่งมอบแล้ว | - | TH209151 | Office of The National Anti-Corruption Commission Phits | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-05-18 | 2020-09-18 | 2021-01-18 | 2021-10-25 | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1123500 | Phitsanulok | ตำบลมะขามสูง | 2020-09-19 | 2020-09-19 | Finished | [34 empty] | 2020-09-18 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-30 | 2021-01-18 | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-26 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-29 | Finished |  |  | 100 | [41 empty] | 2020-11-29 | 2021-04-26 | 2021-04-26 | Finished |  |  | 2021-04-05 | 2021-04-27 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished |  |  | 100 | 2020-11-23 | 2021-05-25 | 2020-11-23 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-25 | Finished | [6 empty] | 90 | 2021-09-30 | Finished | CONSTRUCTION DELAY |  | 2021-09-15 | Finished |  |  | 2020-05-31 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-09-15 | Finished | [13 empty] | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20012486 | 2020-09-18 |  |  |  | HDME001019 | 2020-10-28 | QC Passed
TAC1751-TH | HET | 61000764 | HO | ส่งมอบแล้ว | - | TH209152 | Home K.Phipat | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2020-05-18 | 2020-09-15 | 2020-11-14 | 2020-12-14 | VFI-450-CO60,60S/6F | VFI-II | 450 | 60 | 6 | 6 |  | 900000 | Bangkok | เขตบางรัก | 2020-09-01 | 2020-09-16 | Finished | [34 empty] | 2020-09-15 | 2020-09-16 | 2020-09-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-15 | 2020-10-05 | 2020-09-17 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-20 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 100 | [41 empty] | 2020-09-26 | 2020-11-10 | 2020-11-10 | Finished |  |  | 2020-10-06 | 2020-11-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-14 | Finished |  |  | 100 | 2020-12-02 | 2021-03-12 | 2020-12-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-02 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2020-11-30 | Finished | CONSTRUCTION DELAY |  | 2020-11-23 | Finished |  |  | 2020-05-30 | Finished | [18 empty] | 2020-09-16 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012499 | 2020-09-15 |  |  |  | HDME000978 | 2020-09-16 | QC Passed
TBL0306-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | B1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-09-10 | 2020-12-01 | Finished | [34 empty] | 2020-10-09 | 2020-10-31 | 2020-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-11 | 2020-10-11 | 2020-12-23 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-10 | Finished |  |  | 100 | [41 empty] | 2021-01-10 | 1900-01-01 | 2021-01-10 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 4 | 16 | 104 | 79.2 | Green |  |  | 20012554 | 2020-10-09 |  |  |  | HDME001021 | 2020-10-31
TBL0307-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | C1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-09-10 | 2020-12-01 | Finished | [34 empty] | 2020-10-09 | 2020-10-31 | 2020-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-11 | 2020-10-11 | 2021-01-27 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | [41 empty] | 2021-03-12 | 1900-01-01 | 2021-03-12 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 4 | 16 | 104 | 79.2 | Green |  |  | 20012554 | 2020-10-09 |  |  |  | HDME001021 | 2020-10-31
TBL0308-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | D1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-09-10 | 2020-12-01 | Finished | [34 empty] | 2020-10-09 | 2020-10-31 | 2020-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-11 | 2020-10-11 | 2020-12-23 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-10 | Finished |  |  | 100 | [41 empty] | 2021-01-10 | 1900-01-01 | 2021-01-10 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 4 | 16 | 104 | 79.2 | Green |  |  | 20012554 | 2020-10-09 |  |  |  | HDME001021 | 2020-10-31
TBL0309-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | E1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-09-10 | 2020-12-01 | Finished | [34 empty] | 2020-10-09 | 2020-10-31 | 2020-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-11 | 2020-10-11 | 2021-01-11 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | [41 empty] | 2021-01-25 | 1900-01-01 | 2021-01-25 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-03-18 | 2000-01-01 | 2021-03-18 | Finished |  |  | 2021-03-18 | Finished | [10 empty] | 50 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 0 | 16 | 100 | 80 | Green |  |  | 20012554 | 2020-10-09 |  |  |  | HDME001021 | 2020-10-31
TBL0310-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | F1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-09-10 | 2020-12-01 | Finished | [34 empty] | 2020-10-09 | 2020-10-31 | 2020-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-11 | 2020-10-11 | 2020-12-11 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-09 | Finished |  |  | 100 | [41 empty] | 2021-01-09 | 1900-01-01 | 2021-01-09 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-02-08 | 2000-01-01 | 2021-02-08 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 4 | 16 | 104 | 79.2 | Green |  |  | 20012554 | 2020-10-09 |  |  |  | HDME001021 | 2020-10-31
TBL0311-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | G1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-CO60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-09-10 | 2020-12-01 | Finished | [34 empty] | 2020-10-09 | 2020-10-31 | 2020-10-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-11 | 2020-10-11 | 2021-01-11 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | [41 empty] | 2021-01-25 | 1900-01-01 | 2021-01-25 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-03-18 | 2000-01-01 | 2021-03-18 | Finished |  |  | 2021-03-18 | Finished | [10 empty] | 50 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished |  |  | 2020-10-31 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 0 | 16 | 100 | 80 | Green |  |  | 20012554 | 2020-10-09 |  |  |  | HDME001021 | 2020-10-31
TBL0312-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/6F | OUG-ON1 | 1350 | 60 | 6 | 6 |  | 1155600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-02-01 | Finished | [34 empty] | 2020-10-09 | 2021-01-13 | 2021-01-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-02-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | [41 empty] | 2021-03-25 | 1900-01-01 | 2021-03-25 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-13 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 6 | 16 | 108 | 83.86 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001089 | 2021-01-13
TBL0314-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/6F | OUG-ON1 | 1350 | 60 | 6 | 6 |  | 1155600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-03-08 | Finished | [34 empty] | 2020-10-09 | 2020-12-04 | 2020-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-03-14 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-04-14 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-04-16 | Finished |  |  | 2021-04-16 | Finished |  |  | 100 | [41 empty] | 2021-04-16 | 1900-01-01 | 2021-04-16 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished |  |  | 2021-06-21 | Finished | [10 empty] | 50 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 0 | 16 | 102 | 84.75 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001061 | 2020-12-04
TBL0321-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/6F | OUG-ON1 | 1350 | 60 | 6 | 6 |  | 1155600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-03-08 | Finished | [34 empty] | 2020-10-09 | 2020-12-04 | 2020-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-03-14 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-04-14 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-16 | Finished |  |  | 2021-04-16 | Finished |  |  | 100 | [41 empty] | 2021-04-16 | 1900-01-01 | 2021-04-16 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished |  |  | 2021-06-21 | Finished | [10 empty] | 50 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 0 | 16 | 102 | 84.75 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001061 | 2020-12-04
TBL0315-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/6F | OUG-ON1 | 1350 | 60 | 6 | 6 |  | 1155600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-03-08 | Finished | [34 empty] | 2020-10-09 | 2020-12-09 | 2020-02-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-03-14 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-04-14 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-16 | Finished |  |  | 2021-04-16 | Finished |  |  | 100 | [41 empty] | 2021-04-16 | 1900-01-01 | 2021-04-16 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished |  |  | 2021-06-21 | Finished | [10 empty] | 50 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-09 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-15 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 0 | 16 | 102 | 84.75 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001065 | 2020-12-09
TBL0316-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/6F | OUG-ON1 | 1350 | 60 | 6 | 6 |  | 1155600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-03-08 | Finished | [34 empty] | 2020-10-09 | 2020-12-09 | 2020-02-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-03-14 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-04-14 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-16 | Finished |  |  | 2021-04-16 | Finished |  |  | 100 | [41 empty] | 2021-04-16 | 1900-01-01 | 2021-04-16 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished |  |  | 2021-06-21 | Finished | [10 empty] | 50 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-09 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-15 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 0 | 16 | 102 | 84.75 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001065 | 2020-12-09
TBL0313-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/6F | OUG-ON1 | 1350 | 60 | 6 | 6 |  | 1155600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-02-01 | Finished | [34 empty] | 2020-10-09 | 2021-01-13 | 2021-01-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-01-27 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-14 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | [41 empty] | 2021-02-17 | 1900-01-01 | 2021-02-17 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-03-18 | 2000-01-01 | 2021-03-18 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-13 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 6 | 16 | 108 | 83.86 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001089 | 2021-01-13
TBL0317-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/2F | OUG-ON1 | 1350 | 60 | 2 | 2 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-05-01 | Finished | [34 empty] | 2020-10-09 | 2020-12-04 | 2020-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-05-03 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-23 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-06-23 | 2000-01-01 | 2021-06-23 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished | [22 empty] | 331 | 83 | 16 | 16 | 446 | 0 | 83 | 4 | 16 | 103 | 76.91 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001061 | 2020-12-04
TBL0322-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | PL8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1350-CO60,60S/2F | OUG-ON1 | 1350 | 60 | 2 | 2 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-05-01 | Finished | [34 empty] | 2020-10-09 | 2020-12-04 | 2020-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-05-03 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-23 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-06-23 | 2000-01-01 | 2021-06-23 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished | [22 empty] | 331 | 83 | 16 | 16 | 446 | 0 | 83 | 4 | 16 | 103 | 76.91 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001061 | 2020-12-04
TBL0318-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | SL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-2S60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 1177000 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-03-08 | Finished | [34 empty] | 2020-10-09 | 2020-12-04 | 2020-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-03-14 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | [41 empty] | 2021-08-17 | 1900-01-01 | 2021-08-17 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-06-21 | 2000-01-01 | 2021-06-21 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 6 | 16 | 108 | 83.86 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001061 | 2020-12-04
TBL0319-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | SL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-2S60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 1177000 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-03-08 | Finished | [34 empty] | 2020-10-09 | 2020-12-09 | 2020-02-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-03-14 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-18 | Finished |  |  | 100 | [41 empty] | 2021-05-18 | 1900-01-01 | 2021-05-18 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-06-21 | 2000-01-01 | 2021-06-21 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-09 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-15 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 86 | 6 | 16 | 108 | 83.86 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001065 | 2020-12-09
TBL0320-TH | HET | 61000766 | Install | ยังอยู่ในสัญญา HO | - | TH209097 | Marriott Khao Lak Resort and Spa | SL3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Chanyuth Soithong | 2019-11-07 | 2020-09-30 | 2020-11-30 | 2021-12-31 | OUG-1600-2S60,60S/3F | OUG-ON1 | 1600 | 60 | 3 | 3 |  | 1048600 | Phangnga | อำเภอตะกั่วป่า | 2020-11-10 | 2021-05-01 | Finished | [34 empty] | 2020-10-09 | 2020-12-04 | 2020-12-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-11 | 2021-06-04 | Finished |  |  | 2021-07-07 | Finished |  |  | 2021-07-07 | Finished |  |  | 2021-07-07 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-27 | Finished |  |  | 2021-07-10 | Finished |  |  | 100 | [41 empty] | 2021-07-10 | 1900-01-01 | 2021-07-10 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-07-01 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished | [22 empty] | 384 | 84 | 16 | 16 | 500 | 0 | 84 | 16 | 16 | 116 | 76.8 | Green |  |  | 20012554 | 2020-11-10 |  |  |  | HDME001061 | 2020-12-04
TAK0740-TH | HET | 61000767 | HO | ส่งมอบแล้ว | - | TH209154 | Mithmitree Hospital | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-05-21 | 2020-08-21 | 2020-11-05 | 2021-08-05 | B-1000-2S60,60S/6F | UAG-SN1 | 1000 | 60 | 6 | 6 |  | 1412400 | Nonthaburi | ตำบลท่าทราย | 2020-08-21 | 2020-09-13 | Finished | [34 empty] | 2020-08-26 | 2020-09-09 | 2020-09-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-24 | 2020-11-05 | 2020-09-13 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-15 | Finished |  |  | 100 | [41 empty] | 2020-10-15 | 2021-07-26 | 2021-07-26 | Finished |  |  | 2021-06-20 | 2021-07-26 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 100 | 2021-05-13 | 2021-08-13 | 2021-05-13 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-13 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-19 | Finished |  |  | 2020-06-11 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-09-09 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20012590 | 2020-08-26 |  |  |  | HDME000974 | 2020-09-09 | QC Passed
TAJ0741-TH | HET | 61000767 | HO | ส่งมอบแล้ว | - | TH209154 | Mithmitree Hospital | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-05-21 | 2020-08-21 | 2020-11-05 | 2021-08-05 | P-1000-CO60W2,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1391000 | Nonthaburi | ตำบลท่าทราย | 2020-08-21 | 2020-09-13 | Finished | [34 empty] | 2020-07-16 | 2020-09-09 | 2020-09-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-08-24 | 2020-11-05 | 2020-09-13 | Finished |  |  | 2020-09-16 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-09-19 | Finished |  |  | 2020-09-24 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-15 | Finished |  |  | 100 | [41 empty] | 2020-10-15 | 2021-07-26 | 2021-07-26 | Finished |  |  | 2021-06-20 | 2021-07-26 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 100 | 2020-10-09 | 2021-08-13 | 2020-10-09 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-13 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-19 | Finished |  |  | 2020-06-11 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-09-09 | Finished |  |  | 2020-09-09 | Finished |  |  | 2020-09-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20012590 | 2020-08-26 |  |  |  | HDME000974 | 2020-09-09 | QC Passed
TAC1752-TH | HET | 61000768 | HO | ส่งมอบแล้ว | - | TH209155 | Thanyarak Hospital | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-05-20 | 2020-08-20 | 2020-09-20 | 2020-11-20 | VFI-1000-CO60,60S/3F | VFI-II | 1000 | 60 | 3 | 3 |  | 1200000 | Udon Thani | อำเภอเมืองอุดรธานี | 2020-08-06 | [36 empty] | 2020-08-31 | 2020-08-27 | 2020-08-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-01 | 2020-09-01 | 2020-09-02 | Finished |  |  | 2020-09-02 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-05 | Finished |  |  | 2020-09-06 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-08 | Finished |  |  | 2020-09-09 | Finished |  |  | 100 | [41 empty] | 2020-09-09 | 2020-10-27 | 2020-10-27 | Finished |  |  | 2020-09-19 | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2020-10-30 | Finished |  |  | 100 | 2020-11-11 | 2021-05-12 | 2020-11-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-11-11 | Finished |  |  | 2021-05-12 | Finished |  |  | 100 | 2021-02-15 | Finished | POWER SUPPLY DELAY |  | 2020-11-04 | Finished |  |  | 2020-06-11 | Finished | [18 empty] | 2020-08-27 | Finished |  |  | 2020-08-14 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-11-04 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass | 2021-06-02 | Finished |  |  | 417 | 89 | 16 | 16 | 538 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012552 | 2020-08-31 |  |  |  | HDME000962 | 2020-08-27 | QC Passed
TAC1753-TH | HET | 61000770 | HO | ยังอยู่ในสัญญา HO | - | TH209158 | The Answer Hotel | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-06-04 | 2020-10-05 | 2020-12-05 | 2021-10-28 | VFI-700-CO60,60S/5F | VFI-II | 700 | 60 | 5 | 5 |  | 1180000 | Krabi | อำเภอเมืองกระบี่ | 2020-10-05 | 2020-11-14 | Finished | [34 empty] | 2020-10-05 | 2020-10-06 | 2020-10-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-05 | 2020-12-25 | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-12-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 2021-02-04 | Finished |  |  | 100 | [41 empty] | 2021-02-04 | 1900-01-01 | 2021-02-04 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2021-02-17 | 2000-01-01 | 2021-02-17 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-06-11 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-10-06 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Green |  |  | 20012732 | 2020-10-05 |  |  |  | HDME001002 | 2020-10-08
TAC1754-TH | HET | 61000771 | HO | ยังอยู่ในสัญญา HO | - | TH209157 | Home Khun Jittrawan | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-05-31 | 2020-12-28 | 2021-02-28 | 2021-09-30 | VFI-1000-CO60,60S/4F | VFI-II | 1000 | 60 | 4 | 4 |  | 1250000 | Songkhla | ตำบลบ่อยาง | 2020-12-28 | 2021-01-20 | Finished | [34 empty] | 2020-12-28 | 2021-01-07 | 2021-01-07 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-03 | 2021-01-31 | 2021-01-25 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | [41 empty] | 2021-02-17 | 1900-01-01 | 2021-02-17 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-02-22 | 2000-01-01 | 2021-02-22 | Finished | [14 empty] | 25 | 2021-12-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-14 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-01-08 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-11 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 0 | 90 | 4 | 16 | 110 | 81.48 | Orange |  |  | 20013114 | 2020-12-28 |  |  |  | HDME001085 | 2021-01-08
TAD0456-TH | HET | 61000772 | HO | เลยสัญญา HO | - | TH209159 | Chiang Khan Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2020-07-21 | 2021-01-21 | 2021-03-21 | 2021-09-12 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1625000 | Loei | อำเภอเชียงคาน | 2021-01-07 | 2021-01-21 | Finished | [34 empty] | 2021-01-21 | 2021-01-25 | 2021-01-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-21 | 2021-02-20 | 0 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-09-06 | 2021-09-06 | Finished |  |  | 2021-09-30 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-06-01 | 2000-01-01 | 2021-06-01 | Finished | [14 empty] | 25 | 2021-10-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-03 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-01-25 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 72 | 4 | 16 | 92 | 85.85 | Red |  |  | 20013426 | 2021-01-21 |  |  |  | HDME001105 | 2021-01-25
TAD0457-TH | HET | 61000772 | HO | เลยสัญญา HO | - | TH209159 | Chiang Khan Hospital | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2020-07-21 | 2021-01-21 | 2021-03-21 | 2021-09-12 | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1625000 | Loei | อำเภอเชียงคาน | 2021-01-07 | 2021-01-21 | Finished | [34 empty] | 2021-01-22 | 2021-01-25 | 2021-01-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-21 | 2021-02-20 | 0 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-09-06 | 2021-09-06 | Finished |  |  | 2021-09-30 | 1900-01-01 | Finished | [10 empty] | 20 | 2021-06-01 | 2000-01-01 | 2021-06-01 | Finished | [14 empty] | 25 | 2021-10-08 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-03 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-01-25 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 72 | 4 | 16 | 92 | 85.85 | Red |  |  | 20013426 | 2021-01-21 |  |  |  | HDME001105 | 2021-01-25
TFA1437-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES01-02 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R4.5M,D30 | TX-EN |  |  |  |  | 4500 | 1177000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1438-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES01-02 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R4.5M,D30 | TX-EN |  |  |  |  | 4500 | 1177000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1439-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES03-04 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1440-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES03-04 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1284000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1441-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES05-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R6.5M,D30 | TX-EN |  |  |  |  | 6500 | 1498000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1442-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES05-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R6.5M,D30 | TX-EN |  |  |  |  | 6500 | 1498000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1443-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES05-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R6.5M,D30 | TX-EN |  |  |  |  | 6500 | 1498000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1444-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES05-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R6.5M,D30 | TX-EN |  |  |  |  | 6500 | 1498000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1445-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES05-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R6.5M,D30 | TX-EN |  |  |  |  | 6500 | 1498000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20014107 | 2021-08-17
TFA1446-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | ES05-10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 6 |  | 1 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | 1200TX-EN,R6.5M,D30 | TX-EN |  |  |  |  | 6500 | 1498000 | Bangkok | แขวงวังทองหลาง | 2021-10-15 | [36 empty] | 2021-08-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-02 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20014107 | 2021-08-17
TBL0331-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-01(SL01) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/5F | OUG-ON1 | 1600 | 60 | 5 | 5 |  | 1819000 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 490 | 86 | 16 | 16 | 608 | 490 | 86 | 16 | 16 | 608 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0332-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-01(SL02) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/5F | OUG-ON1 | 1600 | 60 | 5 | 5 |  | 1819000 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 490 | 86 | 16 | 16 | 608 | 490 | 86 | 16 | 16 | 608 | 0 | Green |  |  | 20012619 | 2021-09-01
THA0090-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-02 (SL05) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | LVF-4500-4PCO30,30S/4F | LVF | 4500 | 30 | 3 | 4 |  | 8025000 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2021-09-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-12-22 | Finished |  |  | 2021-08-28 | Finished | [6 empty] | 2022-05-02 | Finished | [38 empty] | 583 | 106 | 48 | 20 | 757 | 583 | 106 | 48 | 20 | 757 | 0 | Green |  |  | 20014984 | 2021-08-17
TBL0333-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-02(SL03) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/5F | OUG-ON1 | 1600 | 60 | 5 | 5 |  | 1738750 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 490 | 86 | 16 | 16 | 608 | 490 | 86 | 16 | 16 | 608 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0334-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-02(SL04) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/6F | OUG-ON1 | 1600 | 60 | 6 | 6 |  | 1738750 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 543 | 86 | 24 | 16 | 669 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0323-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-03(PL01) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 4 | 4 |  | 1658500 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0324-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-03(PL02) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 4 | 4 |  | 1658500 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0325-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-03a(PL03) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 4 | 4 |  | 1658500 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0326-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-03a(PL04) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 4 | 4 |  | 1658500 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0327-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-04(PL05) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/4F | OUG-ON1 | 1600 | 60 | 4 | 4 |  | 1738750 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0328-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-04(PL06) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/4F | OUG-ON1 | 1600 | 60 | 4 | 4 |  | 1738750 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0329-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-04a(PL07) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/5F | OUG-ON1 | 1600 | 60 | 5 | 5 |  | 1819000 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 490 | 86 | 16 | 16 | 608 | 490 | 86 | 16 | 16 | 608 | 0 | Green |  |  | 20012619 | 2021-09-01
TBL0330-TH | HET | 61000776 | HO | ยังอยู่ในสัญญา HO | - | TH219009 | Royal Thai Army International Forum | L-04a(PL08) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | 2020-03-31 | 2021-09-01 | 2022-05-01 |  | OUG-1600-2S60,60S/5F | OUG-ON1 | 1600 | 60 | 5 | 5 |  | 1819000 | Bangkok | แขวงวังทองหลาง | 2021-10-01 | [36 empty] | 2020-09-01 | 2021-09-10 | 2021-09-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-01 | Finished | [6 empty] | 2021-09-10 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 490 | 86 | 16 | 16 | 608 | 490 | 86 | 16 | 16 | 608 | 0 | Green |  |  | 20012619 | 2021-09-01
TAC1760-TH | HET | 61000781 | HO | เลยสัญญา HO | - | TH209167 | Somdechphrapinklao Hospital | BL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-08-03 | 2021-02-03 | 2021-08-03 |  | VFI-1600-2S90,90S/13F | VFI-II | 1600 | 90 | 13 | 13 |  | 2033000 | Bangkok | แขวงบุคคโล | 2021-06-16 | 2021-08-09 | Finished | [34 empty] | 2021-02-03 | 2021-04-28 | 2021-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-16 | 2021-12-01 | 2021-08-23 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-03 | Finished | [18 empty] | 2021-04-28 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Red |  |  | 20013125 | 2021-02-03 |  |  |  | HDME001198 | 2021-04-28
TAC1761-TH | HET | 61000781 | HO | เลยสัญญา HO | - | TH209167 | Somdechphrapinklao Hospital | BL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-08-03 | 2021-02-03 | 2021-08-03 |  | VFI-1600-2S90,90S/13F | VFI-II | 1600 | 90 | 13 | 13 |  | 2033000 | Bangkok | แขวงบุคคโล | 2021-06-16 | 2021-08-09 | Finished | [34 empty] | 2021-02-03 | 2021-04-28 | 2021-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-16 | 2021-12-01 | 2021-08-23 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-03 | Finished | [18 empty] | 2021-04-28 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Red |  |  | 20013125 | 2021-02-03 |  |  |  | HDME001198 | 2021-04-28
TEC0168-TH | HET | 61000781 | HO | เลยสัญญา HO | - | TH209167 | Somdechphrapinklao Hospital | DW-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-08-03 | 2021-02-03 | 2021-08-03 |  | DT-200T-B30,30S/12F | DT | 200 | 30 | 12 | 12 |  | 374500 | Bangkok | แขวงบุคคโล | 2021-06-16 | [36 empty] | 2020-12-03 | 2021-07-06 | 2021-07-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-16 | 2021-08-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-03 | Finished |  |  | 1900-01-01 | Finished | [14 empty] | 2021-07-06 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 449 | 0 | 32 | 0 | 481 | 449 | 0 | 32 | 0 | 481 | 0 | Red |  |  | 20013155 | 2020-12-03
TAC1758-TH | HET | 61000781 | HO | เลยสัญญา HO | - | TH209167 | Somdechphrapinklao Hospital | PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-08-03 | 2021-02-03 | 2021-08-03 |  | VFI-1000-CO120,120S/13F | VFI-II | 1000 | 120 | 13 | 13 |  | 2086500 | Bangkok | แขวงบุคคโล | 2021-06-16 | 2021-08-09 | Finished | [34 empty] | 2021-02-03 | 2021-04-28 | 2021-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-16 | 2021-12-01 | 2021-08-23 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-03 | Finished | [18 empty] | 2021-04-28 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Red |  |  | 20013125 | 2021-02-03 |  |  |  | HDME001198 | 2021-04-28
TAC1759-TH | HET | 61000781 | HO | เลยสัญญา HO | - | TH209167 | Somdechphrapinklao Hospital | PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-08-03 | 2021-02-03 | 2021-08-03 |  | VFI-1000-CO120,120S/13F | VFI-II | 1000 | 120 | 13 | 13 |  | 2086500 | Bangkok | แขวงบุคคโล | 2021-06-16 | 2021-08-09 | Finished | [34 empty] | 2021-02-03 | 2021-04-28 | 2021-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-16 | 2021-12-01 | 2021-08-23 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-03 | Finished | [18 empty] | 2021-04-28 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Red |  |  | 20013125 | 2021-02-03 |  |  |  | HDME001198 | 2021-04-28
TAC1762-TH | HET | 61000781 | HO | เลยสัญญา HO | - | TH209167 | Somdechphrapinklao Hospital | SL-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-08-03 | 2021-02-03 | 2021-08-03 |  | VFI-1600-2S90,90S/13F | VFI-II | 1600 | 90 | 13 | 13 |  | 2086500 | Bangkok | แขวงบุคคโล | 2021-06-16 | 2021-08-09 | Finished | [34 empty] | 2021-02-03 | 2021-04-28 | 2021-04-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-16 | 2021-12-01 | 2021-08-23 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-03 | Finished | [18 empty] | 2021-04-28 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Red |  |  | 20013125 | 2021-02-03 |  |  |  | HDME001198 | 2021-04-28
TAC1757-TH | HET | 61000790 | Install | ยังอยู่ในสัญญา HO | - | TH209165 | Sing Buri Sub-Station | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Thamnul Kongsar | 2020-06-01 | 2021-03-20 | 2021-08-01 | 2021-11-01 | VFI-900-CO60,60S/4F | VFI-II | 900 | 60 | 4 | 4 |  | 1344455 | Sing Buri | ตำบลม่วงหมู่ | 2021-11-01 | [36 empty] | 2021-03-19 | 2021-06-02 | 2021-06-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-01 | 2022-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-01 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-03 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Green |  |  | 20013339 | 2021-05-31 |  |  |  | HDME001230 | 2021-06-02
TAC1763-TH | HET | 61000792 | HO | ส่งมอบแล้ว | - | TH209175 | กรมโยธาธิการและผังเมือง 1,2 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-06-19 | 2020-09-29 | 2020-12-26 |  | VFI-1000-CO150,150S/20F | VFI-II | 1000 | 150 | 20 | 20 |  | 4158000 | Bangkok | เขตพญาไท | 2020-09-29 | [36 empty] | 2020-09-29 | 2020-09-29 | 2020-09-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-29 | 2020-12-23 | 2020-10-02 | Finished |  |  | 2020-10-03 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-13 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | [41 empty] | 2020-10-27 | 2020-12-01 | 2020-12-01 | Finished |  |  | 2020-11-20 | 2020-12-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-07 | 2021-01-07 | 2021-01-07 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-07 | Finished | [6 empty] | 90 | 2020-12-23 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2021-01-26 | Finished |  |  | 2020-06-18 | Finished | [10 empty] | 2020-12-30 | Finished | [6 empty] | 2020-09-29 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 1356 | 113 | 40 | 24 | 1533 | 0 | 0 | 0 | 2 | 2 | 99.87 | Blue |  |  | 20012731 | 2020-09-29 |  |  |  | HDME000994 | 2020-09-30 | QC Passed
TAD0458-TH | HET | 61000792 | HO | ส่งมอบแล้ว | - | TH209175 | กรมโยธาธิการและผังเมือง 1,2 | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-06-19 | 2020-09-29 | 2020-12-26 |  | B-1000-2S105,105S/21F | VFI-II | 1000 | 105 | 21 | 21 |  | 3786750 | Bangkok | เขตพญาไท | 2020-09-29 | [36 empty] | 2020-09-29 | 2020-09-29 | 2020-09-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-29 | 2020-12-23 | 2020-10-02 | Finished |  |  | 2020-10-03 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-10-10 | Finished |  |  | 2020-10-13 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-27 | Finished |  |  | 100 | [41 empty] | 2020-10-27 | 2020-12-02 | 2020-12-02 | Finished |  |  | 2020-11-20 | 2020-12-02 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-07 | 2021-01-07 | 2021-01-07 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-07 | Finished | [6 empty] | 90 | 2020-12-23 | Finished | ADJUSTMENT DEFECT RECTIFICATION DELAY |  | 2021-01-26 | Finished |  |  | 2020-06-18 | Finished | [10 empty] | 2020-12-30 | Finished | [6 empty] | 2020-09-29 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 1411 | 114 | 48 | 24 | 1597 | 0 | 0 | 0 | 2 | 2 | 99.87 | Blue |  |  | 20012731 | 2020-09-29 |  |  |  | HDME000994 | 2020-09-30 | QC Passed
TBL0343-TH | HET | 61000799 | HO | ส่งมอบแล้ว | - | TH209168 | Home Khun Burachat Chantchuchert | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-06-05 | 2020-11-05 | 2020-12-20 | 2021-03-15 | OUG-630-CO60,60S/2F | OUG-ON1 | 630 | 60 | 2 | 2 |  | 1284000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2020-10-22 | [36 empty] | 2020-11-05 | 2020-11-06 | 2020-11-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-05 | 2020-12-05 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-12-01 | 2020-12-01 | Finished |  |  | 2020-12-05 | 2020-12-03 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-08 | Finished |  |  | 100 | 2020-12-14 | 2021-02-23 | 2020-12-14 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-14 | Finished |  |  | 2021-02-23 | Finished |  |  | 100 | 2021-03-15 | Finished | CONSTRUCTION DELAY |  | 2021-03-29 | Finished |  |  | 2020-06-17 | Finished | [10 empty] | 2021-03-29 | Finished | [6 empty] | 2020-11-06 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-11-10 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012781 | 2020-11-05 |  |  |  | HDME001028 | 2020-11-06 | QC Passed
TAJ0782-TH | HET | 61000800 | HO | ส่งมอบแล้ว | - | TH209184 | Beat Condo | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2020-06-09 | 2020-09-09 | 2020-12-09 |  | P-630-CO60D,60S/8F | UAG-SN1 | 630 | 60 | 8 | 8 |  | 909500 | Bangkok | เขตภาษีเจริญ | 2020-08-25 | 2020-08-25 | Finished | [34 empty] | 2020-09-09 | 2020-09-09 | 2020-08-27 | Finished | [14 empty] | 2020-08-25 | 2020-10-09 | 2020-08-25 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-26 | Finished |  |  | 100 | [41 empty] | 2020-09-26 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-23 | Finished |  |  | 100 | 2021-01-12 | 2021-05-13 | 2021-01-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-12-09 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2020-06-18 | Finished | [10 empty] | 2020-12-15 | Finished | [6 empty] | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20012780 | 2020-09-09 |  |  |  | HDME000961 | 2020-08-27 | QC Passed
TAJ0783-TH | HET | 61000800 | HO | ส่งมอบแล้ว | - | TH209184 | Beat Condo | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2020-06-09 | 2020-09-09 | 2020-12-09 |  | P-630-CO60D,60S/8F | UAG-SN1 | 630 | 60 | 8 | 8 |  | 909500 | Bangkok | เขตภาษีเจริญ | 2020-08-25 | 2020-08-25 | Finished | [34 empty] | 2020-09-09 | 2020-09-09 | 2020-08-27 | Finished | [14 empty] | 2020-08-25 | 2020-10-09 | 2020-08-25 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-26 | Finished |  |  | 100 | [41 empty] | 2020-09-26 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-10-23 | Finished |  |  | 100 | 2021-01-12 | 2021-05-13 | 2021-01-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-12-09 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2020-06-18 | Finished | [10 empty] | 2020-12-15 | Finished | [6 empty] | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20012780 | 2020-09-09 |  |  |  | HDME000961 | 2020-08-27 | QC Passed
TAJ0784-TH | HET | 61000800 | HO | ส่งมอบแล้ว | - | TH209184 | Beat Condo | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2020-06-09 | 2020-09-09 | 2020-12-09 |  | P-630-CO60D,60S/8F | UAG-SN1 | 630 | 60 | 8 | 8 |  | 909500 | Bangkok | เขตภาษีเจริญ | 2020-08-25 | 2020-08-25 | Finished | [34 empty] | 2020-09-09 | 2020-09-09 | 2020-08-27 | Finished | [14 empty] | 2020-08-25 | 2020-10-09 | 2020-08-25 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-26 | Finished |  |  | 100 | [41 empty] | 2020-09-26 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-10-23 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-12 | 2021-05-13 | 2021-01-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-12-09 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2020-06-18 | Finished | [10 empty] | 2020-12-15 | Finished | [6 empty] | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20012780 | 2020-09-09 |  |  |  | HDME000961 | 2020-08-27 | QC Passed
TAJ0785-TH | HET | 61000800 | HO | ส่งมอบแล้ว | - | TH209184 | Beat Condo | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Chonticha Angsuwichitkun | 2020-06-09 | 2020-09-09 | 2020-12-09 |  | P-630-CO60D,60S/8F | UAG-SN1 | 630 | 60 | 8 | 8 |  | 909500 | Bangkok | เขตภาษีเจริญ | 2020-08-25 | 2020-08-25 | Finished | [34 empty] | 2020-09-09 | 2020-09-09 | 2020-08-27 | Finished | [14 empty] | 2020-08-25 | 2020-10-09 | 2020-08-25 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-09-01 | Finished |  |  | 2020-09-04 | Finished |  |  | 2020-09-07 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-15 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-26 | Finished |  |  | 100 | [41 empty] | 2020-09-26 | 2020-10-14 | 2020-10-14 | Finished |  |  | 2020-10-14 | 2020-10-23 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-12 | 2021-05-13 | 2021-01-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-12-09 | Finished | POWER SUPPLY DELAY |  | 2020-12-08 | Finished |  |  | 2020-06-18 | Finished | [10 empty] | 2020-12-15 | Finished | [6 empty] | 2020-08-27 | Finished |  |  | 2020-08-27 | Finished |  |  | 2020-08-28 | Finished |  |  | 2020-12-08 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20012780 | 2020-09-09 |  |  |  | HDME000961 | 2020-08-27 | QC Passed
TAJ0786-TH | HET | 61000801 | HO | ส่งมอบแล้ว | - | TH209186 | แกรนด์ ภัทรเพลส | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-06-08 | 2020-10-08 | 2020-12-08 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1000000 | Pathum Thani | หมู่ 3 ถนนรังสิต-ปทุมธานี | 2020-10-08 | 2020-10-14 | Finished | [34 empty] | 2020-10-08 | 2020-10-14 | 2020-10-14 | Finished | STORE AREA | [13 empty] | 2020-10-12 | 2020-12-08 | 2020-10-19 | Finished |  |  | 2020-10-20 | Finished |  |  | 2020-10-23 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-27 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-14 | Finished |  |  | 100 | [41 empty] | 2020-11-14 | 2020-12-01 | 2020-12-01 | Finished |  |  | 2020-11-24 | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-09 | Finished |  |  | 100 | 2020-10-27 | 2021-02-12 | 2020-10-27 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-02-12 | Finished |  |  | 100 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2020-06-18 | Finished | [10 empty] | 2020-12-15 | Finished | [6 empty] | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-10-14 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  | pass | 2021-03-12 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012832 | 2020-10-08 |  |  |  | HDME001005 | 2020-10-14 | QC Passed
TEB0138-TH | HET | 61000802 | HO | ยังอยู่ในสัญญา HO | - | TH209185 | Home Khun Boonchai Laovisuthichai | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2020-06-08 | 2020-12-08 | 2021-02-08 | 2021-10-06 | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 3 | 3 |  | 1100000 | Bangkok | เขตตลิ่งชัน | 2021-01-20 | 2021-01-20 | Finished | [34 empty] | 2020-11-23 | 2020-12-08 | 2020-12-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-20 | 2021-02-08 | 2021-01-20 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 100 | [41 empty] | 2021-01-29 | 1900-01-01 | 2021-01-29 | Waiting | POWER SUPPLY DELAY |  | 2021-10-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-06-26 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-12-09 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-28 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 16 | 16 | 87 | 66.15 | Green |  |  | 20012833 | 2020-11-23 |  |  |  | HDME001066 | 2020-12-09
TBL0344-TH | HET | 61000803 | HO | เลยสัญญา HO | - | TH209187 | Aliston Hotel | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2020-06-12 | 2020-09-27 | 2020-10-27 | 2021-08-30 | OUG-750-CO60,60S/2F | OUG-ON1 | 750 | 60 | 2 | 2 |  | 1170000 | Bangkok | แขวงคลองตัน | 2020-06-28 | 2021-06-10 | Finished | [34 empty] | 2020-11-02 | 2020-09-27 | 2020-10-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-10 | 2021-07-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-20 | 2021-06-20 | Finished |  |  | 2021-06-20 | 2021-06-21 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-08-13 | Finished | [6 empty] | 90 | 2021-09-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-25 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2020-10-09 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-12 | Finished | [17 empty] | no pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 1 | 1 | 99.78 | Red |  |  | 20012886 | 2020-11-02 |  |  |  | HDME001004 | 2020-10-09
TBL0345-TH | HET | 61000803 | HO | เลยสัญญา HO | - | TH209187 | Aliston Hotel | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2020-06-12 | 2020-09-27 | 2020-10-27 | 2021-08-30 | OUG-750-CO60,60S/2F | OUG-ON1 | 750 | 60 | 2 | 2 |  | 1170000 | Bangkok | แขวงคลองตัน | 2020-09-28 | 2021-06-10 | Finished | [34 empty] | 2020-11-02 | 2020-09-27 | 2020-10-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-10 | 2021-07-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-20 | 2021-06-20 | Finished |  |  | 2021-06-20 | 2021-06-21 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-08-13 | Finished | [6 empty] | 90 | 2021-09-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-25 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2020-10-09 | Finished |  |  | 2020-10-09 | Finished |  |  | 2020-10-12 | Finished | [22 empty] | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 1 | 1 | 99.78 | Red |  |  | 20012886 | 2020-11-02 |  |  |  | HDME001004 | 2020-10-09
TAJ0788-TH | HET | 61000804 |  | เลยสัญญา HO | - | TH209188 | Samutsakhon Juvenile and Family Court | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Orawan Kwanpheng | 2020-08-27 | 2020-11-16 | 2021-01-27 | 2021-07-15 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1284000 | Samut Sakhon | ตำบลนาดี | 2021-12-15 | [36 empty] | 2020-12-02 | 2020-11-16 |  |  | PAYMENT DELAY | [13 empty] | 2021-12-15 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-09-18 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20014225 | 2020-12-02
TAJ0787-TH | HET | 61000804 |  | เลยสัญญา HO | - | TH209188 | Samutsakhon Juvenile and Family Court | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Orawan Kwanpheng | 2020-08-27 | 2020-11-16 | 2021-01-27 | 2021-07-15 | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1177000 | Samut Sakhon | ตำบลนาดี | 2021-12-15 | [36 empty] | 2020-12-02 | 2020-11-16 |  |  | PAYMENT DELAY | [13 empty] | 2021-12-15 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-09-18 | Finished | [10 empty] | 2022-02-15 | Finished | [38 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20014225 | 2020-12-02
TAK0789-TH | HET | 61000805 | HO | ส่งมอบแล้ว | - | TH209169 | Jetanin Hospital | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-05-31 | 2020-09-15 | 2020-11-15 |  | B-750-2S60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1658500 | Bangkok | เขตปทุมวัน | 1900-01-01 | [36 empty] | 2020-09-17 | 2020-09-17 | 2020-09-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 1900-01-01 | 1900-01-01 | 2020-09-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2020-10-15 | 2020-10-15 | Finished |  |  | 2020-10-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2020-12-28 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-12-28 | Finished |  |  | 100 | 2020-11-15 | Finished | CONSTRUCTION DELAY |  | 2020-12-22 | Finished |  |  | 2020-07-24 | Finished | [18 empty] | 2020-09-17 | Finished |  |  | 2020-09-17 | Finished |  |  | 2020-09-18 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  | pass | 2021-01-13 | Finished |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012893 | 2020-09-17 |  |  |  | HDME000979 | 2020-09-17 | QC Passed
TAJ0790-TH | HET | 61000806 | HO | ส่งมอบแล้ว | - | TH209183 | ม.ราชภัฎนครราชสีมา อ.หอพักนักศึกษา | PL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-05-22 | 2020-09-22 | 2020-12-22 | 2021-08-20 | P-1000-CO105W2,105S/10F | UAG-SN1 | 1000 | 105 | 10 | 10 |  | 1000000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2020-09-08 | [36 empty] | 2020-09-23 | 2020-09-25 | 2020-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-23 | 2020-10-23 | 2020-10-25 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | [41 empty] | 2020-11-08 | 2021-06-09 | 2021-06-09 | Finished |  |  | 2020-11-07 | 2021-06-12 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-12-28 | 2021-07-26 | 2020-12-28 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-07-26 | Finished | [6 empty] | 90 | 2021-05-04 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-07-08 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-09-25 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-09 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 629 | 85 | 24 | 16 | 754 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20013022 | 2020-09-23 |  |  |  | HDME000984 | 2020-09-25 | QC Passed
TAJ0791-TH | HET | 61000806 | HO | ส่งมอบแล้ว | - | TH209183 | ม.ราชภัฎนครราชสีมา อ.หอพักนักศึกษา | PL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-05-22 | 2020-09-22 | 2020-12-22 | 2021-08-20 | P-1000-CO105W2,105S/10F | UAG-SN1 | 1000 | 105 | 10 | 10 |  | 1000000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2020-09-08 | [36 empty] | 2020-09-23 | 2020-09-25 | 2020-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-23 | 2020-10-23 | 2020-10-25 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | [41 empty] | 2020-11-08 | 2021-06-09 | 2021-06-09 | Finished |  |  | 2020-11-07 | 2021-06-12 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-12-28 | 2021-07-26 | 2020-12-28 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-07-26 | Finished | [6 empty] | 90 | 2021-05-04 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-07-08 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-09-25 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-09 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 629 | 85 | 24 | 16 | 754 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20013022 | 2020-09-23 |  |  |  | HDME000984 | 2020-09-25 | QC Passed
TAK0792-TH | HET | 61000806 | HO | ส่งมอบแล้ว | - | TH209183 | ม.ราชภัฎนครราชสีมา อ.หอพักนักศึกษา | S1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-05-22 | 2020-09-22 | 2020-12-22 | 2021-08-20 | B-1000-2S105,105S/10F | UAG-SN1 | 1000 | 105 | 10 | 10 |  | 1000000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2020-09-08 | [36 empty] | 2020-09-23 | 2020-09-25 | 2020-10-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-09-23 | 2020-10-23 | 2020-10-25 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | [41 empty] | 2020-11-08 | 2021-06-09 | 2021-06-09 | Finished |  |  | 2020-11-07 | 2021-06-12 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2020-12-28 | 2021-07-26 | 2020-12-28 | Finished |  |  | 2021-07-09 | Finished |  |  | 2021-07-26 | Finished | [6 empty] | 90 | 2021-05-04 | Finished | POWER SUPPLY DELAY |  | 2021-07-30 | Finished |  |  | 2020-07-08 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-09-25 | Finished |  |  | 2020-10-08 | Finished |  |  | 2020-10-09 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 629 | 85 | 24 | 16 | 754 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20013022 | 2020-09-23 |  |  |  | HDME000984 | 2020-09-25 | QC Passed
TEB0139-TH | HET | 61000807 | HO | ส่งมอบแล้ว | - | TH209189 | Home Yothin Phatthana 3 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-09 | 2020-09-04 | 2020-10-05 | 2021-02-10 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตลาดพร้าว | 2020-08-20 | 2020-09-20 | Finished | [34 empty] | 2020-08-20 | 2020-09-11 | 2020-09-11 | Finished | SUPPLIER SHIPMENT DELAY | [13 empty] | 2020-08-20 | 2020-09-19 | 2020-09-21 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 100 | [41 empty] | 2020-10-05 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-09-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-08-25 | 2021-06-21 | 2020-08-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-05-20 | Finished | CONSTRUCTION DELAY |  | 2021-02-04 | Finished |  |  | 2020-06-25 | Finished | [10 empty] | 2021-02-04 | Finished | [6 empty] | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-14 | Finished |  |  | 2021-02-04 | Finished | [13 empty] | pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012922 | 2020-08-20 |  |  |  | HDME000976 | 2020-09-11 | QC Passed
TEB0140-TH | HET | 61000807 | HO | ส่งมอบแล้ว | - | TH209189 | Home Yothin Phatthana 3 | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-09 | 2020-09-04 | 2020-10-05 | 2021-02-10 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตลาดพร้าว | 2020-08-20 | 2020-09-20 | Finished | [34 empty] | 2020-08-20 | 2020-10-01 | 2020-09-11 | Finished | SUPPLIER SHIPMENT DELAY | [13 empty] | 2020-08-20 | 2020-09-19 | 2020-09-21 | Finished |  |  | 2020-09-22 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-23 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-09-25 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-05 | Finished |  |  | 100 | [41 empty] | 2020-10-05 | 2020-09-10 | 2020-09-10 | Finished |  |  | 2020-09-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-08-25 | 2021-06-21 | 2020-08-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-05-20 | Finished | CONSTRUCTION DELAY |  | 2021-02-04 | Finished |  |  | 2020-06-25 | Finished | [10 empty] | 2021-02-04 | Finished | [6 empty] | 2020-09-11 | Finished |  |  | 2020-09-11 | Finished |  |  | 2020-09-14 | Finished |  |  | 2021-02-04 | Finished | [13 empty] | pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20012922 | 2020-08-20 |  |  |  | HDME000976 | 2020-09-11 | QC Passed
TEB0141-TH | HET | 61000807 | HO | ส่งมอบแล้ว | - | TH209189 | Home Yothin Phatthana 3 | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-09 | 2020-09-04 | 2020-10-30 | 2021-07-01 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตลาดพร้าว | 2020-09-15 | 2020-09-20 | Finished | [34 empty] | 2020-09-15 | 2020-10-01 | 2020-10-01 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-15 | 2020-09-14 | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-03 | Finished |  |  | 100 | [41 empty] | 2020-12-03 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-09-25 | 1900-01-01 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2020-12-10 | 2021-06-04 | 2020-12-10 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-06-04 | Finished | [6 empty] | 90 | 2021-06-15 | Finished | CONSTRUCTION DELAY |  | 2021-06-30 | Finished |  |  | 2020-06-25 | Finished | [10 empty] | 2021-06-30 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished |  |  | 2021-06-30 | Finished | [13 empty] | no pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20012922 | 2020-09-15 |  |  |  | HDME000998 | 2020-10-01 | QC Passed
TEB0142-TH | HET | 61000807 | Install | ยังอยู่ในสัญญา HO | - | TH209189 | Home Yothin Phatthana 3 | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-09 | 2020-09-04 | 2020-10-30 | 2021-10-01 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตลาดพร้าว | 2020-09-15 | 2020-09-15 | Finished | [34 empty] | 2020-09-15 | 2020-10-01 | 2020-10-01 | Finished | PAYMENT DELAY | [13 empty] | 2020-09-15 | 2020-09-14 | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-03 | Finished |  |  | 100 | [41 empty] | 2020-12-03 | 2021-04-09 | 2021-04-09 | Finished |  |  | 2020-09-25 | 2021-04-09 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | 2020-12-10 | 2021-06-04 | 2020-12-10 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-06-04 | Finished | [6 empty] | 90 | 2021-10-01 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-25 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-01 | Finished |  |  | 2020-10-02 | Finished | [17 empty] | no pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Green |  |  | 20012922 | 2020-09-15 |  |  |  | HDME000998 | 2020-10-01 | QC Passed
TEB0143-TH | HET | 61000807 | Install | ยังอยู่ในสัญญา HO | - | TH209189 | Home Yothin Phatthana 3 | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-09 | 2020-09-04 | 2020-12-25 | 2021-10-01 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตลาดพร้าว | 2020-11-10 | 2020-11-10 | Finished | [34 empty] | 2020-11-10 | 2020-11-03 | 2020-11-04 | Finished | [14 empty] | 2020-11-10 | 2020-11-10 | 2021-01-07 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 100 | [41 empty] | 2021-01-13 | 2021-08-10 | 2021-08-10 | Finished |  |  | 2021-09-10 | 2021-08-12 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-08-14 | Finished |  |  | 100 | 2021-01-28 | 2000-01-01 | 2021-01-28 | Finished | [14 empty] | 25 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-25 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2020-11-03 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished | [17 empty] | in process (defect) |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 4 | 16 | 20 | 92.22 | Green |  |  | 20012922 | 2020-11-10 |  |  |  | HDME001024 | 2020-11-03
TEB0144-TH | HET | 61000807 | Install | ยังอยู่ในสัญญา HO | - | TH209189 | Home Yothin Phatthana 3 | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-04-09 | 2020-09-04 | 2020-12-25 | 2021-10-01 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตลาดพร้าว | 2020-11-10 | 2020-11-10 | Finished | [34 empty] | 2020-11-10 | 2020-11-03 | 2020-11-04 | Finished | [14 empty] | 2020-11-10 | 2020-11-10 | 2021-01-07 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 100 | [41 empty] | 2021-01-13 | 2021-08-10 | 2021-08-10 | Finished |  |  | 2021-09-10 | 2021-08-12 | Finished |  |  | 2021-09-13 | Finished |  |  | 2021-09-14 | Finished |  |  | 100 | 2021-01-28 | 2000-01-01 | 2021-01-28 | Finished | [14 empty] | 25 | 2021-10-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-06-25 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-11-03 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished | [17 empty] | in process (defect) |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 4 | 16 | 20 | 92.22 | Green |  |  | 20012922 | 2020-11-10 |  |  |  | HDME001024 | 2020-11-03
TEB0145-TH | HET | 61000808 | Install | ยังอยู่ในสัญญา HO | - | TH209172 | Sage Thonglor | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-06-18 | 2020-10-18 | 2020-12-18 | 2021-11-26 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 900000 | Bangkok | แขวงคลองตันเหนือ | 2021-09-20 | [36 empty] | 2020-10-03 | 2020-10-18 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-21 | 2021-11-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-10 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished |  |  | 2021-08-12 | Finished | [46 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Green |  |  | 20013148 | 2020-10-03
TEB0146-TH | HET | 61000808 | Install | ยังอยู่ในสัญญา HO | - | TH209172 | Sage Thonglor | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-06-18 | 2020-10-18 | 2020-12-18 | 2021-11-26 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 5 | 5 |  | 900000 | Bangkok | แขวงคลองตันเหนือ | 2021-09-20 | [36 empty] | 2020-10-03 | 2020-10-18 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-21 | 2021-11-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-10 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished |  |  | 2021-08-12 | Finished | [46 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Green |  |  | 20013148 | 2020-10-03
TEB0147-TH | HET | 61000808 | Install | ยังอยู่ในสัญญา HO | - | TH209172 | Sage Thonglor | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-06-18 | 2020-10-18 | 2020-12-18 | 2021-11-26 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 5 | 5 |  | 900000 | Bangkok | แขวงคลองตันเหนือ | 2021-09-20 | [36 empty] | 2020-10-03 | 2020-10-18 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-21 | 2021-11-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-10 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished |  |  | 2021-08-12 | Finished | [46 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Green |  |  | 20013148 | 2020-10-03
TEB0148-TH | HET | 61000808 | Install | ยังอยู่ในสัญญา HO | - | TH209172 | Sage Thonglor | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-06-18 | 2020-10-18 | 2020-12-18 | 2021-11-26 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 5 | 5 |  | 900000 | Bangkok | แขวงคลองตันเหนือ | 2021-09-20 | [36 empty] | 2020-10-03 | 2020-10-18 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-21 | 2021-11-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-10 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished |  |  | 2021-08-12 | Finished | [46 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Green |  |  | 20013148 | 2020-10-03
TAD0459-TH | HET | 61000809 | HO | ยังอยู่ในสัญญา HO | - | TH209190 | Nonghan Hospital | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-10-15 | 2021-01-30 | 2021-04-15 | 2021-09-20 | B-1000-2S60,60S/3F | B-II(VFI-II) | 1000 | 60 | 3 | 3 |  | 1284000 | Udon Thani | อำเภอหนองหาน | 2021-01-16 | 2021-02-09 | Finished | [34 empty] | 2021-01-29 | 2021-02-04 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-30 | 2021-03-01 | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-04 | Finished |  |  | 100 | [41 empty] | 2021-03-04 | 2021-03-16 | 2021-03-16 | Finished |  |  | 2021-03-31 | 2021-03-16 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | 2021-03-11 | 2000-01-01 | 2021-03-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-05-11 | Finished |  |  | 100 | 2021-09-30 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-11-03 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-16 | Finished | [17 empty] | no pass |  |  |  |  | 417 | 89 | 16 | 16 | 538 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20014822 | 2021-01-29 |  |  |  | HDME001118 | 2021-02-04
TAD0460-TH | HET | 61000809 | HO | ยังอยู่ในสัญญา HO | - | TH209190 | Nonghan Hospital | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-10-15 | 2021-01-30 | 2021-04-15 | 2021-09-20 | B-1000-2S60,60S/3F | B-II(VFI-II) | 1000 | 60 | 3 | 3 |  | 1284000 | Udon Thani | อำเภอหนองหาน | 2021-01-16 | 2021-02-09 | Finished | [34 empty] | 2021-01-29 | 2021-02-04 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-30 | 2021-03-01 | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-04 | Finished |  |  | 100 | [41 empty] | 2021-03-04 | 2021-03-16 | 2021-03-16 | Finished |  |  | 2021-03-31 | 2021-03-16 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | 2021-03-11 | 2000-01-01 | 2021-03-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-05-11 | Finished |  |  | 100 | 2021-09-30 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-11-03 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-16 | Finished | [17 empty] | no pass |  |  |  |  | 417 | 89 | 16 | 16 | 538 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20014822 | 2021-01-29 |  |  |  | HDME001118 | 2021-02-04
TFA1382-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1166300 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-11-13 | 2020-11-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-11-13 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-18 | Finished | [17 empty] | in process (defect) |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001033 | 2020-11-13
TFA1391-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES10 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-12 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TFA1383-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 1166300 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-11-13 | 2020-11-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-17 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-17 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-11-13 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-18 | Finished | [17 empty] | in process (defect) |  |  |  |  | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001033 | 2020-11-13
TFA1384-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | STORE AREA | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TFA1385-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TFA1386-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-14 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TFA1387-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TFA1388-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-16 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TFA1389-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-18 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-18 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TFA1390-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | ES9 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-25 | 1200TX-EN,R4M,D30 | TX-EN |  |  |  |  | 4000 | 1112800 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-10-10 | [20 empty] | 2020-10-10 | Finished | [14 empty] | 2020-10-26 | 2020-10-18 | 2020-10-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-10 | 2021-01-10 | [41 empty] | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished | [14 empty] | 25 | 2022-02-08 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-16 | Finished |  |  | 2020-10-16 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | in process (defect) |  |  |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 4 | 21 | 67 | 88.06 | Green |  |  | 20013023 | 2020-10-26 |  |  |  | HDME001010 | 2020-10-16
TAC1765-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-02-24 | 2021-10-20 | VFI-1000-CO90,90S/11F | VFI-II | 1000 | 90 | 11 | 11 |  | 1417750 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-12-25 | 2020-12-25 | Finished | [34 empty] | 2020-12-24 | 2020-12-26 | 2020-12-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-02-24 | 2021-01-05 | Finished |  |  | 2021-01-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-01-31 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-17 | Finished |  |  | 2021-01-26 | Finished |  |  | 100 | [41 empty] | 2021-01-26 | 1900-01-01 | 2021-01-26 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-12-26 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-28 | Finished | [17 empty] | in process (defect) |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 105 | 8 | 20 | 133 | 86.91 | Green |  |  | 20013026 | 2020-12-24 |  |  |  | HDME001080 | 2020-12-26
TAC1766-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-04-24 | 2021-10-20 | VFI-1000-CO90,90S/11F | VFI-II | 1000 | 90 | 11 | 11 |  | 1417750 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-12-25 | 2020-12-25 | Finished | [34 empty] | 2020-12-24 | 2020-12-26 | 2020-12-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-02-24 | 2021-01-05 | Finished |  |  | 2021-01-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-01-31 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished |  |  | 100 | [41 empty] | 2021-01-27 | 1900-01-01 | 2021-01-27 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-12-26 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-28 | Finished | [17 empty] | in process (defect) |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 105 | 8 | 20 | 133 | 86.91 | Green |  |  | 20013026 | 2020-12-24 |  |  |  | HDME001080 | 2020-12-26
TAC1767-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-04-24 | 2021-10-20 | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 1605000 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-12-25 | 2020-12-25 | Finished | [34 empty] | 2020-12-24 | 2020-12-26 | 2020-12-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-02-24 | 2021-01-06 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-03-14 | Finished |  |  | 100 | [41 empty] | 2021-03-14 | 1900-01-01 | 2021-03-14 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-12-26 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-28 | Finished | [17 empty] | in process (defect) |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 105 | 8 | 20 | 133 | 86.91 | Green |  |  | 20013026 | 2020-12-24 |  |  |  | HDME001080 | 2020-12-26
TAC1768-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-04-24 | 2021-10-20 | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 1605000 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-12-25 | 2020-12-25 | Finished | [34 empty] | 2020-12-24 | 2020-12-26 | 2020-12-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-02-24 | 2021-01-06 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-03-15 | Finished |  |  | 100 | [41 empty] | 2021-03-15 | 1900-01-01 | 2021-03-15 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-12-26 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-28 | Finished | [17 empty] | in process (defect) |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 105 | 8 | 20 | 133 | 86.91 | Green |  |  | 20013026 | 2020-12-24 |  |  |  | HDME001080 | 2020-12-26
TAC1769-TH | HET | 61000810 | HO | ส่งมอบแล้ว | - | TH209191 | โรงพยาบาลพุทธชินราช | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-04-24 | 2021-07-24 | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 1605000 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-12-25 | 2020-12-25 | Finished | [34 empty] | 2020-12-24 | 2020-12-26 | 2020-12-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-02-24 | 2021-01-07 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-21 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | [41 empty] | 2021-03-23 | 2021-05-24 | 2021-05-24 | Finished |  |  | 2021-06-10 | 2021-05-24 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-27 | Finished |  |  | 100 | 2021-04-02 | 2021-06-28 | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2021-07-20 | Finished | POWER SUPPLY DELAY |  | 2021-06-08 | Finished |  |  | 2020-07-16 | Finished | [10 empty] | 2021-06-08 | Finished | [6 empty] | 2020-12-26 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013026 | 2020-12-24 |  |  |  | HDME001080 | 2020-12-26 | QC Passed
TAC1770-TH | HET | 61000810 | HO | ส่งมอบแล้ว | - | TH209191 | โรงพยาบาลพุทธชินราช | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-04-24 | 2021-07-24 | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 1605000 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-12-25 | 2020-12-25 | Finished | [34 empty] | 2020-12-24 | 2020-12-26 | 2020-12-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-02-24 | 2021-01-07 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-21 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-03-24 | Finished |  |  | 100 | [41 empty] | 2021-03-24 | 2021-05-24 | 2021-05-24 | Finished |  |  | 2021-06-10 | 2021-05-24 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-27 | Finished |  |  | 100 | 2021-04-02 | 2021-06-28 | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2021-07-20 | Finished | POWER SUPPLY DELAY |  | 2021-06-08 | Finished |  |  | 2020-07-16 | Finished | [10 empty] | 2021-06-08 | Finished | [6 empty] | 2020-12-26 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013026 | 2020-12-24 |  |  |  | HDME001080 | 2020-12-26 | QC Passed
TEC0170-TH | HET | 61000810 | Install | ยังอยู่ในสัญญา HO | - | TH209191 | โรงพยาบาลพุทธชินราช | 7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-06-24 | 2020-10-24 | 2021-04-24 | 2021-10-20 | DT-100S-B30,30S/5F | DT | 100 | 30 | 5 | 5 |  | 374500 | Phitsanulok | อำเภอเมืองพิษณุโลก | 2020-12-25 | 2020-12-25 | Finished | [34 empty] | 2020-12-24 | 2021-01-22 | 2021-01-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-02-24 | 2021-02-08 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-21 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-24 | Finished |  |  | 100 | [41 empty] | 2021-02-24 | 1900-01-01 | 2021-02-24 | Waiting | POWER SUPPLY DELAY |  | 2021-10-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-08 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-07-16 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-01-22 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Green |  |  | 20013027 | 2020-12-24 |  |  |  | HDME001103 | 2021-01-22
TFA1392-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R6M,D35 | TX-EN |  |  |  |  | 6000 | 1430590 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2020-12-02 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 100 | 2021-03-03 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 590 | 42 | 24 | 21 | 677 | 0 | 0 | 0 | 2 | 2 | 99.7 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TFA1393-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R6M,D35 | TX-EN |  |  |  |  | 6000 | 1430590 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2020-12-02 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 100 | 2021-03-03 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 590 | 42 | 24 | 21 | 677 | 0 | 0 | 0 | 2 | 2 | 99.7 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TFA1394-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1291944.83 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-23 | Finished |  |  | 100 | 2020-12-23 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TFA1395-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1291944.83 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-23 | Finished |  |  | 100 | 2020-12-23 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TFA1396-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1291944.83 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-26 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-23 | Finished |  |  | 100 | 2020-12-23 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-19 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TFA1397-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1291944.83 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-26 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-23 | Finished |  |  | 100 | 2020-12-23 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-19 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TFA1398-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1291944.83 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-26 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-23 | Finished |  |  | 100 | 2020-12-23 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-19 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TFA1399-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | 8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 1291944.85 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-10-26 | [20 empty] | 2020-10-26 | Finished | [14 empty] | 2020-10-26 | 2020-10-26 | 2020-11-19 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2020-11-20 | 2021-01-10 | [41 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-26 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-23 | Finished |  |  | 100 | 2020-12-23 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-19 | Finished |  |  | 100 | 2021-03-16 | 2021-05-07 | 2021-03-16 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished | [6 empty] | 90 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-19 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 482 | 42 | 16 | 21 | 561 | 0 | 0 | 0 | 2 | 2 | 99.64 | Blue |  |  | 20013028 | 2020-10-26 |  |  |  | HDME001038 | 2020-11-19 | QC Passed
TAD0461-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | B-1000-2S90,90S/9F | B-II(VFI-II) | 1000 | 90 | 9 | 9 |  | 1872500 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-11-23 | 2020-11-23 | Finished | [34 empty] | 2020-11-23 | 2020-11-23 | 2020-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-28 | 2021-02-07 | 2020-12-04 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-01-10 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-30 | Finished |  |  | 100 | [41 empty] | 2021-01-30 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-02-17 | 2021-06-17 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-06-17 | Finished |  |  | 100 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-06-22 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-06-22 | Finished | [6 empty] | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013029 | 2020-11-23 |  |  |  | HDME001052 | 2020-11-28 | QC Passed
TAD0462-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | B-1000-2S90,90S/9F | B-II(VFI-II) | 1000 | 90 | 9 | 9 |  | 1872500 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-11-23 | 2020-11-23 | Finished | [34 empty] | 2020-11-23 | 2020-11-23 | 2020-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-28 | 2021-02-07 | 2020-12-04 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-01-10 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-30 | Finished |  |  | 100 | [41 empty] | 2021-01-30 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-02-17 | 2021-06-17 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-06-17 | Finished |  |  | 100 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-06-22 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-06-22 | Finished | [6 empty] | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013029 | 2020-11-23 |  |  |  | HDME001052 | 2020-11-28 | QC Passed
TAD0463-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | B-1000-2S90,90S/9F | B-II(VFI-II) | 1000 | 90 | 9 | 9 |  | 1872500 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-11-23 | 2020-11-23 | Finished | [34 empty] | 2020-11-23 | 2020-11-23 | 2020-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-28 | 2021-02-07 | 2020-12-04 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-01-10 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-30 | Finished |  |  | 100 | [41 empty] | 2021-01-30 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-02-17 | 2021-06-17 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-06-17 | Finished |  |  | 100 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-06-22 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-06-22 | Finished | [6 empty] | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013029 | 2020-11-23 |  |  |  | HDME001052 | 2020-11-28 | QC Passed
TAD0464-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | B-1000-2S90,90S/9F | B-II(VFI-II) | 1000 | 90 | 9 | 9 |  | 1872500 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-11-23 | 2020-11-23 | Finished | [34 empty] | 2020-11-23 | 2020-11-23 | 2020-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-28 | 2021-02-07 | 2020-12-04 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-01-10 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-30 | Finished |  |  | 100 | [41 empty] | 2021-01-30 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-02-17 | 2021-06-17 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-06-17 | Finished |  |  | 100 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-06-22 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-06-22 | Finished | [6 empty] | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013029 | 2020-11-23 |  |  |  | HDME001052 | 2020-11-28 | QC Passed
TAD0465-TH | HET | 61000811 | HO | ส่งมอบแล้ว | - | TH209176 | Banphaeo Hospital Research Building | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Thamnul Kongsar | 2020-06-11 | 2020-10-26 | 2021-04-01 | 2021-05-03 | B-1000-2S90,90S/9F | B-II(VFI-II) | 1000 | 90 | 9 | 9 |  | 1852651 | Samut Sakhon | ตำบลบ้านแพ้ว | 2020-11-23 | 2020-11-23 | Finished | [34 empty] | 2020-11-23 | 2020-11-23 | 2020-11-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-28 | 2021-02-07 | 2020-12-04 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-26 | Finished |  |  | 2021-01-10 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-30 | Finished |  |  | 100 | [41 empty] | 2021-01-30 | 2021-03-22 | 2021-03-22 | Finished |  |  | 2021-03-18 | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-08 | Finished |  |  | 100 | 2021-02-17 | 2021-06-17 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-06-17 | Finished |  |  | 100 | 2021-05-01 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-07-09 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-11-28 | Finished |  |  | 2020-11-28 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 748 | 94 | 24 | 16 | 882 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013029 | 2020-11-23 |  |  |  | HDME001052 | 2020-11-28 | QC Passed
TAJ0793-TH | HET | 61000812 | HO | ยังอยู่ในสัญญา HO | - | TH209192 | Apartment Khun Suradet Thanapitak | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-06-23 | 2020-09-23 | 2020-11-07 | 2021-10-11 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1150000 | Chiang Mai | ตำบลสุเทพ | 2020-11-25 | 2020-11-25 | Finished | [34 empty] | 2020-09-28 | 2020-10-18 | 2020-10-18 | Finished | OTHERS | [13 empty] | 2021-01-25 | 2021-02-10 | 2021-12-15 | Finished |  |  | 2021-12-20 | Finished |  |  | 2021-12-22 | Finished |  |  | 2021-12-22 | Finished |  |  | 2021-12-20 | Finished |  |  | 2021-12-20 | Finished |  |  | 2021-12-21 | Finished |  |  | 2021-12-21 | Finished |  |  | 2021-12-22 | Finished |  |  | 2021-12-23 | Finished |  |  | 100 | [41 empty] | 2021-12-23 | 2021-08-10 | 2021-08-10 | Finished |  |  | 2021-11-20 | 2021-08-10 | Finished |  |  | 2021-08-14 | Finished |  |  | 2021-08-17 | Finished |  |  | 100 | 2020-01-04 | 2000-01-01 | 2020-01-04 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 90 | 2021-11-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-07-14 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-10-18 | Finished |  |  | 2020-10-18 | Finished |  |  | 2020-10-19 | Finished | [17 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Green |  |  | 20013049 | 2020-09-28 |  |  |  | HDME001012 | 2020-10-18
TAC1777-TH | HET | 61000815 | HO | ส่งมอบแล้ว | - | TH209194 | Dormitory Thung Song Hospital | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-07-25 | 2020-11-09 | 2020-12-10 | 2021-02-28 | VFI-600-CO60,60S/6F | VFI-II | 600 | 60 | 6 | 6 |  | 1126000 | Nakhon Si Thammarat | อำเภอทุ่งสง | 2020-11-09 | [36 empty] | 2020-11-09 | 2020-11-11 | 2020-11-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-09 | 2020-12-01 | 2020-11-14 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-01 | Finished |  |  | 100 | [41 empty] | 2020-12-01 | 2020-11-29 | 2020-11-29 | Finished |  |  | 2020-11-29 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-22 | 2021-01-05 | 2020-12-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-05 | Finished | [6 empty] | 90 | 2021-02-02 | Finished | CONSTRUCTION DELAY |  | 2020-12-30 | Finished |  |  | 2020-08-13 | Finished | [18 empty] | 2020-11-11 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 1 | 1 | 99.86 | Blue |  |  | 20013457 | 2020-11-09 |  |  |  | HDME001030 | 2020-11-11 | QC Passed
TAJ0806-TH | HET | 61000820 | HO | ยังอยู่ในสัญญา HO | - | TH209197 | Soka Gakkai Thailand @Rayong | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-08-10 | 2020-11-10 | 2020-12-25 | 2021-10-30 | P-1000-CO60W2,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1337500 | Rayong | อำเภอนิคมพัฒนา | 2020-12-25 | 2020-11-01 | Finished | [34 empty] | 2020-11-10 | 2020-11-10 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-10 | 2020-11-03 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-19 | Finished |  |  | 2020-11-20 | Finished |  |  | 100 | [41 empty] | 2020-11-20 | 1900-01-01 | 2020-11-20 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2020-12-14 | 2000-01-01 | 2020-12-14 | Finished | [14 empty] | 25 | 2021-10-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-24 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2020-10-27 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 4 | 16 | 101 | 78.83 | Green |  |  | 20013704 | 2020-11-10 |  |  |  | HDME001016 | 2020-10-27
TAK0819-TH | HET | 61000830 | HO | ส่งมอบแล้ว | - | TH209204 | Pharma and Beyond | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2020-07-22 | 2020-12-22 | 2021-02-22 |  | B-1000-2S60,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1070000 | Bangkok | เขตลาดกระบัง | 2020-11-09 | 2020-11-17 | Finished | [34 empty] | 2020-12-22 | 2020-11-05 | 2020-11-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-09 | 2021-01-05 | 2020-11-20 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-13 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 2021-02-15 | 2021-02-15 | Finished |  |  | 2021-02-15 | 2021-02-18 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-19 | Finished |  |  | 100 | 2021-05-07 | 2021-06-07 | 2021-05-07 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-06-07 | Finished | [6 empty] | 90 | 2021-02-22 | Finished | POWER SUPPLY DELAY |  | 2021-02-19 | Finished |  |  | 2020-08-19 | Finished | [18 empty] | 2020-11-05 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  | pass | 2021-06-11 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20013563 | 2020-12-22 |  |  |  | HDME001027 | 2020-11-05 | QC Passed
TAJ0815-TH | HET | 61000833 | HO | ส่งมอบแล้ว | - | TH209211 | Hotel & Apartment 8 Flr. (Bangyai-Watprangluang) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2020-06-15 | 2020-11-09 | 2020-12-31 | 2021-04-15 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1050000 | Nonthaburi | ตำบลบางใหญ่ | 2020-11-10 | 2020-11-11 | Finished | [34 empty] | 2020-11-09 | 2020-11-09 | 2020-11-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-30 | 2020-12-30 | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-27 | Finished |  |  | 2020-12-30 | Finished |  |  | 100 | [41 empty] | 2020-12-30 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2020-12-12 | 2021-03-17 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-21 | Finished |  |  | 100 | 2021-01-29 | 2021-07-21 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-04-11 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2020-07-14 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-04-30 | Finished | [13 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013088 | 2020-11-09 |  |  |  | HDME001040 | 2020-11-20 | QC Passed
TAJ0824-TH | HET | 61000840 | HO | ส่งมอบแล้ว | - | TH209214 | Chulabhorn Vassal Building | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2020-07-20 | 2020-11-20 | 2021-01-20 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1070000 | Bangkok | เขตหลักสี่ | 2020-11-15 | 2021-01-01 | Finished | [34 empty] | 2020-11-20 | 2020-11-20 | 2020-11-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-20 | 2021-01-20 | 2021-01-02 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-17 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-25 | Finished |  |  | 100 | [41 empty] | 2021-01-25 | 2021-03-10 | 2021-03-10 | Finished |  |  | 2021-03-20 | 2021-03-11 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | 2021-01-29 | 2000-01-01 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-28 | Finished | [6 empty] | 90 | 2021-05-20 | Finished | POWER SUPPLY DELAY |  | 2021-04-23 | Finished |  |  | 2020-08-05 | Finished | [10 empty] | 2021-04-23 | Finished | [6 empty] | 2020-11-23 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2021-04-23 | Finished | [13 empty] | no pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20013400 | 2020-11-20 |  |  |  | HDME001046 | 2020-11-23
TAJ0825-TH | HET | 61000841 | HO | ส่งมอบแล้ว | - | TH209142 | CHEWATHAI HALLMARK LADPRAO-CHOKCHAI 4 (Phase 1) | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-04-30 | 2020-11-02 | 2020-12-30 | 2021-04-01 | P-1000-CO60W1,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1070000 | Bangkok | เขตลาดพร้าว | 2020-11-01 | 2020-12-30 | Finished | [34 empty] | 2020-11-02 | 2020-11-16 | 2020-11-17 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-11-01 | 2021-01-22 | 2020-11-20 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-11 | Finished |  |  | 100 | [41 empty] | 2020-12-11 | 2020-12-22 | 2020-12-22 | Finished |  |  | 2020-12-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-06 | 2021-07-19 | 2020-11-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-07-19 | Finished |  |  | 100 | 2021-03-15 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2020-07-14 | Finished | [18 empty] | 2020-11-16 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013117 | 2020-11-02 |  |  |  | HDME001034 | 2020-11-16 | QC Passed
TAJ0826-TH | HET | 61000841 | HO | ส่งมอบแล้ว | - | TH209142 | CHEWATHAI HALLMARK LADPRAO-CHOKCHAI 4 (Phase 1) | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-04-30 | 2020-11-02 | 2020-12-30 | 2021-04-01 | P-1000-CO60W1,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1070000 | Bangkok | เขตลาดพร้าว | 2020-11-01 | 2020-12-30 | Finished | [34 empty] | 2020-11-02 | 2020-11-16 | 2020-11-17 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-11-01 | 2021-01-22 | 2020-11-20 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-11 | Finished |  |  | 100 | [41 empty] | 2020-12-11 | 2020-12-22 | 2020-12-22 | Finished |  |  | 2020-12-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-06 | 2021-07-19 | 2020-11-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-07-19 | Finished |  |  | 100 | 2021-03-15 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2020-07-14 | Finished | [18 empty] | 2020-11-16 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013117 | 2020-11-02 |  |  |  | HDME001034 | 2020-11-16 | QC Passed
TAJ0827-TH | HET | 61000841 | HO | ส่งมอบแล้ว | - | TH209142 | CHEWATHAI HALLMARK LADPRAO-CHOKCHAI 4 (Phase 1) | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-04-30 | 2020-11-02 | 2020-12-30 | 2021-04-01 | P-1000-CO60W1,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1070000 | Bangkok | เขตลาดพร้าว | 2020-11-01 | 2020-12-30 | Finished | [34 empty] | 2020-11-02 | 2020-11-16 | 2020-11-17 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-11-01 | 2021-01-22 | 2020-11-20 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-11 | Finished |  |  | 100 | [41 empty] | 2020-12-11 | 2020-12-22 | 2020-12-22 | Finished |  |  | 2020-12-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-06 | 2021-08-06 | 2020-11-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-06 | Finished |  |  | 100 | 2021-03-15 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2020-07-14 | Finished | [18 empty] | 2020-11-16 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013117 | 2020-11-02 |  |  |  | HDME001034 | 2020-11-16 | QC Passed
TAJ0828-TH | HET | 61000841 | HO | ส่งมอบแล้ว | - | TH209142 | CHEWATHAI HALLMARK LADPRAO-CHOKCHAI 4 (Phase 1) | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-04-30 | 2020-11-02 | 2020-12-30 | 2021-04-01 | P-1000-CO60W1,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1070000 | Bangkok | เขตลาดพร้าว | 2020-11-01 | 2020-12-30 | Finished | [34 empty] | 2020-11-02 | 2020-11-16 | 2020-11-17 | Finished | SPECIFICATION REVISION | [13 empty] | 2020-11-01 | 2021-01-22 | 2020-11-20 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-11 | Finished |  |  | 100 | [41 empty] | 2020-12-11 | 2020-12-22 | 2020-12-22 | Finished |  |  | 2020-12-22 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-11-06 | 2021-08-06 | 2020-11-06 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-08-06 | Finished |  |  | 100 | 2021-03-15 | Finished | CONSTRUCTION DELAY |  | 2021-03-10 | Finished |  |  | 2020-07-14 | Finished | [18 empty] | 2020-11-16 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013117 | 2020-11-02 |  |  |  | HDME001034 | 2020-11-16 | QC Passed
TAJ0830-TH | HET | 61000842 | HO | ส่งมอบแล้ว | - | TH209215 | National Institute of Metrology | PL1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Chonticha Angsuwichitkun | 2020-07-01 | 2020-11-02 | 2021-01-01 | 2021-06-01 | P-630-CO60W,60S/3F | UAG-SN1 | 630 | 60 | 3 | 3 |  | 1310750 | Pathum Thani | อำเภอคลองหลวง | 2020-11-11 | 2020-11-28 | Finished | [34 empty] | 2020-11-02 | 2020-11-02 | 2020-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-31 | 2020-11-28 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-13 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 2021-01-12 | 2021-01-12 | Finished |  |  | 2021-01-10 | 2021-01-12 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-18 | Finished |  |  | 100 | 2021-01-29 | 2021-05-21 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2021-05-28 | Finished | CONSTRUCTION DELAY |  | 2021-05-28 | Finished |  |  | 2020-07-14 | Finished | [10 empty] | 2021-05-28 | Finished | [6 empty] | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-06 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  | pass | 2021-06-11 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013142 | 2020-11-02 |  |  |  | HDME001025 | 2020-11-04 | QC Passed
TAJ0829-TH | HET | 61000842 | HO | ส่งมอบแล้ว | - | TH209215 | National Institute of Metrology | SL1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Chonticha Angsuwichitkun | 2020-07-01 | 2020-11-02 | 2021-01-01 | 2021-06-01 | P-1050-2S60,60S/4F | UAG-SN1 | 1050 | 60 | 4 | 4 |  | 1364250 | Pathum Thani | อำเภอคลองหลวง | 2020-11-11 | 2020-12-15 | Finished | [34 empty] | 2020-11-02 | 2020-11-02 | 2020-11-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2020-12-31 | 2020-12-15 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-19 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-25 | Finished |  |  | 100 | [41 empty] | 2020-12-25 | 2021-01-12 | 2021-01-12 | Finished |  |  | 2021-01-10 | 2021-01-12 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-16 | Finished |  |  | 100 | 2021-01-29 | 2021-05-21 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | 2021-05-28 | Finished | CONSTRUCTION DELAY |  | 2021-05-28 | Finished |  |  | 2020-07-14 | Finished | [10 empty] | 2021-05-28 | Finished | [6 empty] | 2020-11-04 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-06 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-11 | Finished |  | pass | 2021-06-11 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013142 | 2020-11-02 |  |  |  | HDME001025 | 2020-11-04 | QC Passed
TED0002-TH | HET | 61000843 | Install | ยังอยู่ในสัญญา HO | - | TH209216 | RTWO (Hotel) | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Chanyuth Soithong | 2020-03-27 | 2020-12-31 | 2021-05-31 | 2022-05-31 | HCA-1150-CO210,210S/37F | HCA | 1150 | 210 | 24 | 37 |  | 3745000 | Bangkok | แขวงคลองต้นไทร | 2021-12-15 | [36 empty] | 2020-12-16 | 2021-05-15 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-18 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-19 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 2172 | 120 | 72 | 40 | 2404 | 2172 | 120 | 72 | 40 | 2404 | 0 | Green |  |  | 20013156 | 2021-04-30
TED0003-TH | HET | 61000843 | Install | ยังอยู่ในสัญญา HO | - | TH209216 | RTWO (Hotel) | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Chanyuth Soithong | 2020-03-27 | 2020-12-31 | 2021-05-31 | 2022-05-31 | HCA-1150-CO210,210S/37F | HCA | 1150 | 210 | 24 | 37 |  | 3745000 | Bangkok | แขวงคลองต้นไทร | 2021-12-15 | [36 empty] | 2020-12-16 | 2021-05-15 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-18 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-19 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 2172 | 120 | 72 | 40 | 2404 | 2172 | 120 | 72 | 40 | 2404 | 0 | Green |  |  | 20013156 | 2021-04-30
TED0004-TH | HET | 61000843 | Install | ยังอยู่ในสัญญา HO | - | TH209216 | RTWO (Hotel) | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Chanyuth Soithong | 2020-03-27 | 2020-12-31 | 2021-05-31 | 2022-05-31 | HCA-1150-CO210,210S/37F | HCA | 1150 | 210 | 24 | 37 |  | 3745000 | Bangkok | แขวงคลองต้นไทร | 2021-12-15 | [36 empty] | 2020-12-16 | 2021-05-15 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-18 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-19 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 2172 | 120 | 72 | 40 | 2404 | 2172 | 120 | 72 | 40 | 2404 | 0 | Green |  |  | 20013156 | 2021-04-30
TED0005-TH | HET | 61000843 | Install | ยังอยู่ในสัญญา HO | - | TH209216 | RTWO (Hotel) | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Chanyuth Soithong | 2020-03-27 | 2020-12-31 | 2021-05-31 | 2022-05-31 | HCA-1350-CO180,180S/38F | HCA | 1350 | 180 | 38 | 38 |  | 3745000 | Bangkok | แขวงคลองต้นไทร | 2021-12-15 | [36 empty] | 2020-12-16 | 2021-05-15 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-18 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-19 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 2221 | 121 | 72 | 40 | 2454 | 2221 | 121 | 72 | 40 | 2454 | 0 | Green |  |  | 20013156 | 2021-04-30
TED0006-TH | HET | 61000843 | Install | ยังอยู่ในสัญญา HO | - | TH209216 | RTWO (Hotel) | L7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Chanyuth Soithong | 2020-03-27 | 2020-12-31 | 2021-05-31 | 2022-05-31 | HCA-1350-CO180,180S/38F | HCA | 1350 | 180 | 38 | 38 |  | 3745000 | Bangkok | แขวงคลองต้นไทร | 2021-12-15 | [36 empty] | 2020-12-16 | 2021-05-15 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-18 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-19 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 2221 | 121 | 72 | 40 | 2454 | 2221 | 121 | 72 | 40 | 2454 | 0 | Green |  |  | 20013156 | 2021-04-30
TBL0360-TH | HET | 61000844 | HO | ส่งมอบแล้ว | - | TH209179 | Sukhumvit Hills | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-07-03 | 2020-10-05 | 2021-02-03 | 2021-10-28 | OUG-750-2S90,90S/7F | OUG-ON1 | 750 | 90 | 7 | 7 |  | 1020000 | Bangkok | แขวงบางจาก | 2020-10-05 | 2021-01-15 | Finished | [34 empty] | 2020-10-08 | 2020-10-05 | 2020-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-15 | 2021-02-03 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-17 | 2021-08-17 | Finished |  |  | 2021-08-17 | 2021-08-18 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-22 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished |  |  | 2021-07-30 | Finished | [10 empty] | 50 | 2021-10-28 | Finished | CONSTRUCTION DELAY |  | 2021-08-30 | Finished |  |  | 2020-07-22 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2021-08-30 | Finished | [18 empty] | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 16 | 16 | 97.79 | Blue |  |  | 20013162 | 2020-11-23 |  |  |  | HDME001057 | 2020-12-02
TAJ0831-TH | HET | 61000844 | HO | ส่งมอบแล้ว | - | TH209179 | Sukhumvit Hills | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-07-03 | 2020-10-05 | 2021-02-03 | 2021-10-28 | P-600-CO90D,90S/7F | UAG-SN1 | 600 | 90 | 7 | 7 |  | 820000 | Bangkok | แขวงบางจาก | 2020-10-05 | 2021-01-15 | Finished | [34 empty] | 2020-10-08 | 2020-10-05 | 2020-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-15 | 2021-02-03 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-15 | 2021-06-15 | Finished |  |  | 2021-06-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-07-30 | Finished | [6 empty] | 90 | 2021-10-28 | Finished | CONSTRUCTION DELAY |  | 2021-08-30 | Finished |  |  | 2020-07-22 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2021-08-30 | Finished | [18 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 1 | 1 | 99.84 | Blue |  |  | 20013162 | 2020-10-08 |  |  |  | HDME001057 | 2020-12-02
TAJ0832-TH | HET | 61000845 | HO | ส่งมอบแล้ว | - | TH209206 | บ้านพักอาศัย 4 ชั้น คุณมณีรัตน์ วัฒนสมบัติ | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-07-08 | 2020-10-08 | 2020-11-08 | 2021-01-08 | P-630-CO60W,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 963000 | Bangkok | เขตยานนาวา | 2020-10-01 | [36 empty] | 2020-10-19 | 2020-10-08 | 2020-10-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-08 | 2020-10-17 | 2020-10-21 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-10-24 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-08 | Finished |  |  | 100 | [41 empty] | 2020-11-08 | 2020-12-14 | 2020-12-14 | Finished |  |  | 2020-10-18 | 2020-12-14 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2020-11-08 | Finished | CONSTRUCTION DELAY |  | 2020-12-28 | Finished |  |  | 2020-08-03 | Finished | [18 empty] | 2020-10-21 | Finished |  |  | 2020-10-21 | Finished |  |  | 2020-10-22 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  | pass | 2021-01-25 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20013211 | 2020-10-08 |  |  |  | HDME001014 | 2020-10-21 | QC Passed
TEB0156-TH | HET | 61000846 | HO | ส่งมอบแล้ว | - | TH209170 | Home 4 Floor @ BMP Sukhumvit | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-07-08 | 2020-09-23 | 2020-10-23 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 4 | 4 |  | 950000 | Bangkok | แขวงคลองเตยเหนือ เขตวัฒนา | 2020-11-10 | 2020-12-01 | Finished | [34 empty] | 2020-09-23 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-20 | 2020-10-31 | 2021-01-10 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-10 | Finished |  |  | 100 | [41 empty] | 2021-01-10 | 2021-01-07 | 2021-01-07 | Finished |  |  | 2021-04-27 | 2021-01-07 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 100 | 2021-05-13 | 2021-01-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-18 | Finished | [6 empty] | 90 | 2020-12-15 | Finished | CONSTRUCTION DELAY |  | 2021-01-29 | Finished |  |  | 2020-07-22 | Finished | [18 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-30 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  | pass | 2021-02-16 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20013230 | 2020-09-08 |  |  |  | HDME001020 | 2020-10-28 | QC Passed
TAJ0833-TH | HET | 61000847 | HO | ส่งมอบแล้ว | - | TH209205 | The Motif Hotel | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-07-03 | 2020-11-03 | 2020-12-03 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1140000 | Chanthaburi | เขตเมืองจันทบุรี | 2020-12-03 | 2021-07-07 | Finished | [34 empty] | 2020-11-03 | 2020-11-03 | 2020-11-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-04 | 2020-11-02 | 2020-11-12 | Finished |  |  | 2020-11-14 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-16 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-26 | Finished |  |  | 100 | [41 empty] | 2020-11-26 | 2020-11-20 | 2020-11-20 | Finished |  |  | 2020-11-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-05-13 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-02-25 | Finished | POWER SUPPLY DELAY |  | 2021-05-17 | Finished |  |  | 2020-07-22 | Finished | [10 empty] | 2021-05-17 | Finished | [6 empty] | 2020-11-03 | Finished |  |  | 2020-11-03 | Finished |  |  | 2020-11-04 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  | pass | 2021-05-21 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20013212 | 2020-11-03 |  |  |  | HDME001022 | 2020-11-03 | QC Passed
TAJ0834-TH | HET | 61000848 | HO | ส่งมอบแล้ว | - | TH209161 | Kith Phetkasem Phutthamonthon Sai 7 | A1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-07-01 | 2020-09-15 | 2020-10-15 | 2021-05-31 | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Nakhon Pathom | หมู่ที่ 3 หอมเกร็ด อ.สามพราน | 2021-01-20 | 2021-01-20 | Finished | [34 empty] | 2020-09-29 | 2020-09-15 | 2020-10-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-20 | 2021-02-15 | 2021-01-20 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-06 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-15 | Finished |  |  | 100 | [41 empty] | 2021-02-15 | 2021-02-22 | 2021-02-22 | Finished |  |  | 2021-02-22 | 2021-03-05 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-06-26 | Finished |  |  | 100 | 2021-02-17 | 2021-09-10 | 2021-02-17 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-09-10 | Finished |  |  | 100 | 2021-08-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-27 | Finished |  |  | 2020-07-22 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2021-08-27 | Finished | [13 empty] | no pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013182 | 2020-09-29 |  |  |  | HDME000996 | 2020-10-01 | QC Passed
TAJ0835-TH | HET | 61000848 | HO | ส่งมอบแล้ว | - | TH209161 | Kith Phetkasem Phutthamonthon Sai 7 | B1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-07-01 | 2020-09-15 | 2020-10-15 | 2021-05-31 | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Nakhon Pathom | หมู่ที่ 3 หอมเกร็ด อ.สามพราน | 2020-10-30 | 2020-10-30 | Finished | [34 empty] | 2020-09-29 | 2020-09-15 | 2020-10-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-20 | 2020-11-15 | 2020-10-20 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-03 | Finished |  |  | 100 | [41 empty] | 2020-11-03 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-15 | 2021-01-22 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-02-12 | Finished |  |  | 100 | 2021-02-23 | 2021-07-19 | 2021-02-23 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-07-19 | Finished | [6 empty] | 90 | 2021-06-05 | Finished | CONSTRUCTION DELAY |  | 2021-07-15 | Finished |  |  | 2020-07-22 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20013182 | 2020-09-29 |  |  |  | HDME000996 | 2020-10-01 | QC Passed
TAJ0836-TH | HET | 61000848 | HO | ส่งมอบแล้ว | - | TH209161 | Kith Phetkasem Phutthamonthon Sai 7 | C1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-07-01 | 2020-09-15 | 2020-10-15 | 2021-05-31 | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Nakhon Pathom | หมู่ที่ 3 หอมเกร็ด อ.สามพราน | 2020-11-30 | 2020-11-30 | Finished | [34 empty] | 2020-09-29 | 2020-09-15 | 2020-10-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-20 | 2020-11-15 | 2020-10-20 | Finished |  |  | 2020-11-04 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-10-26 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-02 | Finished |  |  | 2020-11-03 | Finished |  |  | 100 | [41 empty] | 2020-11-03 | 2020-11-06 | 2020-11-06 | Finished |  |  | 2021-01-05 | 2020-11-09 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 100 | 2021-02-17 | 2021-05-06 | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-05-06 | Finished |  |  | 100 | 2021-04-02 | Finished | CONSTRUCTION DELAY |  | 2021-04-23 | Finished |  |  | 2020-07-22 | Finished | [10 empty] | 2021-04-23 | Finished | [6 empty] | 2020-10-01 | Finished |  |  | 2020-10-05 | Finished |  |  | 2020-10-08 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013182 | 2020-09-29 |  |  |  | HDME000996 | 2020-10-01 | QC Passed
TBL0361-TH | HET | 61000849 | HO | ส่งมอบแล้ว | - | TH209166 | Technic Pattaya College | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2020-07-13 | 2020-11-13 | 2021-01-13 |  | OUG-1000-CO60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1100000 | Chon Buri | อำเภอบางละมุง | 2021-01-10 | 2021-01-10 | Finished | [34 empty] | 2020-11-30 | 2020-11-30 | 2020-11-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-01 | 2021-01-10 | 2020-11-26 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-25 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-20 | Finished |  |  | 100 | [41 empty] | 2021-01-20 | 2021-02-16 | 2021-02-16 | Finished |  |  | 2020-12-20 | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-22 | Finished |  |  | 100 | 2021-03-02 | 2021-05-13 | 2021-03-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished | [6 empty] | 90 | 2021-02-20 | Finished | POWER SUPPLY DELAY |  | 2021-02-28 | Finished |  |  | 2020-07-23 | Finished | [18 empty] | 2020-11-13 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-10 | Finished |  | pass | 2021-03-10 | Finished |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 1 | 1 | 99.84 | Blue |  |  | 20013266 | 2020-11-30 |  |  |  | HDME001032 | 2020-11-13 | QC Passed
TBL0363-TH | HET | 61000850 | HO | ส่งมอบแล้ว | - | TH209199 | Institute for Special Investigation | L1(Central Building) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-06-25 | 2020-10-25 | 2021-02-25 | 2021-06-05 | OUG-1050-2S60,60S/3F | OUG-ON1 | 1050 | 60 | 3 | 3 |  | 1102100 | Bangkok |  | 2020-12-25 | [36 empty] | 2020-11-30 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-25 | 2020-12-10 | 2020-10-31 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished |  |  | 100 | [41 empty] | 2020-11-23 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-11-19 | 1900-01-01 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-15 | Finished |  |  | 100 | 2020-12-25 | 2021-07-12 | 2020-12-25 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 90 | 2021-04-25 | Finished | POWER SUPPLY DELAY |  | 2021-05-19 | Finished |  |  | 2020-08-11 | Finished | [10 empty] | 2021-05-19 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 1 | 1 | 99.8 | Blue |  |  | 20013305 | 2020-11-30 |  |  |  | HDME001018 | 2020-10-28 | QC Passed
TBL0364-TH | HET | 61000850 | HO | ส่งมอบแล้ว | - | TH209199 | Institute for Special Investigation | L2(Central Building) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-06-25 | 2020-10-25 | 2021-02-25 | 2021-06-05 | OUG-1050-2S60,60S/3F | OUG-ON1 | 1050 | 60 | 3 | 3 |  | 1102100 | Bangkok |  | 2020-12-25 | [36 empty] | 2020-11-30 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-25 | 2020-12-10 | 2020-10-31 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished |  |  | 100 | [41 empty] | 2020-11-23 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-11-19 | 1900-01-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-02 | Finished |  |  | 100 | 2020-12-25 | 2021-07-12 | 2020-12-25 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 90 | 2021-04-25 | Finished | POWER SUPPLY DELAY |  | 2021-05-19 | Finished |  |  | 2020-08-11 | Finished | [10 empty] | 2021-05-19 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 1 | 1 | 99.8 | Blue |  |  | 20013305 | 2020-11-30 |  |  |  | HDME001018 | 2020-10-28 | QC Passed
TBL0365-TH | HET | 61000850 | HO | ส่งมอบแล้ว | - | TH209199 | Institute for Special Investigation | L3(Administrative Building) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-06-25 | 2020-10-25 | 2021-02-25 | 2021-06-05 | OUG-750-2S60,60S/3F | OUG-ON1 | 750 | 60 | 3 | 3 |  | 1037900 | Bangkok |  | 2020-12-25 | [36 empty] | 2020-11-30 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-25 | 2020-12-10 | 2020-10-31 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-11 | Finished |  |  | 2020-11-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished |  |  | 100 | [41 empty] | 2020-11-23 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2020-11-19 | 1900-01-01 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-05 | Finished |  |  | 100 | 2020-12-25 | 2021-07-12 | 2020-12-25 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 90 | 2021-04-25 | Finished | POWER SUPPLY DELAY |  | 2021-05-19 | Finished |  |  | 2020-08-11 | Finished | [10 empty] | 2021-05-19 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-01 | Finished |  | pass | 2021-08-01 | Finished |  |  | 384 | 84 | 16 | 16 | 500 | 0 | 0 | 0 | 1 | 1 | 99.8 | Blue |  |  | 20013305 | 2020-11-30 |  |  |  | HDME001018 | 2020-10-28 | QC Passed
TAJ0837-TH | HET | 61000850 | HO | เลยสัญญา HO | - | TH209199 | Institute for Special Investigation | L4(Traning accommodation) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-06-25 | 2020-10-25 | 2021-02-25 | 2021-09-10 | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1048600 | Bangkok |  | 2020-10-25 | 2020-10-25 | Finished | [34 empty] | 2020-10-22 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-25 | 2020-12-10 | 2020-11-15 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 100 | [41 empty] | 2020-12-03 | 2021-06-30 | 2021-06-30 | Finished |  |  | 2020-11-19 | 2021-08-01 | Finished |  |  | 2021-09-19 | Finished |  |  | 2021-09-20 | Finished |  |  | 100 | 2020-12-25 | 2000-01-01 | 2020-12-25 | Finished | [14 empty] | 25 | 2021-09-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-11 | Finished | [10 empty] | 2022-11-15 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 4 | 16 | 20 | 96.17 | Red |  |  | 20013305 | 2020-10-22 |  |  |  | HDME001018 | 2020-10-28
TAJ0838-TH | HET | 61000850 | HO | เลยสัญญา HO | - | TH209199 | Institute for Special Investigation | L5(Traning accommodation) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-06-25 | 2020-10-25 | 2021-02-25 | 2021-09-10 | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1048600 | Bangkok |  | 2020-10-25 | 2020-10-25 | Finished | [34 empty] | 2020-10-22 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-25 | 2020-12-10 | 2020-11-15 | Finished |  |  | 2020-11-18 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-11-29 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 100 | [41 empty] | 2020-12-03 | 2021-06-30 | 2021-06-30 | Finished |  |  | 2020-11-19 | 2021-08-01 | Finished |  |  | 2021-09-19 | Finished |  |  | 2021-09-20 | Finished |  |  | 100 | 2020-12-25 | 2000-01-01 | 2020-12-25 | Finished | [14 empty] | 25 | 2021-09-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-11 | Finished | [10 empty] | 2022-11-15 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 4 | 16 | 20 | 96.17 | Red |  |  | 20013305 | 2020-10-22 |  |  |  | HDME001018 | 2020-10-28
TBL0362-TH | HET | 61000850 | HO | ส่งมอบแล้ว | - | TH209199 | Institute for Special Investigation | L6(Parking Building) | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-06-25 | 2020-10-25 | 2021-02-25 | 2021-08-10 | OUG-1000-CO60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1080700 | Bangkok |  | 2020-10-25 | 2020-10-25 | Finished | [34 empty] | 2020-11-30 | 2020-10-28 | 2020-10-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-25 | 2020-12-10 | 2020-11-12 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-13 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 100 | [41 empty] | 2020-12-20 | 2021-05-01 | 2021-05-01 | Finished |  |  | 2020-11-19 | 2021-05-03 | Finished |  |  | 2021-05-22 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | 2020-12-25 | 2000-01-01 | 2020-12-25 | Finished |  |  | 2021-07-12 | Finished | [10 empty] | 50 | 2021-08-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-25 | Finished |  |  | 2020-08-11 | Finished | [10 empty] | 2021-06-08 | Finished | [6 empty] | 2020-10-28 | Finished |  |  | 2020-10-28 | Finished |  |  | 2020-10-29 | Finished |  |  | 2021-06-25 | Finished | [13 empty] | no qc |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 16 | 16 | 97.37 | Blue |  |  | 20013305 | 2020-11-30 |  |  |  | HDME001018 | 2020-10-28
TAJ0839-TH | HET | 61000851 | HO | ส่งมอบแล้ว | - | TH209203 | Le Cannes Hotel | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2020-07-07 | 2021-02-07 | 2021-04-07 |  | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1053950 | Chiang Mai | อำเภอเมือง | 2021-02-08 | 2021-02-08 | Finished | [34 empty] | 2021-02-05 | 2020-12-24 | 2020-12-24 | Finished | [14 empty] | 2021-02-08 | 2021-04-07 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2021-02-25 | 2021-03-16 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2021-01-29 | 2021-03-31 | 2021-01-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-31 | Finished | [6 empty] | 90 | 2021-03-30 | Finished | CONSTRUCTION DELAY |  | 2021-03-31 | Finished |  |  | 2020-08-05 | Finished | [10 empty] | 2021-03-31 | Finished | [6 empty] | 2020-12-24 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  | pass | 2021-04-09 | Finished |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20013267 | 2021-02-05 |  |  |  | HDME001077 | 2020-12-24 | QC Passed
TBL0366-TH | HET | 61000852 |  | เลยสัญญา HO | - | TH209163 | 15 Story Hotel, Mezzanine and 2 Story | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Phumiphat Siprajan | 2020-06-08 | 2020-12-08 | 2021-06-08 |  | OUG-800-CO105,105S/19F | OUG-ON1 | 800 | 105 | 19 | 19 |  | 2487250 | Bangkok | แขวงบางกะปิ | 2021-09-10 | [36 empty] | 2020-12-08 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2021-08-25 | 2021-09-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished |  |  | 2022-08-12 | Finished | [46 empty] | 1232 | 103 | 40 | 20 | 1395 | 1232 | 103 | 40 | 20 | 1395 | 0 | Red |  |  | 20013265 | 2021-01-20
TBL0367-TH | HET | 61000852 |  | เลยสัญญา HO | - | TH209163 | 15 Story Hotel, Mezzanine and 2 Story | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Phumiphat Siprajan | 2020-06-08 | 2020-12-08 | 2021-06-08 |  | OUG-800-CO105,105S/19F | OUG-ON1 | 800 | 105 | 19 | 19 |  | 2487250 | Bangkok | แขวงบางกะปิ | 2021-09-10 | [36 empty] | 2020-12-08 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2021-08-25 | 2021-09-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished |  |  | 2022-08-12 | Finished | [46 empty] | 1232 | 103 | 40 | 20 | 1395 | 1232 | 103 | 40 | 20 | 1395 | 0 | Red |  |  | 20013265 | 2021-01-20
TBL0368-TH | HET | 61000852 |  | เลยสัญญา HO | - | TH209163 | 15 Story Hotel, Mezzanine and 2 Story | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Phumiphat Siprajan | 2020-06-08 | 2020-12-08 | 2021-06-08 |  | OUG-1600-CO105,105S/16F | OUG-ON1 | 1600 | 105 | 16 | 16 |  | 2960500 | Bangkok | แขวงบางกะปิ | 2021-09-10 | [36 empty] | 2020-12-08 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2021-08-25 | 2021-09-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished | [50 empty] | 1073 | 101 | 40 | 20 | 1234 | 1073 | 101 | 40 | 20 | 1234 | 0 | Red |  |  | 20013265 | 2020-12-08
TBL0369-TH | HET | 61000852 |  | เลยสัญญา HO | - | TH209163 | 15 Story Hotel, Mezzanine and 2 Story | L4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Phumiphat Siprajan | 2020-06-08 | 2020-12-08 | 2021-06-08 |  | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 4 | 4 |  | 2100000 | Bangkok | แขวงบางกะปิ | 2021-09-10 | [36 empty] | 2020-12-08 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2021-08-25 | 2021-09-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished |  |  | 2022-08-12 | Finished | [46 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Red |  |  | 20013265 | 2020-12-08
TAK0840-TH | HET | 61000853 | Install | ยังอยู่ในสัญญา HO | - | TH209218 | EGAT Rayong | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-07-10 | 2020-11-10 | 2021-01-10 | 2021-10-30 | B-750-2S60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1284000 | Rayong | ตำบลเชิงเนิน | 2021-01-10 | 2021-01-07 | Finished | [34 empty] | 2020-11-10 | 2020-11-10 | 2020-11-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-11 | 2021-01-05 | 2021-01-08 | Finished |  |  | 2021-01-09 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-16 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-26 | Finished |  |  | 100 | [41 empty] | 2021-01-26 | 2020-12-20 | 2020-12-20 | Finished |  |  | 2020-12-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-01 | Finished | [6 empty] | 90 | 2021-10-01 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-03 | Finished | [18 empty] | 2020-11-11 | Finished |  |  | 2020-11-26 | Finished |  |  | 2020-11-30 | Finished | [17 empty] | pass (defect) |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Green |  |  | 20013268 | 2020-11-10 |  |  |  | HDME001029 | 2020-11-11
TAJ0841-TH | HET | 61000854 | HO | เลยสัญญา HO | - | TH209219 | R3 Hotel | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-07-02 | 2020-12-02 | 2021-02-02 |  | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 941600 | Bangkok | เขตปทุมวัน | 2021-02-01 | 2021-02-01 | Finished | [34 empty] | 2020-12-02 | 2020-11-20 | 2020-11-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-01 | 2021-08-31 | 2021-02-01 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-22 | Finished |  |  | 100 | [41 empty] | 2021-02-22 | 1900-01-01 | 2021-02-22 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2021-03-26 | 2000-01-01 | 2021-03-26 | Finished | [14 empty] | 25 | 2021-10-31 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-19 | Finished | [10 empty] | 2021-09-03 | Finished | [6 empty] | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Red |  |  | 20013269 | 2020-12-02 |  |  |  | HDME001041 | 2020-11-20
TAJ0842-TH | HET | 61000855 | HO | ส่งมอบแล้ว | - | TH209220 | Glory Thewes | PL-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2020-06-15 | 2020-10-15 | 2020-12-15 |  | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1100000 | Bangkok | ถนนกรุงเกษม แขวงบางขุนพรหม | 2020-10-16 | [36 empty] | 2020-11-15 | 2020-10-15 | 2020-10-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-17 | 2020-11-25 | 2020-10-18 | Finished |  |  | 2020-10-25 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-11-05 | Finished |  |  | 2020-11-10 | Finished |  |  | 2020-11-15 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-25 | Finished |  |  | 100 | [41 empty] | 2020-11-25 | 2021-01-11 | 2021-01-11 | Finished |  |  | 2020-11-26 | 2021-01-11 | Finished |  |  | 2021-01-02 | Finished |  |  | 2021-01-05 | Finished |  |  | 100 | 2020-11-13 | 2021-03-04 | 2020-11-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-04 | Finished | [6 empty] | 90 | 2021-02-05 | Finished | POWER SUPPLY DELAY |  | 2021-01-29 | Finished |  |  | 2020-07-29 | Finished | [10 empty] | 2021-01-29 | Finished | [6 empty] | 2020-10-19 | Finished |  |  | 2020-10-19 | Finished |  |  | 2020-10-22 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  | pass | 2021-06-01 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Blue |  |  | 20013340 | 2020-10-15 |  |  |  | HDME001013 | 2020-10-19 | QC Passed
TAJ0843-TH | HET | 61000856 | HO | ยังอยู่ในสัญญา HO | - | TH209221 | Hotel Suksawat Lampang | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-07-14 | 2020-11-13 | 2021-03-14 | 2021-10-15 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 1040000 | Lampang | ตำบลพระบาท | 2020-11-14 | 2020-11-14 | Finished | [34 empty] | 2020-11-13 | 2020-11-17 | 2020-11-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-14 | 2021-03-14 | 2020-12-20 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-23 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-25 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-27 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-29 | Finished |  |  | 100 | [41 empty] | 2020-12-29 | 1900-01-01 | 2020-12-29 | Waiting | POWER SUPPLY DELAY |  | 2021-11-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-03 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2020-11-17 | Finished |  |  | 2020-11-17 | Finished |  |  | 2020-11-18 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 16 | 16 | 113 | 76.31 | Green |  |  | 20013427 | 2020-11-13 |  |  |  | HDME001035 | 2020-11-17
TAC1802-TH | HET | 61000857 | HO | ส่งมอบแล้ว | - | TH209209 | Chalermkwansatree@Phitsanulok | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-07-21 | 2020-11-21 | 2020-12-21 | 2021-04-22 | VFI-900-CO60,60S/6F | VFI-II | 900 | 60 | 6 | 6 |  | 1321450 | Phitsanulok | ต.ในเมือง อ.พิษณุโลก | 2020-11-22 | 2020-11-22 | Finished | [34 empty] | 2020-11-21 | 2020-11-21 | 2020-11-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-22 | 2020-12-21 | 2020-12-10 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-13 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-19 | Finished |  |  | 100 | [41 empty] | 2020-12-19 | 2020-12-21 | 2020-12-21 | Finished |  |  | 2020-03-23 | 2020-12-22 | Finished |  |  | 2020-12-24 | Finished |  |  | 2020-12-26 | Finished |  |  | 100 | 2020-01-04 | 2021-06-14 | 2020-01-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2021-04-01 | Finished | CONSTRUCTION DELAY |  | 2021-03-31 | Finished |  |  | 2020-08-05 | Finished | [18 empty] | 2020-11-21 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass | 2021-06-22 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013401 | 2020-11-21 |  |  |  | HDME001044 | 2020-11-21 | QC Passed
TAC1803-TH | HET | 61000858 | HO | ส่งมอบแล้ว | - | TH209222 | วิทยาลัยนาฎศิลป์ นครศรีธรรมราช | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-07-25 | 2020-11-25 | 2021-01-25 |  | VFI-1000-CO60,60S/5F | VFI-II | 1000 | 60 | 5 | 5 |  | 1177000 | Nakhon Si Thammarat | อำเภอเมือง | 2020-11-27 | [36 empty] | 2020-11-25 | 2020-11-27 | 2020-11-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-27 | 2020-11-27 | 2020-11-27 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 2020-12-20 | Finished |  |  | 100 | [41 empty] | 2020-12-20 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-17 | Finished |  |  | 100 | 2020-12-22 | 2021-02-17 | 2020-12-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-17 | Finished | [6 empty] | 90 | 2021-01-25 | Finished | POWER SUPPLY DELAY |  | 2021-02-17 | Finished |  |  | 2020-11-03 | Finished | [18 empty] | 2020-11-27 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-10 | Finished |  | pass | 2021-03-10 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20013511 | 2020-11-25 |  |  |  | HDME001050 | 2020-11-27 | QC Passed
TAJ0844-TH | HET | 61000859 | HO | ยังอยู่ในสัญญา HO | - | TH209200 | Home Khun Metha Soi Pridi Pranomyong 25 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-07-15 | 2020-10-12 | 2020-11-15 | 2021-12-20 | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1070000 | Bangkok | ถนนสุขุมวิท 71 | 2020-10-12 | 2020-10-12 | Finished | [34 empty] | 2020-10-12 | 2020-10-12 | 2020-10-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-10-12 | 2020-12-12 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-02 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-05 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-10-21 | Finished |  |  | 2020-10-30 | Finished |  |  | 2020-10-30 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 16 | 16 | 113 | 76.31 | Green |  |  | 20013423 | 2020-10-12 |  |  |  | HDME001015 | 2020-10-21
TAC1805-TH | HET | 61000860 | HO | ส่งมอบแล้ว | - | TH209225 | Housing Judicial Court Yala | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-07-04 | 2020-11-04 | 2020-12-04 | 2021-05-04 | VFI-1000-CO60,60S/5F | VFI-II | 1000 | 60 | 5 | 5 |  | 1230000 | Yala | อำเภอเมืองยะลา | 2020-11-01 | 2020-11-02 | Finished | [34 empty] | 2020-07-04 | 2021-01-07 | 2021-01-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-05 | 2020-11-30 | 2021-01-28 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 100 | [41 empty] | 2021-02-05 | 2021-02-23 | 2021-02-23 | Finished |  |  | 2020-12-01 | 2021-03-24 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-12 | Finished |  |  | 100 | 2021-02-22 | 2021-08-04 | 2021-02-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-08-04 | Finished |  |  | 100 | 2021-03-15 | Finished | POWER SUPPLY DELAY |  | 2021-05-28 | Finished |  |  | 2020-08-13 | Finished | [10 empty] | 2021-05-28 | Finished | [6 empty] | 2021-01-08 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-05-28 | Finished | [13 empty] | pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013425 | 2020-11-04 |  |  |  | HDME001086 | 2021-01-08 | QC Passed
TAC1804-TH | HET | 61000861 | HO | ส่งมอบแล้ว | - | TH209224 | บ้านพักศาลปกครอง เชียงใหม่ | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-07-04 | 2020-11-04 | 2020-12-04 | 2021-02-04 | VFI-1000-CO60,60S/5F | VFI-II | 1000 | 60 | 5 | 5 |  | 1220000 | Chiang Mai | อำเภอแม่ริม | 2020-11-05 | 2020-12-01 | Finished | [34 empty] | 2020-11-04 | 2020-12-01 | 2020-02-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-05 | 2020-12-04 | 2020-12-01 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 100 | [41 empty] | 2020-12-10 | 2021-01-11 | 2021-01-11 | Finished |  |  | 2020-11-25 | 2021-01-11 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-14 | Finished |  |  | 100 | 2020-01-04 | 2021-06-14 | 2020-01-04 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2021-04-01 | Finished | CONSTRUCTION DELAY |  | 2021-01-26 | Finished |  |  | 2020-08-13 | Finished | [18 empty] | 2020-12-01 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-03 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-22 | Finished |  | pass | 2021-06-22 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013424 | 2020-11-04 |  |  |  | HDME001055 | 2020-12-01 | QC Passed
TFA1406-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 856000 | Nonthaburi | อำเภอปากเกร็ด | 2021-04-20 | [20 empty] | 2021-04-21 | Finished | [14 empty] | 2020-11-30 | 2021-01-27 | 2021-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-21 | 2021-05-25 | [41 empty] | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | 2021-05-23 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished |  |  | 2021-08-26 | Finished | [10 empty] | 50 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 8 | 0 | 21 | 29 | 95.28 | Green |  |  | 20013698 | 2020-12-11 |  |  |  | HDME001107 | 2021-01-27
TFA1407-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 856000 | Nonthaburi | อำเภอปากเกร็ด | 2021-04-20 | [20 empty] | 2021-04-21 | Finished | [14 empty] | 2020-11-30 | 2021-01-27 | 2021-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-21 | 2021-05-25 | [41 empty] | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | 2021-05-23 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished |  |  | 2021-08-26 | Finished | [10 empty] | 50 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 8 | 0 | 21 | 29 | 95.28 | Green |  |  | 20013698 | 2020-12-11 |  |  |  | HDME001107 | 2021-01-27
TFA1408-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 856000 | Nonthaburi | อำเภอปากเกร็ด | 2021-04-20 | [20 empty] | 2021-04-21 | Finished | [14 empty] | 2020-11-30 | 2021-01-27 | 2021-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-21 | 2021-05-25 | [41 empty] | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | 2021-05-23 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished |  |  | 2021-08-26 | Finished | [10 empty] | 50 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 8 | 0 | 21 | 29 | 95.28 | Green |  |  | 20013698 | 2020-12-11 |  |  |  | HDME001107 | 2021-01-27
TFA1409-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | ES4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 856000 | Nonthaburi | อำเภอปากเกร็ด | 2021-04-20 | [20 empty] | 2021-04-21 | Finished | [14 empty] | 2020-11-30 | 2021-01-27 | 2021-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-21 | 2021-05-25 | [41 empty] | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | 2021-05-23 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished |  |  | 2021-08-26 | Finished | [10 empty] | 50 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 8 | 0 | 21 | 29 | 95.28 | Green |  |  | 20013698 | 2020-12-11 |  |  |  | HDME001107 | 2021-01-27
TFA1410-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | ES5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 856000 | Nonthaburi | อำเภอปากเกร็ด | 2021-04-20 | [20 empty] | 2021-04-21 | Finished | [14 empty] | 2020-11-30 | 2021-01-27 | 2021-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-21 | 2021-05-25 | [41 empty] | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | 2021-05-23 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished |  |  | 2021-08-26 | Finished | [10 empty] | 50 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 8 | 0 | 21 | 29 | 95.28 | Green |  |  | 20013698 | 2020-12-11 |  |  |  | HDME001107 | 2021-01-27
TFA1411-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | ES6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 856000 | Nonthaburi | อำเภอปากเกร็ด | 2021-04-20 | [20 empty] | 2021-04-21 | Finished | [14 empty] | 2020-11-30 | 2021-01-27 | 2021-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-21 | 2021-05-25 | [41 empty] | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | 2021-05-23 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished |  |  | 2021-08-26 | Finished | [10 empty] | 50 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 8 | 0 | 21 | 29 | 95.28 | Green |  |  | 20013698 | 2020-12-11 |  |  |  | HDME001107 | 2021-01-27
TAJ0845-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | P1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 829250 | Nonthaburi | อำเภอปากเกร็ด | 2021-02-15 | 2021-02-08 | Finished | [34 empty] | 2020-12-15 | 2020-12-17 | 2020-12-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-16 | 2021-03-25 | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-05 | Finished |  |  | 100 | [41 empty] | 2021-03-05 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-21 | 2000-01-01 | 2021-05-21 | Finished | [14 empty] | 25 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-22 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 16 | 4 | 16 | 36 | 92.45 | Orange |  |  | 20013702 | 2020-12-15 |  |  |  | HDME001072 | 2020-12-17
TAJ0846-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | P2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 829250 | Nonthaburi | อำเภอปากเกร็ด | 2021-02-15 | 2021-02-08 | Finished | [34 empty] | 2020-12-15 | 2020-12-17 | 2020-12-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-16 | 2021-03-25 | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-05 | Finished |  |  | 100 | [41 empty] | 2021-03-05 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-21 | 2000-01-01 | 2021-05-21 | Finished | [14 empty] | 25 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2020-12-17 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-22 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 16 | 4 | 16 | 36 | 92.45 | Orange |  |  | 20013702 | 2020-12-15 |  |  |  | HDME001072 | 2020-12-17
TBL0370-TH | HET | 61000862 | Install | ยังอยู่ในสัญญา HO | - | TH209226 | Chonprathan Rangsarit Temple | S1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-07-29 | 2020-12-15 | 2021-02-15 | 2021-09-30 | OUG-1600-2S60,60S/4F | OUG-ON1 | 1600 | 60 | 4 | 4 |  | 1551500 | Nonthaburi | อำเภอปากเกร็ด | 2021-04-09 | 2021-04-21 | Finished | [34 empty] | 2020-12-15 | 2021-01-27 | 2021-01-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-21 | 2021-05-25 | 2021-04-23 | Finished |  |  | 2021-04-25 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | [41 empty] | 2021-05-21 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-08-15 | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished | [6 empty] | 80 | 2021-05-21 | 2000-01-01 | 2021-05-21 | Finished | [14 empty] | 25 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-26 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 0 | 17 | 4 | 16 | 37 | 93.32 | Orange |  |  | 20013702 | 2020-12-28 |  |  |  | HDME001107 | 2021-01-27
TAJ0848-TH | HET | 61000867 | HO | ยังอยู่ในสัญญา HO | - | TH209229 | Home Khun Marut | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Janyaruk Choobuakhaw | 2020-10-02 | 2021-02-02 | 2021-04-02 | 2021-10-02 | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1070000 | Songkhla | ตำบลคลองแห | 2021-12-15 | [36 empty] | 2021-02-02 | 2021-02-11 | 2021-02-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-12-15 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2022-08-15 | Finished | [6 empty] | 2021-02-11 | Finished |  |  | 2021-02-11 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Orange |  |  | 20014596 | 2021-02-02 |  |  |  | HDME001130 | 2021-02-11
TAC1809-TH | HET | 61000868 | HO | ส่งมอบแล้ว | - | TH209230 | ศูนย์บริการคนพิการ จังหวัดสุรินทร์ | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2020-08-03 | 2020-11-18 | 2021-01-03 |  | VFI-900-CO60,60S/2F | VFI-II | 900 | 60 | 2 | 2 |  | 963000 | Surin | อำเภอเมืองสุรินทร์ | 2020-11-04 | [36 empty] | 2020-11-18 | 2020-11-20 | 2020-11-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-18 | 2020-12-18 | 2020-11-18 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 100 | [41 empty] | 2020-11-30 | 2021-02-15 | 2021-02-15 | Finished |  |  | 2021-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-02-08 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-04 | Finished |  |  | 2021-02-08 | Finished |  |  | 100 | 2021-05-08 | Finished | CONSTRUCTION DELAY |  | 2021-01-08 | Finished |  |  | 2020-08-19 | Finished | [18 empty] | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-10 | Finished |  | pass | 2021-03-10 | Finished |  |  | 362 | 88 | 16 | 16 | 482 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013590 | 2020-11-18 |  |  |  | HDME001039 | 2020-11-20 | QC Passed
TBL0371-TH | HET | 61000869 | HO | ส่งมอบแล้ว | - | TH209231 | Katsushika Factory | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2020-07-23 | 2021-01-23 | 2021-03-23 | 2021-10-30 | OUG-2000-2S60,60S/4F | OUG-ON1 | 2000 | 60 | 4 | 4 |  | 2696400 | Chachoengsao | อำเภอบางปะกง | 2020-03-23 | 2021-07-07 | Finished | [34 empty] | 2021-01-22 | 2021-01-22 | 2021-01-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-23 | 2020-04-20 | 2021-07-09 | Finished |  |  | 2021-07-11 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-09 | 2021-08-09 | Finished |  |  | 2020-08-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-08-02 | 2000-01-01 | 2021-08-02 | Finished |  |  | 2021-09-01 | Finished |  |  | 2021-09-01 | Finished | [6 empty] | 90 | 2021-09-25 | Finished | CONSTRUCTION DELAY |  | 2021-08-30 | Finished |  |  | 2020-08-24 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-01-25 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | no pass |  |  |  |  | 437 | 85 | 16 | 16 | 554 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20013540 | 2021-01-22 |  |  |  | HDME001104 | 2021-01-25
TBL0376-TH | HET | 61000874 | HO | ส่งมอบแล้ว | - | TH209235 | Public Health Center 51 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-09-14 | 2021-03-14 | 2021-05-14 | 2021-07-15 | OUG-1350-CO60,60S/5F | OUG-ON1 | 1350 | 60 | 5 | 5 |  | 1550000 | Bangkok | แขวงจอมพล | 2021-03-26 | 2021-03-26 | Finished | [34 empty] | 2021-03-14 | 2021-03-25 | 2021-03-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-26 | 2021-04-28 | 2021-04-20 | Finished |  |  | 2021-04-22 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-29 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | [41 empty] | 2021-05-20 | 2021-08-09 | 2021-08-09 | Finished |  |  | 2021-06-20 | 2021-08-13 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 100 | 2021-08-30 | 2021-09-01 | 2021-08-30 | Finished |  |  | 2021-08-30 | Finished |  |  | 2021-09-01 | Finished |  |  | 2021-09-01 | Finished |  |  | 100 | 2021-10-10 | Finished | CONSTRUCTION DELAY |  | 2021-09-01 | Finished |  |  | 2020-10-07 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-09-01 | Finished | [13 empty] | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014283 | 2021-03-12 |  |  |  | HDME001177 | 2021-03-25 | QC Passed
TAJ0856-TH | HET | 61000879 | HO | ส่งมอบแล้ว | - | TH209242 | ศูนย์วิจัยฯ โครงการหลวง อ.ดาต้าเซ็นเตอร์ | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-07-31 | 2021-01-31 | 2021-04-30 | 2021-07-30 | P-1000-CO60W1,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 1070000 | Chiang Mai | อำเภอเมืองเชียงใหม่ | 2021-01-31 | 2021-01-31 | Finished | [34 empty] | 2021-01-29 | 2021-02-03 | 2021-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-05 | 2021-02-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-04-06 | 2021-04-06 | Finished |  |  | 2020-04-20 | 2021-04-06 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-06 | Finished |  |  | 100 | 2021-03-31 | 2021-08-04 | 2021-03-31 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-08-04 | Finished |  |  | 100 | 2021-08-05 | Finished | POWER SUPPLY DELAY |  | 2021-08-05 | Finished |  |  | 2020-08-24 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-02-03 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-08-05 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013564 | 2021-01-29 |  |  |  | HDME001113 | 2021-02-03 | QC Passed
TAJ0859-TH | HET | 61000886 | HO | เลยสัญญา HO | - | TH209247 | Office 4 Floor @Chaengwattana 12 Khun Chaiyuth | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-07-30 | 2020-11-14 | 2020-12-15 | 2021-07-15 | P-600-CO60W,60S/4F | UAG-SN1 | 600 | 60 | 4 | 4 |  | 1250000 | Bangkok | แขวงทุ่งสองห้อง | 2020-11-13 | 2020-11-20 | Finished | [34 empty] | 2020-11-13 | 2020-11-21 | 2020-11-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-13 | 2020-12-15 | 2020-12-01 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 2021-08-20 | 2021-08-20 | Finished |  |  | 2021-08-30 | 2021-08-20 | Finished | [10 empty] | 20 | 2021-01-15 | 2000-01-01 | 2021-01-15 | Finished | [14 empty] | 25 | 2021-09-17 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-08-19 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2020-11-21 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 64 | 4 | 16 | 84 | 82.39 | Red |  |  | 20013562 | 2020-11-13 |  |  |  | HDME001043 | 2020-11-21
TAJ0860-TH | HET | 61000887 | Install | เลยสัญญา HO | - | TH209182 | Show Room Honda | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2020-07-21 | 2020-11-20 | 2020-12-21 | 2021-09-22 | P-1000-CO60W1,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 900000 | Samut Prakan | ตำบลเทพารักษ์ | 2020-11-21 | 2021-02-22 | Finished | [34 empty] | 2020-11-20 | 2020-11-21 | 2020-11-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-22 | 2021-03-12 | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-09 | Finished |  |  | 100 | [41 empty] | 2021-03-09 | 2021-09-03 | 2021-09-03 | Finished |  |  | 2021-10-01 | [12 empty] | 0 | 2021-03-11 | 2000-01-01 | 2021-03-11 | Finished | [14 empty] | 25 | 2021-09-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-19 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-11-21 | Finished |  |  | 2020-11-21 | Finished |  |  | 2020-11-23 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Red |  |  | 20013605 | 2020-11-20 |  |  |  | HDME001045 | 2020-11-21
TEB0157-TH | HET | 61000888 | HO | ส่งมอบแล้ว | - | TH209212 | Baan Baan | H1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-08-04 | 2020-11-04 | 2020-12-04 | 2021-05-03 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 914850 | Bangkok | แขวงจอมพล เขตจตุจักร | 2020-12-04 | [36 empty] | 2020-11-04 | 2020-12-16 | 2020-12-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-04 | 2020-11-14 | 2021-02-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-13 | Finished |  |  | 2021-02-15 | Finished |  |  | 100 | [41 empty] | 2021-02-15 | 2021-03-20 | 2021-03-20 | Finished |  |  | 2021-03-30 | 2021-03-20 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | 2021-02-19 | 2021-07-07 | 2021-02-19 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-07-07 | Finished |  |  | 100 | 2021-05-03 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2020-08-19 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013705 | 2020-10-20 |  |  |  | HDME001071 | 2020-12-16 | QC Passed
TEB0158-TH | HET | 61000888 |  | เลยสัญญา HO | - | TH209212 | Baan Baan | H2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-08-04 | 2020-11-04 | 2021-07-01 | 2021-09-19 | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 914850 | Bangkok | แขวงจอมพล เขตจตุจักร | 2021-10-01 | [36 empty] | 2021-10-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-10-11 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-19 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-08-19 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2022-07-01 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20013705 | 2021-05-17
TEB0159-TH | HET | 61000888 |  | ยังอยู่ในสัญญา HO | - | TH209212 | Baan Baan | H3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-08-04 | 2020-11-04 | 2021-12-01 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 914850 | Bangkok | แขวงจอมพล เขตจตุจักร | 2021-11-01 | [36 empty] | 2021-10-01 | 1900-01-01 | [16 empty] | 2021-11-01 | 2021-11-11 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-19 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2021-10-28 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20013705 | 2021-10-17
TEB0160-TH | HET | 61000888 |  | ยังอยู่ในสัญญา HO | - | TH209212 | Baan Baan | H4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-08-04 | 2020-11-04 | 2022-07-10 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 914850 | Bangkok | แขวงจอมพล เขตจตุจักร | 2022-06-01 | [36 empty] | 2022-06-01 | 1900-01-01 | [16 empty] | 2022-06-01 | 2022-06-11 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-06-19 | [12 empty] | 0 | [18 empty] | 0 | 2022-06-25 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2022-05-28 | Finished | [6 empty] | 2022-07-01 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20013705 | 2022-05-17
TEB0161-TH | HET | 61000888 |  | ยังอยู่ในสัญญา HO | - | TH209212 | Baan Baan | H5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-08-04 | 2020-11-04 | 2022-10-01 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 914850 | Bangkok | แขวงจอมพล เขตจตุจักร | 2022-09-01 | [36 empty] | 2022-09-01 | 1900-01-01 | [16 empty] | 2022-09-01 | 2022-09-11 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-09-19 | [12 empty] | 0 | [18 empty] | 0 | 2022-09-25 | Working | [6 empty] | 2020-08-19 | Finished |  |  | 2022-08-28 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20013705 | 2022-08-17
TAJ0861-TH | HET | 61000889 | HO | ส่งมอบแล้ว | - | TH219015 | Chat Petch Park Condo | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-08-04 | 2021-02-04 | 2021-04-04 | 2021-07-12 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1123500 | Khon Kaen | ตำบลศิลา | 2021-01-21 | 2021-02-15 | Finished | [34 empty] | 2021-02-04 | 2021-02-09 | 2021-02-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-04 | 2021-03-06 | 2021-02-18 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-28 | Finished |  |  | 100 | [41 empty] | 2021-02-28 | 2021-06-19 | 2021-06-19 | Finished |  |  | 2021-02-15 | 2021-06-22 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-09 | Finished | [6 empty] | 90 | 2021-05-08 | Finished | POWER SUPPLY DELAY |  | 2021-06-30 | Finished |  |  | 2020-08-19 | Finished | [10 empty] | 2021-06-30 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-30 | Finished | [13 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20013651 | 2021-02-04 |  |  |  | HDME001128 | 2021-02-09
TAJ0862-TH | HET | 61000889 | HO | ส่งมอบแล้ว | - | TH219015 | Chat Petch Park Condo | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-08-04 | 2021-02-04 | 2021-04-04 | 2021-07-12 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1123500 | Khon Kaen | ตำบลศิลา | 2021-01-21 | 2021-02-15 | Finished | [34 empty] | 2021-02-04 | 2021-02-09 | 2021-02-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-04 | 2021-03-06 | 2021-02-18 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-28 | Finished |  |  | 100 | [41 empty] | 2021-02-28 | 2021-06-19 | 2021-06-19 | Finished |  |  | 2021-02-15 | 2021-06-22 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-12 | 2000-01-01 | 2021-05-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-09 | Finished | [6 empty] | 90 | 2021-05-08 | Finished | POWER SUPPLY DELAY |  | 2021-06-30 | Finished |  |  | 2020-08-19 | Finished | [10 empty] | 2021-06-30 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-30 | Finished | [13 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20013651 | 2021-02-04 |  |  |  | HDME001128 | 2021-02-09
TAK0863-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L1- | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | B-1000-2S90,90S/11F | UAG-SN1 | 1000 | 90 | 11 | 11 |  | 1947400 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-02-09 | 2021-02-09 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-02-03 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2021-06-16 | 2021-07-14 | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | pass |  |  |  |  | 673 | 94 | 32 | 20 | 819 | 0 | 0 | 0 | 2 | 2 | 99.76 | Blue |  |  | 20014426 | 2021-03-10 |  |  |  | HDME001129 | 2021-02-09 | QC Passed
TAK0864-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | B-1000-2S90,90S/11F | UAG-SN1 | 1000 | 90 | 11 | 11 |  | 1947400 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-02-09 | 2021-02-09 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-02-03 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2021-06-16 | 2000-01-01 | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | no pass |  |  |  |  | 673 | 94 | 32 | 20 | 819 | 0 | 0 | 0 | 2 | 2 | 99.76 | Blue |  |  | 20014426 | 2021-03-10 |  |  |  | HDME001129 | 2021-02-09
TAD0476-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | B-1000-2S90,90S/10F | B-II(VFI-II) | 1000 | 90 | 10 | 10 |  | 1904600 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-02-09 | 2021-02-09 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-02-03 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2021-06-16 | 2021-07-14 | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Blue |  |  | 20014426 | 2021-03-10 |  |  |  | HDME001129 | 2021-02-09 | QC Passed
TAD0477-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | B-1000-2S90,90S/10F | B-II(VFI-II) | 1000 | 90 | 10 | 10 |  | 1904600 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-02-09 | 2021-02-09 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-02-03 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2021-06-16 | 2000-01-01 | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | no pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Blue |  |  | 20014426 | 2021-03-10 |  |  |  | HDME001129 | 2021-02-09
TAC1817-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | VFI-1000-CO90,90S/10F | VFI-II | 1000 | 90 | 10 | 10 |  | 1797600 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-02-09 | 2021-02-09 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-02-10 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2021-06-16 | 2021-07-14 | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Blue |  |  | 20014426 | 2021-03-10 |  |  |  | HDME001129 | 2021-02-09 | QC Passed
TAC1818-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | VFI-1000-CO90,90S/10F | VFI-II | 1000 | 90 | 10 | 10 |  | 1797600 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-02-09 | 2021-02-09 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-02-10 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2021-06-16 | 2021-07-14 | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-02-09 | Finished |  |  | 2021-02-09 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Blue |  |  | 20014426 | 2021-03-10 |  |  |  | HDME001129 | 2021-02-09 | QC Passed
TAC1819-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | VFI-1600-CO90,90S/10F | VFI-II | 1600 | 90 | 10 | 10 |  | 2354000 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2020-12-28 | 2021-02-25 | 2021-02-27 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-03-01 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | 2021-06-16 | 2000-01-01 | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 90 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | no pass |  |  |  |  | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Blue |  |  | 20013731 | 2021-03-10 |  |  |  | HDME001143 | 2021-02-25
TEC0182-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | DF-200S-B30,30S/6F | DF | 200 | 30 | 6 | 6 |  | 417300 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-03-10 | 2021-03-01 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-20 | Finished |  |  | 100 | [41 empty] | 2021-03-20 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | [18 empty] | 0 | 2021-06-10 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-03-10 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | no qc |  |  |  |  | 283 | 0 | 24 | 0 | 307 | 0 | 0 | 24 | 0 | 24 | 92.18 | Blue |  |  | 20014431 | 2021-01-29 |  |  |  | HDME001160 | 2021-03-10
TEC0183-TH | HET | 61000890 | HO | ส่งมอบแล้ว | - | TH209223 | Out-Patient Bldg., Maharaj Nakhon Si Thammarat Hospital | L9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Jitphisut Piamsuktana-anan | 2020-08-10 | 2021-03-10 | 2021-07-10 |  | DT-100T-B30,30S/3F | DT | 100 | 30 | 3 | 3 |  | 374500 | Nakhon Si Thammarat | อำเภอเมือง | 2021-03-10 | 2021-03-10 | Finished | [34 empty] | 2021-03-10 | 2021-03-10 | 2021-03-01 | Finished | [14 empty] | 2021-03-10 | 2021-04-18 | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-20 | Finished |  |  | 100 | [41 empty] | 2021-03-20 | 2021-05-26 | 2021-05-26 | Finished |  |  | 2021-05-25 | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-06 | Finished |  |  | 100 | [18 empty] | 0 | 2021-06-21 | Finished | POWER SUPPLY DELAY |  | 2021-06-04 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-06-04 | Finished | [6 empty] | 2021-03-10 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-06-04 | Finished | [13 empty] | no qc |  |  |  |  | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Blue |  |  | 20014431 | 2021-01-29 |  |  |  | HDME001160 | 2021-03-10
TBL0384-TH | HET | 61000892 | HO | ส่งมอบแล้ว | - | TH209213 | Student Residence Group 1 Chiang Mai University | AB | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-08-11 | 2021-01-11 | 2021-03-11 | 2021-08-12 | OUG-630-2S60,60S/5F | OUG-ON1 | 630 | 60 | 5 | 5 |  | 1310750 | Chiang Mai | อ.เมืองเชียงใหม่ | 2021-01-11 | 2021-01-11 | Finished | [34 empty] | 2021-01-11 | 2021-01-12 | 2021-01-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-15 | 2021-02-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-25 | 2021-06-25 | Finished |  |  | 2021-06-27 | 2021-06-25 | Finished |  |  | 2021-06-27 | Finished |  |  | 2021-06-30 | Finished |  |  | 100 | 2021-02-22 | 2000-01-01 | 2021-02-22 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-30 | Finished |  |  | 2020-08-26 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-01-12 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | no pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013775 | 2021-01-11 |  |  |  | HDME001088 | 2021-01-12
TBL0385-TH | HET | 61000892 | HO | ส่งมอบแล้ว | - | TH209213 | Student Residence Group 1 Chiang Mai University | CD | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-08-11 | 2021-01-11 | 2021-03-11 | 2021-08-12 | OUG-630-2S60,60S/5F | OUG-ON1 | 630 | 60 | 5 | 5 |  | 1310750 | Chiang Mai | อ.เมืองเชียงใหม่ | 2021-01-11 | 2021-01-11 | Finished | [34 empty] | 2021-01-11 | 2021-01-12 | 2021-01-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-15 | 2021-02-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-26 | 2021-06-26 | Finished |  |  | 2021-06-27 | 2021-06-26 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-03-31 | 2021-08-24 | 2021-03-31 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-30 | Finished |  |  | 2020-08-26 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-01-12 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013775 | 2021-01-11 |  |  |  | HDME001088 | 2021-01-12 | QC Passed
TBL0386-TH | HET | 61000892 | HO | ส่งมอบแล้ว | - | TH209213 | Student Residence Group 1 Chiang Mai University | EF | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-08-11 | 2021-01-11 | 2021-03-11 | 2021-08-12 | OUG-630-2S60,60S/5F | OUG-ON1 | 630 | 60 | 5 | 5 |  | 1310750 | Chiang Mai | อ.เมืองเชียงใหม่ | 2021-01-11 | 2021-01-11 | Finished | [34 empty] | 2021-01-11 | 2021-01-12 | 2021-01-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-01 | 2021-02-15 | 2021-03-22 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | [41 empty] | 2021-03-31 | 2021-06-27 | 2021-06-27 | Finished |  |  | 2021-07-27 | 2021-06-27 | Finished |  |  | 2021-07-01 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-03-31 | 2021-08-24 | 2021-03-31 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-30 | Finished |  |  | 2020-08-26 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-01-12 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013775 | 2021-01-11 |  |  |  | HDME001088 | 2021-01-12 | QC Passed
TBL0387-TH | HET | 61000892 | HO | ส่งมอบแล้ว | - | TH209213 | Student Residence Group 1 Chiang Mai University | GH | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-08-11 | 2021-01-11 | 2021-03-11 | 2021-08-12 | OUG-630-2S60,60S/5F | OUG-ON1 | 630 | 60 | 5 | 5 |  | 1310750 | Chiang Mai | อ.เมืองเชียงใหม่ | 2021-01-11 | 2021-01-11 | Finished | [34 empty] | 2021-01-11 | 2021-01-12 | 2021-01-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-01 | 2021-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-28 | 2021-06-28 | Finished |  |  | 2021-07-27 | 2021-06-28 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-07-08 | Finished |  |  | 100 | 2021-03-31 | 2021-08-24 | 2021-03-31 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-30 | Finished |  |  | 2020-08-26 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-01-12 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | pass |  |  |  |  | 490 | 86 | 16 | 16 | 608 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013775 | 2021-01-11 |  |  |  | HDME001088 | 2021-01-12 | QC Passed
TAJ0866-TH | HET | 61000893 | HO | ส่งมอบแล้ว | - | TH209245 | Chiang Mai Agricultural Research and Development Center | Bld.1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-07-23 | 2021-01-23 | 2021-04-23 | 2021-10-25 | P-1000-CO60W1,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 1070000 | Chiang Mai | อำเภอเมืองเชียงใหม่ | 2021-01-23 | 2021-01-23 | Finished | [34 empty] | 2021-01-22 | 2021-02-03 | 2021-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-30 | 2021-02-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-07-15 | 2021-07-15 | Finished |  |  | 2021-07-20 | 2021-07-19 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-25 | Finished |  |  | 100 | 2021-03-31 | 2021-08-24 | 2021-03-31 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-22 | Finished |  |  | 2020-08-25 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-02-03 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-08-22 | Finished | [13 empty] | pass |  |  |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013778 | 2021-01-22 |  |  |  | HDME001115 | 2021-02-03 | QC Passed
TAJ0867-TH | HET | 61000894 | HO | ส่งมอบแล้ว | - | TH209246 | ศูนย์วิจัยฯ โครงการหลวง อ.ปฏิบัติการ 1 | Bld.2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-07-23 | 2021-01-23 | 2021-04-23 | 2021-07-24 | P-1050-CO60W1,60S/2F | UAG-SN1 | 1050 | 60 | 2 | 2 |  | 1070000 | Chiang Mai | อำเภอเมืองเชียงใหม่ | 2021-01-23 | 2021-01-23 | Finished | [34 empty] | 2021-01-22 | 2021-02-03 | 2021-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-15 | 2021-03-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-06-21 | 2021-06-21 | Finished |  |  | 2021-06-23 | 2021-06-21 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-24 | Finished |  |  | 100 | 2021-03-31 | 2021-08-04 | 2021-03-31 | Finished |  |  | 2021-07-09 | Finished |  |  | 2021-07-09 | Finished |  |  | 2021-08-04 | Finished |  |  | 100 | 2021-08-05 | Finished | POWER SUPPLY DELAY |  | 2021-08-05 | Finished |  |  | 2020-08-27 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-02-03 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-08-05 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013779 | 2021-01-22 |  |  |  | HDME001116 | 2021-02-03 | QC Passed
TBL0388-TH | HET | 61000895 | HO | ส่งมอบแล้ว | - | TH209244 | Chiang Mai Agricultural Research and Development Center | Bld.6(1) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-07-23 | 2021-01-23 | 2021-04-23 | 2021-10-25 | OUG-1000-CO60,60S/2F | OUG-ON1 | 1000 | 60 | 2 | 2 |  | 1404500 | Chiang Mai | อำเภอเมืองเชียงใหม่ | 2021-01-23 | 2021-01-23 | Finished | [34 empty] | 2021-01-22 | 2021-02-03 | 2021-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-30 | 2021-02-15 | 1900-01-01 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-04-01 | Finished |  |  | 100 | [41 empty] | 2021-04-01 | 2021-07-15 | 2021-07-15 | Finished |  |  | 2021-07-20 | 2021-07-19 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-25 | Finished |  |  | 100 | 2021-03-31 | 2021-08-24 | 2021-03-31 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-22 | Finished |  |  | 2020-08-27 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-02-03 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-08-22 | Finished | [13 empty] | pass |  |  |  |  | 331 | 83 | 16 | 16 | 446 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013780 | 2021-01-22 |  |  |  | HDME001114 | 2021-02-03 | QC Passed
TAJ0868-TH | HET | 61000895 | HO | ส่งมอบแล้ว | - | TH209244 | Chiang Mai Agricultural Research and Development Center | Bld.6(2) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-07-23 | 2021-01-23 | 2021-04-23 | 2021-10-25 | P-1000-CO60W1,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 1110000 | Chiang Mai | อำเภอเมืองเชียงใหม่ | 2021-01-23 | 2021-01-23 | Finished | [34 empty] | 2021-01-22 | 2021-02-03 | 2021-02-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-15 | 2021-03-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-07-15 | 2021-07-15 | Finished |  |  | 2021-07-20 | 2021-07-16 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-03-31 | 2021-08-24 | 2021-03-31 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-08-30 | Finished | POWER SUPPLY DELAY |  | 2021-08-22 | Finished |  |  | 2020-08-27 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-02-03 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-08-22 | Finished | [13 empty] | pass |  |  |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013780 | 2021-01-22 |  |  |  | HDME001114 | 2021-02-03 | QC Passed
TFA1427-TH | HET | 61000896 | HO | ส่งมอบแล้ว | - | TH209248 | Seacon Square Srinakharin (Bridge) | ESC1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-07-31 | 2020-12-10 | 2021-01-15 |  | 1200TX-EN,R3.95M,D30 | TX-EN |  |  |  |  | 3950 | 1391000 | Bangkok | แขวงหนองบอน เขตประเวศ | 2020-12-09 | [20 empty] | 2020-12-09 | Finished | [14 empty] | 2020-12-10 | 2020-12-10 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-11 | 2021-01-01 | [41 empty] | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | 2020-12-18 | 2020-11-09 | 2020-11-09 | Finished |  |  | 2020-11-09 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-02-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-01-15 | Finished | POWER SUPPLY DELAY |  | 2020-12-30 | Finished |  |  | 2020-08-26 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 482 | 32 | 16 | 14 | 544 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013816 | 2020-11-25 |  |  |  | HDME001067 | 2020-12-09 | QC Passed
TFA1428-TH | HET | 61000896 | HO | ส่งมอบแล้ว | - | TH209248 | Seacon Square Srinakharin (Bridge) | ESC2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 6 |  | 1 | Weerapoj Paijitvijarn | Phumiphat Siprajan | 2020-07-31 | 2020-12-10 | 2021-01-15 |  | 1200TX-EN,R3.95M,D30 | TX-EN |  |  |  |  | 3950 | 1391000 | Bangkok | แขวงหนองบอน เขตประเวศ | 2020-12-09 | [20 empty] | 2020-12-09 | Finished | [14 empty] | 2020-12-10 | 2020-12-10 | 2020-12-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-11 | 2021-01-01 | [41 empty] | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | 2020-12-18 | 2020-12-11 | 2020-12-11 | Finished |  |  | 2020-12-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-05-13 | 2021-01-18 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-18 | Finished | [6 empty] | 90 | 2021-01-15 | Finished | POWER SUPPLY DELAY |  | 2020-12-30 | Finished |  |  | 2020-08-26 | Finished | [18 empty] | 2020-12-09 | Finished |  |  | 2020-12-22 | Finished |  |  | 2020-12-28 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  | pass | 2021-02-08 | Finished |  |  | 482 | 32 | 16 | 14 | 544 | 0 | 0 | 0 | 1 | 1 | 99.82 | Blue |  |  | 20013816 | 2020-11-25 |  |  |  | HDME001067 | 2020-12-09 | QC Passed
TAJ0869-TH | HET | 61000897 | Test | เลยสัญญา HO | - | TH209239 | The Sixsense Sukhumvit 45 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2020-08-17 | 2021-01-17 | 2021-03-17 |  | P-1000-CO60W2,60S/6F | UAG-SN1 | 1000 | 60 | 6 | 6 |  | 1000000 | Bangkok | แขวงคลองตันเหนือ | 2021-06-20 | 2021-06-30 | Finished | [34 empty] | 2021-01-18 | 2021-06-19 | 2021-06-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-23 | 2021-07-14 | 2021-07-22 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 100 | [41 empty] | 2021-08-12 | 1900-01-01 | 2021-08-12 | Waiting | POWER SUPPLY DELAY |  | 2021-08-24 | [12 empty] | 0 | 2021-08-18 | 2000-01-01 | 2021-08-18 | Finished | [14 empty] | 25 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-09-01 | Finished | [18 empty] | 2021-06-19 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-06-21 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 6 | 16 | 104 | 81.88 | Red |  |  | 20013923 | 2021-02-10
TAD0478-TH | HET | 61000898 | HO | ส่งมอบแล้ว | - | TH209143 | โรงพยาบาลธรรมศาสตร์ | L1 (Kittiwattana Bld.) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2020-08-18 | 2020-11-16 | 2021-03-15 |  | B-1000-2S90,90S/7F | B-II(VFI-II) | 1000 | 90 | 7 | 7 |  | 2033000 | Pathum Thani | อำเภอคลองหลวง | 2020-11-05 | 2020-11-25 | Finished | [34 empty] | 2020-11-30 | 2020-11-16 | 2020-11-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-16 | 2021-03-05 | 2021-02-18 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | [41 empty] | 2021-03-22 | 2021-03-25 | 2021-03-25 | Finished |  |  | 2021-02-26 | 2021-03-26 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 100 | 2021-04-02 | 2021-07-02 | 2021-04-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-05-15 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-05-21 | Finished |  |  | 2020-09-14 | Finished | [10 empty] | 2021-05-21 | Finished | [6 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013943 | 2020-11-30 |  |  |  | HDME001047 | 2020-11-25 | QC Passed
TAD0482-TH | HET | 61000898 | HO | ส่งมอบแล้ว | - | TH209143 | โรงพยาบาลธรรมศาสตร์ | L10 (Dula Sopak Bld.) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2020-08-18 | 2020-11-16 | 2021-03-15 |  | B-1000-2S90,90S/11F | B-II(VFI-II) | 1000 | 90 | 11 | 11 |  | 2300500 | Pathum Thani | อำเภอคลองหลวง | 2020-11-05 | 2020-11-25 | Finished | [34 empty] | 2020-11-30 | 2020-11-16 | 2020-11-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-16 | 2021-03-05 | 2021-02-10 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | [41 empty] | 2021-03-22 | 2021-03-23 | 2021-03-23 | Finished |  |  | 2021-03-23 | 2021-03-23 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 100 | 2021-04-02 | 2021-07-15 | 2021-04-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-15 | Finished |  |  | 100 | 2021-05-15 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-05-21 | Finished |  |  | 2020-09-14 | Finished | [10 empty] | 2021-05-21 | Finished | [6 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013943 | 2020-11-30 |  |  |  | HDME001047 | 2020-11-25 | QC Passed
TAD0479-TH | HET | 61000898 | HO | ส่งมอบแล้ว | - | TH209143 | โรงพยาบาลธรรมศาสตร์ | L2 (Kittiwattana Bld.) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2020-08-18 | 2020-11-16 | 2021-03-15 |  | B-1000-2S90,90S/7F | B-II(VFI-II) | 1000 | 90 | 7 | 7 |  | 2033000 | Pathum Thani | อำเภอคลองหลวง | 2020-11-05 | 2020-11-25 | Finished | [34 empty] | 2020-11-30 | 2020-11-16 | 2020-11-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-16 | 2021-03-05 | 2021-02-18 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-07 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | [41 empty] | 2021-03-22 | 2021-03-25 | 2021-03-25 | Finished |  |  | 2021-02-26 | 2021-03-26 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 100 | 2021-04-02 | 2021-07-02 | 2021-04-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-05-15 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-05-21 | Finished |  |  | 2020-09-14 | Finished | [10 empty] | 2021-05-21 | Finished | [6 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013943 | 2020-11-30 |  |  |  | HDME001047 | 2020-11-25 | QC Passed
TAD0480-TH | HET | 61000898 | HO | ส่งมอบแล้ว | - | TH209143 | โรงพยาบาลธรรมศาสตร์ | L4 (Kittiwattana Bld.) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2020-08-18 | 2020-11-16 | 2021-03-15 |  | B-1000-2S90,90S/7F | B-II(VFI-II) | 1000 | 90 | 7 | 7 |  | 2033000 | Pathum Thani | อำเภอคลองหลวง | 2020-11-05 | 2020-11-25 | Finished | [34 empty] | 2020-11-30 | 2020-11-16 | 2020-11-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-16 | 2021-03-05 | 2021-02-01 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-20 | Finished |  |  | 100 | [41 empty] | 2021-02-20 | 2021-02-22 | 2021-02-22 | Finished |  |  | 2021-02-26 | 2021-02-24 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 100 | 2021-04-02 | 2021-07-02 | 2021-04-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-02 | Finished |  |  | 100 | 2021-05-15 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-05-21 | Finished |  |  | 2020-09-14 | Finished | [10 empty] | 2021-05-21 | Finished | [6 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013943 | 2020-11-30 |  |  |  | HDME001047 | 2020-11-25 | QC Passed
TAD0481-TH | HET | 61000898 | HO | ส่งมอบแล้ว | - | TH209143 | โรงพยาบาลธรรมศาสตร์ | L9 (Dula Sopak Bld.) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2020-08-18 | 2020-11-16 | 2021-03-15 |  | B-1000-2S90,90S/11F | B-II(VFI-II) | 1000 | 90 | 11 | 11 |  | 2300500 | Pathum Thani | อำเภอคลองหลวง | 2020-11-05 | 2020-11-25 | Finished | [34 empty] | 2020-11-30 | 2020-11-16 | 2020-11-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-16 | 2021-03-05 | 2021-02-10 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 100 | [41 empty] | 2021-03-22 | 2021-03-23 | 2021-03-23 | Finished |  |  | 2021-03-23 | 2021-03-23 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 100 | 2021-04-02 | 2021-07-15 | 2021-04-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-15 | Finished |  |  | 100 | 2021-05-15 | Finished | INSTALLATION DEFECT RECTIFICATION DELAY |  | 2021-05-21 | Finished |  |  | 2020-09-14 | Finished | [10 empty] | 2021-05-21 | Finished | [6 empty] | 2020-11-25 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20013943 | 2020-11-30 |  |  |  | HDME001047 | 2020-11-25 | QC Passed
TAJ0870-TH | HET | 61000899 | HO | ส่งมอบแล้ว | - | TH219016 | ศูนย์ราชการ จังหวัดนราธิวาส | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2021-01-15 | 2021-03-15 | 2021-07-15 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1498000 | Narathiwat | อำเภอเมืองนราธิวาส | 2021-01-15 | [36 empty] | 2021-01-15 | 2021-01-20 | 2021-01-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-15 | 2021-01-31 | 2021-02-04 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-08 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | [41 empty] | 2021-02-16 | 2021-06-11 | 2021-06-11 | Finished |  |  | 2021-05-01 | 2021-06-12 | Finished |  |  | 2021-07-11 | Finished |  |  | 2021-07-12 | Finished |  |  | 100 | 2021-02-22 | 2021-08-13 | 2021-02-22 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | 2021-07-15 | Finished | POWER SUPPLY DELAY |  | 2021-07-19 | Finished |  |  | 2020-10-07 | Finished | [10 empty] | 2021-07-12 | Finished | [6 empty] | 2021-01-20 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass |  |  |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014243 | 2021-01-15 |  |  |  | HDME001100 | 2021-01-20 | QC Passed
TAK0871-TH | HET | 61000900 | HO | ส่งมอบแล้ว | - | TH209249 | Pluakdaeng Hospital | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-08-19 | 2020-11-17 | 2020-12-17 | 2021-06-01 | B-1000-2S60,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 1100000 | Rayong | จังหวัดระยอง | 2020-12-17 | 2020-12-17 | Finished | [34 empty] | 2020-11-25 | 2020-11-25 | 2020-11-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-26 | 2020-12-07 | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-18 | Finished |  |  | 100 | [41 empty] | 2020-12-18 | 2020-12-11 | 2020-12-11 | Finished |  |  | 2020-12-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-26 | 2021-04-01 | 2021-03-26 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 90 | 2021-03-20 | Finished | POWER SUPPLY DELAY |  | 2021-04-12 | Finished |  |  | 2020-09-14 | Finished | [10 empty] | 2021-04-12 | Finished | [6 empty] | 2020-11-26 | Finished |  |  | 2020-11-26 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-04-12 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  | pass | 2021-04-19 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 1 | 1 | 99.74 | Blue |  |  | 20013958 | 2020-11-25 |  |  |  | HDME001048 | 2020-11-26 | QC Passed
TAJ0872-TH | HET | 61000901 | HO | ส่งมอบแล้ว | - | TH209250 | Parking Building @Loeihospital | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-08-13 | 2020-11-27 | 2020-12-28 | 2021-02-20 | P-750-CO90,90S/10F | UAG-SN1 | 750 | 90 | 10 | 10 |  | 1391000 | Loei | ตำบลกุดป่อง | 2020-11-13 | 2020-11-28 | Finished | [34 empty] | 2020-11-27 | 2020-11-27 | 2020-11-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-27 | 2020-12-27 | 2020-11-28 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-04 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-18 | Finished |  |  | 2020-12-23 | Finished |  |  | 100 | [41 empty] | 2020-12-23 | 2021-01-11 | 2021-01-11 | Finished |  |  | 2020-12-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-28 | 2000-01-01 | 2020-12-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-02-22 | Finished | [6 empty] | 90 | 2020-12-19 | Finished | CONSTRUCTION DELAY |  | 2021-02-15 | Finished |  |  | 2020-09-14 | Finished | [18 empty] | 2020-11-27 | Finished |  |  | 2020-11-27 | Finished |  |  | 2020-11-30 | Finished |  |  | 2021-02-15 | Finished | [13 empty] | pass (defect) |  |  |  |  | 629 | 85 | 24 | 16 | 754 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20014028 | 2020-11-27 |  |  |  | HDME001049 | 2020-11-27
TAJ0873-TH | HET | 61000903 | HO | ส่งมอบแล้ว | - | TH209193 | Office Tai Peng Valve Manufacturing Co., Ltd. | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-08-24 | 2021-01-25 | 2021-03-25 | 2021-07-30 | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 909500 | Samut Prakan | หมู่ที่ 12 ถ.บางพลี-กิ่งแก้ว | 2021-01-20 | 2021-01-27 | Finished | [34 empty] | 2021-01-25 | 2021-01-25 | 2021-01-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-27 | 2021-03-05 | 2021-01-27 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-30 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-14 | Finished |  |  | 2021-02-16 | Finished |  |  | 100 | [41 empty] | 2021-02-16 | 2021-06-04 | 2021-06-04 | Finished |  |  | 2021-06-04 | 2021-06-04 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-13 | Finished |  |  | 100 | 2021-04-09 | 2021-08-31 | 2021-04-09 | Finished |  |  | 2021-07-14 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-31 | Finished |  |  | 100 | 2021-07-16 | Finished | POWER SUPPLY DELAY |  | 2021-07-16 | Finished |  |  | 2020-09-22 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-01-25 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass | 2021-09-09 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014003 | 2021-01-25 |  |  |  | HDME001106 | 2021-01-25 | QC Passed
TEB0204-TH | HET | 61000908 | HO | ยังอยู่ในสัญญา HO | - | TH209254 | Home Khun Pakjira | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2020-08-31 | 2020-11-30 | 2020-12-31 | 2021-10-31 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 2 | 2 |  | 700000 | Ranong | อำเภอกระบุรี | 2020-11-30 | 2021-03-20 | Finished | [34 empty] | 2020-11-15 | 2020-12-03 | 2020-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-01 | 2020-12-10 | 2021-03-30 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-01 | Finished |  |  | 100 | [41 empty] | 2021-03-01 | 2021-04-02 | 2021-04-02 | Finished |  |  | 2020-02-28 | 2021-04-02 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 100 | 2021-04-19 | 2000-01-01 | 2021-04-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-19 | Finished | [6 empty] | 90 | 2021-10-10 | Working | OTHERS | [5 empty] | 2020-09-14 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2020-12-03 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-15 | Finished | [17 empty] | no pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Green |  |  | 20014062 | 2020-11-15 |  |  |  | HDME001060 | 2020-12-03
TAJ0886-TH | HET | 61000915 | Install | ยังอยู่ในสัญญา HO | - | TH219025 | Home Khun Tanawin | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-10-16 | 2021-02-16 | 2021-04-16 | 2021-09-30 | P-600-CO60D,60S/3F | UAG-SN1 | 600 | 60 | 3 | 3 |  | 1070000 | Samut Prakan | อำเภอบางบ่อ | 2021-02-20 | 2021-02-22 | Finished | [34 empty] | 2021-02-16 | 2021-02-18 | 2021-02-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-22 | 2021-03-20 | 2021-02-22 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | [41 empty] | 2021-03-23 | 1900-01-01 | 2021-03-23 | Waiting | POWER SUPPLY DELAY |  | 2022-06-15 | [12 empty] | 0 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished | [14 empty] | 25 | 2022-07-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-25 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-02-18 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-19 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Orange |  |  | 20015279 | 2021-02-16 |  |  |  | HDME001137 | 2021-02-18
TAJ0885-TH | HET | 61000916 | HO | ส่งมอบแล้ว | - | TH209256 | พัฒนาพื้นที่เฉพาะชุมชนคลองแดน | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-11-11 | 2021-02-11 | 2021-03-11 | 2021-04-11 | P-750-CO60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1150000 | Nakhon Si Thammarat | อำเภอหัวไทร | 2021-02-10 | 2021-02-11 | Finished | [34 empty] | 2021-02-11 | 2021-02-17 | 2021-02-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-11 | 2021-03-11 | 2021-03-03 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-09 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 100 | [41 empty] | 2021-03-18 | 2021-03-19 | 2021-03-19 | Finished |  |  | 2021-03-01 | 2021-03-19 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-24 | Finished |  |  | 100 | 2021-03-18 | 2021-04-05 | 2021-03-18 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-05 | Finished | [6 empty] | 90 | 2021-03-11 | Finished | POWER SUPPLY DELAY |  | 2021-03-31 | Finished |  |  | 2020-11-25 | Finished | [18 empty] | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass | 2021-05-05 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 1 | 1 | 99.74 | Blue |  |  | 20015215 | 2021-02-11 |  |  |  | HDME001134 | 2021-02-17 | QC Passed
TAJ0891-TH | HET | 61000917 | HO | เลยสัญญา HO | - | TH209251 | Ocean Sand Phuket | A1-A2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | 2020-09-09 | 2021-03-09 | 2021-06-09 | 2021-09-09 | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 7 | 8 |  | 1251900 | Phuket | ตำบลเชิงทะเล | 2021-09-08 | [36 empty] | 2021-03-09 | 2021-03-09 | 2021-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-09 | 2021-10-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-05-14 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Red |  |  | 20014740 | 2021-05-10 |  |  |  | HDME001213 | 2021-05-14
TAJ0892-TH | HET | 61000917 | HO | เลยสัญญา HO | - | TH209251 | Ocean Sand Phuket | A3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | 2020-09-09 | 2021-03-09 | 2021-06-09 | 2021-09-09 | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1209100 | Phuket | ตำบลเชิงทะเล | 2021-08-08 | 2021-08-09 | Finished | [34 empty] | 2021-03-09 | 2021-03-09 | 2021-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-09 | 2021-09-09 | 2021-06-10 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-05-14 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 472 | 83 | 24 | 16 | 595 | 4.03 | Red |  |  | 20014740 | 2021-05-10 |  |  |  | HDME001213 | 2021-05-14
TAJ0893-TH | HET | 61000917 | HO | เลยสัญญา HO | - | TH209251 | Ocean Sand Phuket | B1-B2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | 2020-09-09 | 2021-03-09 | 2021-06-09 | 2021-09-09 | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1209100 | Phuket | ตำบลเชิงทะเล | 2021-08-08 | 2021-08-09 | Finished | [34 empty] | 2021-03-09 | 2021-03-09 | 2021-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-09 | 2021-09-09 | 2021-06-10 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-05-14 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 472 | 83 | 24 | 16 | 595 | 4.03 | Red |  |  | 20014740 | 2021-05-10 |  |  |  | HDME001213 | 2021-05-14
TFA1433-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | 1200TX-EN,R4.5M,D30 | SX-EN |  |  |  |  | 4500 | 949625 | Phayao | ตำบลบ้านต๋อม | 2020-10-15 | [20 empty] | 2020-11-05 | Finished | [14 empty] | 2020-09-28 | 2020-09-26 | 2020-09-26 | Finished | STORE AREA | [13 empty] | 2020-10-30 | 2020-11-25 | [41 empty] | 2020-11-06 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-11-06 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-26 | Finished |  |  | 100 | 2020-11-26 | 2021-08-25 | 2021-08-25 | Finished |  |  | 2021-08-25 | 2021-08-25 | Finished | [10 empty] | 20 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished |  |  | 2021-09-13 | Finished | [10 empty] | 50 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-30 | Finished | [22 empty] | 567 | 42 | 16 | 21 | 646 | 0 | 33 | 0 | 21 | 54 | 91.64 | Green | [7 empty] | HDME000987 | 2020-09-26
TFA1434-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | 1200TX-EN,R4.5M,D30 | SX-EN |  |  |  |  | 4500 | 949625 | Phayao | ตำบลบ้านต๋อม | 2020-10-15 | [20 empty] | 2020-11-05 | Finished | [14 empty] | 2020-09-28 | 2020-09-26 | 2020-09-26 | Finished | STORE AREA | [13 empty] | 2020-10-30 | 2020-11-25 | [41 empty] | 2020-11-06 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-07 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-22 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-11-27 | Finished |  |  | 100 | 2020-11-27 | 2021-08-25 | 2021-08-25 | Finished |  |  | 2021-08-25 | 2021-08-26 | Finished | [10 empty] | 20 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished |  |  | 2021-09-13 | Finished | [10 empty] | 50 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-30 | Finished | [22 empty] | 567 | 42 | 16 | 21 | 646 | 0 | 33 | 0 | 21 | 54 | 91.64 | Green | [7 empty] | HDME000987 | 2020-09-26
TFA1435-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | 1200TX-EN,R4.5M,D30 | SX-EN |  |  |  |  | 4500 | 949625 | Phayao | ตำบลบ้านต๋อม | 2020-10-15 | [20 empty] | 2020-11-05 | Finished | [14 empty] | 2020-09-28 | 2020-09-26 | 2020-09-26 | Finished | STORE AREA | [13 empty] | 2020-10-30 | 2020-11-25 | [41 empty] | 2020-11-06 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-08 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-11-28 | Finished |  |  | 100 | 2020-11-28 | 2021-08-26 | 2021-08-26 | Finished |  |  | 2021-08-25 | 2021-08-27 | Finished | [10 empty] | 20 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished |  |  | 2021-09-13 | Finished | [10 empty] | 50 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-30 | Finished | [22 empty] | 567 | 42 | 16 | 21 | 646 | 0 | 33 | 0 | 21 | 54 | 91.64 | Green | [7 empty] | HDME000987 | 2020-09-26
TFA1436-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | ES4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | 1200TX-EN,R4.5M,D30 | SX-EN |  |  |  |  | 4500 | 949625 | Phayao | ตำบลบ้านต๋อม | 2020-10-15 | [20 empty] | 2020-11-05 | Finished | [14 empty] | 2020-09-28 | 2020-09-26 | 2020-09-26 | Finished | STORE AREA | [13 empty] | 2020-10-30 | 2020-11-25 | [41 empty] | 2020-11-06 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-09 | Finished |  |  | 2020-11-24 | Finished |  |  | 2020-11-23 | Finished |  |  | 2020-11-25 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-11-29 | Finished |  |  | 100 | 2020-11-29 | 2021-08-28 | 2021-08-28 | Finished |  |  | 2021-08-25 | 2021-08-28 | Finished | [10 empty] | 20 | 2020-12-10 | 2000-01-01 | 2020-12-10 | Finished |  |  | 2021-09-13 | Finished | [10 empty] | 50 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-09-26 | Finished |  |  | 2020-09-26 | Finished |  |  | 2020-09-30 | Finished | [22 empty] | 567 | 42 | 16 | 21 | 646 | 0 | 33 | 0 | 21 | 54 | 91.64 | Green | [7 empty] | HDME000987 | 2020-09-26
TEC0187-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | DF1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | DF-300S-B15,15S/4F | DF | 300 | 15 | 4 | 4 |  | 374500 | Phayao | ตำบลบ้านต๋อม | 2021-01-15 | 2021-02-18 | Finished | [34 empty] | 2020-09-28 | 2020-11-20 | 2020-11-20 | Finished | STORE AREA | [13 empty] | 2021-01-15 | 2021-03-25 | 2021-03-25 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 100 | [41 empty] | 2021-03-31 | 1900-01-01 | 2021-03-31 | Waiting | POWER SUPPLY DELAY |  | 2021-10-29 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Green |  |  | 20014154 | 2020-09-28 |  |  |  | HDME001042 | 2020-11-20
TEC0188-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | DF2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | DF-300S-B15,15S/2F | DF | 300 | 15 | 2 | 2 |  | 321000 | Phayao | ตำบลบ้านต๋อม | 2021-01-15 | 2021-02-18 | Finished | [34 empty] | 2020-09-28 | 2020-11-20 | 2020-11-20 | Finished | STORE AREA | [13 empty] | 2021-01-15 | 2021-03-25 | 2021-03-28 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-28 | Finished |  |  | 100 | [41 empty] | 2021-03-28 | 1900-01-01 | 2021-03-28 | Waiting | POWER SUPPLY DELAY |  | 2021-10-29 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-11-20 | Finished |  |  | 2020-11-20 | Finished |  |  | 2020-11-23 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Green |  |  | 20014154 | 2020-09-28 |  |  |  | HDME001042 | 2020-11-20
TAD0489-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | B-1000-2S60,60S/6F | B-II(VFI-II) | 1000 | 60 | 6 | 6 |  | 1444500 | Phayao | ตำบลบ้านต๋อม | 2021-01-15 | 2021-02-18 | Finished | [34 empty] | 2020-09-28 | 2020-10-15 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-01-15 | 2021-01-25 | 2021-02-20 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | [41 empty] | 2021-03-25 | 2021-08-28 | 2021-08-28 | Finished |  |  | 2021-08-25 | 2021-08-29 | Finished | [10 empty] | 20 | 2021-07-09 | 2000-01-01 | 2021-07-09 | Finished | [14 empty] | 25 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 583 | 91 | 24 | 16 | 714 | 0 | 72 | 6 | 16 | 94 | 86.83 | Green | [7 empty] | HDME001009 | 2020-10-15
TAD0490-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | B-1000-2S60,60S/6F | B-II(VFI-II) | 1000 | 60 | 6 | 6 |  | 1444500 | Phayao | ตำบลบ้านต๋อม | 2021-01-15 | 2021-02-18 | Finished | [34 empty] | 2020-09-28 | 2020-10-15 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-01-15 | 2021-01-25 | 2021-02-20 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | [41 empty] | 2021-03-25 | 2021-08-29 | 2021-08-29 | Finished |  |  | 2021-08-25 | 2021-08-30 | Finished | [10 empty] | 20 | 2021-07-09 | 2000-01-01 | 2021-07-09 | Finished | [14 empty] | 25 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 583 | 91 | 24 | 16 | 714 | 0 | 72 | 6 | 16 | 94 | 86.83 | Green | [7 empty] | HDME001009 | 2020-10-15
TAD0491-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | B-1000-2S60,60S/6F | B-II(VFI-II) | 1000 | 60 | 6 | 6 |  | 1444500 | Phayao | ตำบลบ้านต๋อม | 2021-01-15 | 2021-02-18 | Finished | [34 empty] | 2020-09-28 | 2020-10-15 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-01-15 | 2021-02-05 | 2021-02-20 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-25 | Finished |  |  | 100 | [41 empty] | 2021-03-25 | 2021-08-30 | 2021-08-30 | Finished |  |  | 2021-08-25 | 2021-08-31 | Finished | [10 empty] | 20 | 2021-07-09 | 2000-01-01 | 2021-07-09 | Finished | [14 empty] | 25 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 583 | 91 | 24 | 16 | 714 | 0 | 72 | 6 | 16 | 94 | 86.83 | Green | [7 empty] | HDME001009 | 2020-10-15
TAD0492-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | B-1000-2S90,90S/7F | B-II(VFI-II) | 1000 | 90 | 7 | 7 |  | 1498000 | Phayao | ตำบลบ้านต๋อม | 2021-01-15 | 2021-02-18 | Finished | [34 empty] | 2020-09-28 | 2020-10-15 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-02-15 | 2021-03-15 | 2021-03-02 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-12 | Finished |  |  | 100 | [41 empty] | 2021-06-12 | 2021-08-31 | 2021-08-31 | Finished |  |  | 2021-08-25 | 2021-09-01 | Finished | [10 empty] | 20 | 2021-07-09 | 2000-01-01 | 2021-07-09 | Finished | [14 empty] | 25 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 638 | 92 | 24 | 16 | 770 | 0 | 73 | 6 | 16 | 95 | 87.66 | Green | [7 empty] | HDME001009 | 2020-10-15
TAD0493-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | B-1000-2S90,90S/7F | B-II(VFI-II) | 1000 | 90 | 7 | 7 |  | 1498000 | Phayao | ตำบลบ้านต๋อม | 2021-01-15 | 2021-02-18 | Finished | [34 empty] | 2020-09-28 | 2020-10-15 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2021-02-15 | 2021-03-15 | 2021-03-02 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-12 | Finished |  |  | 100 | [41 empty] | 2021-06-12 | 2021-09-01 | 2021-09-01 | Finished |  |  | 2021-08-29 | 2021-09-02 | Finished | [10 empty] | 20 | 2021-07-09 | 2000-01-01 | 2021-07-09 | Finished | [14 empty] | 25 | 2021-12-27 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 638 | 92 | 24 | 16 | 770 | 0 | 73 | 6 | 16 | 95 | 87.66 | Green | [7 empty] | HDME001009 | 2020-10-15
TAD0494-TH | HET | 61000921 | Install | ยังอยู่ในสัญญา HO | - | TH209227 | Phayao Hospital | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-08-25 | 2020-09-28 | 2021-02-28 | 2021-11-02 | B-1000-2S90,90S/7F | B-II(VFI-II) | 1000 | 90 | 7 | 7 |  | 1498000 | Phayao | ตำบลบ้านต๋อม | 2020-10-15 | 2020-11-25 | Finished | [34 empty] | 2020-09-28 | 2020-10-15 | 2020-10-15 | Finished | STORE AREA | [13 empty] | 2020-10-30 | 2020-12-10 | 2020-11-25 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-05-02 | Finished |  |  | 2020-05-03 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-11-30 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-05-03 | Finished |  |  | 2020-12-01 | Finished |  |  | 2020-12-02 | Finished |  |  | 100 | [41 empty] | 2020-12-02 | 1900-01-01 | 2020-12-02 | Waiting | POWER SUPPLY DELAY |  | 2021-10-29 | [12 empty] | 0 | 2021-07-09 | 2000-01-01 | 2021-07-09 | Finished | [14 empty] | 25 | 2022-02-22 | Working | CONTRACT CANCELLATION | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-10-15 | Finished |  |  | 2020-10-15 | Finished |  |  | 2020-10-16 | Finished | [22 empty] | 638 | 92 | 24 | 16 | 770 | 0 | 92 | 6 | 16 | 114 | 85.19 | Green | [7 empty] | HDME001009 | 2020-10-15
TEB0205-TH | HET | 61000923 | HO | ส่งมอบแล้ว | - | TH209162 | Kensington Place kaoyai | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-09-03 | 2020-11-23 | 2020-12-20 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 845300 | Nakhon Ratchasima | อำเภอปากช่อง | 2020-11-09 | [36 empty] | 2020-11-18 | 2020-12-02 | 2020-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-23 | 2020-12-23 | 2020-12-02 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 1900-01-01 | 2020-12-14 | Waiting | POWER SUPPLY DELAY |  | 2021-02-03 | 2021-03-10 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-16 | Finished |  |  | 100 | 2021-05-13 | 2021-02-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-02-07 | Finished | DELIVERY DELAY |  | 2020-12-28 | Finished |  |  | 2020-10-21 | Finished | [18 empty] | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  | pass | 2021-04-09 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014063 | 2020-11-18 |  |  |  | HDME001056 | 2020-12-02 | QC Passed
TEB0206-TH | HET | 61000923 | HO | ส่งมอบแล้ว | - | TH209162 | Kensington Place kaoyai | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-09-03 | 2020-11-23 | 2020-12-20 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 845300 | Nakhon Ratchasima | อำเภอปากช่อง | 2020-11-09 | [36 empty] | 2020-11-18 | 2020-12-02 | 2020-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-23 | 2020-12-23 | 2020-12-02 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 1900-01-01 | 2020-12-14 | Waiting | POWER SUPPLY DELAY |  | 2021-02-03 | 2021-03-11 | Finished |  |  | 2021-03-14 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2021-05-13 | 2021-02-17 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-02-07 | Finished | DELIVERY DELAY |  | 2020-12-28 | Finished |  |  | 2020-10-21 | Finished | [18 empty] | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  | pass | 2021-04-09 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014063 | 2020-11-18 |  |  |  | HDME001056 | 2020-12-02 | QC Passed
TEB0207-TH | HET | 61000923 | HO | ส่งมอบแล้ว | - | TH209162 | Kensington Place kaoyai | 3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-09-03 | 2020-11-23 | 2020-12-20 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 845300 | Nakhon Ratchasima | อำเภอปากช่อง | 2020-11-09 | [36 empty] | 2020-11-18 | 2020-12-02 | 2020-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-23 | 2020-12-23 | 2020-12-02 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 2021-02-03 | 2021-02-03 | Finished |  |  | 2021-02-03 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2021-02-17 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-02-07 | Finished | DELIVERY DELAY |  | 2020-12-28 | Finished |  |  | 2020-10-21 | Finished | [18 empty] | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  | pass | 2021-04-09 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014063 | 2020-11-18 |  |  |  | HDME001056 | 2020-12-02 | QC Passed
TEB0208-TH | HET | 61000923 | HO | ส่งมอบแล้ว | - | TH209162 | Kensington Place kaoyai | 4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-09-03 | 2020-11-23 | 2020-12-20 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 845300 | Nakhon Ratchasima | อำเภอปากช่อง | 2020-11-09 | [36 empty] | 2020-11-18 | 2020-12-02 | 2020-12-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-11-23 | 2020-12-23 | 2020-12-02 | Finished |  |  | 2020-12-05 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-14 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 2021-02-03 | 2021-02-03 | Finished |  |  | 2021-02-03 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2020-12-10 | 2021-02-17 | 2020-12-10 | Finished |  |  | 2021-05-13 | Finished |  |  | 2020-01-04 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-02-07 | Finished | DELIVERY DELAY |  | 2020-12-28 | Finished |  |  | 2020-10-21 | Finished | [18 empty] | 2020-12-02 | Finished |  |  | 2020-12-02 | Finished |  |  | 2020-12-03 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  | pass | 2021-04-09 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014063 | 2020-11-18 |  |  |  | HDME001056 | 2020-12-02 | QC Passed
TAJ0895-TH | HET | 61000924 |  | ยังอยู่ในสัญญา HO | - | TH209262 | Showroom Ram164 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Thamnul Kongsar | 2020-09-01 | 2021-05-01 | 2021-09-01 | 2021-10-20 | P-1050-CO60W2,60S/4F | UAG-SN1 | 1050 | 60 | 4 | 4 |  | 925015 | Bangkok | แขวงหัวหมาก | 2021-12-15 | [36 empty] | 2021-11-30 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-15 | 2022-02-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-15 | Working | [6 empty] | 2020-09-17 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-11-15 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Yellow |  |  | 20014108 | 2021-04-30
TEB0209-TH | HET | 61000925 | HO | ยังอยู่ในสัญญา HO | - | TH209207 | Panara Thepharak | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-08-28 | 2020-11-27 | 2020-12-28 | 2021-10-01 | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 3 | 3 |  | 749000 | Samut Prakan | ต.บางปลา | 2020-11-27 | 2020-12-05 | Finished | [34 empty] | 2020-11-12 | 2020-12-03 | 2020-12-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-15 | 2020-12-30 | 2020-12-05 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-06 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-07 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-08 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-10 | Finished |  |  | 2020-12-11 | Finished |  |  | 100 | [41 empty] | 2020-12-11 | 1900-01-01 | 2020-12-11 | Waiting | POWER SUPPLY DELAY |  | 2021-09-30 | [12 empty] | 0 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished | [14 empty] | 25 | 2021-10-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2020-12-04 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-15 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 55 | 4 | 16 | 75 | 70.82 | Orange |  |  | 20014103 | 2020-11-12 |  |  |  | HDME001062 | 2020-12-04
TEB0210-TH | HET | 61000925 | Delivery | ยังอยู่ในสัญญา HO | - | TH209207 | Panara Thepharak | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-08-28 | 2020-11-27 | 2021-03-30 | 2021-11-01 | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 3 | 3 |  | 749000 | Samut Prakan | ต.บางปลา | 2021-09-15 | [36 empty] | 2020-11-12 | 2021-01-29 | 2021-02-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-09-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-10 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-09-22 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-01-29 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-04 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Green |  |  | 20014103 | 2021-01-12 |  |  |  | HDME001110 | 2021-01-29
TAD0495-TH | HET | 61000926 | HO | ส่งมอบแล้ว | - | TH219028 | อ.กองบัญชาการหน่วยข่าวกรองทางทหาร(ใหม่) | FL | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-08-31 | 2021-01-08 | 2021-02-28 | 2021-06-28 | B-1000-2S60,60S/6F | B-II(VFI-II) | 1000 | 60 | 6 | 6 |  | 1391000 | Bangkok | เขตดุสิต | 2020-12-21 | 2020-12-22 | Finished | [34 empty] | 2020-12-21 | 2020-12-21 | 2020-12-21 | Finished | [14 empty] | 2020-12-21 | 2021-01-30 | 2021-01-04 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-02-01 | Finished |  |  | 100 | [41 empty] | 2021-02-01 | 2021-04-07 | 2021-04-07 | Finished |  |  | 2021-04-05 | 2021-04-07 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-12 | 2021-08-10 | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-08-10 | Finished |  |  | 100 | 2021-06-28 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014215 | 2020-12-21 |  |  |  | HDME001074 | 2020-12-21 | QC Passed
TAC1828-TH | HET | 61000926 | HO | ส่งมอบแล้ว | - | TH219028 | อ.กองบัญชาการหน่วยข่าวกรองทางทหาร(ใหม่) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-08-31 | 2021-01-08 | 2021-02-28 | 2021-06-28 | VFI-900-CO60,60S/6F | VFI-II | 900 | 60 | 6 | 6 |  | 1190375 | Bangkok | เขตดุสิต | 2020-12-21 | 2020-12-22 | Finished | [34 empty] | 2020-12-21 | 2020-12-21 | 2020-12-21 | Finished | [14 empty] | 2020-12-21 | 2021-01-30 | 2021-01-04 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-02-01 | Finished |  |  | 100 | [41 empty] | 2021-02-01 | 2021-04-07 | 2021-04-07 | Finished |  |  | 2021-04-05 | 2021-04-07 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-12 | 2021-08-10 | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-08-10 | Finished |  |  | 100 | 2021-06-28 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014215 | 2020-12-21 |  |  |  | HDME001074 | 2020-12-21 | QC Passed
TAC1829-TH | HET | 61000926 | HO | ส่งมอบแล้ว | - | TH219028 | อ.กองบัญชาการหน่วยข่าวกรองทางทหาร(ใหม่) | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-08-31 | 2021-01-08 | 2021-02-28 | 2021-06-28 | VFI-900-CO60,60S/6F | VFI-II | 900 | 60 | 6 | 6 |  | 1190375 | Bangkok | เขตดุสิต | 2020-12-21 | 2020-12-22 | Finished | [34 empty] | 2020-12-21 | 2020-12-21 | 2020-12-21 | Finished | [14 empty] | 2020-12-21 | 2021-01-30 | 2021-01-04 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-10 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-02-01 | Finished |  |  | 100 | [41 empty] | 2021-02-01 | 2021-04-07 | 2021-04-07 | Finished |  |  | 2021-04-05 | 2021-04-07 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-12 | 2021-08-10 | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-08-10 | Finished |  |  | 100 | 2021-06-28 | Finished | POWER SUPPLY DELAY |  | 2021-05-31 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-05-31 | Finished | [6 empty] | 2020-12-21 | Finished |  |  | 2020-12-21 | Finished |  |  | 2020-12-22 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 583 | 91 | 24 | 16 | 714 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014215 | 2020-12-21 |  |  |  | HDME001074 | 2020-12-21 | QC Passed
TAJ0896-TH | HET | 61000927 | HO | ส่งมอบแล้ว | - | TH209208 | Home Khun Boonyasith Chokwatana | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-08-10 | 2020-11-10 | 2020-12-10 | 2021-01-10 | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 1465900 | Bangkok | เขตยานนาวา | 2020-12-07 | 2020-12-07 | Finished | [34 empty] | 2020-12-04 | 2020-12-04 | 2020-12-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-07 | 2020-12-17 | 2020-12-08 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-11 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-09 | Finished |  |  | 2020-12-13 | Finished |  |  | 2020-12-13 | Finished |  |  | 2020-12-13 | Finished |  |  | 2020-12-14 | Finished |  |  | 100 | [41 empty] | 2020-12-14 | 2020-11-09 | 2020-11-09 | Finished |  |  | 2020-11-09 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-01-11 | 2021-03-19 | 2021-01-11 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-03-19 | Finished |  |  | 100 | 2020-12-30 | Finished | CONSTRUCTION DELAY |  | 2020-12-30 | Finished |  |  | 2020-10-07 | Finished | [18 empty] | 2020-12-07 | Finished |  |  | 2020-12-15 | Finished |  |  | 2020-12-16 | Finished |  |  | 2020-12-30 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  |  | 2021-05-01 | Finished |  | pass | 2021-05-01 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014258 | 2020-12-04 |  |  |  | HDME001063 | 2020-12-07 | QC Passed
TAD0496-TH | HET | 61000928 | Install | เลยสัญญา HO | - | TH209263 | Cure-Heart Center-Cancer Center and Diagnose Building a | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-09-09 | 2020-12-30 | 2021-04-09 | 2021-09-15 | B-1000-2S90,90S/12F | B-II(VFI-II) | 1000 | 90 | 12 | 12 |  | 1961666.67 | Nakhon Phanom | อำเภอเมืองนครพนม | 2020-12-16 | 2020-12-30 | Finished | [34 empty] | 2021-01-04 | 2021-01-13 | 2021-01-13 | Finished | PAYMENT DELAY | [13 empty] | 2020-12-30 | 2021-09-29 | 2021-02-12 | Finished |  |  | 2021-02-17 | Finished | [10 empty] | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-26 | Working | [6 empty] | 2020-10-07 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 914 | 106 | 32 | 20 | 1072 | 228 | 106 | 32 | 20 | 386 | 63.99 | Red |  |  | 20014256 | 2021-01-04 |  |  |  | HDME001091 | 2021-01-13
TAD0497-TH | HET | 61000928 | Install | เลยสัญญา HO | - | TH209263 | Cure-Heart Center-Cancer Center and Diagnose Building a | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-09-09 | 2020-12-30 | 2021-04-09 | 2021-09-15 | B-1000-2S90,90S/12F | B-II(VFI-II) | 1000 | 90 | 12 | 12 |  | 1961666.67 | Nakhon Phanom | อำเภอเมืองนครพนม | 2020-12-16 | 2020-12-30 | Finished | [34 empty] | 2021-01-04 | 2021-01-13 | 2021-01-13 | Finished | PAYMENT DELAY | [13 empty] | 2020-12-30 | 2021-09-29 | 2021-02-12 | Finished |  |  | 2021-02-17 | Finished | [10 empty] | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-26 | Working | [6 empty] | 2020-10-07 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 914 | 106 | 32 | 20 | 1072 | 228 | 106 | 32 | 20 | 386 | 63.99 | Red |  |  | 20014256 | 2021-01-04 |  |  |  | HDME001091 | 2021-01-13
TAD0498-TH | HET | 61000928 | Install | เลยสัญญา HO | - | TH209263 | Cure-Heart Center-Cancer Center and Diagnose Building a | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-09-09 | 2020-12-30 | 2021-04-09 | 2021-09-15 | B-1000-2S90,90S/12F | B-II(VFI-II) | 1000 | 90 | 12 | 12 |  | 1961666.66 | Nakhon Phanom | อำเภอเมืองนครพนม | 2020-12-16 | 2020-12-30 | Finished | [34 empty] | 2021-01-04 | 2021-01-13 | 2021-01-13 | Finished | PAYMENT DELAY | [13 empty] | 2020-12-30 | 2021-09-29 | 2021-02-12 | Finished |  |  | 2021-02-17 | Finished | [10 empty] | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-25 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-26 | Working | [6 empty] | 2020-10-07 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-01-13 | Finished |  |  | 2021-01-13 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 914 | 106 | 32 | 20 | 1072 | 228 | 106 | 32 | 20 | 386 | 63.99 | Red |  |  | 20014256 | 2021-01-04 |  |  |  | HDME001091 | 2021-01-13
TAJ0897-TH | HET | 61000929 | HO | ยังอยู่ในสัญญา HO | - | TH209228 | Building 6 FL (@Prawet) | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2020-08-13 | 2020-12-14 | 2021-02-13 | 2021-10-28 | P-1000-CO60W2,60S/6F | UAG-SN1 | 1000 | 60 | 6 | 6 |  | 1230500 | Bangkok | แขวงประเวศ | 2021-09-15 | [36 empty] | 2020-12-23 | 2020-12-13 | 2021-01-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-16 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-28 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-01-11 | Finished |  |  | 2021-01-14 | Finished |  |  | 2021-01-25 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Green |  |  | 20014569 | 2020-12-23 |  |  |  | HDME001087 | 2021-01-11
TAD0499-TH | HET | 61000930 | HO | เลยสัญญา HO | - | TH219029 | Kabin Buri Hospital | EL1,EL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-09-17 | 2021-03-17 | 2021-05-17 | 2021-09-07 | B-1000-2S60,60S/4F | B-II(VFI-II) | 1000 | 60 | 4 | 4 |  | 1350000 | Phrachin Buri | อำเภอกบินทร์ | 2021-06-03 | 2021-03-17 | Finished | [34 empty] | 2021-03-17 | 2021-04-07 | 2021-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-17 | 2021-04-16 | 0 | Finished |  |  | 0 | Finished | [10 empty] | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 85 | [41 empty] | 1900-01-06 | 1900-01-01 | 1900-01-06 | Waiting | POWER SUPPLY DELAY |  | 2021-09-02 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-10-01 | Working | OTHERS | [5 empty] | 2020-12-23 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-04-07 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 70 | 90 | 4 | 16 | 180 | 69.7 | Red |  |  | 20014334 | 2021-03-17 |  |  |  | HDME001192 | 2021-04-07
TAD0500-TH | HET | 61000930 | HO | เลยสัญญา HO | - | TH219029 | Kabin Buri Hospital | EL1,EL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-09-17 | 2021-03-17 | 2021-05-17 | 2021-09-07 | B-1000-2S60,60S/4F | B-II(VFI-II) | 1000 | 60 | 4 | 4 |  | 1350000 | Phrachin Buri | อำเภอกบินทร์ | 2021-06-03 | 2021-03-17 | Finished | [34 empty] | 2021-03-17 | 2021-04-07 | 2021-04-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-17 | 2021-04-16 | 0 | Finished |  |  | 0 | Finished | [10 empty] | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 85 | [41 empty] | 1900-01-06 | 1900-01-01 | 1900-01-06 | Waiting | POWER SUPPLY DELAY |  | 2021-09-02 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-10-01 | Working | OTHERS | [5 empty] | 2020-12-23 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-04-07 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 70 | 90 | 4 | 16 | 180 | 69.7 | Red |  |  | 20014334 | 2021-03-17 |  |  |  | HDME001192 | 2021-04-07
TAJ0898-TH | HET | 61000931 | HO | ยังอยู่ในสัญญา HO | - | TH209264 | Home Khun Manut Chearavanont | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-09-21 | 2020-12-21 | 2021-02-21 | 2021-09-30 | P-600-CO60W,60S/5F | UAG-SN1 | 600 | 60 | 5 | 5 |  | 1070000 | Bangkok | แขวงคลองตันเหนือ | 2021-02-21 | 2021-02-15 | Finished | [34 empty] | 2020-12-21 | 2020-12-21 | 2020-12-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-15 | 2021-03-28 | 2021-02-15 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-28 | Finished |  |  | 100 | [41 empty] | 2021-03-28 | 2021-04-20 | 2021-04-20 | Finished |  |  | 2021-04-20 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-12 | 2021-07-02 | 2021-03-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-02 | Finished | [6 empty] | 90 | 2021-09-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-07 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2020-12-26 | Finished |  |  | 2020-12-27 | Finished |  |  | 2020-12-28 | Finished | [17 empty] | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 1 | 1 | 99.81 | Green |  |  | 20014335 | 2020-12-21 |  |  |  | HDME001081 | 2020-12-26 | QC Passed
TAJ0902-TH | HET | 61000933 | Install | ยังอยู่ในสัญญา HO | - | TH209265 | Andaz Resort Pattaya | E1-E01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-06-15 | 2020-12-15 | 2021-02-20 | 2021-10-15 | P-1600-CO60,60S/3F | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1538660 | Chon Buri | ตำบลนาจอมเทียน | 2021-02-02 | 2021-03-25 | Finished | [34 empty] | 2020-12-15 | 2020-12-15 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-17 | 2021-02-01 | 2021-03-26 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 1900-01-01 | 2021-04-09 | Waiting | POWER SUPPLY DELAY |  | 2021-09-24 | [12 empty] | 0 | 2021-05-18 | 2000-01-01 | 2021-05-18 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-22 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-08 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Green |  |  | 20014401 | 2020-12-15 |  |  |  | HDME001119 | 2021-02-04
TAJ0903-TH | HET | 61000933 | Install | ยังอยู่ในสัญญา HO | - | TH209265 | Andaz Resort Pattaya | G3-E01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-06-15 | 2020-12-15 | 2021-02-20 | 2021-10-15 | P-1600-CO60,60S/3F | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1526890 | Chon Buri | ตำบลนาจอมเทียน | 2021-02-02 | 2021-03-25 | Finished | [34 empty] | 2020-12-15 | 2020-12-15 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-17 | 2021-02-01 | 2021-03-26 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 1900-01-01 | 2021-04-09 | Waiting | POWER SUPPLY DELAY |  | 2021-09-24 | [12 empty] | 0 | 2021-05-18 | 2000-01-01 | 2021-05-18 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-23 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-08 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Green |  |  | 20014401 | 2020-12-15 |  |  |  | HDME001119 | 2021-02-04
TAJ0904-TH | HET | 61000933 | Install | ยังอยู่ในสัญญา HO | - | TH209265 | Andaz Resort Pattaya | G3-E02 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-06-15 | 2020-12-15 | 2021-02-20 | 2021-10-15 | P-1600-CO60,60S/3F | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1526890 | Chon Buri | ตำบลนาจอมเทียน | 2021-02-02 | 2021-03-25 | Finished | [34 empty] | 2020-12-15 | 2020-12-15 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-17 | 2021-02-01 | 2021-03-26 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 1900-01-01 | 2021-04-09 | Waiting | POWER SUPPLY DELAY |  | 2021-09-24 | [12 empty] | 0 | 2021-05-18 | 2000-01-01 | 2021-05-18 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-24 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-08 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Green |  |  | 20014401 | 2020-12-15 |  |  |  | HDME001119 | 2021-02-04
TAJ0905-TH | HET | 61000933 | Install | ยังอยู่ในสัญญา HO | - | TH209265 | Andaz Resort Pattaya | G4-E01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-06-15 | 2020-12-15 | 2021-02-20 | 2021-10-15 | P-1600-CO60,60S/3F | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1526890 | Chon Buri | ตำบลนาจอมเทียน | 2021-02-02 | 2021-02-09 | Finished | [34 empty] | 2020-12-15 | 2020-12-15 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-17 | 2021-02-01 | 2021-02-11 | Finished |  |  | 2021-02-13 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 100 | [41 empty] | 2021-03-03 | 1900-01-01 | 2021-03-03 | Waiting | POWER SUPPLY DELAY |  | 2021-09-24 | [12 empty] | 0 | 2021-03-26 | 2000-01-01 | 2021-03-26 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-25 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-08 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Green |  |  | 20014401 | 2020-12-15 |  |  |  | HDME001119 | 2021-02-04
TAJ0906-TH | HET | 61000933 | Install | ยังอยู่ในสัญญา HO | - | TH209265 | Andaz Resort Pattaya | G4-E02 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-06-15 | 2020-12-15 | 2021-02-20 | 2021-10-15 | P-1600-CO60,60S/3F | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1526890 | Chon Buri | ตำบลนาจอมเทียน | 2021-02-02 | 2021-02-09 | Finished | [34 empty] | 2020-12-15 | 2020-12-15 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-17 | 2021-02-01 | 2021-02-11 | Finished |  |  | 2021-02-13 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 100 | [41 empty] | 2021-03-03 | 1900-01-01 | 2021-03-03 | Waiting | POWER SUPPLY DELAY |  | 2021-09-24 | [12 empty] | 0 | 2021-03-26 | 2000-01-01 | 2021-03-26 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-26 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-08 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Green |  |  | 20014401 | 2020-12-15 |  |  |  | HDME001119 | 2021-02-04
TAJ0907-TH | HET | 61000933 | Install | ยังอยู่ในสัญญา HO | - | TH209265 | Andaz Resort Pattaya | G5-E01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-06-15 | 2020-12-15 | 2021-02-20 | 2021-10-15 | P-1600-CO60,60S/3F | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1526890 | Chon Buri | ตำบลนาจอมเทียน | 2021-02-02 | 2021-03-15 | Finished | [34 empty] | 2020-12-15 | 2020-12-15 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-17 | 2021-02-01 | 2021-03-16 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | [41 empty] | 2021-03-26 | 1900-01-01 | 2021-03-26 | Waiting | POWER SUPPLY DELAY |  | 2021-09-24 | [12 empty] | 0 | 2021-05-18 | 2000-01-01 | 2021-05-18 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-27 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-08 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Green |  |  | 20014401 | 2020-12-15 |  |  |  | HDME001119 | 2021-02-04
TAJ0908-TH | HET | 61000933 | Install | ยังอยู่ในสัญญา HO | - | TH209265 | Andaz Resort Pattaya | G5-E02 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-06-15 | 2020-12-15 | 2021-02-20 | 2021-10-15 | P-1600-CO60,60S/3F | UAG-SN1 | 1600 | 60 | 3 | 3 |  | 1526890 | Chon Buri | ตำบลนาจอมเทียน | 2021-02-02 | 2021-03-15 | Finished | [34 empty] | 2020-12-15 | 2020-12-15 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-17 | 2021-02-01 | 2021-03-16 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-26 | Finished |  |  | 100 | [41 empty] | 2021-03-26 | 1900-01-01 | 2021-03-26 | Waiting | POWER SUPPLY DELAY |  | 2021-09-24 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-04-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-28 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-08 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 16 | 16 | 112 | 74.07 | Green |  |  | 20014401 | 2020-12-15 |  |  |  | HDME001119 | 2021-02-04
TAJ0909-TH | HET | 61000934 | HO | ส่งมอบแล้ว | - | TH209004 | Dream Creation Living | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2020-09-22 | 2021-01-06 | 2021-02-22 |  | P-1000-CO60W1,60S/8F | UAG-SN1 | 1000 | 60 | 8 | 8 |  | 1050000 | Nakhon Pathom | อำเภอกำแพงแสน | 2021-01-06 | 2021-01-06 | Finished | [34 empty] | 2021-01-06 | 2021-01-06 | 2021-01-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-06 | 2021-01-30 | 2021-01-10 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-30 | Finished |  |  | 100 | [41 empty] | 2021-01-30 | 2021-01-15 | 2021-01-15 | Finished |  |  | 2021-01-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-02-17 | 2021-03-12 | 2021-02-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-12 | Finished | [6 empty] | 90 | 2021-02-24 | Finished | POWER SUPPLY DELAY |  | 2021-02-28 | Finished |  |  | 2020-10-07 | Finished | [18 empty] | 2021-01-06 | Finished |  |  | 2021-01-06 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-05 | Finished |  | pass | 2021-04-05 | Finished |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20014432 | 2021-01-06 |  |  |  | HDME001083 | 2021-01-06 | QC Passed
TAJ0910-TH | HET | 61000939 | HO | ส่งมอบแล้ว | - | TH209257 | Beauty Clinic Town in Town | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-09-25 | 2020-12-25 | 2021-02-25 | 2021-04-25 | P-1000-CO60W2,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1000000 | Bangkok | เขตวังทองหลาง | 2021-02-05 | 2021-02-05 | Finished | [34 empty] | 2020-12-25 | 2021-02-05 | 2021-02-05 | Finished | STORE AREA | [13 empty] | 2021-02-05 | 2021-02-28 | 2021-02-05 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-13 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 100 | [41 empty] | 2021-02-23 | 2021-05-06 | 2021-05-06 | Finished |  |  | 2021-05-12 | 2021-05-07 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | 2021-03-01 | 2021-09-25 | 2021-03-01 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-09-25 | Finished | [6 empty] | 90 | 2021-05-20 | Finished | POWER SUPPLY DELAY |  | 2021-05-28 | Finished |  |  | 2020-10-07 | Finished | [10 empty] | 2021-05-28 | Finished | [6 empty] | 2021-02-11 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20014455 | 2020-12-25 |  |  |  | HDME001131 | 2021-02-11 | QC Passed
TAD0501-TH | HET | 61000940 | HO | ยังอยู่ในสัญญา HO | - | TH219034 | Bang Lamung Hospital | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-10-01 | 2021-01-15 | 2021-03-28 | 2021-11-01 | B-1000-2S105,105S/10F | B-II(VFI-II) | 1000 | 105 | 10 | 10 |  | 1551500 | Chon Buri | อำเภอบางละมุง | 2021-03-28 | 2020-11-19 | Finished | [34 empty] | 2021-01-15 | 2020-01-15 | 2020-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-16 | 2021-02-15 | 2020-11-20 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 100 | [41 empty] | 2021-02-07 | 2021-02-11 | 2021-02-11 | Finished |  |  | 2021-02-10 | 2021-02-14 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished | [6 empty] | 90 | 2021-08-27 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-01-15 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Green |  |  | 20014592 | 2021-01-15 |  |  |  | HDME001096 | 2021-01-15
TAD0502-TH | HET | 61000940 | HO | ยังอยู่ในสัญญา HO | - | TH219034 | Bang Lamung Hospital | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-10-01 | 2021-01-15 | 2021-03-28 | 2021-11-01 | B-1000-2S105,105S/10F | B-II(VFI-II) | 1000 | 105 | 10 | 10 |  | 1551500 | Chon Buri | อำเภอบางละมุง | 2021-03-28 | 2020-11-19 | Finished | [34 empty] | 2021-01-15 | 2020-01-15 | 2020-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-16 | 2021-02-15 | 2020-11-20 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 100 | [41 empty] | 2021-02-07 | 2021-02-11 | 2021-02-11 | Finished |  |  | 2021-02-10 | 2021-02-14 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished | [6 empty] | 90 | 2021-09-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-01-15 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Green |  |  | 20014592 | 2021-01-15 |  |  |  | HDME001096 | 2021-01-15
TAD0503-TH | HET | 61000940 | HO | ยังอยู่ในสัญญา HO | - | TH219034 | Bang Lamung Hospital | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-10-01 | 2021-01-15 | 2021-03-28 | 2021-11-01 | B-1000-2S105,105S/10F | B-II(VFI-II) | 1000 | 105 | 10 | 10 |  | 1551500 | Chon Buri | อำเภอบางละมุง | 2021-03-28 | 2020-11-19 | Finished | [34 empty] | 2021-01-15 | 2020-01-15 | 2020-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-16 | 2021-02-15 | 2020-11-20 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 100 | [41 empty] | 2021-02-07 | 2021-02-11 | 2021-02-11 | Finished |  |  | 2021-02-10 | 2021-02-14 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished | [6 empty] | 90 | 2021-09-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-01-15 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Green |  |  | 20014592 | 2021-01-15 |  |  |  | HDME001096 | 2021-01-15
TAD0504-TH | HET | 61000940 | HO | ยังอยู่ในสัญญา HO | - | TH219034 | Bang Lamung Hospital | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-10-01 | 2021-01-15 | 2021-03-28 | 2021-11-01 | B-1000-2S105,105S/10F | B-II(VFI-II) | 1000 | 105 | 10 | 10 |  | 1551500 | Chon Buri | อำเภอบางละมุง | 2021-03-28 | 2021-06-03 | Finished | [34 empty] | 2021-01-15 | 2020-01-15 | 2020-11-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-16 | 2021-02-15 | 2020-11-20 | Finished |  |  | 2020-12-12 | Finished |  |  | 2020-12-17 | Finished |  |  | 2020-12-20 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-12 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 100 | [41 empty] | 2021-02-07 | 2021-02-11 | 2021-02-11 | Finished |  |  | 2021-02-10 | 2021-02-14 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 100 | 2021-03-01 | 2000-01-01 | 2021-03-01 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished | [6 empty] | 90 | 2021-08-27 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-01-15 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 0 | 0 | 0 | 1 | 1 | 99.89 | Green |  |  | 20014592 | 2021-01-15 |  |  |  | HDME001096 | 2021-01-15
TAJ0911-TH | HET | 61000941 | HO | เลยสัญญา HO | - | TH219035 | The Room Boutique Sakon Nakhon | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Somsak Denpraphat | THANASAK SRIASAWIN | 2020-09-28 | 2021-01-28 | 2021-03-28 | 2021-09-15 | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1102100 | Sakon Nakhon | ตำบลธาตุเชิงชุม | 2021-01-14 | 2021-01-15 | Finished | [34 empty] | 2021-01-28 | 2021-01-29 | 2021-01-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-28 | 2021-02-27 | 2021-01-05 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-05 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 2021-01-08 | Finished |  |  | 100 | [41 empty] | 2021-01-08 | 1900-01-01 | 2021-01-08 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-01-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-01-29 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-01-29 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 16 | 16 | 114 | 78.16 | Red |  |  | 20014479 | 2021-01-28 |  |  |  | HDME001109 | 2021-01-29
TAJ0920-TH | HET | 61000947 | HO | ส่งมอบแล้ว | - | TH219036 | K&A Apartment | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-10-19 | 2021-02-19 | 2021-04-19 | 2021-07-18 | P-630-CO60W,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 1284000 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-02-19 | 2021-05-10 | Finished | [34 empty] | 2021-02-19 | 2021-02-27 | 2021-02-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-18 | 2021-06-30 | 2021-05-11 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | [41 empty] | 2021-06-05 | 2021-07-01 | 2021-07-01 | Finished |  |  | 2021-06-26 | 2021-07-01 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-03 | Finished |  |  | 100 | 2021-06-16 | 2021-09-08 | 2021-06-16 | Finished |  |  | 2021-07-14 | Finished |  |  | 2021-07-14 | Finished |  |  | 2021-09-08 | Finished |  |  | 100 | 2021-07-10 | Finished | CONSTRUCTION DELAY |  | 2021-07-30 | Finished |  |  | 2020-11-05 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-07-30 | Finished | [13 empty] | pass |  |  |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014903 | 2021-02-19 |  |  |  | HDME001144 | 2021-02-25 | QC Passed
TAJ0926-TH | HET | 61000956 | HO | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | CP1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | P-1000-CO90W2,90S/6F | UAG-SN1 | 1000 | 90 | 6 | 6 |  | 769723 | Nonthaburi | ตำบลบางตลาด | 2021-03-16 | 2021-03-22 | Finished | [34 empty] | 2021-01-11 | 2021-03-06 | 2021-03-06 | Finished | PAYMENT DELAY | [13 empty] | 2021-03-22 | 2021-05-30 | 2021-03-23 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-22 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | [41 empty] | 2021-05-21 | 1900-01-01 | 2021-05-21 | Waiting | POWER SUPPLY DELAY |  | 2021-10-16 | [12 empty] | 0 | 2021-05-17 | 2000-01-01 | 2021-05-17 | Finished | [14 empty] | 25 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished | [10 empty] | 2021-12-30 | Finished | [6 empty] | 2021-03-06 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 6 | 16 | 104 | 81.88 | Green |  |  | 20014536 | 2021-01-11
TAJ0927-TH | HET | 61000956 | HO | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | CP2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | P-1000-CO90W2,90S/6F | UAG-SN1 | 1000 | 90 | 6 | 6 |  | 769723 | Nonthaburi | ตำบลบางตลาด | 2021-03-16 | 2021-03-22 | Finished | [34 empty] | 2021-01-11 | 2021-03-06 | 2021-03-06 | Finished | PAYMENT DELAY | [13 empty] | 2021-03-22 | 2021-05-30 | 2021-03-23 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-22 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-21 | Finished |  |  | 100 | [41 empty] | 2021-05-21 | 1900-01-01 | 2021-05-21 | Waiting | POWER SUPPLY DELAY |  | 2021-10-16 | [12 empty] | 0 | 2021-05-17 | 2000-01-01 | 2021-05-17 | Finished | [14 empty] | 25 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished | [10 empty] | 2021-12-30 | Finished | [6 empty] | 2021-03-06 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 82 | 6 | 16 | 104 | 81.88 | Green |  |  | 20014536 | 2021-01-11
TAC1849-TH | HET | 61000956 | Delivery | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | LP1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | VFI-1600-CO150,150S/17F | VFI-II | 1600 | 150 | 17 | 17 |  | 2759922.2 | Nonthaburi | ตำบลบางตลาด | 2021-10-30 | [36 empty] | 2021-04-15 | 2021-06-05 | 2021-06-06 | Finished | PAYMENT DELAY | [13 empty] | 2021-11-01 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-06-05 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-05 | Finished | [22 empty] | 1190 | 110 | 40 | 20 | 1360 | 1190 | 110 | 40 | 20 | 1360 | 0 | Green |  |  | 20014536 | 2021-05-05 |  |  |  | HDME001232 | 2021-06-05
TAC1850-TH | HET | 61000956 | Delivery | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | LP2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | VFI-1600-CO150,150S/17F | VFI-II | 1600 | 150 | 17 | 17 |  | 2759922.2 | Nonthaburi | ตำบลบางตลาด | 2021-10-30 | [36 empty] | 2021-04-15 | 2021-06-05 | 2021-06-06 | Finished | PAYMENT DELAY | [13 empty] | 2021-11-01 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-06-05 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-05 | Finished | [22 empty] | 1190 | 110 | 40 | 20 | 1360 | 1190 | 110 | 40 | 20 | 1360 | 0 | Green |  |  | 20014536 | 2021-05-05 |  |  |  | HDME001232 | 2021-06-05
TAC1851-TH | HET | 61000956 | Delivery | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | LP3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | VFI-1600-CO150,150S/17F | VFI-II | 1600 | 150 | 17 | 17 |  | 2759922.2 | Nonthaburi | ตำบลบางตลาด | 2021-10-30 | [36 empty] | 2021-04-15 | 2021-06-05 | 2021-06-06 | Finished | PAYMENT DELAY | [13 empty] | 2021-11-01 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-06-05 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-05 | Finished | [22 empty] | 1190 | 110 | 40 | 20 | 1360 | 1190 | 110 | 40 | 20 | 1360 | 0 | Green |  |  | 20014536 | 2021-05-05 |  |  |  | HDME001232 | 2021-06-05
TAC1852-TH | HET | 61000956 | Delivery | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | LP4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | VFI-1600-CO150,150S/17F | VFI-II | 1600 | 150 | 17 | 17 |  | 2759922.2 | Nonthaburi | ตำบลบางตลาด | 2021-10-30 | [36 empty] | 2021-04-15 | 2021-06-22 | 2021-06-22 | Finished | PAYMENT DELAY | [13 empty] | 2021-11-01 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-06-22 | Finished |  |  | 2021-06-30 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 1190 | 110 | 40 | 20 | 1360 | 1190 | 110 | 40 | 20 | 1360 | 0 | Green |  |  | 20014536 | 2021-05-05
TAC1853-TH | HET | 61000956 | HO | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | LP5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | VFI-1600-CO150,150S/17F | VFI-II | 1600 | 150 | 17 | 17 |  | 2759922.2 | Nonthaburi | ตำบลบางตลาด | 2021-10-30 | [36 empty] | 2021-04-15 | 2021-06-22 | 2021-06-22 | Finished | PAYMENT DELAY | [13 empty] | 2021-11-01 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-06-22 | Finished |  |  | 2021-06-30 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 1190 | 110 | 40 | 20 | 1360 | 1190 | 110 | 40 | 20 | 1360 | 0 | Green |  |  | 20014536 | 2021-05-05
TBK0206-TH | HET | 61000956 | HO | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | LP-6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | HVF-1600-CO180,180S/17F | HVF-5 | 1600 | 180 | 17 | 17 |  | 2374723 | Nonthaburi | ตำบลบางตลาด | 2021-10-30 | [36 empty] | 2021-04-15 | 2021-05-24 | 2021-05-22 | Finished | PAYMENT DELAY | [13 empty] | 2021-11-01 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-28 | Finished | [22 empty] | 1192 | 98 | 40 | 20 | 1350 | 1192 | 98 | 40 | 20 | 1350 | 0 | Green |  |  | 20014536 | 2021-05-05 |  |  |  | HDME001218 | 2021-05-21
TAJ0925-TH | HET | 61000956 | HO | ยังอยู่ในสัญญา HO | - | TH219044 | Department of Water Resources | SL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2020-09-17 | 2021-01-11 | 2021-06-30 | 2022-03-30 | P-1600-CO90D2,90S/18F | UAG-SN1 | 1600 | 90 | 18 | 18 |  | 1786220 | Nonthaburi | ตำบลบางตลาด | 2021-10-30 | [36 empty] | 2021-01-11 | 2021-03-06 | 2021-03-06 | Finished | PAYMENT DELAY | [13 empty] | 2021-11-01 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-11-06 | Finished | [10 empty] | 2021-12-30 | Finished | [6 empty] | 2021-03-06 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished | [22 empty] | 983 | 99 | 40 | 20 | 1142 | 983 | 99 | 40 | 20 | 1142 | 0 | Green |  |  | 20014536 | 2021-01-11
TAJ0928-TH | HET | 61000958 | Install | ยังอยู่ในสัญญา HO | - | TH209273 | Mudman PLC | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-11-05 | 2021-02-25 | 2021-04-15 | 2021-10-26 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1016500 | Bangkok | แขวงพัฒนาการ | 2021-05-16 | 2021-05-16 | Finished | [34 empty] | 2021-02-25 | 2021-03-08 | 2021-03-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-17 | 2021-07-25 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-09-18 | [12 empty] | 0 | 2021-08-13 | 2000-01-01 | 2021-08-13 | Finished | [14 empty] | 25 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-11-25 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-03-08 | Finished |  |  | 2021-03-08 | Finished |  |  | 2021-03-10 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 4 | 16 | 101 | 78.83 | Green |  |  | 20015192 | 2021-02-25 |  |  |  | HDME001154 | 2021-03-08
TAC1854-TH | HET | 61000960 | HO | ส่งมอบแล้ว | - | TH209243 | College of Nursing Phapokklao Chanthaburi Dormitory | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-09-25 | 2021-01-08 | 2021-02-25 |  | VFI-1000-2S90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1337500 | Chanthaburi | ตำบลวัดใหม่ | 2021-02-25 | 2021-02-25 | Finished | [34 empty] | 2021-01-11 | 2021-01-11 | 2021-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-12 | 2021-01-10 | 2021-03-02 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | [41 empty] | 2021-04-10 | 2021-07-10 | 2021-07-10 | Finished |  |  | 2021-04-04 | 2021-07-14 | Finished |  |  | 2021-07-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-07-29 | 2021-07-29 | 2021-07-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-29 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-05 | Finished |  |  | 2020-11-06 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-01-19 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-05 | Finished | [13 empty] | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20014556 | 2021-01-11 |  |  |  | HDME001098 | 2021-01-19 | QC Passed
TAC1855-TH | HET | 61000960 | HO | ส่งมอบแล้ว | - | TH209243 | College of Nursing Phapokklao Chanthaburi Dormitory | EL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-09-25 | 2021-01-08 | 2021-02-25 |  | VFI-1000-2S90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1337500 | Chanthaburi | ตำบลวัดใหม่ | 2021-02-25 | 2021-02-25 | Finished | [34 empty] | 2021-01-11 | 2021-01-11 | 2021-01-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-12 | 2021-01-10 | 2021-03-02 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-13 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | [41 empty] | 2021-04-10 | 2021-07-10 | 2021-07-10 | Finished |  |  | 2021-04-04 | 2021-07-14 | Finished |  |  | 2021-07-16 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-07-29 | 2021-07-29 | 2021-07-29 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-29 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | CONSTRUCTION DELAY |  | 2021-08-05 | Finished |  |  | 2020-11-06 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-01-19 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-08-05 | Finished | [13 empty] | pass |  |  |  |  | 638 | 92 | 24 | 16 | 770 | 0 | 0 | 0 | 1 | 1 | 99.87 | Blue |  |  | 20014556 | 2021-01-11 |  |  |  | HDME001098 | 2021-01-19 | QC Passed
TAJ0930-TH | HET | 61000961 | Install | ยังอยู่ในสัญญา HO | - | TH209275 | The Standard Huahin | FL1 (Building A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-11 | 2020-12-25 | 2021-03-31 | 2021-09-30 | P-1000-CO90D,90S/6F | UAG-SN1 | 1000 | 90 | 6 | 6 |  | 800000 | Prachuap Khiri Khan | ตำบลหัวหิน | 2021-02-10 | 2021-02-10 | Finished | [34 empty] | 2021-01-07 | 2021-01-07 | 2021-01-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-01-20 | 2020-12-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-02-03 | Finished |  |  | 100 | [41 empty] | 2021-02-03 | 2021-04-30 | 2021-04-30 | Finished |  |  | 2021-04-20 | 2021-05-10 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-15 | Finished |  |  | 100 | 2021-02-17 | 2000-01-01 | 2021-02-17 | Finished |  |  | 2021-08-23 | Finished | [10 empty] | 50 | 2021-09-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-01-07 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-11 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 16 | 16 | 97.21 | Green |  |  | 20014564 | 2021-01-07 |  |  |  | HDME001084 | 2021-01-07
TAJ0931-TH | HET | 61000961 | Install | ยังอยู่ในสัญญา HO | - | TH209275 | The Standard Huahin | FL2 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-11 | 2020-12-25 | 2021-03-31 | 2021-09-30 | P-1000-CO90D,90S/6F | UAG-SN1 | 1000 | 90 | 6 | 6 |  | 800000 | Prachuap Khiri Khan | ตำบลหัวหิน | 2021-02-10 | 2021-01-06 | Finished | [34 empty] | 2021-01-07 | 2021-01-07 | 2021-01-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2020-12-25 | 2021-01-20 | 2020-12-15 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-04-30 | 2021-04-30 | Finished |  |  | 2021-04-20 | 2021-05-10 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-15 | Finished |  |  | 100 | 2021-02-17 | 2000-01-01 | 2021-02-17 | Finished |  |  | 2021-08-23 | Finished | [10 empty] | 50 | 2021-09-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-01-07 | Finished |  |  | 2021-01-07 | Finished |  |  | 2021-01-11 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 16 | 16 | 97.21 | Green |  |  | 20014564 | 2021-01-07 |  |  |  | HDME001084 | 2021-01-07
TBL0408-TH | HET | 61000961 | Install | ยังอยู่ในสัญญา HO | - | TH209275 | The Standard Huahin | L1 (Building A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-11 | 2020-12-25 | 2021-03-31 | 2021-09-30 | OUG-1000-CO90,90S/6F | OUG-ON1 | 1000 | 90 | 6 | 6 |  | 850000 | Prachuap Khiri Khan | ตำบลหัวหิน | 2021-02-10 | 2021-02-10 | Finished | [34 empty] | 2021-02-19 | 2021-02-20 | 2021-02-20 | Finished | STORE AREA | [13 empty] | 2021-02-10 | 2021-02-28 | 2020-12-15 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-06 | Finished |  |  | 100 | [41 empty] | 2021-03-06 | 2021-04-30 | 2021-04-30 | Finished |  |  | 2021-04-20 | 2021-05-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-09-03 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished |  |  | 2021-08-23 | Finished | [10 empty] | 50 | 2021-09-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 16 | 16 | 97.61 | Green |  |  | 20014564 | 2021-02-19 |  |  |  | HDME001139 | 2021-02-20
TBL0409-TH | HET | 61000961 | Install | ยังอยู่ในสัญญา HO | - | TH209275 | The Standard Huahin | L2 (Building A) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-11 | 2020-12-25 | 2021-03-31 | 2021-09-30 | OUG-1000-CO90,90S/6F | OUG-ON1 | 1000 | 90 | 6 | 6 |  | 850000 | Prachuap Khiri Khan | ตำบลหัวหิน | 2021-02-10 | 2021-02-10 | Finished | [34 empty] | 2021-02-19 | 2021-02-20 | 2021-02-20 | Finished | STORE AREA | [13 empty] | 2021-02-10 | 2021-02-28 | 2020-12-15 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-25 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-06 | Finished |  |  | 100 | [41 empty] | 2021-03-06 | 2021-04-30 | 2021-04-30 | Finished |  |  | 2021-04-20 | 2021-05-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-09-03 | Finished |  |  | 100 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished |  |  | 2021-08-23 | Finished | [10 empty] | 50 | 2021-09-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 16 | 16 | 97.61 | Green |  |  | 20014564 | 2021-02-19 |  |  |  | HDME001139 | 2021-02-20
TBL0410-TH | HET | 61000961 | Install | ยังอยู่ในสัญญา HO | - | TH209275 | The Standard Huahin | L3 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-11 | 2020-12-25 | 2021-03-31 | 2021-09-30 | OUG-1000-CO90,90S/6F | OUG-ON1 | 1000 | 90 | 6 | 6 |  | 850000 | Prachuap Khiri Khan | ตำบลหัวหิน | 2021-02-10 | 2021-02-10 | Finished | [34 empty] | 2021-01-19 | 2021-02-20 | 2021-02-20 | Finished | STORE AREA | [13 empty] | 2021-02-10 | 2021-02-28 | 2020-12-15 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-02-01 | Finished |  |  | 2021-02-03 | Finished |  |  | 100 | [41 empty] | 2021-02-03 | 2021-04-30 | 2021-04-30 | Finished |  |  | 2021-04-20 | 2021-05-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-09-03 | Finished |  |  | 100 | 2021-03-29 | 2000-01-01 | 2021-03-29 | Finished |  |  | 2021-08-23 | Finished | [10 empty] | 50 | 2021-09-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 16 | 16 | 97.61 | Green |  |  | 20014564 | 2021-02-19 |  |  |  | HDME001139 | 2021-02-20
TBL0411-TH | HET | 61000961 | Install | ยังอยู่ในสัญญา HO | - | TH209275 | The Standard Huahin | L4 (Building B) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-11 | 2020-12-25 | 2021-03-31 | 2021-09-30 | OUG-1000-CO90,90S/6F | OUG-ON1 | 1000 | 90 | 6 | 6 |  | 850000 | Prachuap Khiri Khan | ตำบลหัวหิน | 2021-02-10 | 2021-02-10 | Finished | [34 empty] | 2021-01-19 | 2021-02-20 | 2021-02-20 | Finished | STORE AREA | [13 empty] | 2021-02-10 | 2021-02-28 | 2020-12-15 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-21 | Finished |  |  | 100 | [41 empty] | 2021-03-21 | 2021-04-30 | 2021-04-30 | Finished |  |  | 2021-04-20 | 2021-05-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-09-03 | Finished |  |  | 100 | 2021-03-29 | 2000-01-01 | 2021-03-29 | Finished |  |  | 2021-08-23 | Finished | [10 empty] | 50 | 2021-09-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-02-20 | Finished |  |  | 2021-02-20 | Finished |  |  | 2021-02-22 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 16 | 16 | 97.61 | Green |  |  | 20014564 | 2021-02-19 |  |  |  | HDME001139 | 2021-02-20
TAJ0932-TH | HET | 61000962 | HO | เลยสัญญา HO | - | TH219045 | Resident Khun Alisana | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-10-05 | 2021-02-05 | 2021-04-05 | 2021-08-06 | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 1070000 | Bangkok | แขวงดินแดง | 2021-03-30 | 2021-03-30 | Finished | [34 empty] | 2021-02-05 | 2021-02-26 | 2021-02-26 | Finished | STORE AREA | [13 empty] | 2021-03-30 | 2021-05-30 | 2021-05-04 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-23 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-28 | Finished |  |  | 100 | [41 empty] | 2021-05-28 | 1900-01-01 | 2021-05-28 | Waiting | POWER SUPPLY DELAY |  | 2021-07-06 | [12 empty] | 0 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-10-29 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-10-21 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-02-26 | Finished |  |  | 2021-02-26 | Finished |  |  | 2021-02-28 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Red |  |  | 20014593 | 2021-02-05 |  |  |  | HDME001145 | 2021-02-26
TFA1463-TH | HET | 61000963 | Install | ยังอยู่ในสัญญา HO | - | TH209276 | Thaniya Building | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 934692.08 | Bangkok | แขวงสีลม | 2021-05-14 | [20 empty] | 2021-05-17 | Finished | [14 empty] | 2021-04-05 | 2021-05-17 | 2021-05-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-07 | 2021-05-30 | [41 empty] | 2021-05-17 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | 2021-06-05 | 1900-01-01 | 2021-06-05 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-11-15 | Working | [6 empty] | 2021-01-11 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-17 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-21 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Orange |  |  | 20014722 | 2021-04-20 |  |  |  | HDME001215 | 2021-05-17
TFA1464-TH | HET | 61000963 | Install | ยังอยู่ในสัญญา HO | - | TH209276 | Thaniya Building | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 934692.08 | Bangkok | แขวงสีลม | 2021-05-14 | [20 empty] | 2021-05-17 | Finished | [14 empty] | 2021-04-05 | 2021-05-17 | 2021-05-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-07 | 2021-05-30 | [41 empty] | 2021-05-17 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | 2021-06-05 | 1900-01-01 | 2021-06-05 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-11-15 | Working | [6 empty] | 2021-01-11 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-17 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-21 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 0 | 42 | 4 | 21 | 67 | 89.11 | Orange |  |  | 20014722 | 2021-04-20 |  |  |  | HDME001215 | 2021-05-17
TFA1465-TH | HET | 61000963 | Install | ยังอยู่ในสัญญา HO | - | TH209276 | Thaniya Building | ES3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | 1200TX-EN,R3.65M,D35 | TX-EN |  |  |  |  | 3650 | 900391.09 | Bangkok | แขวงสีลม | 2021-05-14 | [20 empty] | 2021-05-17 | Finished | [14 empty] | 2021-04-05 | 2021-05-17 | 2021-05-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-07 | 2021-05-30 | [41 empty] | 2021-05-17 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | 2021-06-05 | 1900-01-01 | 2021-06-05 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-11-15 | Working | [6 empty] | 2021-01-11 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-17 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-21 | Finished | [22 empty] | 482 | 32 | 16 | 14 | 544 | 0 | 32 | 4 | 14 | 50 | 90.81 | Orange |  |  | 20014722 | 2021-04-20 |  |  |  | HDME001215 | 2021-05-17
TFA1466-TH | HET | 61000963 | Install | ยังอยู่ในสัญญา HO | - | TH209276 | Thaniya Building | ES4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | 1200TX-EN,R3.65M,D35 | TX-EN |  |  |  |  | 3650 | 900391.09 | Bangkok | แขวงสีลม | 2021-05-14 | [20 empty] | 2021-05-17 | Finished | [14 empty] | 2021-04-05 | 2021-05-17 | 2021-05-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-07 | 2021-05-30 | [41 empty] | 2021-05-17 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | 2021-06-05 | 1900-01-01 | 2021-06-05 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-11-15 | Working | [6 empty] | 2021-01-11 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-17 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-21 | Finished | [22 empty] | 482 | 32 | 16 | 14 | 544 | 0 | 32 | 4 | 14 | 50 | 90.81 | Orange |  |  | 20014722 | 2021-04-20 |  |  |  | HDME001215 | 2021-05-17
TFA1467-TH | HET | 61000963 | Install | ยังอยู่ในสัญญา HO | - | TH209276 | Thaniya Building | ES5 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | 1200TX-EN,R3.55M,D35 | TX-EN |  |  |  |  | 3550 | 891815.04 | Bangkok | แขวงสีลม | 2021-05-14 | [20 empty] | 2021-05-17 | Finished | [14 empty] | 2021-03-05 | 2021-05-17 | 2021-05-17 | Finished | CONSTRUCTION STOP | [13 empty] | 2021-05-07 | 2021-05-30 | [41 empty] | 2021-05-17 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | 2021-06-05 | 1900-01-01 | 2021-06-05 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-11-15 | Working | [6 empty] | 2021-01-11 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-17 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-21 | Finished | [22 empty] | 482 | 32 | 16 | 14 | 544 | 0 | 32 | 4 | 14 | 50 | 90.81 | Orange |  |  | 20014722 | 2021-04-10 |  |  |  | HDME001215 | 2021-05-17
TFA1468-TH | HET | 61000963 | Install | ยังอยู่ในสัญญา HO | - | TH209276 | Thaniya Building | ES6 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | 1200TX-EN,R3.55M,D35 | TX-EN |  |  |  |  | 3550 | 891815.04 | Bangkok | แขวงสีลม | 2021-05-14 | [20 empty] | 2021-05-17 | Finished | [14 empty] | 2021-03-05 | 2021-05-17 | 2021-05-17 | Finished | CONSTRUCTION STOP | [13 empty] | 2021-05-07 | 2021-05-30 | [41 empty] | 2021-05-17 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 100 | 2021-06-05 | 1900-01-01 | 2021-06-05 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-06-10 | 2000-01-01 | 2021-06-10 | Finished | [14 empty] | 25 | 2021-11-15 | Working | [6 empty] | 2021-01-11 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-17 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-21 | Finished | [22 empty] | 482 | 32 | 16 | 14 | 544 | 0 | 32 | 4 | 14 | 50 | 90.81 | Orange |  |  | 20014722 | 2021-04-10 |  |  |  | HDME001215 | 2021-05-17
TAC1856-TH | HET | 61000963 | Install | ยังอยู่ในสัญญา HO | - | TH209276 | Thaniya Building | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | VFI-900-CO105,105S/11F | VFI-II | 900 | 105 | 11 | 11 |  | 1577828.42 | Bangkok | แขวงสีลม | 2021-06-20 | 2021-07-31 | Finished | [34 empty] | 2021-01-20 | 2021-03-25 | 2021-03-25 | Finished | OTHERS | [13 empty] | 2021-08-01 | 2021-09-10 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-16 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-11 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-20 | Working | [6 empty] | 2021-01-11 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-31 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 300 | 105 | 32 | 20 | 457 | 55.02 | Orange |  |  | 20014723 | 2021-03-10 |  |  |  | HDME001176 | 2021-03-25
TAC1857-TH | HET | 61000963 | HO | ส่งมอบแล้ว | - | TH209276 | Thaniya Building | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | VFI-900-CO105,105S/11F | VFI-II | 900 | 105 | 11 | 11 |  | 1577828.42 | Bangkok | แขวงสีลม | 2021-02-25 | 2021-02-25 | Finished | [34 empty] | 2021-04-20 | 2021-02-19 | 2021-02-19 | Finished | [14 empty] | 2021-02-19 | 2021-03-18 | 2021-03-01 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-28 | Finished |  |  | 2021-03-30 | Finished |  |  | 100 | [41 empty] | 2021-03-30 | 2021-03-31 | 2021-03-31 | Finished |  |  | 2021-03-30 | 2021-03-31 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | 2021-07-08 | 2000-01-01 | 2021-07-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-08 | Finished | [6 empty] | 90 | 2021-06-20 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-01-11 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-02-19 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-07-30 | Finished | [13 empty] | no pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 2 | 2 | 99.8 | Blue |  |  | 20014723 | 2021-02-10 |  |  |  | HDME001138 | 2021-02-19
TAC1858-TH | HET | 61000963 | HO | ส่งมอบแล้ว | - | TH209276 | Thaniya Building | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2020-08-20 | 2021-01-20 | 2021-06-30 | 2021-09-30 | VFI-900-CO105,105S/11F | VFI-II | 900 | 105 | 11 | 11 |  | 1577828.42 | Bangkok | แขวงสีลม | 2021-05-20 | 2021-05-20 | Finished | [34 empty] | 2021-04-20 | 2021-03-25 | 2021-06-07 | Finished | STORE AREA | [13 empty] | 2021-05-20 | 2021-06-26 | 2021-06-01 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-12 | Finished |  |  | 2021-06-12 | Finished |  |  | 2021-06-20 | Finished |  |  | 2021-06-23 | Finished |  |  | 100 | [41 empty] | 2021-06-23 | 2021-06-27 | 2021-06-27 | Finished |  |  | 2021-06-26 | 2021-06-27 | Finished |  |  | 2021-07-01 | Finished |  |  | 2021-07-05 | Finished |  |  | 100 | 2021-03-19 | 2021-06-15 | 2021-03-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-15 | Finished |  |  | 100 | 2021-07-10 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-01-11 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2021-05-21 | Finished | [6 empty] | 2021-06-07 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-05-21 | Finished | [13 empty] | pass |  |  |  |  | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014723 | 2021-04-20 |  |  |  | HDME001233 | 2021-06-07 | QC Passed
TBK0210-TH | HET | 61000964 | Install | เลยสัญญา HO | - | TH219046 | The Estelle Phrom-Phong | L1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-10-10 | 2021-03-18 | 2021-05-18 |  | HVF-1000-CO240,240S/19F | HVF-5 | 1000 | 240 | 19 | 19 |  | 4708000 | Bangkok | แขวงคลองตัน | 2021-11-15 | [36 empty] | 2021-05-14 | 2021-03-19 | 2021-06-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-24 | 2021-04-27 | 2021-05-21 | Finished | [14 empty] | 2021-08-05 | Finished |  |  | 2021-08-06 | Finished |  |  | 2021-06-03 | Finished | [6 empty] | 2021-08-16 | Finished |  |  | 2021-06-15 | Finished |  |  | 75 | [41 empty] | 2021-06-15 | 1900-01-01 | 2021-06-15 | Waiting | POWER SUPPLY DELAY |  | 2021-04-28 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | [8 empty] | 2020-12-04 | Finished |  |  | 2021-05-01 | Finished | [14 empty] | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished | [22 empty] | 1290 | 107 | 40 | 20 | 1457 | 322 | 107 | 40 | 20 | 489 | 66.44 | Red |  |  | 20014739 | 2021-05-14 |  |  |  | HDME001227 | 2021-06-01
TBK0207-TH | HET | 61000964 | Install | ยังอยู่ในสัญญา HO | - | TH219046 | The Estelle Phrom-Phong | L2 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-10-10 | 2021-03-18 | 2021-10-30 |  | HVF-1000-CO240,240S/32F | HVF-5 | 1000 | 240 | 32 | 32 |  | 5029000 | Bangkok | แขวงคลองตัน | 2021-12-15 | [36 empty] | 2021-07-26 | 2021-08-17 | 2021-08-28 | Finished | [14 empty] | 2021-08-17 | 2021-10-12 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-14 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2020-12-04 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-27 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-31 | Finished | [22 empty] | 1927 | 116 | 64 | 32 | 2139 | 1927 | 116 | 64 | 32 | 2139 | 0 | Orange |  |  | 20014739 | 2021-07-26
TBK0208-TH | HET | 61000964 | Install | ยังอยู่ในสัญญา HO | - | TH219046 | The Estelle Phrom-Phong | L3 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-10-10 | 2021-03-18 | 2021-10-30 |  | HVF-1000-CO240,240S/32F | HVF-5 | 1000 | 240 | 32 | 32 |  | 5029000 | Bangkok | แขวงคลองตัน | 2021-12-15 | [36 empty] | 2021-07-26 | 2021-08-17 | [16 empty] | 2021-08-17 | 2021-10-12 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-14 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2020-12-04 | Finished |  |  | 2021-08-12 | Finished | [46 empty] | 1927 | 116 | 64 | 32 | 2139 | 1927 | 116 | 64 | 32 | 2139 | 0 | Orange |  |  | 20014739 | 2021-07-26
TBK0211-TH | HET | 61000964 | Install | ยังอยู่ในสัญญา HO | - | TH219046 | The Estelle Phrom-Phong | L4 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-10-10 | 2021-03-18 | 2021-10-30 |  | HVF-1000-CO240,240S/36F | HVF-5 | 1000 | 240 | 36 | 36 |  | 5457000 | Bangkok | แขวงคลองตัน | 2021-11-15 | [36 empty] | 2021-08-16 | 2021-08-17 | [16 empty] | 2021-08-17 | 2021-10-13 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-14 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2020-12-04 | Finished |  |  | 2021-08-27 | Finished | [46 empty] | 2123 | 119 | 72 | 40 | 2354 | 2123 | 119 | 72 | 40 | 2354 | 0 | Orange |  |  | 20014739 | 2021-08-16
TBK0212-TH | HET | 61000964 | Install | ยังอยู่ในสัญญา HO | - | TH219046 | The Estelle Phrom-Phong | L5 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-10-10 | 2021-03-18 | 2021-10-08 |  | HVF-1000-CO240,240S/32F | HVF-5 | 1000 | 240 | 32 | 32 |  | 5029000 | Bangkok | แขวงคลองตัน | 2021-11-15 | [36 empty] | 2021-07-26 | 2021-07-26 | [16 empty] | 2021-07-26 | 2021-09-21 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-22 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2020-12-04 | Finished |  |  | 2021-08-12 | Finished | [46 empty] | 1927 | 116 | 64 | 32 | 2139 | 1927 | 116 | 64 | 32 | 2139 | 0 | Orange |  |  | 20014739 | 2021-07-26
TBK0209-TH | HET | 61000964 | Install | ยังอยู่ในสัญญา HO | - | TH219046 | The Estelle Phrom-Phong | L6 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-10-10 | 2021-03-18 | 2021-10-30 |  | HVF-1600-2S180,180S/36F | HVF-5 | 1600 | 180 | 36 | 36 |  | 5671000 | Bangkok | แขวงคลองตัน | 2021-11-15 | [36 empty] | 2021-08-16 | 2021-08-17 | [16 empty] | 2021-08-17 | 2021-10-13 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-14 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2020-12-04 | Finished |  |  | 2021-08-27 | Finished | [46 empty] | 2123 | 119 | 72 | 40 | 2354 | 2123 | 119 | 72 | 40 | 2354 | 0 | Orange |  |  | 20014739 | 2021-08-16
TEC0193-TH | HET | 61000964 | Install | ยังอยู่ในสัญญา HO | - | TH219046 | The Estelle Phrom-Phong | P1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-10-10 | 2021-03-18 | 2021-11-30 |  | DT-500S-B20,20S/2F | DT | 500 | 20 | 2 | 2 |  | 1177000 | Bangkok | แขวงคลองตัน | 2021-12-15 | [36 empty] | 2021-08-17 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2020-12-04 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Green |  |  | 20016453 | 2021-08-17
TAJ0933-TH | HET | 61000965 | HO | เลยสัญญา HO | - | TH209195 | Sai Ma Parking Building | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-10-09 | 2020-12-25 | 2021-01-30 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1030000.01 | Bangkok | ตำบลไทรม้า | 2020-12-30 | 2021-01-23 | Finished | [34 empty] | 2021-01-06 | 2021-01-18 | 2021-01-18 | Finished | PAYMENT DELAY | [13 empty] | 2021-01-05 | 2021-01-30 | 2021-01-25 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-27 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-05 | Finished |  |  | 100 | [41 empty] | 2021-05-05 | 2021-06-16 | 2021-06-16 | Finished |  |  | 2021-06-13 | 2021-06-16 | Finished |  |  | 2021-06-17 | Finished |  |  | 2021-06-29 | Finished |  |  | 100 | 2021-05-24 | 2021-09-10 | 2021-05-24 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-09-10 | Finished | [6 empty] | 90 | 2021-09-25 | Working | [6 empty] | 2020-11-03 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-01-18 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-25 | Finished | [17 empty] | no pass |  |  |  |  | 541 | 84 | 24 | 16 | 665 | 0 | 0 | 0 | 1 | 1 | 99.85 | Red |  |  | 20014782 | 2021-01-06 |  |  |  | HDME001097 | 2021-01-18 | QC Passed
TBL0412-TH | HET | 61000966 | Test | ยังอยู่ในสัญญา HO | - | TH209171 | IOT1 Building | L-01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-10-15 | 2021-03-30 | 2021-06-29 | 2021-10-15 | OUG-1000-CO60,60S/4F | OUG-ON1 | 1000 | 60 | 4 | 4 |  | 1712000 | Chon Buri | อำเภอศรีราชา | 2021-06-30 | 2021-06-29 | Finished | [34 empty] | 2021-03-30 | 2021-03-30 | 2021-05-24 | Finished | PAYMENT DELAY | [13 empty] | 2021-03-31 | 2021-05-25 | 2021-07-16 | Finished |  |  | 2021-07-18 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 2021-07-24 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-07-28 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-04 | Finished |  |  | 100 | [41 empty] | 2021-08-04 | 1900-01-01 | 2021-08-04 | Waiting | POWER SUPPLY DELAY |  | 2021-09-30 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-05-24 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-05-28 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 0 | 85 | 4 | 16 | 105 | 81.05 | Green |  |  | 20016048 | 2021-05-24 |  |  |  | HDME001220 | 2021-05-24
TAJ0934-TH | HET | 61000966 | Test | ยังอยู่ในสัญญา HO | - | TH209171 | IOT1 Building | L-02 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-10-15 | 2021-03-30 | 2021-06-29 | 2021-10-15 | P-1000-CO60W2,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1070000 | Chon Buri | อำเภอศรีราชา | 2021-03-30 | 2021-06-29 | Finished | [34 empty] | 2021-03-30 | 2021-03-30 | 2021-04-06 | Finished | PAYMENT DELAY | [13 empty] | 2021-03-31 | 2021-05-25 | 2021-07-16 | Finished |  |  | 2021-07-18 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-21 | Finished |  |  | 2021-07-23 | Finished |  |  | 2021-07-24 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-07-28 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-04 | Finished |  |  | 100 | [41 empty] | 2021-08-04 | 1900-01-01 | 2021-08-04 | Waiting | POWER SUPPLY DELAY |  | 2021-09-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-04-06 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-12 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 16 | 16 | 113 | 76.31 | Green |  |  | 20016048 | 2021-03-30 |  |  |  | HDME001190 | 2021-04-06
TAC1859-TH | HET | 61000967 | HO | ยังอยู่ในสัญญา HO | - | TH209277 | Apartment K.Puwit Somnuek | L-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2020-10-09 | 2021-02-09 | 2021-04-09 | 2021-09-30 | VFI-600-CO60,60S/5F | VFI-II | 600 | 60 | 5 | 5 |  | 1050000 | Samut Prakan | อำเภอบางพลี | 2021-04-30 | 2021-04-22 | Finished | [34 empty] | 2021-02-09 | 2021-02-18 | 2021-02-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-30 | 2021-05-20 | 2021-04-22 | Finished |  |  | 2021-04-24 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-05-02 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-08 | Finished |  |  | 100 | [41 empty] | 2021-05-08 | 1900-01-01 | 2021-05-08 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2021-05-21 | 2000-01-01 | 2021-05-21 | Finished | [14 empty] | 25 | 2021-11-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-11-02 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-02-18 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-22 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Orange |  |  | 20014751 | 2021-02-09 |  |  |  | HDME001136 | 2021-02-18
TEB0212-TH | HET | 61000968 | HO | ส่งมอบแล้ว | - | TH219042 | Home Khun Earth-Lin | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-10-06 | 2021-01-06 | 2021-02-06 | 2021-06-20 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 856000 | Bangkok | แขวงลาดพร้าว | 2021-03-01 | 2021-01-17 | Finished | [34 empty] | 2020-12-22 | 2021-01-22 | 2021-01-28 | Finished | OTHERS | [13 empty] | 2021-01-06 | 2021-01-26 | 2021-01-17 | Finished |  |  | 2021-01-17 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-22 | Finished |  |  | 100 | [41 empty] | 2021-01-22 | 2021-06-15 | 2021-06-15 | Finished |  |  | 2021-04-12 | 2021-06-17 | Finished |  |  | 2021-06-21 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | 2021-05-13 | 2000-01-01 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-04 | Finished | [6 empty] | 90 | 2021-06-20 | Finished | POWER SUPPLY DELAY |  | 2021-07-01 | Finished |  |  | 2020-11-02 | Finished | [10 empty] | 2021-07-01 | Finished | [6 empty] | 2021-01-22 | Finished |  |  | 2021-01-28 | Finished |  |  | 2021-01-29 | Finished |  |  | 2021-07-01 | Finished | [13 empty] | no pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20014748 | 2020-12-22 |  |  |  | HDME001102 | 2021-01-22
TAJ0935-TH | HET | 61000969 | HO | ส่งมอบแล้ว | - | TH209255 | Siam Country Club Bangkok | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2020-10-15 | 2021-02-15 | 2021-03-15 | 2021-09-11 | P-1050-CO60W2,60S/2F | UAG-SN1 | 1050 | 60 | 2 | 2 |  | 791800 | Samut Prakan | แขวงบางนา | 2021-02-15 | 2021-02-16 | Finished | [34 empty] | 2021-02-15 | 2021-03-10 | 2021-03-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-15 | 2021-03-30 | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-02 | Finished |  |  | 100 | [41 empty] | 2021-04-02 | 2021-08-11 | 2021-08-11 | Finished |  |  | 2021-08-09 | 2021-08-12 | Finished |  |  | 2021-08-14 | Finished |  |  | 2021-08-16 | Finished |  |  | 100 | 2021-04-09 | 2021-08-26 | 2021-04-09 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-26 | Finished | [6 empty] | 90 | 2021-09-22 | Finished | CONSTRUCTION DELAY |  | 2021-08-30 | Finished |  |  | 2020-11-02 | Finished | [18 empty] | 2021-03-10 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | pass |  |  |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 1 | 1 | 99.74 | Blue |  |  | 20014834 | 2021-02-15 |  |  |  | HDME001161 | 2021-03-10 | QC Passed
TAJ0938-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-05-11 | 2021-05-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-05-11 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20014853 | 2021-03-15 |  |  |  | HDME001210 | 2021-05-11
TAJ0939-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-03-25 | 2021-03-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2021-05-24 | 2000-01-01 | 2021-05-24 | Finished |  |  | 2021-05-24 | Finished | [10 empty] | 50 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 0 | 16 | 461 | 3.35 | Green |  |  | 20014853 | 2021-01-29 |  |  |  | HDME001175 | 2021-03-25
TAJ0940-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-06-01 | 2021-06-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20014853 | 2021-05-04 |  |  |  | HDME001228 | 2021-06-01
TAJ0941-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-02-15 | 2021-02-20 | Finished | [34 empty] | 2021-01-15 | 2021-05-22 | 2021-02-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-28 | 2021-03-30 | 2021-03-05 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-30 | Finished |  |  | 100 | [41 empty] | 2021-03-30 | 2021-04-01 | 2021-04-01 | Finished |  |  | 2021-04-01 | 2021-04-01 | Finished | [10 empty] | 20 | 2021-04-05 | 2000-01-01 | 2021-04-05 | Finished |  |  | 2021-05-24 | Finished | [10 empty] | 50 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-02-23 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-28 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 64 | 0 | 16 | 80 | 83.23 | Green |  |  | 20014853 | 2021-01-29 |  |  |  | HDME001140 | 2021-02-23
TAJ0942-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-05-11 | 2021-05-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-05-11 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20014853 | 2021-03-15 |  |  |  | HDME001210 | 2021-05-11
TAJ0943-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-03-25 | 2021-03-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2021-05-24 | 2000-01-01 | 2021-05-24 | Finished |  |  | 2021-05-24 | Finished | [10 empty] | 50 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 0 | 16 | 461 | 3.35 | Green |  |  | 20014853 | 2021-01-29 |  |  |  | HDME001175 | 2021-03-25
TAJ0944-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-03-24 | 2021-03-24 | Finished | [34 empty] | 2021-01-15 | 2021-03-25 | 2021-03-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-25 | 2021-04-30 | 2021-03-25 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-10 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-21 | Finished |  |  | 2021-04-21 | Finished |  |  | 100 | [41 empty] | 2021-04-21 | 1900-01-01 | 2021-04-21 | Waiting | POWER SUPPLY DELAY |  | 2021-10-16 | [12 empty] | 0 | 2021-05-24 | 2000-01-01 | 2021-05-24 | Finished |  |  | 2021-05-24 | Finished | [10 empty] | 50 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-03-25 | Finished |  |  | 2021-03-25 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 0 | 16 | 97 | 79.66 | Green |  |  | 20014853 | 2021-01-29 |  |  |  | HDME001175 | 2021-03-25
TAJ0945-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-(B,C,D,E,F,G,H,I)-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 856000 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-06-01 | 2021-06-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished | [18 empty] | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20014853 | 2021-05-04 |  |  |  | HDME001228 | 2021-06-01
TAJ0936-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-A-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO90W1,90S/9F | UAG-SN1 | 1000 | 90 | 9 | 9 |  | 1123500 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-07-06 | 2021-07-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-06 | Finished |  |  | 2021-07-06 | Finished |  |  | 2021-07-08 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Green |  |  | 20014853 | 2021-05-04
TAJ0937-TH | HET | 61000970 | Install | ยังอยู่ในสัญญา HO | - | TH209174 | Inter Continental Residences Hua Hin | P-A-02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2020-09-24 | 2021-01-15 | 2021-12-15 |  | P-1000-CO90W1,90S/9F | UAG-SN1 | 1000 | 90 | 9 | 9 |  | 1123500 | Prachuap Khiri Khan | จังหวัดประจวบคีรีขันธ์ | 2021-09-20 | [36 empty] | 2021-01-15 | 2021-07-06 | 2021-07-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2020-11-03 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-06 | Finished |  |  | 2021-07-06 | Finished |  |  | 2021-07-08 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Green |  |  | 20014853 | 2021-05-04
TAJ0946-TH | HET | 61000971 | HO | ส่งมอบแล้ว | - | TH209278 | Home Pracharaj | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-10-19 | 2021-01-19 | 2021-03-06 | 2021-09-30 | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1107450 | Bangkok | แขวงห้วยขวาง เขตห้วยขวาง | 2021-02-01 | 2021-02-05 | Finished | [34 empty] | 2021-01-19 | 2021-02-05 | 2021-02-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-08 | 2021-02-18 | 2021-02-10 | Finished |  |  | 2021-02-13 | Finished |  |  | 2021-02-13 | Finished |  |  | 2021-02-13 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-02-28 | Finished |  |  | 100 | [41 empty] | 2021-02-28 | 2021-05-05 | 2021-05-05 | Finished |  |  | 2021-02-19 | 2021-05-07 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-22 | Finished |  |  | 100 | 2021-05-13 | 2021-07-21 | 2021-05-13 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-28 | Finished |  |  | 2021-07-21 | Finished |  |  | 100 | 2021-05-31 | Finished | CONSTRUCTION DELAY |  | 2021-06-24 | Finished |  |  | 2020-11-06 | Finished | [10 empty] | 2021-06-24 | Finished | [6 empty] | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-06-24 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished |  | pass | 2021-07-19 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20014878 | 2021-01-19 |  |  |  | HDME001122 | 2021-02-05 | QC Passed
TAJ0947-TH | HET | 61000972 | HO | ส่งมอบแล้ว | - | TH209266 | Fine Home Office | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2020-10-15 | 2021-02-15 | 2021-04-15 | 2021-05-15 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 930000 | Bangkok | แขวงออเงิน เขตสายไหม | 2021-03-12 | 2021-03-18 | Finished | [34 empty] | 2021-02-15 | 2021-03-02 | 2021-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-18 | 2021-04-30 | 2021-03-18 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-05-06 | Finished |  |  | 100 | [41 empty] | 2021-05-06 | 2021-06-17 | 2021-06-17 | Finished |  |  | 2021-06-10 | 2021-06-17 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-25 | Finished |  |  | 100 | 2021-05-10 | 2021-07-16 | 2021-05-10 | Finished |  |  | 2021-07-06 | Finished |  |  | 2021-07-16 | Finished | [6 empty] | 90 | 2021-07-16 | Finished | CONSTRUCTION DELAY |  | 2021-07-15 | Finished |  |  | 2020-11-03 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-03-02 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20014882 | 2021-02-15 |  |  |  | HDME001149 | 2021-03-02 | QC Passed
TFA1469-TH | HET | 61000973 | Install | ยังอยู่ในสัญญา HO | - | TH219047 | Academy of Dermatology (ADD) | ES7 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-10-27 | 2021-02-25 | 2021-04-25 | 2021-12-30 | 1200SX-EN,R3.9M,D35 | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงทุ่งพญาไท | 2021-01-10 | [20 empty] | 2021-01-10 | Finished | [14 empty] | 2021-02-10 | 2021-02-05 | 2021-02-07 | Finished | [14 empty] | 2021-02-25 | 2021-03-22 | [41 empty] | 2021-02-08 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-04 | Finished |  |  | 100 | 2021-03-04 | 1900-01-01 | 2021-03-04 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2022-03-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-25 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-02-16 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 4 | 14 | 50 | 92.05 | Green |  |  | 20014909 | 2021-02-10 |  |  |  | HDME001121 | 2021-02-05
TFA1470-TH | HET | 61000973 | Install | ยังอยู่ในสัญญา HO | - | TH219047 | Academy of Dermatology (ADD) | ES8 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-10-27 | 2021-02-25 | 2021-04-25 | 2021-12-30 | 1200SX-EN,R3.9M,D35 | SX-EN |  |  |  |  | 3900 | 1230500 | Bangkok | แขวงทุ่งพญาไท | 2021-01-10 | [20 empty] | 2021-01-10 | Finished | [14 empty] | 2021-02-10 | 2021-02-05 | 2021-02-07 | Finished | [14 empty] | 2021-02-25 | 2021-03-22 | [41 empty] | 2021-02-08 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-18 | Finished |  |  | 2021-02-19 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-27 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-04 | Finished |  |  | 100 | 2021-03-04 | 1900-01-01 | 2021-03-04 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2022-03-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-25 | Finished | [10 empty] | 2022-01-30 | Finished | [6 empty] | 2021-02-05 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-02-16 | Finished | [22 empty] | 567 | 32 | 16 | 14 | 629 | 0 | 32 | 4 | 14 | 50 | 92.05 | Green |  |  | 20014909 | 2021-02-10 |  |  |  | HDME001121 | 2021-02-05
TBL0413-TH | HET | 61000974 | HO | ยังอยู่ในสัญญา HO | - | TH209279 | Home Kedworrachai | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-10-16 | 2021-03-03 | 2021-03-31 | 2022-01-15 | OUG-600-CO60,60S/2F | OUG-ON1 | 600 | 60 | 2 | 2 |  | 1100000 | Bangkok | แขวงดอนเมือง | 2021-03-03 | 2021-03-03 | Finished | [34 empty] | 2021-03-15 | 2021-03-03 | 2021-02-17 | Finished | [14 empty] | 2021-03-03 | 2021-03-15 | 2021-03-15 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | [41 empty] | 2021-04-10 | 1900-01-01 | 2021-04-10 | Waiting | POWER SUPPLY DELAY |  | 2022-04-01 | [12 empty] | 0 | 2021-03-12 | 2000-01-01 | 2021-03-12 | Finished | [14 empty] | 25 | 2022-05-15 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2020-11-04 | Finished |  |  | 2021-04-01 | Finished | [14 empty] | 2021-02-17 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished | [22 empty] | 331 | 83 | 16 | 16 | 446 | 0 | 83 | 4 | 16 | 103 | 76.91 | Green |  |  | 20014964 | 2021-03-15 |  |  |  | HDME001135 | 2021-02-17
TAC1860-TH | HET | 61000975 | HO | เลยสัญญา HO | - | TH209280 | TINT Org 5 Floors | PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2020-10-21 | 2021-02-21 | 2021-04-21 | 2021-06-15 | VFI-900-CO60,60S/5F | VFI-II | 900 | 60 | 5 | 5 |  | 1123500 | Nakhon Nayok | ตำบลทรายมูล | 1900-01-01 | [36 empty] | 2021-02-22 | 2021-03-11 | 2021-03-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 1900-01-01 | 1900-01-01 | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-07 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-09 | Finished |  |  | 100 | [41 empty] | 2021-03-09 | 1900-01-01 | 2021-03-09 | Waiting | POWER SUPPLY DELAY |  | 2021-09-17 | [12 empty] | 0 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished | [14 empty] | 25 | 2021-10-04 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-12-04 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-11 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Red |  |  | 20015016 | 2021-02-22 |  |  |  | HDME001162 | 2021-03-11
TAC1861-TH | HET | 61000975 | HO | เลยสัญญา HO | - | TH209280 | TINT Org 5 Floors | PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2020-10-21 | 2021-02-21 | 2021-04-21 | 2021-06-15 | VFI-900-CO60,60S/5F | VFI-II | 900 | 60 | 5 | 5 |  | 1123500 | Nakhon Nayok | ตำบลทรายมูล | 1900-01-01 | [36 empty] | 2021-02-22 | 2021-03-11 | 2021-03-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 1900-01-01 | 1900-01-01 | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-07 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-09 | Finished |  |  | 100 | [41 empty] | 2021-03-09 | 1900-01-01 | 2021-03-09 | Waiting | POWER SUPPLY DELAY |  | 2021-09-17 | [12 empty] | 0 | 2021-05-28 | 2000-01-01 | 2021-05-28 | Finished | [14 empty] | 25 | 2021-10-04 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-12-04 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-11 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-16 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 4 | 16 | 111 | 82.92 | Red |  |  | 20015016 | 2021-02-22 |  |  |  | HDME001162 | 2021-03-11
TAJ0948-TH | HET | 61000977 | HO | ส่งมอบแล้ว | - | TH219050 | Innovative Glove¦s storey Staff Building | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2020-12-01 | 2021-03-01 | 2021-04-01 | 2021-07-01 | P-630-CO60W,60S/3F | UAG-SN1 | 630 | 60 | 3 | 3 |  | 1150000 | Songkhla | ตำบลทุ่งตำเสา | 2021-04-19 | 2021-04-12 | Finished | [34 empty] | 2021-03-01 | 2021-03-01 | 2021-03-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-01 | 2021-04-01 | 2021-04-25 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-12 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-22 | Finished |  |  | 100 | [41 empty] | 2021-05-22 | 2021-05-24 | 2021-05-24 | Finished |  |  | 2021-05-20 | 2021-05-25 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-09 | Finished |  |  | 100 | 2021-07-02 | 2000-01-01 | 2021-07-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-26 | Finished | [6 empty] | 90 | 2021-06-01 | Finished | CONSTRUCTION DELAY |  | 2021-07-08 | Finished |  |  | 2020-12-24 | Finished | [10 empty] | 2021-07-05 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-07-08 | Finished | [13 empty] | no pass |  |  |  |  | 320 | 80 | 16 | 16 | 432 | 0 | 0 | 0 | 1 | 1 | 99.77 | Blue |  |  | 20015574 | 2021-03-01 |  |  |  | HDME001167 | 2021-03-16
TAJ0950-TH | HET | 61000980 | HO | ส่งมอบแล้ว | - | TH219051 | Office Mityon | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-11 | 2021-01-29 | 2021-03-26 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 3 | 5 |  | 963000 | Bangkok | เขตจตุจักร | 2021-02-01 | 2021-02-02 | Finished | [34 empty] | 2021-02-02 | 2021-02-01 | 2021-02-02 | Finished | [14 empty] | 2021-02-01 | 2021-02-28 | 2021-02-02 | Finished |  |  | 2021-02-03 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-02-05 | Finished |  |  | 2021-02-06 | Finished |  |  | 2021-02-07 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-17 | Finished |  |  | 2021-02-19 | Finished |  |  | 100 | [41 empty] | 2021-02-19 | 2021-03-08 | 2021-03-08 | Finished |  |  | 2021-03-01 | 2021-03-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-03-12 | 2021-04-09 | 2021-03-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | 2021-03-26 | Finished | POWER SUPPLY DELAY |  | 2021-03-24 | Finished |  |  | 2020-11-25 | Finished | [18 empty] | 2021-02-02 | Finished |  |  | 2021-02-02 | Finished |  |  | 2021-02-04 | Finished |  |  | 2021-03-24 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  | pass | 2021-05-05 | Finished |  |  | 408 | 82 | 16 | 16 | 522 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20015245 | 2021-02-02 |  |  |  | HDME001112 | 2021-02-02 | QC Passed
TAJ0955-TH | HET | 61000981 | Install | ยังอยู่ในสัญญา HO | - | TH209281 | Oakwood Sukhumvit 36 | PL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-03-06 | 2021-01-15 | 2021-03-31 | 2021-10-28 | P-1000-CO90W1,90S/10F | UAG-SN1 | 1000 | 90 | 10 | 10 |  | 1219800 | Bangkok | แขวงคลองตัน | 2021-03-20 | 2021-03-20 | Finished | [34 empty] | 2021-01-25 | 2021-03-27 | 2021-03-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-22 | 2021-05-22 | 2021-03-23 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-17 | Finished |  |  | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-22 | Finished |  |  | 100 | [41 empty] | 2021-05-22 | 1900-01-01 | 2021-05-22 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-12-03 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 0 | 85 | 24 | 16 | 125 | 83.42 | Green |  |  | 20015176 | 2021-02-01 |  |  |  | HDME001185 | 2021-03-27
TAJ0956-TH | HET | 61000981 | Install | ยังอยู่ในสัญญา HO | - | TH209281 | Oakwood Sukhumvit 36 | PL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-03-06 | 2021-01-15 | 2021-03-31 | 2021-10-28 | P-1000-CO90W1,90S/10F | UAG-SN1 | 1000 | 90 | 10 | 10 |  | 1241200 | Bangkok | แขวงคลองตัน | 2021-03-20 | 2021-03-20 | Finished | [34 empty] | 2021-01-25 | 2021-03-27 | 2021-03-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-22 | 2021-05-22 | 2021-03-23 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-17 | Finished |  |  | 2021-04-22 | Finished |  |  | 2021-04-26 | Finished |  |  | 2021-04-28 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-22 | Finished |  |  | 100 | [41 empty] | 2021-05-22 | 1900-01-01 | 2021-05-22 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-12-03 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 0 | 85 | 24 | 16 | 125 | 83.42 | Green |  |  | 20015176 | 2021-02-01 |  |  |  | HDME001185 | 2021-03-27
TBL0414-TH | HET | 61000981 | Install | ยังอยู่ในสัญญา HO | - | TH209281 | Oakwood Sukhumvit 36 | SL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Jitphisut Piamsuktana-anan | 2020-03-06 | 2021-01-15 | 2021-03-31 | 2021-10-28 | OUG-1000-CO90,90S/10F | OUG-ON1 | 1000 | 90 | 10 | 10 |  | 1284000 | Bangkok | แขวงคลองตัน | 2021-04-28 | 2021-04-28 | Finished | [34 empty] | 2021-03-26 | 2021-05-22 | 2021-05-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-31 | 2021-09-28 | 2021-06-10 | Finished |  |  | 2021-06-13 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-19 | Finished | [26 empty] | 25 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-28 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-12-03 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-05-22 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 755 | 89 | 24 | 16 | 884 | 566 | 89 | 24 | 16 | 695 | 21.38 | Yellow |  |  | 20015176 | 2021-03-26 |  |  |  | HDME001219 | 2021-05-22
TBF0033-TH | HET | 61000985 | HO | ยังอยู่ในสัญญา HO | - | TH219054 | M&H Factory | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Somsak Sutthosri | 2021-03-08 | 2021-11-30 | 2021-12-30 |  | F-2000-2S45,45S/4F | F-EL | 2000 | 45 | 4 | 4 |  | 2942500 | Samut Prakan | ตำบลปากน้ำ | 2022-02-20 | [36 empty] | 2021-11-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-02-21 | 2022-03-21 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-22 | [12 empty] | 0 | [18 empty] | 0 | 2022-04-10 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-11-26 | Finished | [6 empty] | 2021-12-30 | Finished | [38 empty] | 583 | 106 | 48 | 20 | 757 | 583 | 106 | 48 | 20 | 757 | 0 | Green |  |  | 20017569 | 2022-02-14
TBF0034-TH | HET | 61000990 | HO | ยังอยู่ในสัญญา HO | - | TH219061 | Post Office Rayong | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2020-12-10 | 2021-07-09 | 2021-10-10 |  | F-1000-2S60,60S/3F | F-EL | 1000 | 60 | 3 | 3 |  | 2022300 | Rayong | ตำบลท่าประดู่ | 2021-08-23 | 2021-08-24 | Finished | [34 empty] | 2021-07-14 | 2021-04-17 | 2021-08-09 | Finished | STORE AREA | [13 empty] | 2021-08-23 | 2021-09-10 | 2021-08-26 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-29 | Finished |  |  | 2021-08-30 | Finished | [22 empty] | 45 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-11 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-26 | Working | [6 empty] | 2020-12-24 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-08-04 | Finished |  |  | 2021-08-04 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 515 | 94 | 36 | 20 | 665 | 283 | 94 | 36 | 20 | 433 | 34.89 | Orange |  |  | 20015705 | 2021-07-14
TBF0035-TH | HET | 61000990 | HO | ยังอยู่ในสัญญา HO | - | TH219061 | Post Office Rayong | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2020-12-10 | 2021-07-09 | 2021-10-10 |  | F-1000-2S60,60S/3F | F-EL | 1000 | 60 | 3 | 3 |  | 2022300 | Rayong | ตำบลท่าประดู่ | 2021-08-23 | 2021-08-24 | Finished | [34 empty] | 2021-07-14 | 2021-04-17 | 2021-08-09 | Finished | STORE AREA | [13 empty] | 2021-08-23 | 2021-09-10 | 2021-08-26 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-29 | Finished |  |  | 2021-08-30 | Finished | [22 empty] | 45 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-11 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-26 | Working | [6 empty] | 2020-12-24 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-08-04 | Finished |  |  | 2021-08-04 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 515 | 94 | 36 | 20 | 665 | 283 | 94 | 36 | 20 | 433 | 34.89 | Orange |  |  | 20015705 | 2021-07-14
TAJ0970-TH | HET | 61000996 | HO | ยังอยู่ในสัญญา HO | - | TH209286 | Chiangmai Grandview Hotel | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-11-17 | 2021-03-17 | 2021-05-17 | 2021-08-14 | P-1000-CO60W2,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1230500 | Chiang Mai | แขวงช้างเผือก | 2021-04-17 | 2021-04-18 | Finished | [34 empty] | 2021-03-26 | 2021-04-29 | 2021-04-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-17 | 2021-05-01 | 2021-05-21 | Finished |  |  | 2021-05-22 | Finished |  |  | 2021-05-23 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-05-29 | Finished |  |  | 2021-05-30 | Finished |  |  | 100 | [41 empty] | 2021-05-30 | 2021-08-13 | 2021-08-13 | Finished |  |  | 2021-12-16 | 2021-08-14 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-06-14 | 2021-08-24 | 2021-06-14 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-08-24 | Finished |  |  | 2021-08-24 | Finished |  |  | 100 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-01-14 | Finished | [10 empty] | 2021-09-01 | Finished | [6 empty] | 2021-04-29 | Finished |  |  | 2021-04-29 | Finished |  |  | 2021-04-30 | Finished | [17 empty] | pass |  |  |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 0 | 0 | 0 | 100 | Green |  |  | 20016024 | 2021-03-26 |  |  |  | HDME001202 | 2021-04-29 | QC Passed
TAC1876-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | P-CL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | VFI-1000-CO60,60S/10F | VFI-II | 1000 | 60 | 10 | 10 |  | 1203750 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | 2021-08-20 | Finished | [34 empty] | 2021-07-28 | 2021-07-28 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-10-12 | Finished | [6 empty] | 2022-02-28 | Finished | [6 empty] | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 763 | 95 | 24 | 16 | 898 | 4.37 | Green |  |  | 20015089 | 2021-07-28
TAC1877-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | P-CL-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | VFI-1000-CO60,60S/10F | VFI-II | 1000 | 60 | 10 | 10 |  | 1203750 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | 2021-08-20 | Finished | [34 empty] | 2021-07-28 | 2021-07-28 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-10-12 | Finished | [6 empty] | 2022-02-28 | Finished | [6 empty] | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 763 | 95 | 24 | 16 | 898 | 4.37 | Green |  |  | 20015089 | 2021-07-28
TEC0194-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | R-DL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | DT-100T-B30,30S/13F | DT | 100 | 30 | 13 | 13 |  | 695500 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | [36 empty] | 2021-07-28 | 2021-08-16 | 2021-08-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2022-02-28 | Finished | [38 empty] | 476 | 0 | 32 | 0 | 508 | 476 | 0 | 32 | 0 | 508 | 0 | Green |  |  | 20015090 | 2021-07-28
TAC1871-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | R-PL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | VFI-1000-CO120,120S/13F | VFI-II | 1000 | 120 | 13 | 13 |  | 1872500 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | 2021-08-20 | Finished | [34 empty] | 2021-07-28 | 2021-07-28 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-10-12 | Finished | [6 empty] | 2022-02-28 | Finished | [6 empty] | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Green |  |  | 20015089 | 2021-07-28
TAC1872-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | R-PL-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | VFI-1000-CO120,120S/13F | VFI-II | 1000 | 120 | 13 | 13 |  | 1872500 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | 2021-08-20 | Finished | [34 empty] | 2021-07-28 | 2021-07-28 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-10-12 | Finished | [6 empty] | 2022-02-28 | Finished | [6 empty] | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Green |  |  | 20015089 | 2021-07-28
TAC1873-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | R-PL-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | VFI-1000-CO120,120S/13F | VFI-II | 1000 | 120 | 13 | 13 |  | 1872500 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | 2021-08-20 | Finished | [34 empty] | 2021-07-28 | 2021-07-28 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-10-12 | Finished | [6 empty] | 2022-02-28 | Finished | [6 empty] | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Green |  |  | 20015089 | 2021-07-28
TAC1874-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | R-PL-4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | VFI-1000-CO120,120S/13F | VFI-II | 1000 | 120 | 13 | 13 |  | 1872500 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | 2021-08-20 | Finished | [34 empty] | 2021-07-28 | 2021-07-28 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-10-12 | Finished | [6 empty] | 2022-02-28 | Finished | [6 empty] | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Green |  |  | 20015089 | 2021-07-28
TAC1875-TH | HET | 61001002 | HO | ยังอยู่ในสัญญา HO | - | TH219014 | Medical Technology Research and Transfer Building | R-SL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-28 | 2021-07-28 | 2021-11-28 |  | VFI-1600-2S120,120S/13F | VFI-II | 1600 | 120 | 13 | 13 |  | 2140000 | Songkhla | ตำบลคอหงส์ | 2021-10-15 | 2021-08-20 | Finished | [34 empty] | 2021-07-28 | 2021-07-28 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2022-01-15 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-10-12 | Finished | [6 empty] | 2022-02-28 | Finished | [6 empty] | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished | [22 empty] | 969 | 107 | 32 | 20 | 1128 | 920 | 107 | 32 | 20 | 1079 | 4.34 | Green |  |  | 20015089 | 2021-07-28
TAK0973-TH | HET | 61001003 | Install | เลยสัญญา HO | - | TH219067 | EGAT Sriracha | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-10-26 | 2021-02-26 | 2021-04-26 | 2021-08-26 | B-750-2S60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1284000 | Chon Buri | อำเภอศรีราชา | 2021-04-26 | 2021-05-01 | Finished | [34 empty] | 2021-02-26 | 2021-02-26 | 2021-05-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-28 | 2021-03-28 | 2021-06-04 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-04 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-20 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-23 | Finished |  |  | 2021-07-24 | Finished |  |  | 100 | [41 empty] | 2021-07-24 | 2021-08-01 | 2021-08-01 | Finished |  |  | 2021-04-04 | 2021-08-01 | Finished |  |  | 2021-08-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 100 | 2021-09-01 | 2000-01-01 | 2021-09-01 | Finished |  |  | 2021-09-01 | Finished | [10 empty] | 50 | 2021-08-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-25 | Finished | [10 empty] | 2021-07-15 | Finished | [6 empty] | 2021-05-25 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-28 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 16 | 16 | 96.65 | Red |  |  | 20015123 | 2021-02-26 |  |  |  | HDME001221 | 2021-05-25
TEC0196-TH | HET | 61001004 | HO | ยังอยู่ในสัญญา HO | - | TH219068 | Library Building at Sukhothai Thammathirat | D1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-03 | 2021-03-15 | 2021-07-15 | 2021-11-30 | DF-200S-B30,30S/4F | DF | 200 | 30 | 4 | 4 |  | 395900 | Nonthaburi | อำเภอปากเกร็ด | 2021-08-01 | 2021-08-01 | Finished | [34 empty] | 2021-03-15 | 2021-03-29 | 2021-03-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-01 | 2021-09-30 | 2021-08-02 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-25 | Working | [6 empty] | 2020-11-27 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-29 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-01 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 242 | 0 | 16 | 0 | 258 | 4.8 | Green |  |  | 20015121 | 2021-03-15 |  |  |  | HDME001187 | 2021-03-29
TAJ0978-TH | HET | 61001004 | HO | ยังอยู่ในสัญญา HO | - | TH219068 | Library Building at Sukhothai Thammathirat | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-03 | 2021-03-15 | 2021-07-15 | 2021-11-30 | P-1000-CO105W1,105S/11F | UAG-SN1 | 1000 | 105 | 11 | 11 |  | 1530100 | Nonthaburi | อำเภอปากเกร็ด | 2021-05-05 | 2021-05-06 | Finished | [34 empty] | 2021-03-15 | 2021-03-20 | 2021-03-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-05 | 2021-08-30 | 2021-05-06 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-30 | Finished |  |  | 100 | [41 empty] | 2021-08-30 | 1900-01-01 | 2021-08-30 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2021-08-23 | 2000-01-01 | 2021-08-23 | Finished | [14 empty] | 25 | 2022-03-30 | Working | [6 empty] | 2020-11-27 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-20 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished | [17 empty] | in process (defect) |  |  |  |  | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20015120 | 2021-03-15 |  |  |  | HDME001171 | 2021-03-20
TAJ0979-TH | HET | 61001004 | HO | ยังอยู่ในสัญญา HO | - | TH219068 | Library Building at Sukhothai Thammathirat | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-03 | 2021-03-15 | 2021-07-15 | 2021-11-30 | P-1000-CO105W1,105S/11F | UAG-SN1 | 1000 | 105 | 11 | 11 |  | 1530100 | Nonthaburi | อำเภอปากเกร็ด | 2021-05-05 | 2021-05-06 | Finished | [34 empty] | 2021-03-15 | 2021-03-20 | 2021-03-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-05 | 2021-08-30 | 2021-05-06 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-30 | Finished |  |  | 100 | [41 empty] | 2021-08-30 | 1900-01-01 | 2021-08-30 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2021-08-23 | 2000-01-01 | 2021-08-23 | Finished | [14 empty] | 25 | 2022-03-30 | Working | [6 empty] | 2020-11-27 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-20 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished | [17 empty] | in process (defect) |  |  |  |  | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20015120 | 2021-03-15 |  |  |  | HDME001171 | 2021-03-20
TAJ0980-TH | HET | 61001004 | HO | ยังอยู่ในสัญญา HO | - | TH219068 | Library Building at Sukhothai Thammathirat | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-03 | 2021-03-15 | 2021-07-15 | 2021-11-30 | P-1000-CO105W1,105S/11F | UAG-SN1 | 1000 | 105 | 11 | 11 |  | 1530100 | Nonthaburi | อำเภอปากเกร็ด | 2021-05-05 | 2021-05-06 | Finished | [34 empty] | 2021-03-15 | 2021-03-20 | 2021-03-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-05 | 2021-08-30 | 2021-05-06 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-30 | Finished |  |  | 100 | [41 empty] | 2021-08-30 | 1900-01-01 | 2021-08-30 | Waiting | POWER SUPPLY DELAY |  | 2021-10-01 | [12 empty] | 0 | 2021-08-23 | 2000-01-01 | 2021-08-23 | Finished | [14 empty] | 25 | 2022-03-30 | Working | [6 empty] | 2020-11-27 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-20 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished | [17 empty] | in process (defect) |  |  |  |  | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20015120 | 2021-03-15 |  |  |  | HDME001171 | 2021-03-20
TBL0417-TH | HET | 61001004 | HO | ส่งมอบแล้ว | - | TH219068 | Library Building at Sukhothai Thammathirat | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-03 | 2021-03-15 | 2021-07-15 | 2021-11-30 | OUG-1000-CO105,105S/10F | OUG-ON1 | 1000 | 105 | 10 | 10 |  | 1498000 | Nonthaburi | อำเภอปากเกร็ด | 2021-05-05 | 2021-05-06 | Finished | [34 empty] | 2021-03-15 | 2021-03-27 | 2021-03-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-05 | 2021-08-30 | 2021-05-06 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-06 | Finished |  |  | 2021-06-07 | Finished |  |  | 100 | [41 empty] | 2021-06-07 | 2021-08-17 | 2021-08-17 | Finished |  |  | 2021-08-16 | 2021-08-19 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-08-23 | 2000-01-01 | 2021-08-23 | Finished |  |  | 2021-08-23 | Finished | [10 empty] | 50 | 2021-08-30 | Finished |  |  | 2021-08-24 | Finished |  |  | 2020-11-27 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-08-24 | Finished | [13 empty] | in process (defect) |  |  |  |  | 755 | 89 | 24 | 16 | 884 | 0 | 0 | 0 | 16 | 16 | 98.19 | Blue |  |  | 20015120 | 2021-03-26 |  |  |  | HDME001182 | 2021-03-27
TBL0418-TH | HET | 61001004 | HO | ยังอยู่ในสัญญา HO | - | TH219068 | Library Building at Sukhothai Thammathirat | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-03 | 2021-03-15 | 2021-07-15 | 2021-11-30 | OUG-1000-CO60,60S/7F | OUG-ON1 | 1000 | 60 | 7 | 7 |  | 1679900 | Nonthaburi | อำเภอปากเกร็ด | 2021-08-01 | 2021-08-01 | Finished | [34 empty] | 2021-03-15 | 2021-03-27 | 2021-03-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-01 | 2021-09-30 | 2021-08-02 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-25 | Working | [6 empty] | 2020-11-27 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 596 | 87 | 24 | 16 | 723 | 566 | 87 | 24 | 16 | 693 | 4.15 | Green |  |  | 20015120 | 2021-03-26 |  |  |  | HDME001182 | 2021-03-27
TBL0419-TH | HET | 61001004 | HO | ยังอยู่ในสัญญา HO | - | TH219068 | Library Building at Sukhothai Thammathirat | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-03 | 2021-03-15 | 2021-07-15 | 2021-11-30 | OUG-1000-CO60,60S/7F | OUG-ON1 | 1000 | 60 | 7 | 7 |  | 1679900 | Nonthaburi | อำเภอปากเกร็ด | 2021-08-01 | 2021-08-01 | Finished | [34 empty] | 2021-03-15 | 2021-03-27 | 2021-03-27 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-01 | 2021-09-30 | 2021-08-02 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-25 | Working | [6 empty] | 2020-11-27 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 596 | 87 | 24 | 16 | 723 | 566 | 87 | 24 | 16 | 693 | 4.15 | Green |  |  | 20015120 | 2021-03-26 |  |  |  | HDME001182 | 2021-03-27
TAJ0981-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-A-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-02-28 | 2021-12-01 | P-1000-CO90W1,90S/7F | UAG-SN1 | 1000 | 90 | 7 | 7 |  | 1005800 | Bangkok | แขวงวัดพระยาไกร | 2021-03-05 | 2021-03-06 | Finished | [34 empty] | 2021-02-02 | 2021-02-08 | 2021-02-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-05 | 2021-03-29 | 2021-03-08 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-21 | Finished |  |  | 100 | [41 empty] | 2021-03-21 | 1900-01-01 | 2021-03-21 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-03-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-12-03 | Finished | [18 empty] | 2021-02-08 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 83 | 6 | 16 | 105 | 83.06 | Green |  |  | 20015246 | 2021-02-02 |  |  |  | HDME001126 | 2021-02-08
TAJ0982-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-A-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-02-28 | 2021-12-01 | P-1000-CO90W1,90S/7F | UAG-SN1 | 1000 | 90 | 7 | 7 |  | 1005800 | Bangkok | แขวงวัดพระยาไกร | 2021-03-05 | 2021-03-06 | Finished | [34 empty] | 2021-02-02 | 2021-02-08 | 2021-02-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-05 | 2021-03-29 | 2021-03-08 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-21 | Finished |  |  | 2021-03-21 | Finished |  |  | 100 | [41 empty] | 2021-03-21 | 1900-01-01 | 2021-03-21 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2022-03-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-12-03 | Finished | [18 empty] | 2021-02-08 | Finished |  |  | 2021-02-10 | Finished |  |  | 2021-02-15 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 83 | 6 | 16 | 105 | 83.06 | Green |  |  | 20015246 | 2021-02-02 |  |  |  | HDME001126 | 2021-02-08
TAJ0983-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-B-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-03-31 | 2021-12-01 | P-1000-CO90W1,90S/11F | UAG-SN1 | 1000 | 90 | 11 | 11 |  | 1048600 | Bangkok | แขวงวัดพระยาไกร | 2021-05-15 | 2021-08-10 | Finished | [34 empty] | 2021-02-15 | 2021-03-12 | 2021-03-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-10 | 2021-09-10 | 2021-08-13 | Finished |  |  | 2021-08-20 | Finished | [34 empty] | 10 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-12-03 | Finished | [18 empty] | 2021-03-12 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 605 | 94 | 32 | 20 | 751 | 8.3 | Green |  |  | 20015246 | 2021-02-15 |  |  |  | HDME001164 | 2021-03-12
TAJ0984-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-B-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-03-31 | 2021-12-01 | P-1000-CO90W1,90S/11F | UAG-SN1 | 1000 | 90 | 11 | 11 |  | 1048600 | Bangkok | แขวงวัดพระยาไกร | 2021-05-15 | 2021-08-10 | Finished | [34 empty] | 2021-02-15 | 2021-03-12 | 2021-03-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-10 | 2021-09-10 | 2021-08-13 | Finished |  |  | 2021-08-20 | Finished | [34 empty] | 10 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-12-03 | Finished | [18 empty] | 2021-03-12 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 605 | 94 | 32 | 20 | 751 | 8.3 | Green |  |  | 20015246 | 2021-02-15 |  |  |  | HDME001164 | 2021-03-12
TAJ0985-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-B-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-03-31 | 2021-12-01 | P-1000-CO90W1,90S/11F | UAG-SN1 | 1000 | 90 | 11 | 11 |  | 1048600 | Bangkok | แขวงวัดพระยาไกร | 2021-05-15 | 2021-08-10 | Finished | [34 empty] | 2021-02-15 | 2021-03-12 | 2021-03-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-10 | 2021-09-10 | 2021-08-12 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-26 | Finished |  |  | 2021-08-26 | Finished |  |  | 2021-08-30 | Finished |  |  | 2021-08-30 | Finished | [10 empty] | 80 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-12-03 | Finished | [18 empty] | 2021-03-12 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 134 | 94 | 32 | 20 | 280 | 65.81 | Green |  |  | 20015246 | 2021-02-15 |  |  |  | HDME001164 | 2021-03-12
TAJ0986-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-C-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-04-30 | 2021-12-01 | P-1000-CO90W1,90S/10F | UAG-SN1 | 1000 | 90 | 10 | 10 |  | 1027200 | Bangkok | แขวงวัดพระยาไกร | 2021-06-04 | 2021-09-11 | Finished | [34 empty] | 2021-03-15 | 2021-03-27 | 2021-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-11 | 2021-10-11 | 2021-08-20 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-12-03 | Finished | [18 empty] | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 597 | 85 | 24 | 16 | 722 | 4.24 | Green |  |  | 20015246 | 2021-03-15 |  |  |  | HDME001181 | 2021-03-27
TAJ0987-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-C-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-04-30 | 2021-12-01 | P-1000-CO90W1,90S/10F | UAG-SN1 | 1000 | 90 | 10 | 10 |  | 1027200 | Bangkok | แขวงวัดพระยาไกร | 2021-06-04 | 2021-09-11 | Finished | [34 empty] | 2021-03-15 | 2021-04-03 | 2021-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-11 | 2021-10-11 | 2021-08-20 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-12-03 | Finished | [18 empty] | 2021-04-03 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-07 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 597 | 85 | 24 | 16 | 722 | 4.24 | Green |  |  | 20015246 | 2021-03-15
TAJ0988-TH | HET | 61001005 | Install | ยังอยู่ในสัญญา HO | - | TH219069 | The Salil Riverside | LP-C-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-15 | 2021-01-15 | 2021-04-30 | 2021-12-01 | P-1000-CO90W1,90S/10F | UAG-SN1 | 1000 | 90 | 10 | 10 |  | 1027200 | Bangkok | แขวงวัดพระยาไกร | 2021-06-04 | 2021-09-11 | Finished | [34 empty] | 2021-03-15 | 2021-04-03 | 2021-04-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-11 | 2021-10-11 | 2021-08-20 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-12-03 | Finished | [18 empty] | 2021-04-03 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-07 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 597 | 85 | 24 | 16 | 722 | 4.24 | Green |  |  | 20015246 | 2021-03-15
TBL0420-TH | HET | 61001006 | Install | เลยสัญญา HO | - | TH219007 | Niche Mono Itsaraphap | A1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-10-28 | 2021-03-31 | 2021-06-30 |  | OUG-630-CO60,60S/8F | OUG-ON1 | 630 | 60 | 8 | 8 |  | 832460 | Bangkok | เขตบางกอกใหญ่ | 2021-07-31 | [36 empty] | 2021-04-05 | 2021-04-29 | 2021-04-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-31 | 2021-06-30 | 2021-05-28 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-13 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-17 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | [41 empty] | 2021-06-21 | 1900-01-01 | 2021-06-21 | Waiting | POWER SUPPLY DELAY |  | 2021-06-05 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-31 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-27 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-05 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 649 | 88 | 24 | 16 | 777 | 0 | 88 | 24 | 16 | 128 | 83.53 | Red |  |  | 20015313 | 2021-04-05 |  |  |  | HDME001207 | 2021-05-05
TBL0421-TH | HET | 61001006 | Install | เลยสัญญา HO | - | TH219007 | Niche Mono Itsaraphap | A2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-10-28 | 2021-03-31 | 2021-06-30 |  | OUG-630-CO60,60S/8F | OUG-ON1 | 630 | 60 | 8 | 8 |  | 832460 | Bangkok | เขตบางกอกใหญ่ | 2021-07-31 | [36 empty] | 2021-04-06 | 2021-04-29 | 2021-04-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-31 | 2021-06-30 | 2021-05-28 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-13 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-17 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-06-21 | Finished |  |  | 100 | [41 empty] | 2021-06-21 | 1900-01-01 | 2021-06-21 | Waiting | POWER SUPPLY DELAY |  | 2021-06-05 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-31 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-27 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-05 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 649 | 88 | 24 | 16 | 777 | 0 | 88 | 24 | 16 | 128 | 83.53 | Red |  |  | 20015313 | 2021-04-05 |  |  |  | HDME001207 | 2021-05-05
TBL0422-TH | HET | 61001006 | Install | เลยสัญญา HO | - | TH219007 | Niche Mono Itsaraphap | B1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-10-28 | 2021-03-31 | 2021-06-30 |  | OUG-630-CO60,60S/8F | OUG-ON1 | 630 | 60 | 8 | 8 |  | 832460 | Bangkok | เขตบางกอกใหญ่ | 2021-03-31 | [36 empty] | 2021-04-07 | 2021-04-07 | 2021-04-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-31 | 2021-06-30 | 2021-04-28 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-06-24 | Finished |  |  | 2021-06-27 | Finished |  |  | 100 | [41 empty] | 2021-06-27 | 1900-01-01 | 2021-06-27 | Waiting | POWER SUPPLY DELAY |  | 2021-06-05 | [12 empty] | 0 | 2021-06-14 | 2000-01-01 | 2021-06-14 | Finished | [14 empty] | 25 | 2021-10-31 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-27 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-05 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 649 | 88 | 24 | 16 | 777 | 0 | 88 | 6 | 16 | 110 | 85.84 | Red |  |  | 20015313 | 2021-04-05 |  |  |  | HDME001207 | 2021-05-05
TBL0423-TH | HET | 61001006 | Install | เลยสัญญา HO | - | TH219007 | Niche Mono Itsaraphap | B2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-10-28 | 2021-03-31 | 2021-06-30 |  | OUG-630-CO60,60S/8F | OUG-ON1 | 630 | 60 | 8 | 8 |  | 832460 | Bangkok | เขตบางกอกใหญ่ | 2021-03-31 | [36 empty] | 2021-04-08 | 2021-04-07 | 2021-04-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-31 | 2021-06-30 | 2021-04-28 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-08 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-06-24 | Finished |  |  | 2021-06-27 | Finished |  |  | 100 | [41 empty] | 2021-06-27 | 1900-01-01 | 2021-06-27 | Waiting | POWER SUPPLY DELAY |  | 2021-06-05 | [12 empty] | 0 | 2021-06-14 | 2000-01-01 | 2021-06-14 | Finished | [14 empty] | 25 | 2021-10-31 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-11-27 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-05 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 649 | 88 | 24 | 16 | 777 | 0 | 88 | 6 | 16 | 110 | 85.84 | Red |  |  | 20015313 | 2021-04-05 |  |  |  | HDME001207 | 2021-05-05
TBL0429-TH | HET | 61001007 | HO | ส่งมอบแล้ว | - | TH219070 | Bangsaray Heights | S2-A | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-11-11 | 2021-04-09 | 2021-07-11 |  | OUG-1350-CO60,60S/6F | OUG-ON1 | 1350 | 60 | 6 | 6 |  | 2193500 | Chon Buri | อำเภอสัตหีบ | 2021-04-25 | 2021-04-25 | Finished | [34 empty] | 2021-04-09 | 2021-04-11 | 2021-04-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-01 | 2021-04-25 | 2021-05-02 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-06-02 | Finished |  |  | 100 | [41 empty] | 2021-06-02 | 2021-05-20 | 2021-05-20 | Finished |  |  | 2021-04-27 | 2021-06-05 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-14 | Finished |  |  | 100 | 2021-06-28 | 2000-01-01 | 2021-06-28 | Finished |  |  | 2021-07-19 | Finished |  |  | 2021-07-19 | Finished | [6 empty] | 90 | 2021-07-11 | Finished | CONSTRUCTION DELAY |  | 2021-06-30 | Finished |  |  | 2020-12-03 | Finished | [10 empty] | 2021-06-30 | Finished | [6 empty] | 2021-03-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-06-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Working |  |  | 2021-07-16 | Working |  | no pass |  |  |  |  | 543 | 86 | 24 | 16 | 669 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20015244 | 2021-04-09 |  |  |  | HDME001173 | 2021-03-23
TBL0428-TH | HET | 61001007 | HO | ส่งมอบแล้ว | - | TH219070 | Bangsaray Heights | S2-B | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | APHIRADA BUNKUEA | 2020-11-11 | 2021-04-09 | 2021-07-11 |  | OUG-1350-CO60,60S/7F | OUG-ON1 | 1350 | 60 | 7 | 7 |  | 2257700 | Chon Buri | อำเภอสัตหีบ | 2021-07-11 | 2021-05-01 | Finished | [34 empty] | 2021-04-09 | 2021-04-11 | 2021-03-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-01 | 2021-04-25 | 2021-05-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-20 | Finished |  |  | 2021-06-22 | Finished |  |  | 100 | [41 empty] | 2021-06-22 | 2021-06-28 | 2021-06-28 | Finished |  |  | 2021-04-27 | 2021-06-29 | Finished |  |  | 2021-07-01 | Finished |  |  | 2021-07-03 | Finished |  |  | 100 | 2021-06-28 | 2021-06-28 | 2021-06-28 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-06-28 | Finished | [6 empty] | 90 | 2021-07-11 | Finished | H/O DOCUMENT DELAY |  | 2021-07-29 | Finished |  |  | 2020-12-03 | Finished | [10 empty] | 2021-07-15 | Finished | [6 empty] | 2021-03-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-07-29 | Finished | [13 empty] | no qc |  |  |  |  | 596 | 87 | 24 | 16 | 723 | 0 | 0 | 0 | 1 | 1 | 99.86 | Blue |  |  | 20015244 | 2021-04-09 |  |  |  | HDME001173 | 2021-03-23 | QC Passed
TAC1878-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-03-16 | 2021-03-16 | 2021-04-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-08 | 2021-06-16 | 2021-03-17 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-21 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-03-16 |  |  |  | HDME001195 | 2021-04-21
TAC1887-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L10 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-04-20 | 2021-04-16 | 2021-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-18 | 2021-08-14 | 2021-06-02 | Finished | [14 empty] | 2021-08-10 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-06-25 | Finished |  |  | 80 | [41 empty] | 2021-06-25 | 1900-01-01 | 2021-06-25 | Waiting | POWER SUPPLY DELAY |  | 2021-07-17 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 138 | 93 | 24 | 16 | 271 | 67.19 | Red |  |  | 20015319 | 2021-04-20 |  |  |  | HDME001204 | 2021-04-30
TAC1879-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L2 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-03-16 | 2021-03-16 | 2021-04-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-08 | 2021-06-16 | 2021-03-17 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-16 | Finished |  |  | 2021-05-04 | Finished |  |  | 2021-05-06 | Finished |  |  | 2021-05-18 | Finished |  |  | 2021-05-20 | Finished |  |  | 100 | [41 empty] | 2021-05-20 | 1900-01-01 | 2021-05-20 | Waiting | POWER SUPPLY DELAY |  | 2021-05-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-21 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-03-16 |  |  |  | HDME001195 | 2021-04-21
TAC1880-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L3 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-03-16 | 2021-03-16 | 2021-04-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-09 | 2021-07-02 | 2021-03-17 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | [41 empty] | 2021-05-23 | 1900-01-01 | 2021-05-23 | Waiting | POWER SUPPLY DELAY |  | 2021-06-04 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-21 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-03-16 |  |  |  | HDME001195 | 2021-04-21
TAC1881-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L4 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-03-16 | 2021-03-16 | 2021-04-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-09 | 2021-07-02 | 2021-03-17 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-10 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | [41 empty] | 2021-05-23 | 1900-01-01 | 2021-05-23 | Waiting | POWER SUPPLY DELAY |  | 2021-06-04 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-21 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-03-16 |  |  |  | HDME001195 | 2021-04-21
TAC1882-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L5 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-03-16 | 2021-03-16 | 2021-04-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-09 | 2021-07-17 | 2021-05-05 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-05-30 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | [41 empty] | 2021-05-23 | 1900-01-01 | 2021-05-23 | Waiting | POWER SUPPLY DELAY |  | 2021-06-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-21 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-03-16 |  |  |  | HDME001195 | 2021-04-21
TAC1883-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L6 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-03-16 | 2021-03-16 | 2021-04-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-09 | 2021-07-17 | 2021-05-05 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-05-30 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | [41 empty] | 2021-05-23 | 1900-01-01 | 2021-05-23 | Waiting | POWER SUPPLY DELAY |  | 2021-06-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-21 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-03-16 |  |  |  | HDME001195 | 2021-04-21
TAC1884-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L7 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-04-20 | 2021-04-16 | 2021-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-17 | 2021-08-03 | 2021-05-05 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-05-30 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-22 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 100 | [41 empty] | 2021-06-03 | 1900-01-01 | 2021-06-03 | Waiting | POWER SUPPLY DELAY |  | 2021-07-06 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-04-20 |  |  |  | HDME001204 | 2021-04-30
TAC1885-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L8 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-04-20 | 2021-04-16 | 2021-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-17 | 2021-08-03 | 2021-05-05 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-05-30 | Finished |  |  | 2021-05-15 | Finished |  |  | 2021-05-22 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-03 | Finished |  |  | 100 | [41 empty] | 2021-06-03 | 1900-01-01 | 2021-06-03 | Waiting | POWER SUPPLY DELAY |  | 2021-07-06 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 0 | 93 | 24 | 16 | 133 | 83.9 | Red |  |  | 20015319 | 2021-04-20 |  |  |  | HDME001204 | 2021-04-30
TAC1886-TH | HET | 61001008 | HO | เลยสัญญา HO | - | TH209196 | Supalai City Resort Sukhumvit 107 | L9 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-03-16 | 2021-08-15 |  | VFI-750-CO60,60S/8F | VFI-II | 750 | 60 | 8 | 8 |  | 950000 | Samut Prakan | ต. สำโรงเหนือ | 2021-08-15 | [36 empty] | 2021-04-20 | 2021-04-16 | 2021-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-18 | 2021-08-14 | 2021-06-02 | Finished | [14 empty] | 2021-08-10 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-06-25 | Finished |  |  | 80 | [41 empty] | 2021-06-25 | 1900-01-01 | 2021-06-25 | Waiting | POWER SUPPLY DELAY |  | 2021-07-17 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 |  |  | CONSTRUCTION DELAY | [5 empty] | 2020-11-30 | Finished |  |  | 2021-05-01 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 693 | 93 | 24 | 16 | 826 | 138 | 93 | 24 | 16 | 271 | 67.19 | Red |  |  | 20015319 | 2021-04-20 |  |  |  | HDME001204 | 2021-04-30
TAK0989-TH | HET | 61001009 | HO | เลยสัญญา HO | - | TH219058 | Home K.Khantirak (Ladprao Soi 33) | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2020-11-09 | 2021-03-09 | 2021-04-24 |  | B-1000-2S60,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1284000 | Bangkok | แขวงลาดพร้าว | 2021-03-09 | 2021-03-08 | Finished | [34 empty] | 2021-03-09 | 2021-03-09 | 2021-03-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-09 | 2021-04-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-06-18 | 2000-01-01 | 2021-06-18 | Finished | [14 empty] | 25 | 2022-03-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-12-03 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-18 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 0 | 83 | 6 | 16 | 105 | 83.06 | Red |  |  | 20015372 | 2021-03-09 |  |  |  | HDME001169 | 2021-03-16
TFA1471-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | ES.1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-03-05 | 1200TX-EN,R5.2M,D35 | TX-EN |  |  |  |  | 5200 | 1177000 | Bangkok | แขวงจอมพล | 2021-09-29 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-29 | 2022-02-10 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20015638 | 2021-06-15
TFA1472-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | ES.2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 6 |  | 1 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-03-05 | 1200TX-EN,R5.2M,D35 | TX-EN |  |  |  |  | 5200 | 1177000 | Bangkok | แขวงจอมพล | 2021-09-29 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-29 | 2022-02-10 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20015638 | 2021-06-15
TBK0213-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | HVF-1600-CO210,210S/26F | HVF-5 | 1600 | 210 | 26 | 26 |  | 4601000 | Bangkok | แขวงจอมพล | 2021-12-01 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 1633 | 112 | 56 | 24 | 1825 | 1633 | 112 | 56 | 24 | 1825 | 0 | Green |  |  | 20015641 | 2021-12-01
TBK0214-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | HVF-1600-CO210,210S/26F | HVF-5 | 1600 | 210 | 26 | 26 |  | 4601000 | Bangkok | แขวงจอมพล | 2021-12-01 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 1633 | 112 | 56 | 24 | 1825 | 1633 | 112 | 56 | 24 | 1825 | 0 | Green |  |  | 20015641 | 2021-12-01
TBK0215-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | HVF-1600-CO210,210S/26F | HVF-5 | 1600 | 210 | 26 | 26 |  | 4601000 | Bangkok | แขวงจอมพล | 2021-12-01 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 1633 | 112 | 56 | 24 | 1825 | 1633 | 112 | 56 | 24 | 1825 | 0 | Green |  |  | 20015641 | 2021-12-01
TBK0216-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | HVF-1600-CO210,210S/26F | HVF-5 | 1600 | 210 | 26 | 26 |  | 4601000 | Bangkok | แขวงจอมพล | 2021-12-01 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 1633 | 112 | 56 | 24 | 1825 | 1633 | 112 | 56 | 24 | 1825 | 0 | Green |  |  | 20015641 | 2021-12-01
TBK0217-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | HVF-1600-CO210,210S/26F | HVF-5 | 1600 | 210 | 26 | 26 |  | 4601000 | Bangkok | แขวงจอมพล | 2021-12-01 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 1633 | 112 | 56 | 24 | 1825 | 1633 | 112 | 56 | 24 | 1825 | 0 | Green |  |  | 20015641 | 2021-12-01
TAC1888-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | VFI-900-CO90,90S/6F | VFI-II | 900 | 90 | 6 | 6 |  | 1337500 | Bangkok | แขวงจอมพล | 2021-09-29 | 2021-09-02 | Finished | [34 empty] | 2021-06-15 | 2021-08-08 | 2021-08-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-29 | 2022-02-10 | 2021-09-02 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2022-05-15 | Finished | [6 empty] | 2021-08-08 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 583 | 91 | 24 | 16 | 714 | 553 | 91 | 24 | 16 | 684 | 4.2 | Green |  |  | 20019172 | 2021-07-29
TAC1889-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | 7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | VFI-900-CO90,90S/6F | VFI-II | 900 | 90 | 6 | 6 |  | 1337500 | Bangkok | แขวงจอมพล | 2021-09-29 | 2021-09-02 | Finished | [34 empty] | 2021-06-15 | 2021-08-08 | 2021-08-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-29 | 2022-02-10 | 2021-09-02 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2022-05-15 | Finished | [6 empty] | 2021-08-08 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 583 | 91 | 24 | 16 | 714 | 553 | 91 | 24 | 16 | 684 | 4.2 | Green |  |  | 20019172 | 2021-07-29
TAC1890-TH | HET | 61001010 | Install | ยังอยู่ในสัญญา HO | - | TH219071 | Court of Justice | FL | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-03-16 | 2021-06-30 | 2021-09-29 | 2022-02-05 | VFI-1600-CO150,150S/26F | VFI-II | 1600 | 150 | 26 | 26 |  | 4066000 | Bangkok | แขวงจอมพล | 2021-12-01 | [36 empty] | 2021-06-15 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-05 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-05-15 | Finished | [38 empty] | 1688 | 118 | 56 | 24 | 1886 | 1688 | 118 | 56 | 24 | 1886 | 0 | Green |  |  | 20015641 | 2021-12-01
TAJ0992-TH | HET | 61001012 | HO | ส่งมอบแล้ว | - | TH219052 | Soken Warehouse | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-11-16 | 2021-03-02 | 2021-04-20 |  | P-1050-CO60D,60S/6F | UAG-SN1 | 1050 | 60 | 6 | 6 |  | 1123500 | Bangkok | เขตบางขุนเทียน | 2021-05-15 | 2021-05-24 | Finished | [34 empty] | 2021-03-02 | 2021-03-02 | 2021-03-05 | Finished | STORE AREA | [13 empty] | 2021-05-25 | 2021-06-30 | 2021-05-27 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-12 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-17 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-19 | Finished |  |  | 100 | [41 empty] | 2021-06-19 | 2021-06-30 | 2021-06-30 | Finished |  |  | 2021-06-30 | 2021-07-01 | Finished |  |  | 2021-07-05 | Finished |  |  | 2021-07-09 | Finished |  |  | 100 | 2021-06-21 | 2021-07-21 | 2021-06-21 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-21 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-07-15 | Finished |  |  | 2020-12-04 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-03-05 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 452 | 82 | 24 | 16 | 574 | 0 | 0 | 0 | 1 | 1 | 99.83 | Blue |  |  | 20015378 | 2021-03-02 | [5 empty] | QC Passed
TAJ0993-TH | HET | 61001013 | HO | ยังอยู่ในสัญญา HO | - | TH209201 | Click Sathorn 11 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-09-18 | 2021-02-10 | 2021-07-10 | 2021-10-10 | P-750-CO105,105S/11F | UAG-SN1 | 750 | 105 | 11 | 11 |  | 1070000 | Bangkok | ถนนสาทรใต้ | 2021-09-15 | [36 empty] | 2021-02-10 | 2021-03-20 | 2021-03-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-11-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | [6 empty] | 2020-12-04 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-20 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 673 | 94 | 32 | 20 | 819 | 0 | Orange |  |  | 20015388 | 2021-02-10 |  |  |  | HDME001172 | 2021-03-20
TAJ0994-TH | HET | 61001013 | HO | ยังอยู่ในสัญญา HO | - | TH209201 | Click Sathorn 11 | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-09-18 | 2021-02-10 | 2021-07-10 | 2021-10-10 | P-750-CO105,105S/11F | UAG-SN1 | 750 | 105 | 11 | 11 |  | 1070000 | Bangkok | ถนนสาทรใต้ | 2021-09-15 | [36 empty] | 2021-02-10 | 2021-03-20 | 2021-03-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-11-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-30 | Working | [6 empty] | 2020-12-04 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-03-20 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 673 | 94 | 32 | 20 | 819 | 0 | Orange |  |  | 20015388 | 2021-02-10 |  |  |  | HDME001172 | 2021-03-20
TAJ0995-TH | HET | 61001013 | HO | ยังอยู่ในสัญญา HO | - | TH209201 | Click Sathorn 11 | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Somsak Denpraphat | Prapaipim Netnonthai | 2020-09-18 | 2021-02-10 | 2021-07-10 | 2021-10-10 | P-600-CO105D,105S/11F | UAG-SN1 | 600 | 105 | 11 | 11 |  | 1037900 | Bangkok | ถนนสาทรใต้ | 2021-02-10 | 2021-02-26 | Finished | [34 empty] | 2021-02-10 | 2021-02-16 | 2021-02-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-27 | 2021-06-10 | 2021-03-02 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-18 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-03-23 | Finished |  |  | 100 | [41 empty] | 2021-03-23 | 1900-01-01 | 2021-03-23 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2021-04-02 | 2000-01-01 | 2021-04-02 | Finished | [14 empty] | 25 | 2021-12-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2020-12-04 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-02-16 | Finished |  |  | 2021-02-16 | Finished |  |  | 2021-02-17 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20015388 | 2021-02-10 |  |  |  | HDME001133 | 2021-02-16
TAJ0996-TH | HET | 61001014 | Install | เลยสัญญา HO | - | TH209272 | Car Parking Building Trok Chan | PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-06 | 2021-03-05 | 2021-05-06 |  | P-750-CO90,90S/9F | UAG-SN1 | 750 | 90 | 9 | 9 |  | 1250000 | Bangkok | แขวงทุ่งวัดดอน | 2021-10-01 | [36 empty] | 2021-03-05 | 2021-03-06 | 2021-03-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-05 | 2021-12-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-12-04 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-03-06 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Red |  |  | 20015417 | 2021-03-05
TAJ0997-TH | HET | 61001014 | Install | เลยสัญญา HO | - | TH209272 | Car Parking Building Trok Chan | PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Phumiphat Siprajan | 2020-10-06 | 2021-03-05 | 2021-05-06 |  | P-750-CO90,90S/9F | UAG-SN1 | 750 | 90 | 9 | 9 |  | 1250000 | Bangkok | แขวงทุ่งวัดดอน | 2021-10-01 | [36 empty] | 2021-03-05 | 2021-03-06 | 2021-03-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-05 | 2021-12-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2020-12-04 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-03-06 | Finished |  |  | 2021-03-06 | Finished |  |  | 2021-03-10 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Red |  |  | 20015417 | 2021-03-05
TAJ0998-TH | HET | 61001015 | HO | ส่งมอบแล้ว | - | TH219072 | Grand Rajchapruek | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-11-10 | 2021-02-25 | 2021-04-25 | 2021-12-25 | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1000000 | Bangkok | อำเภอปากเกร็ด | 2021-03-07 | 2021-03-07 | Finished | [34 empty] | 2021-02-25 | 2021-02-25 | 2021-02-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-08 | 2021-04-15 | 2021-03-08 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-15 | Finished |  |  | 2021-03-20 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-11 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-21 | Finished |  |  | 100 | [41 empty] | 2021-03-21 | 2021-06-22 | 2021-06-22 | Finished |  |  | 2021-06-25 | 2021-06-23 | Finished |  |  | 2021-06-28 | Finished |  |  | 2021-06-29 | Finished |  |  | 100 | 2021-04-02 | 2021-07-30 | 2021-04-02 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-07-30 | Finished | [6 empty] | 90 | 2021-07-25 | Finished | POWER SUPPLY DELAY |  | 2021-07-15 | Finished |  |  | 2021-01-05 | Finished | [10 empty] | 2021-07-30 | Finished | [6 empty] | 2021-03-02 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20015461 | 2021-02-25 |  |  |  | HDME001148 | 2021-03-02 | QC Passed
TEC0197-TH | HET | 61001016 | HO | เลยสัญญา HO | - | TH209202 | Court of Chaiyaphum | DW1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Somsak Sutthosri | 2020-11-14 | 2021-04-19 | 2021-06-14 | 2021-09-07 | DT-100S-B30,30S/4F | DT | 100 | 30 | 4 | 4 |  | 321000 | Chaiyaphum | อำเภอเมืองชัยภูมิ | 2021-08-15 | 2021-04-18 | Finished | [34 empty] | 2021-04-19 | 2021-07-06 | 2021-07-29 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-19 | 2021-05-19 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-15 | Working | [6 empty] | 2020-12-25 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2021-09-15 | Finished | [6 empty] | 2021-07-06 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 0 | 0 | 16 | 0 | 16 | 94.1 | Red |  |  | 20015489 | 2021-04-19
TAJ0999-TH | HET | 61001016 | HO | เลยสัญญา HO | - | TH209202 | Court of Chaiyaphum | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Somsak Sutthosri | 2020-11-14 | 2021-04-19 | 2021-06-14 | 2021-09-07 | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1408500 | Chaiyaphum | อำเภอเมืองชัยภูมิ | 2021-04-05 | 2021-04-19 | Finished | [34 empty] | 2021-04-19 | 2021-04-23 | 2021-04-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-19 | 2021-09-19 | 2021-05-08 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-11 | Finished | [14 empty] | 2021-05-11 | Finished |  |  | 2021-05-11 | Finished |  |  | 65 | [41 empty] | 2021-05-11 | 1900-01-01 | 2021-05-11 | Waiting | POWER SUPPLY DELAY |  | 2021-12-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2020-12-25 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-04-23 | Finished |  |  | 2021-04-23 | Finished |  |  | 2021-04-30 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 127 | 81 | 16 | 16 | 240 | 49.69 | Red |  |  | 20015488 | 2021-04-19 |  |  |  | HDME001196 | 2021-04-23
TAC1891-TH | HET | 61001016 | HO | เลยสัญญา HO | - | TH209202 | Court of Chaiyaphum | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | Somsak Sutthosri | 2020-11-14 | 2021-04-19 | 2021-06-14 | 2021-09-07 | VFI-900-CO60,60S/4F | VFI-II | 900 | 60 | 4 | 4 |  | 1408500 | Chaiyaphum | อำเภอเมืองชัยภูมิ | 2021-04-05 | 2021-04-19 | Finished | [34 empty] | 2021-04-19 | 2021-04-23 | 2021-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-19 | 2021-05-19 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-01-15 | Working | [6 empty] | 2020-12-25 | Finished |  |  | 2021-04-01 | Finished | [6 empty] | 2021-09-15 | Finished | [6 empty] | 2021-04-30 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 0 | 90 | 16 | 16 | 122 | 79.46 | Red |  |  | 20015488 | 2021-04-19 |  |  |  | HDME001203 | 2021-04-30
TAC1892-TH | HET | 61001019 | HO | ส่งมอบแล้ว | - | TH219074 | Indochina Grand Hotel | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2020-11-16 | 2021-03-16 | 2021-05-16 |  | VFI-750-CO60,60S/5F | VFI-II | 750 | 60 | 5 | 5 |  | 1070000 | Sa Kaeo | อำเภออรัญประเทศ | 2021-05-16 | 2021-05-16 | Finished | [34 empty] | 2021-03-16 | 2021-03-16 | 2021-03-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-17 | 2021-04-17 | 2021-04-04 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-11 | Finished |  |  | 2021-05-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-25 | Finished |  |  | 100 | [41 empty] | 2021-05-25 | 2021-05-25 | 2021-05-25 | Finished |  |  | 2021-04-18 | 2021-05-26 | Finished |  |  | 2021-06-28 | Finished |  |  | 2021-06-29 | Finished |  |  | 100 | 2021-05-17 | 2021-07-05 | 2021-05-17 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-05 | Finished | [6 empty] | 90 | 2021-05-16 | Finished | CONSTRUCTION DELAY |  | 2021-06-30 | Finished |  |  | 2020-12-24 | Finished | [10 empty] | 2021-06-30 | Finished | [6 empty] | 2021-03-19 | Finished |  |  | 2021-03-19 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-06-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-07-16 | Finished |  | pass | 2021-07-16 | Finished |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20015541 | 2021-03-16 |  |  |  | HDME001170 | 2021-03-19 | QC Passed
TAJ1004-TH | HET | 61001023 | HO | ส่งมอบแล้ว | - | TH219063 | Watthasup Mantion 2 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2020-11-29 | 2021-02-26 | 2021-04-29 |  | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1337500 | Suphan Buri | อำเภอเมืองสุพรรณบุรี | 2021-02-01 | 2021-02-01 | Finished | [34 empty] | 2021-02-26 | 2021-03-02 | 2021-03-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-02-26 | 2021-03-15 | 2021-03-02 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-07 | Finished |  |  | 2021-03-07 | Finished |  |  | 2021-03-07 | Finished |  |  | 2021-03-10 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-14 | Finished |  |  | 2021-03-15 | Finished |  |  | 100 | [41 empty] | 2021-03-15 | 2021-03-16 | 2021-03-16 | Finished |  |  | 2021-03-16 | 2021-03-16 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-18 | Finished |  |  | 100 | 2021-03-12 | 2021-03-29 | 2021-03-12 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-29 | Finished | [6 empty] | 90 | 2021-03-19 | Finished | POWER SUPPLY DELAY |  | 2021-03-29 | Finished |  |  | 2020-12-24 | Finished | [18 empty] | 2021-03-02 | Finished |  |  | 2021-03-02 | Finished |  |  | 2021-03-03 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  | pass | 2021-05-21 | Finished |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 1 | 1 | 99.79 | Blue |  |  | 20015610 | 2021-02-26 |  |  |  | HDME001147 | 2021-03-02 | QC Passed
TAK1005-TH | HET | 61001026 | HO | เลยสัญญา HO | - | TH219043 | Home Navatanee | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Prapaipim Netnonthai | 2020-09-30 | 2021-04-30 | 2021-06-30 | 2021-08-30 | B-750-2S60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1391000 | Bangkok | แขวงบึงกุ่ม | 2021-11-15 | [36 empty] | 2021-04-30 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-11-15 | 2021-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-07-17 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-09 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-10-15 | Finished | [38 empty] | 276 | 79 | 16 | 16 | 387 | 276 | 79 | 16 | 16 | 387 | 0 | Red |  |  | 20016170 | 2021-04-30
TBL0430-TH | HET | 61001028 | Test | ยังอยู่ในสัญญา HO | - | TH219082 | Ekamai Internation School | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2021-01-07 | 2021-06-07 | 2021-07-22 | 2021-10-26 | OUG-1000-CO60,60S/6F | OUG-ON1 | 1000 | 60 | 6 | 6 |  | 1337500 | Bangkok | แขวงคลองตันเหนือ | 2021-06-14 | 2021-06-14 | Finished | [34 empty] | 2021-06-07 | 2021-06-09 | 2021-06-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-21 | 2021-09-28 | 2021-06-18 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-09-01 | Finished |  |  | 2021-09-02 | Finished |  |  | 2021-09-03 | Finished |  |  | 2021-09-04 | Finished | [6 empty] | 90 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-16 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 54 | 86 | 24 | 16 | 180 | 73.09 | Green |  |  | 20016147 | 2021-06-07
TBL0431-TH | HET | 61001028 | Test | ยังอยู่ในสัญญา HO | - | TH219082 | Ekamai Internation School | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2021-01-07 | 2021-06-07 | 2021-07-22 | 2021-10-26 | OUG-1000-CO60,60S/6F | OUG-ON1 | 1000 | 60 | 6 | 6 |  | 1337500 | Bangkok | แขวงคลองตันเหนือ | 2021-06-14 | 2021-06-14 | Finished | [34 empty] | 2021-06-07 | 2021-06-09 | 2021-06-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-21 | 2021-09-28 | 2021-06-18 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-09-01 | Finished |  |  | 2021-09-02 | Finished |  |  | 2021-09-03 | Finished |  |  | 2021-09-04 | Finished | [6 empty] | 90 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-26 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-06-09 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-16 | Finished | [22 empty] | 543 | 86 | 24 | 16 | 669 | 54 | 86 | 24 | 16 | 180 | 73.09 | Green |  |  | 20016147 | 2021-06-07
TEB0217-TH | HET | 61001037 | HO | ส่งมอบแล้ว | - | TH219078 | Home Khun Wannee Natsakul | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-12-01 | 2021-03-01 | 2021-04-01 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 3 | 3 |  | 760000 | Bangkok | เขตบางคอแหลม | 1900-01-01 | [36 empty] | 2021-02-14 | 2021-03-12 | 2021-03-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 1900-01-01 | 1900-01-01 | 2021-03-29 | Finished |  |  | 2021-03-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-01 | Finished |  |  | 2021-04-02 | Finished |  |  | 2021-04-03 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-07 | Finished |  |  | 100 | [41 empty] | 2021-04-07 | 1900-01-01 | 2021-04-07 | Waiting | POWER SUPPLY DELAY |  | 1900-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-26 | Finished | [6 empty] | 90 | 2021-06-30 | Finished | CONSTRUCTION DELAY |  | 2021-06-30 | Finished |  |  | 2020-12-25 | Finished | [10 empty] | 2021-06-30 | Finished | [6 empty] | 2021-03-12 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-06-30 | Finished | [13 empty] | no qc |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20015645 | 2021-02-14 |  |  |  | HDME001166 | 2021-03-12
TAD0525-TH | HET | 61001038 | HO | ส่งมอบแล้ว | - | TH209138 | Health Center 58 | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2021-11-27 | 2021-03-26 | 2021-05-27 |  | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1250000 | Bangkok | แขวงบางปะกอก | 2021-03-26 | 2021-03-23 | Finished | [34 empty] | 2021-03-26 | 2021-03-26 | 2021-03-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-03-26 | 2021-05-05 | 2021-03-23 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 100 | [41 empty] | 2021-04-09 | 2021-04-12 | 2021-04-12 | Finished |  |  | 2021-04-20 | 2021-04-18 | Finished |  |  | 2021-04-19 | Finished |  |  | 2021-04-22 | Finished |  |  | 100 | 2021-05-17 | 2021-05-24 | 2021-05-17 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-17 | Finished |  |  | 2021-05-24 | Finished |  |  | 100 | 2021-10-25 | Finished | CONSTRUCTION DELAY |  | 2021-08-30 | Finished |  |  | 2020-12-24 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-03-26 | Finished |  |  | 2021-03-26 | Finished |  |  | 2021-03-29 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20015697 | 2021-03-26 |  |  |  | HDME001179 | 2021-03-26 | QC Passed
TAJ1020-TH | HET | 61001039 | HO | ส่งมอบแล้ว | - | TH219055 | Student Activity Center | P1(Bld.A) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2020-12-01 | 2021-02-19 | 2021-03-19 |  | P-1050-CO60W1,60S/4F | UAG-SN1 | 1050 | 60 | 4 | 4 |  | 1144900 | Pathum Thani | ตำบลคลองหนึ่ง | 2021-02-19 | 2021-02-19 | Finished | [34 empty] | 2021-03-08 | 2021-02-19 | 2021-02-23 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2021-02-19 | 2021-03-19 | 2021-02-19 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-06 | Finished |  |  | 100 | [41 empty] | 2021-03-06 | 2021-03-06 | 2021-03-06 | Finished |  |  | 2021-03-06 | 2021-03-07 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-15 | Finished |  |  | 100 | 2021-04-02 | 2021-07-16 | 2021-04-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-26 | Finished | H/O DOCUMENT DELAY |  | 2021-05-05 | Finished |  |  | 2020-12-24 | Finished | [10 empty] | 2021-05-05 | Finished | [6 empty] | 2021-03-03 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20015765 | 2021-03-08 |  |  |  | HDME001150 | 2021-03-03 | QC Passed
TAJ1021-TH | HET | 61001039 | HO | ส่งมอบแล้ว | - | TH219055 | Student Activity Center | P2(Bld.B) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2020-12-01 | 2021-02-19 | 2021-03-19 |  | P-1050-CO60W1,60S/4F | UAG-SN1 | 1050 | 60 | 4 | 4 |  | 1144900 | Pathum Thani | ตำบลคลองหนึ่ง | 2021-02-19 | 2021-02-19 | Finished | [34 empty] | 2021-03-08 | 2021-02-19 | 2021-02-23 | Finished | FACTORY SHIPMENT DELAY | [13 empty] | 2021-02-19 | 2021-03-19 | 2021-02-19 | Finished |  |  | 2021-02-22 | Finished |  |  | 2021-02-23 | Finished |  |  | 2021-02-24 | Finished |  |  | 2021-02-28 | Finished |  |  | 2021-03-01 | Finished |  |  | 2021-03-04 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-05 | Finished |  |  | 2021-03-06 | Finished |  |  | 100 | [41 empty] | 2021-03-06 | 2021-03-06 | 2021-03-06 | Finished |  |  | 2021-03-06 | 2021-03-07 | Finished |  |  | 2021-03-12 | Finished |  |  | 2021-03-15 | Finished |  |  | 100 | 2021-04-02 | 2021-07-16 | 2021-04-02 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-04-26 | Finished | H/O DOCUMENT DELAY |  | 2021-05-05 | Finished |  |  | 2020-12-24 | Finished | [10 empty] | 2021-05-05 | Finished | [6 empty] | 2021-03-03 | Finished |  |  | 2021-03-22 | Finished |  |  | 2021-03-23 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  | pass |  |  |  |  | 364 | 81 | 16 | 16 | 477 | 0 | 0 | 0 | 0 | 0 | 100 | Blue |  |  | 20015765 | 2021-03-08 |  |  |  | HDME001150 | 2021-03-03 | QC Passed
TAC1897-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | P1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1000-CO150,150S/29F | VFI-II | 1000 | 150 | 29 | 29 |  | 2788845 | Bangkok | แขวงลุมพินี | 2021-12-15 | [36 empty] | 2021-04-12 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-15 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2022-08-12 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 1853 | 120 | 56 | 24 | 2053 | 1853 | 120 | 56 | 24 | 2053 | 0 | Green |  |  | 20015956 | 2021-04-12
TAC1899-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | P2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1000-CO150,150S/31F | VFI-II | 1000 | 150 | 31 | 31 |  | 2902755 | Bangkok | แขวงลุมพินี | 2021-09-11 | [36 empty] | 2021-05-04 | 2021-08-21 | 2021-08-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2022-08-12 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-08-21 | Finished |  |  | 2021-08-21 | Finished |  |  | 2021-08-25 | Finished | [22 empty] | 1964 | 122 | 64 | 32 | 2182 | 1964 | 122 | 64 | 32 | 2182 | 0 | Green |  |  | 20015956 | 2021-05-04
TAC1904-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | P3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1000-CO150,150S/29F | VFI-II | 1000 | 150 | 29 | 29 |  | 2788845 | Bangkok | แขวงลุมพินี | 2021-04-30 | 2021-04-23 | Finished | [34 empty] | 2021-04-12 | 2021-05-09 | 2021-05-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-24 | 2021-07-01 | 2021-05-19 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | [41 empty] | 2021-05-23 | 1900-01-01 | 2021-05-23 | Waiting | POWER SUPPLY DELAY |  | 2022-01-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-01-29 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-05-09 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 1853 | 120 | 56 | 24 | 2053 | 0 | 120 | 56 | 24 | 200 | 90.26 | Green |  |  | 20015956 | 2021-04-12 |  |  |  | HDME001209 | 2021-05-09
TAC1901-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | P4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1000-CO150,150S/33F | VFI-II | 1000 | 150 | 33 | 33 |  | 3016665 | Bangkok | แขวงลุมพินี | 2021-12-16 | [36 empty] | 2021-05-17 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2022-08-12 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 2074 | 124 | 64 | 32 | 2294 | 2074 | 124 | 64 | 32 | 2294 | 0 | Green |  |  | 20015956 | 2021-05-17
TAC1902-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | P5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1600-CO150,150S/34F | VFI-II | 1600 | 150 | 34 | 34 |  | 3348620 | Bangkok | แขวงลุมพินี | 2021-12-16 | [36 empty] | 2021-06-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2022-08-12 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 2130 | 125 | 64 | 32 | 2351 | 2130 | 125 | 64 | 32 | 2351 | 0 | Green |  |  | 20015956 | 2021-06-01
TAC1898-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | P6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1000-CO150,150S/29F | VFI-II | 1000 | 150 | 29 | 29 |  | 2788845 | Bangkok | แขวงลุมพินี | 2021-04-30 | 2021-04-23 | Finished | [34 empty] | 2021-04-12 | 2021-05-09 | 2021-05-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-24 | 2021-07-01 | 2021-05-19 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-05-19 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 100 | [41 empty] | 2021-05-23 | 1900-01-01 | 2021-05-23 | Waiting | POWER SUPPLY DELAY |  | 2022-01-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-01-29 | Finished | [10 empty] | 2022-03-15 | Finished | [6 empty] | 2021-05-09 | Finished |  |  | 2021-05-09 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 1853 | 120 | 56 | 24 | 2053 | 0 | 120 | 56 | 24 | 200 | 90.26 | Green |  |  | 20015956 | 2021-04-12 |  |  |  | HDME001209 | 2021-05-09
TAC1900-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | P7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1000-CO150,150S/31F | VFI-II | 1000 | 150 | 31 | 31 |  | 2902755 | Bangkok | แขวงลุมพินี | 2021-09-11 | [36 empty] | 2021-05-04 | 2021-08-21 | 2021-08-21 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2022-01-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2022-08-12 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-08-21 | Finished |  |  | 2021-08-21 | Finished |  |  | 2021-08-25 | Finished | [22 empty] | 1964 | 122 | 64 | 32 | 2182 | 1964 | 122 | 64 | 32 | 2182 | 0 | Green |  |  | 20015956 | 2021-05-04
TAC1903-TH | HET | 61001040 | HO | ยังอยู่ในสัญญา HO | - | TH219090 | Scope Langsuan | S1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 | Weerapoj Paijitvijarn | Chanyuth Soithong | 2020-03-11 | 2021-04-01 | 2022-02-28 |  | VFI-1600-CO150,150S/34F | VFI-II | 1600 | 150 | 34 | 34 |  | 2800000 | Bangkok | แขวงลุมพินี | 2021-12-16 | [36 empty] | 2021-06-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-16 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-28 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2022-08-12 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 2130 | 125 | 64 | 32 | 2351 | 2130 | 125 | 64 | 32 | 2351 | 0 | Green |  |  | 20015956 | 2021-06-01
TAJ1029-TH | HET | 61001050 | HO | เลยสัญญา HO | - | TH219098 | PTT Property Phetkasem 110 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Thamnul Kongsar | 2021-01-20 | 2021-06-20 | 2021-08-20 |  | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1160950 | Bangkok | แขวงหนองค้างพลู | 2021-08-09 | 2021-08-23 | Finished | [34 empty] | 2021-06-18 | 2021-06-20 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-24 | 2021-09-24 | 2021-08-24 | Finished |  |  | 2021-08-27 | Finished | [10 empty] | 2021-08-31 | Finished |  |  | 2021-09-02 | Finished |  |  | 2021-09-04 | Finished | [14 empty] | 60 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-31 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-15 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-28 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 198 | 83 | 24 | 16 | 321 | 48.23 | Red |  |  | 20016317 | 2021-06-18
TEB0220-TH | HET | 61001061 | HO | ส่งมอบแล้ว | - | TH219056 | Home Khun Supang Cherngchavano | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2020-12-23 | 2021-03-23 | 2021-04-23 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 2 | 2 |  | 900000 | Bangkok | แขวงบางโคล่ | 1900-01-01 | [36 empty] | 2021-03-08 | 2021-03-16 | 2021-03-16 | Finished | [14 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 1900-01-01 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-04-09 | 2000-01-01 | 2021-04-09 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-26 | Finished | [6 empty] | 90 | 2021-09-07 | Finished | CONSTRUCTION DELAY |  | 2021-07-16 | Finished |  |  | 2021-01-29 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-03-16 | Finished |  |  | 2021-07-16 | Finished | [13 empty] | no pass |  |  |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20016026 | 2021-03-08 |  |  |  | HDME001178 | 2021-03-25
TAJ1040-TH | HET | 61001063 | HO | ยังอยู่ในสัญญา HO | - | TH219049 | The Medical Student Dormitory Bld. | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-12-30 | 2021-03-15 | 2021-08-25 | 2021-09-30 | P-1000-CO105W1,105S/18F | UAG-SN1 | 1000 | 105 | 18 | 18 |  | 1952750 | Bangkok | แขวงทุ่งพญาไท | 2021-03-23 | 2021-03-30 | Finished | [34 empty] | 2021-03-30 | 2021-03-27 | 2021-03-20 | Finished | OTHERS | [13 empty] | 2021-03-30 | 2021-07-15 | 2021-03-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-03 | Finished |  |  | 100 | [41 empty] | 2021-06-03 | 2021-06-03 | 2021-06-03 | Finished |  |  | 2021-07-16 | 2021-06-05 | Finished | [10 empty] | 20 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 983 | 99 | 40 | 20 | 1142 | 0 | 79 | 40 | 20 | 139 | 87.83 | Orange |  |  | 20016092 | 2021-03-30 |  |  |  | HDME001184 | 2021-03-27
TAJ1041-TH | HET | 61001063 | HO | ยังอยู่ในสัญญา HO | - | TH219049 | The Medical Student Dormitory Bld. | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-12-30 | 2021-03-15 | 2021-08-25 | 2021-09-30 | P-1000-CO105W1,105S/18F | UAG-SN1 | 1000 | 105 | 18 | 18 |  | 1952750 | Bangkok | แขวงทุ่งพญาไท | 2021-03-23 | 2021-03-30 | Finished | [34 empty] | 2021-03-30 | 2021-03-27 | 2021-03-20 | Finished | OTHERS | [13 empty] | 2021-03-30 | 2021-07-15 | 2021-03-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-03 | Finished |  |  | 100 | [41 empty] | 2021-06-03 | 2021-06-03 | 2021-06-03 | Finished |  |  | 2021-07-16 | 2021-06-05 | Finished | [10 empty] | 20 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 983 | 99 | 40 | 20 | 1142 | 0 | 79 | 40 | 20 | 139 | 87.83 | Orange |  |  | 20016092 | 2021-03-30 |  |  |  | HDME001184 | 2021-03-27
TAK1042-TH | HET | 61001063 | HO | ยังอยู่ในสัญญา HO | - | TH219049 | The Medical Student Dormitory Bld. | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-12-30 | 2021-03-15 | 2021-08-25 | 2021-09-30 | B-1000-2S105,105S/19F | UAG-SN1 | 1000 | 105 | 19 | 19 |  | 1979500 | Bangkok | แขวงทุ่งพญาไท | 2021-03-23 | 2021-03-30 | Finished | [34 empty] | 2021-03-30 | 2021-03-27 | 2021-03-02 | Finished | OTHERS | [13 empty] | 2021-03-30 | 2021-07-15 | 2021-03-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-23 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-03 | Finished |  |  | 100 | [41 empty] | 2021-06-03 | 2021-06-03 | 2021-06-03 | Finished |  |  | 2021-07-16 | 2021-06-10 | Finished | [10 empty] | 20 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-03-27 | Finished |  |  | 2021-03-27 | Finished |  |  | 2021-03-29 | Finished | [22 empty] | 1027 | 99 | 40 | 20 | 1186 | 0 | 79 | 40 | 20 | 139 | 88.28 | Orange |  |  | 20016092 | 2021-03-30 |  |  |  | HDME001184 | 2021-03-27
TAD0527-TH | HET | 61001064 | HO | ยังอยู่ในสัญญา HO | - | TH209210 | OPD Sung Men Hospital | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2021-01-04 | 2021-08-04 | 2021-10-04 |  | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1337500 | Phrae | ตำบลพระหลวง | 2021-08-07 | 2021-08-10 | Finished | [34 empty] | 2021-08-04 | 2021-08-11 | 2021-08-11 | Finished | PAYMENT DELAY | [13 empty] | 2021-10-04 | 2021-11-20 | 2021-08-17 | Finished |  |  | 2021-08-18 | Finished | [6 empty] | 2021-08-20 | Finished |  |  | 2021-08-21 | Finished |  |  | 2021-08-22 | Finished | [18 empty] | 55 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-08-15 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-11 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 237 | 91 | 16 | 16 | 360 | 44.62 | Orange |  |  | 20016137 | 2021-08-04
TAD0528-TH | HET | 61001064 | HO | ยังอยู่ในสัญญา HO | - | TH209210 | OPD Sung Men Hospital | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2021-01-04 | 2021-08-04 | 2021-10-04 |  | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1337500 | Phrae | ตำบลพระหลวง | 2021-08-07 | 2021-08-10 | Finished | [34 empty] | 2021-08-04 | 2021-08-11 | 2021-08-11 | Finished | PAYMENT DELAY | [13 empty] | 2021-10-04 | 2021-11-20 | 2021-08-17 | Finished |  |  | 2021-08-18 | Finished | [6 empty] | 2021-08-20 | Finished |  |  | 2021-08-21 | Finished |  |  | 2021-08-22 | Finished | [18 empty] | 55 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-01-29 | Finished |  |  | 2021-08-15 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-11 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 237 | 91 | 16 | 16 | 360 | 44.62 | Orange |  |  | 20016137 | 2021-08-04
TEB0221-TH | HET | 61001065 | HO | ส่งมอบแล้ว | - | TH219096 | Sukee Foundation | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2020-12-24 | 2021-03-24 | 2021-03-24 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 2 | 2 |  | 802500 | Bangkok | แขวงศาลาธรรมสพน์ เขตทวีวัฒนา | 2021-04-02 | 2021-04-02 | Finished | [34 empty] | 2021-03-13 | 2021-03-24 | 2021-03-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-02 | 2021-04-24 | 2021-04-03 | Finished |  |  | 2021-04-04 | Finished |  |  | 2021-04-05 | Finished |  |  | 2021-04-06 | Finished |  |  | 2021-04-07 | Finished |  |  | 2021-04-08 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-09 | Finished |  |  | 2021-04-10 | Finished |  |  | 100 | [41 empty] | 2021-04-10 | 2021-04-20 | 2021-04-20 | Finished |  |  | 2021-04-20 | 2021-04-21 | Finished |  |  | 2021-04-22 | Finished |  |  | 2021-04-23 | Finished |  |  | 100 | 2021-05-05 | 2021-05-05 | 2021-05-05 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-05-05 | Finished | [6 empty] | 90 | 2021-04-30 | Finished | CONSTRUCTION DELAY |  | 2021-04-30 | Finished |  |  | 2021-01-29 | Finished | [10 empty] | 2021-04-30 | Finished | [6 empty] | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-04-30 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-21 | Finished |  | pass | 2021-05-21 | Finished |  |  | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 0 | 1 | 1 | 99.61 | Blue |  |  | 20016144 | 2021-03-13 |  |  |  | HDME001188 | 2021-03-31 | QC Passed
TEC0200-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | DW-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | DF-100S-B30,30S/10F | DF | 100 | 30 | 10 | 10 |  | 500000 | Ratchaburi | ตำบลหน้าเมือง | 2021-09-19 | [36 empty] | 2021-08-02 | 2021-08-16 | 2021-08-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-19 | 2021-10-19 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-19 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2021-10-30 | Finished | [6 empty] | 2021-08-16 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-08-27 | Finished | [22 empty] | 393 | 0 | 24 | 0 | 417 | 393 | 0 | 24 | 0 | 417 | 0 | Green |  |  | 20016204 | 2021-08-02
TAC1910-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1000-CO90,90S/11F | VFI-II | 1000 | 90 | 11 | 11 |  | 1800000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-06-29 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-09-02 | Finished |  |  | 85 | [41 empty] | 2021-09-02 | 1900-01-01 | 2021-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-06-29 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 128 | 105 | 32 | 20 | 285 | 71.95 | Green |  |  | 20016203 | 2021-08-02
TAC1911-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1000-CO90,90S/11F | VFI-II | 1000 | 90 | 11 | 11 |  | 1800000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-06-29 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-09-02 | Finished |  |  | 85 | [41 empty] | 2021-09-02 | 1900-01-01 | 2021-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-06-29 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 128 | 105 | 32 | 20 | 285 | 71.95 | Green |  |  | 20016203 | 2021-08-02
TAC1912-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2050000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-06-29 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-09-02 | Finished |  |  | 85 | [41 empty] | 2021-09-02 | 1900-01-01 | 2021-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-06-29 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 128 | 105 | 32 | 20 | 285 | 71.95 | Green |  |  | 20016203 | 2021-08-02
TAC1913-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2050000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-06-29 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-09-02 | Finished |  |  | 85 | [41 empty] | 2021-09-02 | 1900-01-01 | 2021-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-06-29 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 128 | 105 | 32 | 20 | 285 | 71.95 | Green |  |  | 20016203 | 2021-08-02
TAC1914-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2050000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-06-29 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-10-30 | Finished | [6 empty] | 2021-06-29 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 214 | 105 | 32 | 20 | 371 | 63.48 | Green |  |  | 20016203 | 2021-08-02
TAC1915-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2050000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-07-02 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-10-30 | Finished | [6 empty] | 2021-07-02 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-08 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 214 | 105 | 32 | 20 | 371 | 63.48 | Green |  |  | 20016203 | 2021-08-02
TAC1916-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2050000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-07-02 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-10-30 | Finished | [6 empty] | 2021-07-02 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-08 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 214 | 105 | 32 | 20 | 371 | 63.48 | Green |  |  | 20016203 | 2021-08-02
TAC1917-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2050000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-07-02 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-10-30 | Finished | [6 empty] | 2021-07-02 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-08 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 214 | 105 | 32 | 20 | 371 | 63.48 | Green |  |  | 20016203 | 2021-08-02
TAC1918-TH | HET | 61001066 | Install | ยังอยู่ในสัญญา HO | - | TH219111 | Ratchaburi Hospital | L9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | 2020-12-30 | 2021-07-19 | 2021-10-30 |  | VFI-1600-2S90,90S/11F | VFI-II | 1600 | 90 | 11 | 11 |  | 2050000 | Ratchaburi | ตำบลหน้าเมือง | 2021-07-19 | 2021-07-01 | Finished | [34 empty] | 2021-08-02 | 2021-07-19 | 2021-07-02 | Finished | [14 empty] | 2021-07-19 | 2021-09-19 | 2021-07-03 | Finished |  |  | 2021-08-07 | Finished | [10 empty] | 2021-08-02 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-19 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | CUSTOMER DECORATION DELAY | [5 empty] | 2021-01-29 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-10-30 | Finished | [6 empty] | 2021-07-02 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-08 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 214 | 105 | 32 | 20 | 371 | 63.48 | Green |  |  | 20016203 | 2021-08-02
TAC1919-TH | HET | 61001068 | HO | ยังอยู่ในสัญญา HO | - | TH209269 | One Stop Service & Consultation Center | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2020-12-29 | 2021-07-20 | 2021-08-29 | 2021-09-30 | VFI-1600-CO60,60S/10F | VFI-II | 1600 | 60 | 10 | 10 |  | 1979500 | Bangkok | ตำบลตลาดขวัญ | 2021-06-22 | 2021-06-22 | Finished | [34 empty] | 2021-07-20 | 2021-06-29 | 2021-06-29 | Finished | [14 empty] | 2021-08-09 | 2021-09-15 | 2021-08-21 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-11 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-01 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-09-30 | Finished | [6 empty] | 2021-06-29 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 281 | 95 | 24 | 16 | 416 | 55.7 | Orange |  |  | 20016238 | 2021-07-20
TAJ1044-TH | HET | 61001069 | HO | ส่งมอบแล้ว | - | TH209288 | Thaveeboon Home | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Weerapoj Paijitvijarn | Somsak Sutthosri | 2020-10-06 | 2020-12-25 | 2021-01-25 |  | P-750-CO60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1267250 | Samut Prakan | อำเภอบางบ่อ | 2020-12-26 | 2021-01-25 | Finished | [34 empty] | 2020-12-25 | 2020-12-25 | 2021-02-26 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-01-15 | 2021-01-30 | 2021-01-17 | Finished |  |  | 2021-01-18 | Finished |  |  | 2021-01-20 | Finished |  |  | 2021-01-21 | Finished |  |  | 2021-01-22 | Finished |  |  | 2021-01-23 | Finished |  |  | 2021-01-24 | Finished |  |  | 2021-01-25 | Finished |  |  | 2021-01-26 | Finished |  |  | 2021-01-27 | Finished |  |  | 100 | [41 empty] | 2021-01-27 | 2021-02-10 | 2021-02-10 | Finished |  |  | 2021-02-02 | 2021-02-11 | Finished |  |  | 2021-02-12 | Finished |  |  | 2021-01-13 | Finished |  |  | 100 | 2021-02-08 | 2021-03-05 | 2021-02-08 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-03-05 | Finished | [6 empty] | 90 | 2021-02-15 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-02-09 | Finished | [18 empty] | 2020-12-24 | Finished |  |  | 2020-12-26 | Finished |  |  | 2020-12-28 | Finished |  |  | 2021-02-15 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  |  | 2021-03-17 | Finished |  | pass | 2021-03-17 | Finished |  |  | 276 | 79 | 16 | 16 | 387 | 0 | 0 | 0 | 1 | 1 | 99.74 | Blue | [9 empty] | QC Passed
TAC1920-TH | HET | 61001070 | HO | ส่งมอบแล้ว | - | TH219091 | Joon Chee Factory Phase 2 | EL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2021-01-12 | 2021-05-12 | 2021-07-12 | 2021-08-30 | VFI-1000-CO105,105S/5F | VFI-II | 1000 | 105 | 5 | 5 |  | 1450000 | Chon Buri | อำเภอศรีราชา | 2021-05-13 | 2021-05-22 | Finished | [34 empty] | 2021-05-12 | 2021-05-12 | 2021-05-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-14 | 2021-06-14 | 2021-05-26 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-03 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-06 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-15 | Finished |  |  | 100 | [41 empty] | 2021-06-15 | 2021-06-15 | 2021-06-15 | Finished |  |  | 2021-06-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-06-28 | 2000-01-01 | 2021-06-28 | Finished |  |  | 2021-09-01 | Finished |  |  | 2021-09-01 | Finished | [6 empty] | 90 | 2021-08-27 | Finished | POWER SUPPLY DELAY |  | 2021-08-30 | Finished |  |  | 2021-02-09 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-05-12 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | no pass |  |  |  |  | 527 | 91 | 16 | 16 | 650 | 0 | 0 | 0 | 1 | 1 | 99.85 | Blue |  |  | 20016308 | 2021-05-12 |  |  |  | HDME001211 | 2021-05-12
TAC1921-TH | HET | 61001071 | HO | เลยสัญญา HO | - | TH219085 | Faculty of Environment KU | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-01-11 | 2021-06-11 | 2021-08-11 | 2021-09-11 | VFI-1000-CO90,90S/4F | VFI-II | 1000 | 90 | 4 | 4 |  | 1070000 | Bangkok | จังหวัดกรุงเทพมหานคร 10220 | 2021-05-25 | 2021-06-28 | Finished | [34 empty] | 2021-04-27 | 2021-05-20 | 2021-05-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-15 | 2021-07-15 | 2021-06-29 | Finished |  |  | 2021-07-05 | Finished |  |  | 2021-07-05 | Finished |  |  | 2021-07-09 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-07-20 | Finished |  |  | 2021-07-23 | Finished |  |  | 2021-07-27 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-06 | Finished |  |  | 100 | [41 empty] | 2021-08-06 | 1900-01-01 | 2021-08-06 | Waiting | POWER SUPPLY DELAY |  | 2021-07-10 | [12 empty] | 0 | 2021-08-03 | 2000-01-01 | 2021-08-03 | Finished | [14 empty] | 25 | 2021-10-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-28 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-05-31 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 0 | 90 | 4 | 16 | 110 | 81.48 | Red |  |  | 20016313 | 2021-04-27 |  |  |  | HDME001224 | 2021-05-28
TAJ1045-TH | HET | 61001072 | HO | เลยสัญญา HO | - | TH219108 | Home Khun Somjet | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-01-08 | 2021-06-08 | 2021-08-08 |  | P-1000-CO60W1,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 900000 | Kanchanaburi | อำเภอเมือง | 2021-06-01 | [36 empty] | 2021-06-08 | 2021-06-08 | 2021-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-10 | 2021-08-08 | 2021-06-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-08-25 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-31 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-01-29 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-10 | Finished | [22 empty] | 276 | 79 | 16 | 16 | 387 | 0 | 79 | 16 | 16 | 111 | 71.32 | Red |  |  | 20016359 | 2021-06-08 |  |  |  | HDME001235 | 2021-06-08
TAJ1046-TH | HET | 61001073 | HO | ยังอยู่ในสัญญา HO | - | TH209198 | Walailak University Building 6 | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-01-18 | 2021-05-03 | 2021-07-03 | 2021-10-28 | P-1000-2S60,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1070000 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-05-14 | 2021-05-07 | Finished | [34 empty] | 2021-05-03 | 2021-05-07 | 2021-05-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-03 | 2021-06-03 | 2021-05-11 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | [41 empty] | 2021-06-10 | 1900-01-01 | 2021-06-10 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2021-07-14 | 2000-01-01 | 2021-07-14 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-07 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 4 | 16 | 101 | 78.83 | Green |  |  | 20016388 | 2021-05-03 |  |  |  | HDME001208 | 2021-05-07
TAJ1047-TH | HET | 61001073 | HO | ยังอยู่ในสัญญา HO | - | TH209198 | Walailak University Building 6 | EL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-01-18 | 2021-05-03 | 2021-07-03 | 2021-10-28 | P-1000-2S60,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1070000 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-05-14 | 2021-05-07 | Finished | [34 empty] | 2021-05-03 | 2021-05-07 | 2021-05-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-03 | 2021-06-03 | 2021-05-11 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-05-20 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-10 | Finished |  |  | 100 | [41 empty] | 2021-06-10 | 1900-01-01 | 2021-06-10 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2021-07-14 | 2000-01-01 | 2021-07-14 | Finished | [14 empty] | 25 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-10-15 | Finished | [6 empty] | 2021-05-07 | Finished |  |  | 2021-05-07 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 0 | 81 | 4 | 16 | 101 | 78.83 | Green |  |  | 20016388 | 2021-05-03 |  |  |  | HDME001208 | 2021-05-07
TAJ1048-TH | HET | 61001074 | HO | ยังอยู่ในสัญญา HO | - | TH219048 | Apartment Khun Pakorn | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2021-01-26 | 2021-06-25 | 2021-10-26 |  | P-630-CO60W,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 1070000 | Chon Buri | อำเภอพานทอง | 2021-06-28 | 2021-08-09 | Finished | [34 empty] | 2021-06-25 | 2021-06-26 | 2021-07-22 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-29 | 2021-09-21 | 2021-08-10 | Finished |  |  | 2021-08-13 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-19 | Finished | [14 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-27 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-12 | Working | [6 empty] | 2021-03-11 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-10-21 | Finished | [6 empty] | 2021-07-22 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 102 | 82 | 16 | 16 | 216 | 58.62 | Green |  |  | 20016547 | 2021-06-25
TAJ1049-TH | HET | 61001075 | Install | ยังอยู่ในสัญญา HO | - | TH209008 | Human Resource Development Center, KMUTNB Rayong | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2021-01-21 | 2021-04-21 | 2021-07-21 | 2021-12-25 | P-1000-CO105W1,105S/11F | UAG-SN1 | 1000 | 105 | 11 | 11 |  | 1588950 | Rayong | อำเภอบ้านค่าย | 2021-04-26 | 2021-06-25 | Finished | [34 empty] | 2021-04-21 | 2021-04-21 | 2021-05-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-27 | 2021-06-05 | 2021-06-26 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-10 | Finished |  |  | 2021-07-12 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-01 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-12-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-04-28 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-08 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20016479 | 2021-04-21 |  |  |  | HDME001201 | 2021-04-28
TAJ1050-TH | HET | 61001075 | Install | ยังอยู่ในสัญญา HO | - | TH209008 | Human Resource Development Center, KMUTNB Rayong | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2021-01-21 | 2021-04-21 | 2021-07-21 | 2021-12-25 | P-1000-CO105W1,105S/11F | UAG-SN1 | 1000 | 105 | 11 | 11 |  | 1588950 | Rayong | อำเภอบ้านค่าย | 2021-04-26 | 2021-06-25 | Finished | [34 empty] | 2021-04-21 | 2021-04-21 | 2021-05-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-27 | 2021-06-05 | 2021-06-26 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-10 | Finished |  |  | 2021-07-12 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-01 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-12-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-04-28 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-08 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20016479 | 2021-04-21 |  |  |  | HDME001201 | 2021-04-28
TAJ1051-TH | HET | 61001075 | Install | ยังอยู่ในสัญญา HO | - | TH209008 | Human Resource Development Center, KMUTNB Rayong | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2021-01-21 | 2021-04-21 | 2021-07-21 | 2021-12-25 | P-1000-CO105W1,105S/11F | UAG-SN1 | 1000 | 105 | 11 | 11 |  | 1588950 | Rayong | อำเภอบ้านค่าย | 2021-04-26 | 2021-06-25 | Finished | [34 empty] | 2021-04-21 | 2021-04-21 | 2021-05-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-27 | 2021-06-05 | 2021-06-26 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-10 | Finished |  |  | 2021-07-12 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-01 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-12-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-04-28 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-08 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20016479 | 2021-04-21 |  |  |  | HDME001201 | 2021-04-28
TAJ1052-TH | HET | 61001075 | Install | ยังอยู่ในสัญญา HO | - | TH209008 | Human Resource Development Center, KMUTNB Rayong | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2021-01-21 | 2021-04-21 | 2021-07-21 | 2021-12-25 | P-1000-CO105W1,105S/11F | UAG-SN1 | 1000 | 105 | 11 | 11 |  | 1588950 | Rayong | อำเภอบ้านค่าย | 2021-04-26 | 2021-06-25 | Finished | [34 empty] | 2021-04-21 | 2021-04-21 | 2021-06-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-27 | 2021-06-05 | 2021-06-26 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-10 | Finished |  |  | 2021-07-12 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-12-01 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-12-25 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished | [22 empty] | 673 | 94 | 32 | 20 | 819 | 0 | 94 | 8 | 20 | 122 | 85.1 | Green |  |  | 20016479 | 2021-04-21 |  |  |  | HDME001226 | 2021-06-01
TAJ1053-TH | HET | 61001075 | Install | เลยสัญญา HO | - | TH209008 | Human Resource Development Center, KMUTNB Rayong | L5 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | 2021-01-21 | 2021-04-21 | 2021-07-21 | 2021-08-21 | P-1000-CO90W1,90S/10F | UAG-SN1 | 1000 | 90 | 9 | 10 |  | 1519400 | Rayong | อำเภอบ้านค่าย | 2021-09-30 | [36 empty] | 2021-04-21 | 2021-04-21 | 2021-06-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-30 | 2021-10-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-25 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished |  |  | 2021-06-01 | Finished | [22 empty] | 629 | 85 | 24 | 16 | 754 | 629 | 85 | 24 | 16 | 754 | 0 | Red |  |  | 20016479 | 2021-04-21 |  |  |  | HDME001226 | 2021-06-01
TAJ1054-TH | HET | 61001076 | Install | เลยสัญญา HO | - | TH219077 | Hotel 5 Fl. Soi Phahonyothin 1 (Real One) | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-12-25 | 2021-04-30 | 2021-06-15 |  | P-750-CO60,60S/5F | UAG-SN1 | 750 | 60 | 5 | 5 |  | 1123500 | Bangkok | แขวงสามเสนใน | 2021-04-28 | 2021-04-27 | Finished | [34 empty] | 2021-04-30 | 2021-04-28 | 2021-05-05 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-04-28 | 2021-05-15 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2022-07-16 | [12 empty] | 0 | 2021-07-30 | 2000-01-01 | 2021-07-30 | Finished | [14 empty] | 25 | 2022-06-13 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2022-02-15 | Finished | [6 empty] | 2021-05-05 | Finished |  |  | 2021-05-05 | Finished |  |  | 2021-05-08 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Red |  |  | 20016480 | 2021-04-30 |  |  |  | HDME001206 | 2021-05-05
TAC1922-TH | HET | 61001077 | Install | ยังอยู่ในสัญญา HO | - | TH219115 | 230/115kv Terminal Klongdan | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Thamnul Kongsar | 2021-01-25 | 2021-05-25 | 2021-07-25 | 2021-12-30 | VFI-700-CO60,60S/4F | VFI-II | 700 | 60 | 4 | 4 |  | 1230500 | Samut Prakan | อำเภอบางบ่อ | 2021-11-25 | [36 empty] | 2021-05-25 | 2021-06-08 | 2021-06-08 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-11-25 | 2021-12-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-10 | Finished | [10 empty] | 2021-08-25 | Finished | [6 empty] | 2021-06-08 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-10 | Finished | [22 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Green |  |  | 20016490 | 2021-05-25 |  |  |  | HDME001234 | 2021-06-08
TBL0478-TH | HET | 61001080 | Test | เลยสัญญา HO | - | TH219116 | Suksanari School | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Yosvaris Limmethaphant | 2021-01-25 | 2021-06-16 | 2021-07-10 |  | OUG-1000-CO60,60S/7F | OUG-ON1 | 1000 | 60 | 7 | 7 |  | 1337500 | Bangkok | แขวงกัลยา | 2021-06-01 | [36 empty] | 2021-06-17 | 2021-06-18 | 2021-06-18 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-21 | 2021-07-10 | 2021-06-08 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-08-30 | [12 empty] | 0 | 2021-08-23 | 2000-01-01 | 2021-08-23 | Finished | [14 empty] | 25 | 2021-09-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-09 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-06-18 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-21 | Finished | [22 empty] | 596 | 87 | 24 | 16 | 723 | 0 | 87 | 6 | 16 | 109 | 84.92 | Red |  |  | 20016478 | 2021-06-17
TFA1951-TH | HET | 61001084 | HO | เลยสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-07-31 |  | 1200TX-EN,R5.2M,D30 | TX-EN |  |  |  |  | 5200 | 1310750 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-06-11 | 2021-06-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-28 | Finished | [18 empty] | 2021-06-11 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20016539 | 2021-06-10
TFA1960-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC10 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R4.75M,D30 | TX-EN |  |  |  |  | 4750 | 1230500 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-07-12 | 2021-07-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-12 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20016539 | 2021-06-10
TFA1961-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC11 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1962-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC12 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1963-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC13 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1964-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC14 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1965-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC15 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1966-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC16 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1967-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC17 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1968-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC18 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R7.05M,D30 | TX-EN |  |  |  |  | 7050 | 1732062.5 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-08-12 | 2021-09-04 | 2021-09-04 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-23 | Finished | [14 empty] | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Green |  |  | 20016539 | 2021-08-12
TFA1952-TH | HET | 61001084 | HO | เลยสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-07-31 |  | 1200TX-EN,R5.2M,D30 | TX-EN |  |  |  |  | 5200 | 1310750 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-06-11 | 2021-06-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-28 | Finished | [18 empty] | 2021-06-11 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20016539 | 2021-06-10
TFA1953-TH | HET | 61001084 | HO | เลยสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC3 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-07-31 |  | 1200TX-EN,R5.2M,D30 | TX-EN |  |  |  |  | 5200 | 1310750 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-06-11 | 2021-06-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-28 | Finished | [18 empty] | 2021-06-11 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20016539 | 2021-06-10
TFA1954-TH | HET | 61001084 | HO | เลยสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC4 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-07-31 |  | 1200TX-EN,R5.2M,D30 | TX-EN |  |  |  |  | 5200 | 1310750 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-06-11 | 2021-06-11 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-02-28 | Finished | [18 empty] | 2021-06-11 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20016539 | 2021-06-10
TFA1955-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC5 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R4.75M,D30 | TX-EN |  |  |  |  | 4750 | 1230500 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-07-12 | 2021-07-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-12 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20016539 | 2021-06-10
TFA1956-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC6 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R4.75M,D30 | TX-EN |  |  |  |  | 4750 | 1230500 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-07-12 | 2021-07-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-12 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20016539 | 2021-06-10
TFA1957-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC7 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R4.75M,D30 | TX-EN |  |  |  |  | 4750 | 1230500 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-07-12 | 2021-07-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-12 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20016539 | 2021-06-10
TFA1958-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC8 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R4.75M,D30 | TX-EN |  |  |  |  | 4750 | 1230500 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-07-12 | 2021-07-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-12 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20016539 | 2021-06-10
TFA1959-TH | HET | 61001084 | HO | ยังอยู่ในสัญญา HO | - | TH219084 | The Tunnel (Maharat and Na Phra Lan Rd.) | ESC9 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 6 |  | 1 |  | Phumiphat Siprajan | 2020-12-25 | 2021-06-15 | 2021-11-30 |  | 1200TX-EN,R4.75M,D30 | TX-EN |  |  |  |  | 4750 | 1230500 | Bangkok | แขวงพระบรมมหาราชวัง | 2021-10-01 | [36 empty] | 2021-06-10 | 2021-07-12 | 2021-07-13 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-11-30 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-30 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-07-12 | Finished | [14 empty] | 2021-07-12 | Finished |  |  | 2021-07-13 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20016539 | 2021-06-10
TAC1929-TH | HET | 61001088 | Test | ยังอยู่ในสัญญา HO | - | TH219118 | Art Museum Krabi | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2021-02-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | VFI-1000-CO60,60S/5F | VFI-II | 1000 | 60 | 5 | 5 |  | 1200000 | Krabi | อำเภอเมืองกระบี่ | 2021-08-01 | 2021-08-01 | Finished | [34 empty] | 2021-07-15 | 2021-07-28 | 2021-07-28 | Finished | [14 empty] | 2021-08-01 | 2021-08-25 | 2021-08-01 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-08-05 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-19 | Finished |  |  | 100 | [41 empty] | 2021-08-19 | 1900-01-01 | 2021-08-19 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-03-31 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-07-28 | Finished |  |  | 2021-07-28 | Finished |  |  | 2021-07-29 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 16 | 16 | 123 | 81.08 | Orange |  |  | 20016601 | 2021-07-15
TAC1930-TH | HET | 61001088 | Test | ยังอยู่ในสัญญา HO | - | TH219118 | Art Museum Krabi | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2021-02-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | VFI-1000-CO60,60S/5F | VFI-II | 1000 | 60 | 5 | 5 |  | 1200000 | Krabi | อำเภอเมืองกระบี่ | 2021-08-01 | 2021-08-01 | Finished | [34 empty] | 2021-07-15 | 2021-07-28 | 2021-07-28 | Finished | [14 empty] | 2021-08-01 | 2021-08-25 | 2021-08-01 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-08-05 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-19 | Finished |  |  | 100 | [41 empty] | 2021-08-19 | 1900-01-01 | 2021-08-19 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-03-31 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-07-28 | Finished |  |  | 2021-07-28 | Finished |  |  | 2021-07-29 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 0 | 91 | 16 | 16 | 123 | 81.08 | Orange |  |  | 20016601 | 2021-07-15
TFA1979-TH | HET | 61001102 | Install | ยังอยู่ในสัญญา HO | - | TH219134 | Sky Walk (Gateway Bang Sue) | 1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 6 |  | 1 |  | Orawan Kwanpheng | 2021-02-01 | 2021-06-01 | 2021-07-01 | 2021-11-30 | 1200TX-EN,R4.95M,D30 | TX-EN |  |  |  |  | 4950 | 1498000 | Bangkok | แขวงบางซื่อ | 2021-10-26 | [36 empty] | 2021-05-17 | 2021-07-03 | 2021-07-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-27 | 2021-11-10 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-25 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-07-03 | Finished |  |  | 2021-07-03 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Green |  |  | 20016577 | 2021-05-17
TFA1980-TH | HET | 61001103 | Install | ยังอยู่ในสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-ES-1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-09-28 | 2021-08-25 | 2022-02-14 |  | 1200TX-EN,R6M,D30 | TX-EN |  |  |  |  | 6000 | 802500 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 2021-09-09 | 2021-09-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-15 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-12 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-21 | Finished | [14 empty] | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20016568 | 2021-08-10
TFA1981-TH | HET | 61001103 | Install | ยังอยู่ในสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-ES-2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-09-28 | 2021-08-25 | 2022-02-14 |  | 1200TX-EN,R6M,D30 | TX-EN |  |  |  |  | 6000 | 802500 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 2021-09-09 | 2021-09-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-15 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-12 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-21 | Finished | [14 empty] | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Green |  |  | 20016568 | 2021-08-10
TFA1982-TH | HET | 61001103 | Install | ยังอยู่ในสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-ES-3 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-09-28 | 2021-08-25 | 2022-02-14 |  | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 749000 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 2021-09-09 | 2021-09-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-15 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-12 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-21 | Finished | [14 empty] | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20016568 | 2021-08-10
TFA1983-TH | HET | 61001103 | Install | ยังอยู่ในสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-ES-4 |  | 1 |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 6 |  | 1 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-09-28 | 2021-08-25 | 2022-02-14 |  | 1200TX-EN,R5M,D30 | TX-EN |  |  |  |  | 5000 | 749000 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 2021-09-09 | 2021-09-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-15 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-12 | Working | [6 empty] | 2021-02-28 | Finished |  |  | 2021-08-21 | Finished | [14 empty] | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Green |  |  | 20016568 | 2021-08-10
TAJ1082-TH | HET | 61001104 | HO | เลยสัญญา HO | - | TH219076 | EGAT Bangkrui (Control Building) | PL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2020-12-26 | 2021-05-28 | 2021-07-30 | 2021-09-15 | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1200000 | Nonthaburi | อำเภอบางกรวย | 2021-06-08 | 2021-06-08 | Finished | [34 empty] | 2021-05-28 | 2021-05-28 | 2021-05-28 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-09 | 2021-09-15 | 2021-06-10 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-11 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-21 | Working | [6 empty] | 2021-03-11 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-05-28 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-05-31 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 127 | 81 | 16 | 16 | 240 | 49.69 | Red |  |  | 20016647 | 2021-05-28 |  |  |  | HDME001223 | 2021-05-28
TAK1083-TH | HET | 61001105 | Install | เลยสัญญา HO | - | TH219105 | MRI Building Thonburi2 Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-05-05 | 2021-06-04 | 2021-07-20 |  | B-1000-2S60,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1250000 | Bangkok | แขวงศาลาธรรมสพน์ | 2021-05-19 | 2021-05-19 | Finished | [34 empty] | 2021-05-12 | 2021-05-05 | 2021-05-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-20 | 2021-06-25 | 2021-05-22 | Finished |  |  | 2021-06-06 | Finished |  |  | 2021-06-12 | Finished |  |  | 2021-06-10 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-19 | Finished |  |  | 100 | [41 empty] | 2021-06-19 | 1900-01-01 | 2021-06-19 | Waiting | POWER SUPPLY DELAY |  | 2021-09-25 | [12 empty] | 0 | 2021-06-21 | 2000-01-01 | 2021-06-21 | Finished | [14 empty] | 25 | 2021-10-05 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-02-28 | Finished | [10 empty] | 2021-09-15 | Finished | [6 empty] | 2021-05-19 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-05-28 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Red |  |  | 20016638 | 2021-05-12 |  |  |  | HDME001216 | 2021-05-19
TFA1984-TH | HET | 61001106 | HO | เลยสัญญา HO | - | TH219017 | Walailak University (Medical Center Bld.) Add | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | -154092 | -153952 | -153843 |  | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 775750 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-07-15 | [20 empty] | 2021-07-15 | Finished | [14 empty] | 2021-06-11 | 2021-07-12 | 2021-07-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-15 | 2021-07-20 | [41 empty] | 2021-07-20 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-02 | Finished |  |  | 2021-08-05 | Finished |  |  | 2021-08-07 | Finished |  |  | 2021-08-08 | Finished |  |  | 100 | 2021-08-08 | 1900-01-01 | 2021-08-08 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-07-14 | Finished | [6 empty] | 2021-11-20 | Finished | [6 empty] | 2021-07-12 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 16 | 21 | 79 | 85.92 | Red |  |  | 20016608 | 2021-06-11 |  |  |  | HDME001261 | -153938
TFA1985-TH | HET | 61001106 | HO | เลยสัญญา HO | - | TH219017 | Walailak University (Medical Center Bld.) Add | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 6 |  | 1 | Somsak Denpraphat | Orawan Kwanpheng | -154092 | -153952 | -153843 |  | 1200TX-EN,R4M,D35 | TX-EN |  |  |  |  | 4000 | 775750 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-07-15 | [20 empty] | 2021-07-15 | Finished | [14 empty] | 2021-06-11 | 2021-07-12 | 2021-07-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-15 | 2021-07-20 | [41 empty] | 2021-07-20 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-29 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-01 | Finished |  |  | 2021-08-02 | Finished |  |  | 2021-08-05 | Finished |  |  | 2021-08-07 | Finished |  |  | 2021-08-08 | Finished |  |  | 100 | 2021-08-08 | 1900-01-01 | 2021-08-08 | Waiting | POWER SUPPLY DELAY |  | 2021-11-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-26 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-07-13 | Finished | [6 empty] | 2021-11-20 | Finished | [6 empty] | 2021-07-12 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 482 | 42 | 16 | 21 | 561 | 0 | 42 | 16 | 21 | 79 | 85.92 | Red |  |  | 20016608 | 2021-06-11 |  |  |  | HDME001261 | -153938
TAC1937-TH | HET | 61001106 | HO | เลยสัญญา HO | - | TH219017 | Walailak University (Medical Center Bld.) Add | P4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | -154092 | -153952 | -153843 |  | VFI-1600-2S105,105S/10F | VFI-II | 1600 | 105 | 10 | 10 |  | 1979500 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-07-15 | 2021-07-15 | Finished | [34 empty] | 2021-08-27 | 2021-07-08 | 2021-07-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-15 | 2021-08-15 | 2021-07-15 | Finished |  |  | 2021-08-07 | Finished | [6 empty] | 2021-07-28 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-18 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-09-02 | Finished |  |  | 90 | [41 empty] | 2021-09-02 | 1900-01-01 | 2021-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-09-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-05 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-07-13 | Finished | [6 empty] | 2021-11-20 | Finished | [6 empty] | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 80 | 95 | 24 | 16 | 215 | 77.1 | Red |  |  | 20016857 | 2021-08-27 |  |  |  | HDME001260 | -153942
TAC1938-TH | HET | 61001106 | HO | เลยสัญญา HO | - | TH219017 | Walailak University (Medical Center Bld.) Add | P5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | -154092 | -153952 | -153843 |  | VFI-1600-2S105,105S/10F | VFI-II | 1600 | 105 | 10 | 10 |  | 1979500 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-07-15 | 2021-07-15 | Finished | [34 empty] | 2021-08-27 | 2021-07-08 | 2021-07-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-15 | 2021-08-15 | 2021-07-15 | Finished |  |  | 2021-08-07 | Finished | [6 empty] | 2021-07-28 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-18 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-09-02 | Finished |  |  | 90 | [41 empty] | 2021-09-02 | 1900-01-01 | 2021-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-09-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-05 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-07-13 | Finished | [6 empty] | 2021-11-20 | Finished | [6 empty] | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 80 | 95 | 24 | 16 | 215 | 77.1 | Red |  |  | 20016857 | 2021-08-27 |  |  |  | HDME001260 | -153942
TAC1939-TH | HET | 61001106 | HO | เลยสัญญา HO | - | TH219017 | Walailak University (Medical Center Bld.) Add | P6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Orawan Kwanpheng | -154092 | -153952 | -153843 |  | VFI-1600-2S105,105S/10F | VFI-II | 1600 | 105 | 10 | 10 |  | 1979500 | Nakhon Si Thammarat | อำเภอท่าศาลา | 2021-07-15 | 2021-07-15 | Finished | [34 empty] | 2021-08-27 | 2021-07-08 | 2021-07-15 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-15 | 2021-08-15 | 2021-07-15 | Finished |  |  | 2021-08-07 | Finished | [6 empty] | 2021-07-28 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-18 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-09-02 | Finished |  |  | 90 | [41 empty] | 2021-09-02 | 1900-01-01 | 2021-09-02 | Waiting | POWER SUPPLY DELAY |  | 2021-09-20 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-05 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-07-13 | Finished | [6 empty] | 2021-11-20 | Finished | [6 empty] | 2021-07-08 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-15 | Finished | [22 empty] | 804 | 95 | 24 | 16 | 939 | 80 | 95 | 24 | 16 | 215 | 77.1 | Red |  |  | 20016857 | 2021-08-27 |  |  |  | HDME001260 | -153942
TAJ1084-TH | HET | 61001107 | Install | ยังอยู่ในสัญญา HO | - | TH219113 | Chase Asia Building | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 |  | Unchaleeporn Wongrak | 2021-02-05 | 2021-05-05 | 2021-06-05 | 2021-12-30 | P-1600-CO60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1471250 | Nonthaburi | อำเภอปากเกร็ด | 2021-09-29 | [36 empty] | 2021-05-05 | 2021-05-14 | 2021-05-14 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-30 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-25 | Working | [6 empty] | 2021-02-28 | Finished | [10 empty] | 2021-12-15 | Finished | [6 empty] | 2021-05-14 | Finished |  |  | 2021-05-14 | Finished |  |  | 2021-05-17 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Green |  |  | 20016646 | 2021-05-05 |  |  |  | HDME001212 | 2021-05-14
TAJ1085-TH | HET | 61001108 | Install | ยังอยู่ในสัญญา HO | - | TH219095 | Bearing Residence | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Unchaleeporn Wongrak | 2021-02-02 | 2021-07-01 | 2021-11-01 |  | P-1000-CO60W2,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1070000 | Bangkok | แขวงบางนา | 2021-09-27 | [36 empty] | 2021-07-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-27 | 2021-10-27 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-03-11 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Green |  |  | 20016714 | 2021-08-16
TAJ1086-TH | HET | 61001108 | Install | ยังอยู่ในสัญญา HO | - | TH219095 | Bearing Residence | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Unchaleeporn Wongrak | 2021-02-02 | 2021-07-01 | 2021-11-01 |  | P-1000-CO60W2,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1070000 | Bangkok | แขวงบางนา | 2021-09-27 | [36 empty] | 2021-07-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-27 | 2021-10-27 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-03-11 | Finished |  |  | 2021-08-27 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Green |  |  | 20016714 | 2021-08-16
TAC1932-TH | HET | 61001109 |  | เลยสัญญา HO | - | TH209005 | Car Park Building at Royal Irrigation Department | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-02-17 | 2021-06-01 | 2021-07-20 |  | VFI-1000-CO105,105S/9F | VFI-II | 1000 | 105 | 9 | 9 |  | 1284000 | Bangkok | แขวงถนนนครไชยศรี | 2021-09-10 | [36 empty] | 2021-06-01 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-02-15 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-14 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2021-03-11 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 748 | 94 | 24 | 16 | 882 | 748 | 94 | 24 | 16 | 882 | 0 | Red |  |  | 20016782 | 2021-06-01
TAC1933-TH | HET | 61001109 |  | เลยสัญญา HO | - | TH209005 | Car Park Building at Royal Irrigation Department | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-02-17 | 2021-06-01 | 2021-07-20 |  | VFI-1000-CO105,105S/9F | VFI-II | 1000 | 105 | 9 | 9 |  | 1284000 | Bangkok | แขวงถนนนครไชยศรี | 2021-09-10 | [36 empty] | 2021-06-01 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2022-02-15 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-14 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2021-03-11 | Finished | [10 empty] | 2022-03-15 | Finished | [38 empty] | 748 | 94 | 24 | 16 | 882 | 748 | 94 | 24 | 16 | 882 | 0 | Red |  |  | 20016782 | 2021-06-01
TAC1934-TH | HET | 61001110 | HO | ส่งมอบแล้ว | - | TH219089 | Yensabai Condotel | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2021-02-09 | 2021-05-28 | 2021-12-08 |  | VFI-750-CO105,105S/12F | VFI-II | 750 | 105 | 12 | 12 |  | 1666667 | Chon Buri | จังหวัดชลบุรี | 2021-06-01 | 2021-12-05 | Finished | [34 empty] | 2021-06-01 | 2021-06-21 | 2021-06-21 | Finished | PAYMENT DELAY | [13 empty] | 2021-06-01 | 2021-10-10 | 2021-06-14 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-20 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-23 | Finished |  |  | 2021-06-24 | Finished |  |  | 2021-06-26 | Finished |  |  | 2021-06-27 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | [41 empty] | 2021-06-28 | 2021-07-01 | 2021-07-01 | Finished |  |  | 2021-10-11 | 2021-04-02 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-07-19 | 2021-07-19 | 2021-07-19 | Finished |  |  | 2021-05-13 | Finished |  |  | 2021-07-19 | Finished | [6 empty] | 90 | 2021-08-01 | Finished | CONSTRUCTION DELAY |  | 2021-07-16 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-07-19 | Finished | [6 empty] | 2021-07-20 | Finished | [6 empty] | 2021-06-21 | Finished |  |  | 2021-07-14 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-07-16 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  | pass | 2021-08-18 | Finished |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 2 | 2 | 99.81 | Blue |  |  | 20016846 | 2021-06-16 | [5 empty] | QC Passed
TAC1935-TH | HET | 61001110 | HO | ส่งมอบแล้ว | - | TH219089 | Yensabai Condotel | EL2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2021-02-09 | 2021-05-28 | 2021-12-08 |  | VFI-750-CO105,105S/12F | VFI-II | 750 | 105 | 12 | 12 |  | 1666666.5 | Chon Buri | จังหวัดชลบุรี | 2021-06-01 | 2021-07-20 | Finished | [34 empty] | 2021-07-05 | 2021-05-28 | 2021-07-20 | Finished | PAYMENT DELAY | [13 empty] | 2021-06-01 | 2021-10-10 | 2021-07-22 | Finished |  |  | 2021-07-24 | Finished |  |  | 2021-07-26 | Finished |  |  | 2021-07-28 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-11 | 2021-08-11 | Finished |  |  | 2021-08-11 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | 2021-08-23 | 2021-08-23 | 2021-08-23 | Finished |  |  | 2021-08-23 | Finished |  |  | 2021-08-23 | Finished | [6 empty] | 90 | 2021-08-24 | Finished | POWER SUPPLY DELAY |  | 2021-08-30 | Finished |  |  | 2021-03-31 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-08-20 | Finished | [6 empty] | 2021-07-20 | Finished |  |  | 2021-07-27 | Finished |  |  | 2021-07-30 | Finished |  |  | 2021-08-30 | Finished | [13 empty] | pass |  |  |  |  | 914 | 106 | 32 | 20 | 1072 | 0 | 0 | 0 | 2 | 2 | 99.81 | Blue |  |  | 20017411 | 2021-07-30 | [5 empty] | QC Passed
TAC1936-TH | HET | 61001110 |  | ยังอยู่ในสัญญา HO | - | TH219089 | Yensabai Condotel | EL3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | Somsak Sutthosri | 2021-02-09 | 2021-05-28 | 2021-12-08 |  | VFI-750-CO105,105S/12F | VFI-II | 750 | 105 | 12 | 12 |  | 1666666.5 | Chon Buri | จังหวัดชลบุรี | 2021-09-01 | [36 empty] | 2021-07-05 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2021-09-01 | 2021-10-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-02 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-08 | Working | [6 empty] | 2021-03-31 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-09-20 | Finished | [38 empty] | 914 | 106 | 32 | 20 | 1072 | 914 | 106 | 32 | 20 | 1072 | 0 | Green |  |  | 20017411 | 2021-10-15
TEB0229-TH | HET | 61001111 | HO | ส่งมอบแล้ว | - | TH219135 | KR Legacy | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | 2021-02-18 | 2021-05-18 | 2021-07-06 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 909500 | Bangkok | แขวงสวนหลวง | 2021-05-18 | 2021-06-11 | Finished | [34 empty] | 2021-05-03 | 2021-05-17 | 2021-05-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-11 | 2021-06-30 | 2021-06-14 | Finished |  |  | 2021-06-15 | Finished |  |  | 2021-06-17 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-06-20 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-24 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-26 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | [41 empty] | 2021-06-28 | 2021-07-13 | 2021-07-13 | Finished |  |  | 2021-07-13 | 2021-07-14 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-07-16 | Finished |  |  | 100 | 2021-07-02 | 2000-01-01 | 2021-07-02 | Finished |  |  | 2021-08-03 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 90 | 2021-08-05 | Finished | POWER SUPPLY DELAY |  | 2021-07-29 | Finished |  |  | 2021-03-11 | Finished | [10 empty] | 2021-08-15 | Finished | [6 empty] | 2021-05-17 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-07-29 | Finished | [13 empty] | no pass |  |  |  |  | 170 | 27 | 16 | 16 | 229 | 0 | 0 | 0 | 1 | 1 | 99.56 | Blue |  |  | 20016835 | 2021-05-03 |  |  |  | HDME001214 | 2021-05-17
TAJ1087-TH | HET | 61001112 | HO | ยังอยู่ในสัญญา HO | - | TH219011 | Supalai Lite Thaphra - Wongwian Yai | P01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-05-03 | 2021-11-30 |  | P-750-CO105,105S/22F | UAG-SN1 | 750 | 105 | 22 | 22 |  | 1600000 | Bangkok | แขวงวัดท่าพระ | 2021-09-16 | [36 empty] | 2021-06-01 | 2021-06-02 | 2021-06-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-16 | 2021-11-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-03-11 | Finished | [10 empty] | 2021-11-30 | Finished | [6 empty] | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 1160 | 101 | 0 | 24 | 1285 | 1160 | 101 | 0 | 24 | 1285 | 0 | Green |  |  | 20016854 | 2021-06-01 |  |  |  | HDME001231 | 2021-06-02
TAJ1088-TH | HET | 61001112 | HO | ยังอยู่ในสัญญา HO | - | TH219011 | Supalai Lite Thaphra - Wongwian Yai | P02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-05-03 | 2021-11-30 |  | P-750-CO105,105S/22F | UAG-SN1 | 750 | 105 | 22 | 22 |  | 1600000 | Bangkok | แขวงวัดท่าพระ | 2021-09-16 | [36 empty] | 2021-06-01 | 2021-06-02 | 2021-06-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-16 | 2021-11-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-15 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-03-11 | Finished | [10 empty] | 2021-11-30 | Finished | [6 empty] | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 1160 | 101 | 0 | 24 | 1285 | 1160 | 101 | 0 | 24 | 1285 | 0 | Green |  |  | 20016854 | 2021-06-01 |  |  |  | HDME001231 | 2021-06-02
TAJ1089-TH | HET | 61001112 | HO | เลยสัญญา HO | - | TH219011 | Supalai Lite Thaphra - Wongwian Yai | P03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-05-03 | 2021-08-01 |  | P-750-CO105,105S/22F | UAG-SN1 | 750 | 105 | 22 | 22 |  | 1600000 | Bangkok | แขวงวัดท่าพระ | 2021-06-01 | [36 empty] | 2021-05-14 | 2021-06-02 | 2021-06-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-01 | 2021-07-30 | 2021-06-10 | Finished | [10 empty] | 2021-06-14 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-18 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-11 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-20 | Finished |  |  | 85 | [41 empty] | 2021-08-20 | 1900-01-01 | 2021-08-20 | Waiting | POWER SUPPLY DELAY |  | 2021-08-30 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-15 | Working | [6 empty] | 2021-03-11 | Finished | [10 empty] | 2021-11-30 | Finished | [6 empty] | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 1160 | 101 | 0 | 24 | 1285 | 174 | 101 | 0 | 24 | 299 | 76.73 | Red |  |  | 20016854 | 2021-05-14 |  |  |  | HDME001231 | 2021-06-02
TAJ1090-TH | HET | 61001112 | HO | ส่งมอบแล้ว | - | TH219011 | Supalai Lite Thaphra - Wongwian Yai | P4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Chonticha Angsuwichitkun | 2020-08-17 | 2021-05-03 | 2021-07-01 |  | P-1050-CO105W2,105S/22F | UAG-SN1 | 1050 | 105 | 22 | 22 |  | 1700000 | Bangkok | แขวงวัดท่าพระ | 2021-05-06 | [36 empty] | 2021-05-14 | 2021-06-02 | 2021-06-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-06 | 2021-06-30 | 2021-05-06 | Finished | [10 empty] | 2021-05-21 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-31 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-15 | Finished |  |  | 85 | [41 empty] | 2021-06-15 | 1900-01-01 | 2021-06-15 | Waiting | POWER SUPPLY DELAY |  | 2021-09-10 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-09-06 | Finished | OTHERS |  | 2021-08-30 | Finished |  |  | 2021-03-11 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished |  |  | 2021-08-30 | Finished | [18 empty] | 1160 | 101 | 0 | 24 | 1285 | 174 | 101 | 0 | 24 | 299 | 76.73 | Blue |  |  | 20016854 | 2021-05-14 |  |  |  | HDME001231 | 2021-06-02
TAC1942-TH | HET | 61001121 |  | เลยสัญญา HO | - | TH219146 | Suankularb Wittayalai Thonburi School | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Yosvaris Limmethaphant | 2021-03-08 | 2021-07-08 | 2021-09-08 |  | VFI-700-CO60,60S/6F | VFI-II | 700 | 60 | 6 | 6 |  | 1284000 | Bangkok | แขวงท่าข้าม | 2021-09-08 | [36 empty] | 2021-07-08 | 2021-07-08 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-09 | 2021-10-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-10 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-15 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2021-03-25 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-09-15 | Finished | [38 empty] | 583 | 91 | 24 | 16 | 714 | 583 | 91 | 24 | 16 | 714 | 0 | Red |  |  | 20017096 | 2021-07-08
TAJ1104-TH | HET | 61001129 | HO | ยังอยู่ในสัญญา HO | - | TH219137 | Enhance Patient Health Panyanantha Medical Center | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-02-15 | 2021-05-16 | 2022-02-20 |  | P-750-CO60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1070000 | Nonthaburi | อำเภอปากเกร็ด | 2021-05-30 | 2021-05-17 | Finished | [34 empty] | 2021-05-24 | 2021-05-23 | 2021-04-30 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-05-31 | 2021-09-03 | 2021-05-19 | Finished |  |  | 2021-05-21 | Finished |  |  | 2021-05-22 | Finished |  |  | 2021-05-24 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-26 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-27 | Finished |  |  | 2021-05-28 | Finished |  |  | 2021-06-02 | Finished |  |  | 100 | [41 empty] | 2021-06-02 | 1900-01-01 | 2021-06-02 | Waiting | POWER SUPPLY DELAY |  | 2021-08-03 | [12 empty] | 0 | 2021-08-26 | 2000-01-01 | 2021-08-26 | Finished | [14 empty] | 25 | 2021-10-20 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-04-19 | Finished | [10 empty] | 2021-10-03 | Finished | [6 empty] | 2021-05-25 | Finished |  |  | 2021-05-25 | Finished |  |  | 2021-05-28 | Finished | [22 empty] | 276 | 79 | 16 | 16 | 387 | 0 | 79 | 4 | 16 | 99 | 74.42 | Green |  |  | 20016937 | 2021-05-24 |  |  |  | HDME001222 | 2021-05-25
TAK1105-TH | HET | 61001129 | HO | ยังอยู่ในสัญญา HO | - | TH219137 | Enhance Patient Health Panyanantha Medical Center | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-02-15 | 2021-05-16 | 2022-02-20 |  | B-1000-2S60,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1337500 | Nonthaburi | อำเภอปากเกร็ด | 2021-12-01 | [36 empty] | 1900-01-01 | 2021-11-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-04-19 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-02-20 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20017917 | 2021-12-01
TAK1106-TH | HET | 61001129 | HO | ยังอยู่ในสัญญา HO | - | TH219137 | Enhance Patient Health Panyanantha Medical Center | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-02-15 | 2021-05-16 | 2022-02-20 |  | B-1000-2S60,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1337500 | Nonthaburi | อำเภอปากเกร็ด | 2021-12-01 | [36 empty] | 1900-01-01 | 2021-11-30 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-12-01 | 2022-02-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-04-19 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-02-20 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Green |  |  | 20017917 | 2021-12-01
TAJ1108-TH | HET | 61001131 | HO | ยังอยู่ในสัญญา HO | - | TH219059 | State Audit Office of The Kingdom of Thailand (Sa Kaeo) | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2021-02-17 | 2021-05-17 | 2021-07-17 | 2021-09-30 | P-1000-CO60W1,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1070000 | Sa Kaeo | จังหวัดสระแก้ว 27000 | 2021-07-17 | 2021-05-30 | Finished | [34 empty] | 2021-05-31 | 2021-05-31 | 2021-06-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-01 | 2021-06-20 | 2021-06-03 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-17 | Finished |  |  | 100 | [41 empty] | 2021-06-17 | 1900-01-01 | 2021-06-17 | Waiting | POWER SUPPLY DELAY |  | 2021-09-15 | [12 empty] | 0 | 2021-06-23 | 2000-01-01 | 2021-06-23 | Finished | [14 empty] | 25 | 2021-10-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-03-25 | Finished | [10 empty] | 2021-10-17 | Finished | [6 empty] | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Orange |  |  | 20017064 | 2021-05-31 |  |  |  | HDME001229 | 2021-06-02
TAJ1109-TH | HET | 61001131 | HO | ยังอยู่ในสัญญา HO | - | TH219059 | State Audit Office of The Kingdom of Thailand (Sa Kaeo) | 2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 | Somsak Denpraphat | SIRIRAT YUANGNGAM | 2021-02-17 | 2021-05-17 | 2021-07-17 | 2021-09-30 | P-1000-CO60W1,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1070000 | Sa Kaeo | จังหวัดสระแก้ว 27000 | 2021-07-17 | 2021-05-30 | Finished | [34 empty] | 2021-05-31 | 2021-05-31 | 2021-06-02 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-01 | 2021-06-20 | 2021-06-03 | Finished |  |  | 2021-06-05 | Finished |  |  | 2021-06-07 | Finished |  |  | 2021-06-08 | Finished |  |  | 2021-06-09 | Finished |  |  | 2021-06-11 | Finished |  |  | 2021-06-13 | Finished |  |  | 2021-06-14 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-17 | Finished |  |  | 100 | [41 empty] | 2021-06-17 | 1900-01-01 | 2021-06-17 | Waiting | POWER SUPPLY DELAY |  | 2021-09-15 | [12 empty] | 0 | 2021-06-23 | 2000-01-01 | 2021-06-23 | Finished | [14 empty] | 25 | 2021-10-10 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-03-25 | Finished | [10 empty] | 2021-10-17 | Finished | [6 empty] | 2021-06-02 | Finished |  |  | 2021-06-02 | Finished |  |  | 2021-06-04 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 0 | 80 | 4 | 16 | 100 | 76.85 | Orange |  |  | 20017064 | 2021-05-31 |  |  |  | HDME001229 | 2021-06-02
TAJ1110-TH | HET | 61001132 | HO | เลยสัญญา HO | - | TH219154 | Science Park Administration Building | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2021-02-18 | 2021-06-18 | 2021-09-18 |  | P-1600-CO60,60S/4F | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1210000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2021-09-15 | [36 empty] | 2021-06-18 | 2021-06-19 | 2021-06-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-06 | Working | [6 empty] | 2021-03-25 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-06-19 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-06-21 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20016938 | 2021-06-18
TAJ1111-TH | HET | 61001132 | HO | เลยสัญญา HO | - | TH219154 | Science Park Administration Building | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2021-02-18 | 2021-06-18 | 2021-09-18 |  | P-1600-CO60,60S/4F | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1210000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2021-09-15 | [36 empty] | 2021-06-18 | 2021-06-19 | 2021-06-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-06 | Working | [6 empty] | 2021-03-25 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-06-19 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-06-21 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20016938 | 2021-06-18
TAJ1112-TH | HET | 61001132 | HO | เลยสัญญา HO | - | TH219154 | Science Park Administration Building | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2021-02-18 | 2021-06-18 | 2021-09-18 |  | P-1600-2S60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1270000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2021-06-04 | 2021-06-19 | Finished | [34 empty] | 2021-06-18 | 2021-06-19 | 2021-06-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-18 | 2021-07-18 | 0 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 100 | [41 empty] | 1900-01-06 | 1900-01-01 | 1900-01-06 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | [6 empty] | 2021-03-25 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-06-19 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-06-21 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Red |  |  | 20016938 | 2021-06-18
TAJ1113-TH | HET | 61001132 | HO | เลยสัญญา HO | - | TH219154 | Science Park Administration Building | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2021-02-18 | 2021-06-18 | 2021-09-18 |  | P-1600-2S60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1270000 | Nakhon Ratchasima | อำเภอเมืองนครราชสีมา | 2021-06-04 | 2021-06-19 | Finished | [34 empty] | 2021-06-18 | 2021-06-19 | 2021-06-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-18 | 2021-07-18 | 0 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-03 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 1900-01-06 | Finished |  |  | 100 | [41 empty] | 1900-01-06 | 1900-01-01 | 1900-01-06 | Waiting | POWER SUPPLY DELAY |  | 2021-12-20 | [12 empty] | 0 | 2021-07-26 | 2000-01-01 | 2021-07-26 | Finished | [14 empty] | 25 | 2022-01-15 | Working | [6 empty] | 2021-03-25 | Finished | [10 empty] | 2021-11-15 | Finished | [6 empty] | 2021-06-19 | Finished |  |  | 2021-06-19 | Finished |  |  | 2021-06-21 | Finished | [22 empty] | 408 | 82 | 16 | 16 | 522 | 0 | 82 | 4 | 16 | 102 | 80.46 | Red |  |  | 20016938 | 2021-06-18
TAD0536-TH | HET | 61001133 | HO | ยังอยู่ในสัญญา HO | - | TH219060 | OPD Ban Phai Hospital | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2021-03-05 | 2021-09-20 | 2021-11-05 |  | B-1000-2S60,60S/3F | B-II(VFI-II) | 1000 | 60 | 3 | 3 |  | 1358900 | Khon Kaen | ตำบลในเมือง | 2021-07-15 | 2021-07-15 | Finished | [34 empty] | 2021-09-27 | 2021-07-17 | 2021-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-15 | 2021-11-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 90 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-14 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-10-08 | Finished | [6 empty] | 2021-11-05 | Finished | [6 empty] | 2021-07-17 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-20 | Finished | [22 empty] | 417 | 89 | 16 | 16 | 538 | 41 | 89 | 16 | 16 | 162 | 69.89 | Green |  |  | 20017027 | 2021-09-27
TAD0537-TH | HET | 61001133 | HO | ยังอยู่ในสัญญา HO | - | TH219060 | OPD Ban Phai Hospital | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | APHIRADA BUNKUEA | 2021-03-05 | 2021-09-20 | 2021-11-05 |  | B-1000-2S60,60S/3F | B-II(VFI-II) | 1000 | 60 | 3 | 3 |  | 1358900 | Khon Kaen | ตำบลในเมือง | 2021-07-15 | 2021-07-15 | Finished | [34 empty] | 2021-09-27 | 2021-07-17 | 2021-07-17 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-15 | 2021-11-14 | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 90 | [41 empty] | 1900-01-01 | 1900-01-01 | 1900-01-01 | Waiting | POWER SUPPLY DELAY |  | 2021-11-14 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-10-08 | Finished | [6 empty] | 2021-11-05 | Finished | [6 empty] | 2021-07-17 | Finished |  |  | 2021-07-17 | Finished |  |  | 2021-07-20 | Finished | [22 empty] | 417 | 89 | 16 | 16 | 538 | 41 | 89 | 16 | 16 | 162 | 69.89 | Green |  |  | 20017027 | 2021-09-27
TAJ1118-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-750-CO105,105S/17F | UAG-SN1 | 750 | 105 | 17 | 17 |  | 1476600 | Chiang Mai | ตำบลช้างคลาน | 2021-09-10 | [36 empty] | 2021-07-30 | 2021-09-07 | 2021-09-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-09-07 | Finished |  |  | 2021-09-07 | Finished |  |  | 2021-09-09 | Finished | [22 empty] | 939 | 98 | 40 | 20 | 1097 | 939 | 98 | 40 | 20 | 1097 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1120-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-750-CO105,105S/17F | UAG-SN1 | 750 | 105 | 17 | 17 |  | 1476600 | Chiang Mai | ตำบลช้างคลาน | 2021-09-10 | [36 empty] | 2021-07-30 | 2021-09-07 | 2021-09-07 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-09-07 | Finished |  |  | 2021-09-07 | Finished |  |  | 2021-09-09 | Finished | [22 empty] | 939 | 98 | 40 | 20 | 1097 | 939 | 98 | 40 | 20 | 1097 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1119-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-750-CO105,105S/17F | UAG-SN1 | 750 | 105 | 17 | 17 |  | 1476600 | Chiang Mai | ตำบลช้างคลาน | 2021-10-10 | [36 empty] | 2021-07-30 | 2021-09-03 | 2021-09-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-09-03 | Finished |  |  | 2021-09-03 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 939 | 98 | 40 | 20 | 1097 | 939 | 98 | 40 | 20 | 1097 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1121-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-1000-2S105,105S/17F | UAG-SN1 | 1000 | 105 | 17 | 17 |  | 1476600 | Chiang Mai | ตำบลช้างคลาน | 2021-10-10 | [36 empty] | 2021-07-30 | 2021-09-03 | 2021-09-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-09-03 | Finished |  |  | 2021-09-03 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 939 | 98 | 40 | 20 | 1097 | 939 | 98 | 40 | 20 | 1097 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1114-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-750-CO105,105S/18F | UAG-SN1 | 750 | 105 | 18 | 18 |  | 1584100 | Chiang Mai | ตำบลช้างคลาน | 2021-10-10 | [36 empty] | 2021-07-30 | 2021-09-03 | 2021-09-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-09-03 | Finished |  |  | 2021-09-03 | Finished |  |  | 2021-09-08 | Finished | [22 empty] | 983 | 99 | 40 | 20 | 1142 | 983 | 99 | 40 | 20 | 1142 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1116-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-750-CO105,105S/18F | UAG-SN1 | 750 | 105 | 18 | 18 |  | 1584100 | Chiang Mai | ตำบลช้างคลาน | 2021-10-10 | [36 empty] | 2021-07-30 | 2021-08-18 | 2021-08-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-18 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 983 | 99 | 40 | 20 | 1142 | 983 | 99 | 40 | 20 | 1142 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1115-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-750-CO105,105S/18F | UAG-SN1 | 750 | 105 | 18 | 18 |  | 1584100 | Chiang Mai | ตำบลช้างคลาน | 2021-10-10 | [36 empty] | 2021-07-30 | 2021-08-18 | 2021-08-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-18 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 983 | 99 | 40 | 20 | 1142 | 983 | 99 | 40 | 20 | 1142 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1117-TH | HET | 61001134 | Install | ยังอยู่ในสัญญา HO | - | TH219155 | Astra Sky River | 8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-11-30 | 2021-07-30 | 2022-03-31 |  | P-1000-2S105,105S/18F | UAG-SN1 | 1000 | 105 | 18 | 18 |  | 1584100 | Chiang Mai | ตำบลช้างคลาน | 2021-10-10 | [36 empty] | 2021-07-30 | 2021-08-18 | 2021-08-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-10 | 2022-03-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-05-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-03-25 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-18 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 983 | 99 | 40 | 20 | 1142 | 983 | 99 | 40 | 20 | 1142 | 0 | Green |  |  | 20017066 | 2021-07-30
TAJ1122-TH | HET | 61001135 |  | ยังอยู่ในสัญญา HO | - | TH219117 | Apartment 6 Floor@Khun Nop | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | APHIRADA BUNKUEA | 2021-03-15 | 2021-10-15 | 2021-11-30 |  | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1251900 | Bangkok | แขวงบางแคเหนือ | 2021-10-15 | [36 empty] | 2021-10-15 | 2021-10-14 | [16 empty] | 2021-10-15 | 2021-11-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-10 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-20 | Working | [6 empty] | 2021-04-08 | Finished |  |  | 2021-10-26 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Green |  |  | 20017389 | 2021-10-15
TAC1949-TH | HET | 61001137 | Delivery | ยังอยู่ในสัญญา HO | - | TH219041 | Boonnak Building King Mongkut¦s Institute of Tehnology | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Benjapol Butprom | 4 |  | 2 |  | Prapaipim Netnonthai | 2021-02-24 | 2021-06-24 | 2021-08-24 | 2021-11-24 | VFI-700-CO90,90S/5F | VFI-II | 700 | 90 | 5 | 5 |  | 1177000 | Bangkok | แขวงลาดกระบัง | 2021-09-15 | [36 empty] | 2021-08-28 | 2021-09-07 | 2021-09-09 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-19 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-04-19 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-09-15 | Finished | [6 empty] | 2021-09-09 | Finished |  |  | 2021-09-09 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Green |  |  | 20017256 | 2021-06-28
TAJ1124-TH | HET | 61001138 | Test | ยังอยู่ในสัญญา HO | - | TH219156 | One Budget Phase 2 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | 2021-03-16 | 2021-07-16 | 2021-09-16 | 2021-11-01 | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1177000 | Chiang Rai | อำเภอเมืองเชียงราย | 2021-08-07 | 2021-08-10 | Finished | [34 empty] | 2021-07-16 | 2021-07-20 | 2021-07-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2021-11-30 | 2021-08-20 | Finished |  |  | 2021-08-21 | Finished |  |  | 2021-08-24 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-31 | Finished |  |  | 2021-09-01 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-11-30 | Working | POWER SUPPLY DELAY | [5 empty] | 2021-04-08 | Finished |  |  | 2021-07-27 | Finished | [6 empty] | 2022-02-15 | Finished | [6 empty] | 2021-07-20 | Finished |  |  | 2021-07-20 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 158 | 82 | 6 | 16 | 262 | 54.36 | Green |  |  | 20017277 | 2021-07-16
TAJ1126-TH | HET | 61001140 | HO | เลยสัญญา HO | - | TH219151 | Avaron (Ramintra 19) | L-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | 2021-03-12 | 2021-06-11 | 2021-07-27 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1000000 | Bangkok | แขวงอนุสาวรีย์ | 2021-06-10 | 2021-06-19 | Finished | [34 empty] | 2021-06-11 | 2021-06-10 | 2021-06-16 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-11 | 2021-09-20 | 2021-06-22 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-07-02 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-07-15 | Finished |  |  | 2021-07-22 | Finished |  |  | 2021-07-27 | Finished |  |  | 2021-08-04 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | [41 empty] | 2021-08-13 | 1900-01-01 | 2021-08-13 | Waiting | POWER SUPPLY DELAY |  | 2021-07-17 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-29 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-03-25 | Finished | [18 empty] | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished |  |  | 2021-06-16 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 0 | 84 | 24 | 16 | 124 | 81.35 | Red |  |  | 20017221 | 2021-06-11
TAJ1127-TH | HET | 61001142 | HO | เลยสัญญา HO | - | TH219099 | Redemptorist School Kumpavaphi Udon Thani | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | THANASAK SRIASAWIN | 2021-03-09 | 2021-07-09 | 2021-09-09 |  | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1157740 | Udon Thani | ตำบลกุมภวาปี | 2021-10-15 | [36 empty] | 2021-07-09 | 2021-08-19 | 2021-08-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-14 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2021-03-26 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Red |  |  | 20017242 | 2021-07-09
TAK1128-TH | HET | 61001143 | HO | ส่งมอบแล้ว | - | TH219083 | Ratchasima Hospital | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 | Weerapoj Paijitvijarn | THANASAK SRIASAWIN | 2021-02-01 | 2021-06-15 | 2021-08-15 |  | B-1000-2S60,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1519400 | Nakhon Ratchasima | ตำบลในเมือง | 2021-06-01 | 2021-06-14 | Finished | [34 empty] | 2021-06-15 | 2021-07-06 | 2021-07-06 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-15 | 2021-07-15 | 2021-07-06 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 1900-01-01 | Finished |  |  | 100 | [41 empty] | 1900-01-01 | 2021-08-15 | 2021-08-15 | Finished |  |  | 2021-07-15 | 2021-08-16 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-30 | Finished |  |  | 100 | 2021-08-10 | 2000-01-01 | 2021-08-10 | Finished | [14 empty] | 25 | 2021-10-31 | Finished | CONSTRUCTION DELAY |  | 2021-09-15 | Finished |  |  | 2021-04-08 | Finished | [10 empty] | 2022-01-15 | Finished | [6 empty] | 2021-07-06 | Finished |  |  | 2021-07-06 | Finished |  |  | 2021-07-08 | Finished |  |  | 2021-09-15 | Finished | [13 empty] | in process (defect) |  |  |  |  | 497 | 83 | 24 | 16 | 620 | 0 | 0 | 6 | 16 | 22 | 96.45 | Blue |  |  | 20017248 | 2021-06-15
TAJ1129-TH | HET | 61001144 | Install | ยังอยู่ในสัญญา HO | - | TH219087 | NACC Surat Thani | L 1 (Office) | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-04-16 | 2021-07-30 | 2021-10-01 |  | P-1000-CO60D,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1070000 | Surat Thani | อำเภอเมืองสุราษฎร์ธานี | 2021-09-10 | [36 empty] | 2021-07-30 | 2021-08-14 | 2021-08-17 | Finished | STORE AREA | [13 empty] | 2021-09-25 | 2021-10-18 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-18 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-05 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-05-10 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-14 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-18 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Orange |  |  | 20017647 | 2021-07-30
TAJ1130-TH | HET | 61001144 | Install | ยังอยู่ในสัญญา HO | - | TH219087 | NACC Surat Thani | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-04-16 | 2021-07-30 | 2021-10-01 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1070000 | Surat Thani | อำเภอเมืองสุราษฎร์ธานี | 2021-07-30 | 2021-07-29 | Finished | [34 empty] | 2021-07-30 | 2021-07-31 | 2021-07-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-30 | 2021-08-18 | 2021-08-01 | Finished |  |  | 2021-08-19 | Finished | [10 empty] | 2021-08-15 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-09-02 | Finished | [6 empty] | 2021-09-01 | Finished | [6 empty] | 70 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-18 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-05 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-05-10 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-07-31 | Finished |  |  | 2021-07-31 | Finished |  |  | 2021-07-31 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 109 | 81 | 16 | 16 | 222 | 53.46 | Orange |  |  | 20017647 | 2021-07-30
TAJ1131-TH | HET | 61001144 | Install | ยังอยู่ในสัญญา HO | - | TH219087 | NACC Surat Thani | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-04-16 | 2021-07-30 | 2021-10-01 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1070000 | Surat Thani | อำเภอเมืองสุราษฎร์ธานี | 2021-08-25 | 2021-08-29 | Finished | [34 empty] | 2021-07-30 | 2021-08-14 | 2021-08-17 | Finished | STORE AREA | [13 empty] | 2021-08-25 | 2021-09-18 | 2021-08-30 | Finished |  |  | 2021-09-02 | Finished | [10 empty] | 2021-08-31 | Finished |  |  | 2021-09-01 | Finished | [18 empty] | 50 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-18 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-05 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-05-10 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-14 | Finished |  |  | 2021-08-17 | Finished |  |  | 2021-08-18 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 182 | 81 | 16 | 16 | 295 | 38.16 | Orange |  |  | 20017647 | 2021-07-30
TAJ1132-TH | HET | 61001144 | Install | ยังอยู่ในสัญญา HO | - | TH219087 | NACC Surat Thani | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-04-16 | 2021-07-30 | 2021-10-01 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1070000 | Surat Thani | อำเภอเมืองสุราษฎร์ธานี | 2021-07-30 | 2021-07-29 | Finished | [34 empty] | 2021-07-30 | 2021-07-31 | 2021-07-31 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-07-30 | 2021-08-18 | 2021-08-01 | Finished |  |  | 2021-08-19 | Finished | [10 empty] | 2021-08-15 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-09-02 | Finished | [6 empty] | 2021-09-01 | Finished | [6 empty] | 70 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-18 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-05 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-05-10 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-07-31 | Finished |  |  | 2021-07-31 | Finished |  |  | 2021-07-31 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 109 | 81 | 16 | 16 | 222 | 53.46 | Orange |  |  | 20017647 | 2021-07-30
TAJ1133-TH | HET | 61001145 |  | ยังอยู่ในสัญญา HO | - | TH219143 | Home Office Khun Narumon | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Yosvaris Limmethaphant | 2021-02-22 | 2021-09-22 | 2021-12-22 |  | P-750-CO60,60S/2F | UAG-SN1 | 750 | 60 | 2 | 2 |  | 1150000 | Bangkok | แขวงเจ้าคุณสิงห์ | 2021-09-28 | [36 empty] | 2021-09-22 | 2021-09-21 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-28 | 2021-12-22 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-04-08 | Finished |  |  | 2021-10-03 | Finished | [6 empty] | 2021-12-22 | Finished | [38 empty] | 276 | 79 | 16 | 16 | 387 | 276 | 79 | 16 | 16 | 387 | 0 | Green |  |  | 20017388 | 2021-09-22
TAC1950-TH | HET | 61001146 | HO | ยังอยู่ในสัญญา HO | - | TH219138 | Building 40 Years KMUT | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-02-19 | 2021-06-20 | 2021-09-17 | 2021-10-17 | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 2683025 | Bangkok | แขวงวงศ์สว่าง | 2021-07-07 | 2021-07-09 | Finished | [34 empty] | 2021-07-05 | 2021-07-01 | 2021-07-13 | Finished | OTHERS | [13 empty] | 2021-07-09 | 2021-09-14 | 2021-07-14 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-08-07 | Finished |  |  | 2021-08-23 | Finished |  |  | 2021-07-24 | Finished |  |  | 2021-07-28 | Finished |  |  | 2021-07-31 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-04 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | [41 empty] | 2021-08-13 | 2021-08-10 | 2021-08-10 | Finished |  |  | 2021-06-20 | 2021-08-17 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-08-31 | Finished |  |  | 100 | 2021-08-30 | 2000-01-01 | 2021-08-30 | Finished | [14 empty] | 25 | 2021-11-01 | Working | [6 empty] | 2021-04-08 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-09-30 | Finished | [6 empty] | 2021-07-13 | Finished |  |  | 2021-07-20 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 8 | 20 | 28 | 97.24 | Green |  |  | 20017400 | 2021-07-05
TAC1951-TH | HET | 61001146 | HO | ยังอยู่ในสัญญา HO | - | TH219138 | Building 40 Years KMUT | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-02-19 | 2021-06-20 | 2021-09-17 | 2021-10-17 | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 2683025 | Bangkok | แขวงวงศ์สว่าง | 2021-07-07 | 2021-07-09 | Finished | [34 empty] | 2021-07-05 | 2021-07-01 | 2021-07-13 | Finished | OTHERS | [13 empty] | 2021-07-09 | 2021-09-14 | 2021-07-14 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-08-07 | Finished |  |  | 2021-08-23 | Finished |  |  | 2021-07-24 | Finished |  |  | 2021-07-28 | Finished |  |  | 2021-07-31 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-04 | Finished |  |  | 2021-08-13 | Finished |  |  | 100 | [41 empty] | 2021-08-13 | 2021-08-10 | 2021-08-10 | Finished |  |  | 2021-06-20 | 2021-08-17 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-08-31 | Finished |  |  | 100 | 2021-08-30 | 2000-01-01 | 2021-08-30 | Finished | [14 empty] | 25 | 2021-11-01 | Working | [6 empty] | 2021-04-08 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-09-30 | Finished | [6 empty] | 2021-07-13 | Finished |  |  | 2021-07-20 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 0 | 0 | 8 | 20 | 28 | 97.24 | Green |  |  | 20017400 | 2021-07-05
TAC1952-TH | HET | 61001146 | HO | ยังอยู่ในสัญญา HO | - | TH219138 | Building 40 Years KMUT | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-02-19 | 2021-06-20 | 2021-09-17 | 2021-10-17 | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 2683025 | Bangkok | แขวงวงศ์สว่าง | 2021-07-07 | [36 empty] | 2021-07-05 | 2021-07-01 | 2021-07-13 | Finished | OTHERS | [13 empty] | 2021-09-15 | 2021-11-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-06-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-01 | Working | [6 empty] | 2021-04-08 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-09-30 | Finished | [6 empty] | 2021-07-13 | Finished |  |  | 2021-07-20 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Orange |  |  | 20017400 | 2021-07-05
TAC1953-TH | HET | 61001146 | HO | ยังอยู่ในสัญญา HO | - | TH219138 | Building 40 Years KMUT | L4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 | Weerapoj Paijitvijarn | Thamnul Kongsar | 2021-02-19 | 2021-06-20 | 2021-09-17 | 2021-10-17 | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 2683025 | Bangkok | แขวงวงศ์สว่าง | 2021-07-07 | [36 empty] | 2021-07-05 | 2021-07-01 | 2021-07-13 | Finished | OTHERS | [13 empty] | 2021-09-15 | 2021-11-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-06-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-01 | Working | [6 empty] | 2021-04-08 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-09-30 | Finished | [6 empty] | 2021-07-13 | Finished |  |  | 2021-07-20 | Finished |  |  | 2021-07-23 | Finished | [22 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Orange |  |  | 20017400 | 2021-07-05
TEB0231-TH | HET | 61001148 | HO | ยังอยู่ในสัญญา HO | - | TH219157 | Bu Gaan Yothinpattana | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2021-03-01 | 2021-05-31 | 2021-06-30 | 2021-10-15 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตบางกะปิ | 2021-06-15 | 2021-06-20 | Finished | [34 empty] | 2021-05-31 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-06-15 | 2021-06-30 | 2021-06-21 | Finished |  |  | 2021-06-22 | Finished |  |  | 2021-06-24 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 2021-06-25 | Finished |  |  | 100 | [41 empty] | 2021-06-25 | 2021-06-28 | 2021-06-28 | Finished |  |  | 2021-06-21 | 2021-06-28 | Finished |  |  | 2021-06-28 | Finished |  |  | 2021-06-28 | Finished |  |  | 100 | 2021-07-08 | 2000-01-01 | 2021-07-08 | Finished | [14 empty] | 25 | 2021-10-15 | Working | DELIVERY DELAY | [5 empty] | 2021-04-19 | Finished | [10 empty] | 2021-08-30 | Finished | [6 empty] | 2021-06-25 | Finished |  |  | 2021-06-29 | Finished |  |  | 2021-06-30 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 0 | 0 | 4 | 16 | 20 | 92.22 | Green |  |  | 20017402 | 2021-05-31
TEC0203-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | D-1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | DT-100S-B30,30S/3F | DT | 100 | 30 | 3 | 3 |  | 295000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONTRACT CANCELLATION | [5 empty] | 2021-06-02 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red
TEC0204-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | D-2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | DT-100S-B30,30S/3F | DT | 100 | 30 | 3 | 3 |  | 295000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONTRACT CANCELLATION | [13 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 |  |  | CONTRACT CANCELLATION | [5 empty] | 2021-06-02 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red
TED0045-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | FL-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | HCA-1600-CO180,180S/33F | HCA | 1600 | 180 | 27 | 33 |  | 2830000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2022-01-10 | 2022-03-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-02 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 1976 | 117 | 64 | 32 | 2189 | 1976 | 117 | 64 | 32 | 2189 | 0 | Red |  |  | 20017374 | 2021-09-15
TED0040-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | L-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | HCA-1350-CO180,180S/33F | HCA | 1350 | 180 | 25 | 33 |  | 3050000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2022-02-01 | 2022-03-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-21 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-02 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 1976 | 117 | 64 | 32 | 2189 | 1976 | 117 | 64 | 32 | 2189 | 0 | Red |  |  | 20017374 | 2021-09-15
TED0041-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | L-02 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | HCA-1350-CO180,180S/33F | HCA | 1350 | 180 | 25 | 33 |  | 3050000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2022-02-01 | 2022-03-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-21 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-02 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 1976 | 117 | 64 | 32 | 2189 | 1976 | 117 | 64 | 32 | 2189 | 0 | Red |  |  | 20017374 | 2021-09-15
TED0042-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | L-03 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | HCA-1600-CO180,180S/33F | HCA | 1600 | 180 | 25 | 33 |  | 3050000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2022-02-01 | 2022-03-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-21 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-02 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 1976 | 117 | 64 | 32 | 2189 | 1976 | 117 | 64 | 32 | 2189 | 0 | Red |  |  | 20017374 | 2021-09-15
TED0043-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | L-04(HD) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | HCA-1600-CO180,180S/33F | HCA | 1600 | 180 | 25 | 33 |  | 3050000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2022-02-01 | 2022-03-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-21 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-02 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 1976 | 117 | 64 | 32 | 2189 | 1976 | 117 | 64 | 32 | 2189 | 0 | Red |  |  | 20017374 | 2021-09-15
TED0044-TH | HET | 61001150 |  | เลยสัญญา HO | - | TH209237 | One Sukhumvit 59 Hotel | S-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153930 | -153807 |  | HCA-1600-CO180,180S/33F | HCA | 1600 | 180 | 27 | 33 |  | 2830000 | Bangkok | แขวงคลองตัน | 2021-12-01 | [36 empty] | 2021-07-20 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2022-01-10 | 2022-03-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-02 | [12 empty] | 0 | [18 empty] | 0 | 2022-05-31 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-02 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-05-31 | Finished | [38 empty] | 1976 | 117 | 64 | 32 | 2189 | 1976 | 117 | 64 | 32 | 2189 | 0 | Red |  |  | 20017374 | 2021-09-15
TEB0232-TH | HET | 61001151 | Test | เลยสัญญา HO | - | TH219109 | Home Khun Ekapong | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 | Weerapoj Paijitvijarn | Siraprapa Sihamart | 2021-03-18 | 2021-06-18 | 2021-07-18 | 2021-09-20 | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 840000 | Bangkok | แขวงลาดยาว | 2021-08-10 | 2021-08-10 | Finished | [34 empty] | 2021-08-10 | 2021-08-10 | 2021-08-10 | Finished | PAYMENT DELAY | [13 empty] | 2021-08-11 | 2021-09-20 | 2021-08-11 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-08 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-30 | Working | CUSTOMER PAYMENT DELAY | [5 empty] | 2021-04-08 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2022-02-15 | Finished | [6 empty] | 2021-08-10 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 161 | 55 | 16 | 16 | 248 | 3.5 | Red |  |  | 20017401 | 2021-06-03
TFA2647-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-1 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R2M,D30 | TX-EN |  |  |  |  | 2000 | 790000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 429 | 32 | 16 | 14 | 491 | 429 | 32 | 16 | 14 | 491 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2648-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-2 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R2.5M,D30 | TX-EN |  |  |  |  | 2500 | 855000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 429 | 32 | 16 | 14 | 491 | 429 | 32 | 16 | 14 | 491 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2649-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-3-1 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1000TX-EN,R6M,D35 | TX-EN |  |  |  |  | 6000 | 925000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2650-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-3-2 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1000TX-EN,R6M,D35 | TX-EN |  |  |  |  | 6000 | 925000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2651-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-4-1 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R4.75M,D35 | TX-EN |  |  |  |  | 4750 | 720000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2652-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-4-2 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R4.75M,D35 | TX-EN |  |  |  |  | 4750 | 720000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2653-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-4-3 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R4.75M,D35 | TX-EN |  |  |  |  | 4750 | 720000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2654-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-4-4 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R4.75M,D35 | TX-EN |  |  |  |  | 4750 | 720000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2655-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-4-5 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R4.75M,D35 | TX-EN |  |  |  |  | 4750 | 720000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20017397 | 2021-09-03
TFA2656-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | ES-4-6 |  | 1 |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 6 |  | 1 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | 1200TX-EN,R4.75M,D35 | TX-EN |  |  |  |  | 4750 | 720000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20017397 | 2021-09-03
TED0049-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | FL | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | MCA-1600-CO150,150S/30F | MCA | 1600 | 150 | 30 | 30 |  | 2650000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 1909 | 121 | 56 | 24 | 2110 | 1909 | 121 | 56 | 24 | 2110 | 0 | Red |  |  | 20017397 | 2021-09-03
TED0048-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | H1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | HCA-1350-CO210,210S/29F | HCA | 1350 | 210 | 23 | 29 |  | 2575000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 1780 | 114 | 56 | 24 | 1974 | 1780 | 114 | 56 | 24 | 1974 | 0 | Red |  |  | 20017397 | 2021-09-03
TBL0698-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | R&F | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | OUG-1000-CO90,90S/10F | OUG-ON1 | 1000 | 90 | 10 | 10 |  | 1230000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 755 | 89 | 24 | 16 | 884 | 755 | 89 | 24 | 16 | 884 | 0 | Red |  |  | 20017399 | 2021-09-20
TBL0697-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | S1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | OUG-1600-CO60,60S/8F | OUG-ON1 | 1600 | 60 | 8 | 8 |  | 1280000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 649 | 88 | 24 | 16 | 777 | 649 | 88 | 24 | 16 | 777 | 0 | Red |  |  | 20017399 | 2021-09-20
TED0050-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | S2 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | MCA-1600-CO150,150S/22F | MCA | 1600 | 150 | 22 | 22 |  | 2200000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 1467 | 114 | 48 | 24 | 1653 | 1467 | 114 | 48 | 24 | 1653 | 0 | Red |  |  | 20017397 | 2021-09-03
TED0046-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | SA1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | HCA-1350-CO180,180S/29F | HCA | 1350 | 180 | 23 | 29 |  | 2575000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 1780 | 114 | 56 | 24 | 1974 | 1780 | 114 | 56 | 24 | 1974 | 0 | Red |  |  | 20017397 | 2021-09-03
TED0047-TH | HET | 61001152 | HO | เลยสัญญา HO | - | TH209238 | ONE PhromPhong | SA2 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Phongchon Suraphakwanich | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153715 |  | HCA-1350-CO180,180S/29F | HCA | 1350 | 180 | 23 | 29 |  | 2575000 | Bangkok | แขวงคลองตัน | 2021-09-20 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished | [10 empty] | 2022-08-31 | Finished | [38 empty] | 1780 | 114 | 56 | 24 | 1974 | 1780 | 114 | 56 | 24 | 1974 | 0 | Red |  |  | 20017397 | 2021-09-03
TAC1954-TH | HET | 61001153 | HO | ยังอยู่ในสัญญา HO | - | TH219159 | Khun Visut Ladprao 80 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Thamnul Kongsar | 2021-04-21 | 2021-10-21 | 2021-12-21 |  | VFI-600-CO60,60S/5F | VFI-II | 600 | 60 | 5 | 5 |  | 1016500 | Bangkok | เขตวังทองหลาง | 2021-10-21 | [36 empty] | 2021-10-21 | 1900-01-01 | [16 empty] | 2021-10-21 | 2021-11-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-21 | Working | [6 empty] | 2021-05-16 | Finished |  |  | 2021-11-06 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Green |  |  | 20017797 | 2021-10-26
TAC1955-TH | HET | 61001156 | Install | ยังอยู่ในสัญญา HO | - | TH219160 | Health Innovation Bldg., Srinakharinwirot Univ. | L1, | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2021-02-01 | 2021-09-01 | 2021-12-01 |  | VFI-1000-CO105,105S/9F | VFI-II | 1000 | 105 | 9 | 9 |  | 1444500 | Nakhon Nayok | ตำบลองครักษ์ | 2021-10-03 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-15 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-26 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-10-25 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 748 | 94 | 24 | 16 | 882 | 748 | 94 | 24 | 16 | 882 | 0 | Green |  |  | 20017418 | 2021-10-14
TAC1956-TH | HET | 61001156 | Install | ยังอยู่ในสัญญา HO | - | TH219160 | Health Innovation Bldg., Srinakharinwirot Univ. | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2021-02-01 | 2021-09-01 | 2021-12-01 |  | VFI-1000-CO105,105S/9F | VFI-II | 1000 | 105 | 9 | 9 |  | 1444500 | Nakhon Nayok | ตำบลองครักษ์ | 2021-10-03 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-15 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-26 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-10-25 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 748 | 94 | 24 | 16 | 882 | 748 | 94 | 24 | 16 | 882 | 0 | Green |  |  | 20017418 | 2021-10-14
TAC1957-TH | HET | 61001156 | Install | ยังอยู่ในสัญญา HO | - | TH219160 | Health Innovation Bldg., Srinakharinwirot Univ. | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2021-02-01 | 2021-09-01 | 2021-12-01 |  | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 1465900 | Nakhon Nayok | ตำบลองครักษ์ | 2021-10-03 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-18 | 2021-11-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-26 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-10-25 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Green |  |  | 20017418 | 2021-10-14
TAC1958-TH | HET | 61001156 | Install | ยังอยู่ในสัญญา HO | - | TH219160 | Health Innovation Bldg., Srinakharinwirot Univ. | L4 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2021-02-01 | 2021-09-01 | 2021-12-01 |  | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 1465900 | Nakhon Nayok | ตำบลองครักษ์ | 2021-10-03 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-18 | 2021-11-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-26 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-10-25 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Green |  |  | 20017418 | 2021-10-14
TAC1959-TH | HET | 61001156 | Install | ยังอยู่ในสัญญา HO | - | TH219160 | Health Innovation Bldg., Srinakharinwirot Univ. | L5 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | 2021-02-01 | 2021-09-01 | 2021-12-01 |  | VFI-1150-CO105,105S/11F | VFI-II | 1150 | 105 | 11 | 11 |  | 1562200 | Nakhon Nayok | ตำบลองครักษ์ | 2021-10-03 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-18 | 2021-11-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-26 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-10-25 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Green |  |  | 20017418 | 2021-10-14
TED0055-TH | HET | 61001157 | HO | เลยสัญญา HO | - | TH209236 | ONE 24 | FL | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153777 |  | MCA-1600-CO150,150S/25F | MCA | 1600 | 150 | 25 | 25 |  | 2400000 | Bangkok | แขวงคลองตัน | 1900-01-01 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished |  |  | 2021-09-14 | Finished | [6 empty] | 2022-06-30 | Finished | [38 empty] | 1632 | 117 | 48 | 24 | 1821 | 1632 | 117 | 48 | 24 | 1821 | 0 | Red |  |  | 20017424 | 2021-09-03
TED0053-TH | HET | 61001157 | HO | เลยสัญญา HO | - | TH209236 | ONE 24 | H1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153777 |  | MCA-1350-CO180,180S/24F | MCA | 1350 | 180 | 16 | 24 |  | 2400000 | Bangkok | แขวงคลองตัน | 1900-01-01 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished |  |  | 2021-09-14 | Finished | [6 empty] | 2022-06-30 | Finished | [38 empty] | 1577 | 116 | 48 | 24 | 1765 | 1577 | 116 | 48 | 24 | 1765 | 0 | Red |  |  | 20017424 | 2021-09-03
TED0054-TH | HET | 61001157 | HO | เลยสัญญา HO | - | TH209236 | ONE 24 | S | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153777 |  | MCA-1600-CO150,150S/25F | MCA | 1600 | 150 | 18 | 25 |  | 2300000 | Bangkok | แขวงคลองตัน | 1900-01-01 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished |  |  | 2021-09-14 | Finished | [6 empty] | 2022-06-30 | Finished | [38 empty] | 1632 | 117 | 48 | 24 | 1821 | 1632 | 117 | 48 | 24 | 1821 | 0 | Red |  |  | 20017424 | 2021-09-03
TED0051-TH | HET | 61001157 | HO | เลยสัญญา HO | - | TH209236 | ONE 24 | SA1 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153777 |  | MCA-1350-CO180,180S/24F | MCA | 1350 | 180 | 17 | 24 |  | 2400000 | Bangkok | แขวงคลองตัน | 1900-01-01 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished |  |  | 2021-09-14 | Finished | [6 empty] | 2022-06-30 | Finished | [38 empty] | 1577 | 116 | 48 | 24 | 1765 | 1577 | 116 | 48 | 24 | 1765 | 0 | Red |  |  | 20017424 | 2021-09-03
TED0052-TH | HET | 61001157 | HO | เลยสัญญา HO | - | TH209236 | ONE 24 | SA2 | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153777 |  | MCA-1350-CO180,180S/24F | MCA | 1350 | 180 | 17 | 24 |  | 2400000 | Bangkok | แขวงคลองตัน | 1900-01-01 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished |  |  | 2021-09-14 | Finished | [6 empty] | 2022-06-30 | Finished | [38 empty] | 1577 | 116 | 48 | 24 | 1765 | 1577 | 116 | 48 | 24 | 1765 | 0 | Red |  |  | 20017424 | 2021-09-03
TAJ1149-TH | HET | 61001158 | HO | ยังอยู่ในสัญญา HO | - | TH219162 | Show Room Thaipipat Hardware | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Yosvaris Limmethaphant | 2021-03-30 | 2021-08-30 | 2021-10-30 |  | P-1000-2S60,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1177000 | Khon Kaen | ตำบลในเมือง | 2021-10-15 | [36 empty] | 2021-08-30 | 2021-08-30 | 2021-09-01 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-15 | 2021-11-29 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-15 | Working | [6 empty] | 2021-04-09 | Finished |  |  | 2021-09-10 | Finished | [6 empty] | 2021-10-30 | Finished | [6 empty] | 2021-09-01 | Finished |  |  | 2021-09-01 | Finished |  |  | 2021-09-03 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Green |  |  | 20017471 | 2021-08-30
TBF0037-TH | HET | 61001159 |  | ยังอยู่ในสัญญา HO | - | TH219136 | Joon Chee Factory Phase 3 | FL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | 2021-03-15 | 2021-10-15 | 2021-11-15 |  | F-2000-2S45,45S/3F | F-EL | 2000 | 45 | 3 | 3 |  | 2675000 | Chon Buri | อำเภอศรีราชา | 2021-10-01 | [36 empty] | 2021-10-15 | 1900-01-01 | [16 empty] | 2021-10-15 | 2021-10-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2021-12-15 | Finished | [38 empty] | 515 | 94 | 36 | 20 | 665 | 515 | 94 | 36 | 20 | 665 | 0 | Green |  |  | 20017430 | 2021-09-30
TAJ1152-TH | HET | 61001161 |  | ยังอยู่ในสัญญา HO | - | TH219161 | Nanomed New Office | L-02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2021-05-05 | 2021-09-03 | 2021-11-05 |  | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 914850 | Bangkok | แขวงดอนเมือง | 2021-09-03 | [36 empty] | 2021-09-03 | 1900-01-01 | [16 empty] | 2021-09-25 | 2021-10-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-05 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-09-14 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Green |  |  | 20017925 | 2021-09-03
TAJ1153-TH | HET | 61001162 |  | เลยสัญญา HO | - | TH219163 | Suan Sunandha Rajabhat University Nakhon Pathorn | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Yosvaris Limmethaphant | -153896 | -153742 | -153684 |  | P-1000-CO60W1,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1444500 | Nakhon Pathom | อำเภอพุทธมณฑล | 1900-01-01 | [36 empty] | 2022-01-24 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20019614 | 2022-01-24
TAJ1154-TH | HET | 61001163 |  | ยังอยู่ในสัญญา HO | - | TH219164 | Apartment Khun Suppakorn | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Yosvaris Limmethaphant | 2021-04-01 | 2021-12-01 | 2022-03-01 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 1150000 | Bangkok | แขวงสวนหลวง | 2021-12-01 | [36 empty] | 2021-12-01 | 1900-01-01 | [16 empty] | 2021-12-01 | 2022-01-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-01 | Working | [6 empty] | 2021-05-23 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-03-01 | Finished | [38 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Green |  |  | 20017926 | 2021-12-01
TAC1960-TH | HET | 61001166 |  | ยังอยู่ในสัญญา HO | - | TH219169 | MEA Jorrakaeyai | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Siraprapa Sihamart | 2021-04-05 | 2021-08-05 | 2021-10-05 |  | VFI-700-CO60,60S/5F | VFI-II | 700 | 60 | 5 | 5 |  | 1100000 | Samut Prakan | ตำบลบางปู | 2021-09-30 | [36 empty] | 2021-08-05 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-30 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-25 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-08-16 | Finished | [6 empty] | 2021-11-15 | Finished | [38 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Orange |  |  | 20017601 | 2021-08-05
TAJ1157-TH | HET | 61001169 |  | เลยสัญญา HO | - | TH219172 | Ban Chaba | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Siraprapa Sihamart | -153991 | -153885 | -153853 |  | P-1000-CO60W2,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1348200 | Bangkok | แขวงช่องนนทรี | 2021-09-03 | [36 empty] | 2021-09-03 | 1900-01-01 |  |  | FACTORY SHIPMENT DELAY | [13 empty] | 2021-10-01 | 2021-10-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-05 | Working | DELIVERY DELAY | [5 empty] | 2021-06-21 | Finished |  |  | 2021-09-14 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20018407 | 2021-09-03
TAJ1166-TH | HET | 61001171 | Install | เลยสัญญา HO | - | TH219176 | The Cube Loft Srinakarin-Thepharak | L1 (Building A) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Samut Prakan | อำเภอเมืองสมุทรปราการ | 2021-08-30 | 2021-08-30 | Finished | [34 empty] | 2021-08-05 | 2021-08-09 | 2021-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-31 | 2021-09-20 | 2021-09-03 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-15 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 555 | 84 | 24 | 16 | 679 | 4.23 | Red |  |  | 20017512 | 2021-06-25
TAJ1168-TH | HET | 61001171 | Install | เลยสัญญา HO | - | TH219176 | The Cube Loft Srinakarin-Thepharak | L1 (Building B) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 900000 | Samut Prakan | อำเภอเมืองสมุทรปราการ | 2021-09-03 | 2021-09-03 | Finished | [34 empty] | 2021-08-05 | 2021-08-09 | 2021-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-06 | 2021-09-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-15 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Red |  |  | 20017512 | 2021-06-25
TAJ1167-TH | HET | 61001171 | Install | เลยสัญญา HO | - | TH219176 | The Cube Loft Srinakarin-Thepharak | L2 (Building A) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Samut Prakan | อำเภอเมืองสมุทรปราการ | 2021-08-30 | 2021-08-30 | Finished | [34 empty] | 2021-08-05 | 2021-08-09 | 2021-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-31 | 2021-09-20 | 2021-09-03 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-15 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 555 | 84 | 24 | 16 | 679 | 4.23 | Red |  |  | 20017512 | 2021-06-25
TAJ1169-TH | HET | 61001171 | Install | เลยสัญญา HO | - | TH219176 | The Cube Loft Srinakarin-Thepharak | L2 (Building B) | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 900000 | Samut Prakan | อำเภอเมืองสมุทรปราการ | 2021-09-03 | 2021-09-03 | Finished | [34 empty] | 2021-08-05 | 2021-08-09 | 2021-08-10 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-06 | 2021-09-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-21 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-15 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-08-09 | Finished |  |  | 2021-08-09 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Red |  |  | 20017512 | 2021-06-25
TAJ1158-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L1(Building A,B,C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Bangkok | แขวงทุ่งสองห้อง | 2021-09-15 | [36 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Red |  |  | 20017511 | 2021-06-25
TAJ1160-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L1(Building A,B,C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Bangkok | แขวงทุ่งสองห้อง | 2021-08-18 | 2021-08-05 | Finished | [34 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-01 | 2021-10-15 | 2021-08-09 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-25 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 204 | 84 | 24 | 16 | 328 | 53.74 | Red |  |  | 20017511 | 2021-06-25
TAJ1162-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L1(Building A,B,C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Bangkok | แขวงทุ่งสองห้อง | 2021-06-18 | 2021-06-25 | Finished | [34 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-01 | 2021-10-15 | 2021-08-09 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-25 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 204 | 84 | 24 | 16 | 328 | 53.74 | Red |  |  | 20017511 | 2021-06-25
TAJ1164-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L1(Building D) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงทุ่งสองห้อง | 2021-09-15 | [36 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Red |  |  | 20017511 | 2021-06-25
TAJ1159-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L2(Building A,B,C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Bangkok | แขวงทุ่งสองห้อง | 2021-09-15 | [36 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Red |  |  | 20017511 | 2021-06-25
TAJ1161-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L2(Building A,B,C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Bangkok | แขวงทุ่งสองห้อง | 2021-08-18 | 2021-08-05 | Finished | [34 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-01 | 2021-10-15 | 2021-08-09 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-25 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 204 | 84 | 24 | 16 | 328 | 53.74 | Red |  |  | 20017511 | 2021-06-25
TAJ1163-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L2(Building A,B,C) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/9F | UAG-SN1 | 750 | 60 | 9 | 9 |  | 930000 | Bangkok | แขวงทุ่งสองห้อง | 2021-06-18 | 2021-06-25 | Finished | [34 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-01 | 2021-10-15 | 2021-08-09 | Finished |  |  | 2021-08-10 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-25 | Finished | [18 empty] | 65 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 585 | 84 | 24 | 16 | 709 | 204 | 84 | 24 | 16 | 328 | 53.74 | Red |  |  | 20017511 | 2021-06-25
TAJ1165-TH | HET | 61001172 | Install | เลยสัญญา HO | - | TH219175 | The Cube South Chaengwattana 15/1 | L2(Building D) | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | 2021-03-26 | 2021-06-26 | 2021-09-13 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงทุ่งสองห้อง | 2021-09-15 | [36 empty] | 2021-06-25 | 2021-06-25 | 2021-06-25 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-16 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-13 | Working | PARTIAL DELIVERY | [5 empty] | 2021-04-30 | Finished |  |  | 2021-08-12 | Finished | [14 empty] | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Red |  |  | 20017511 | 2021-06-25
TBL0702-TH | HET | 61001173 | HO | เลยสัญญา HO | - | TH209236 | ONE 24 | C | 1 |  |  | 1 | Naret Meesilapawikkai | Tachakorn Atcharojarek | Sittichot Palangsuriya | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -154172 | -153868 | -153807 |  | OUG-630-CO90,90S/10F | OUG-ON1 | 630 | 90 | 9 | 10 |  | 1050000 | Bangkok | แขวงคลองตัน | 1900-01-01 | [36 empty] | 2021-09-20 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-06-02 | Finished |  |  | 2021-12-12 | Finished | [6 empty] | 2022-06-30 | Finished | [38 empty] | 755 | 89 | 24 | 16 | 884 | 755 | 89 | 24 | 16 | 884 | 0 | Red |  |  | 20017602 | 2021-09-20
TAJ1170-MM | HET | 61001174 | HO | เลยสัญญา HO | - | TH209271 | Wat Phrathat Saimerng Tachileik | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | 2020-12-28 | 2021-07-01 | 2021-08-01 |  | P-1000-CO60W2,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1551500 | Tachilek | จังหวัดเชียงราย 57130 | 2021-09-30 | [36 empty] | 2021-07-06 | 2021-08-12 | 2021-08-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-30 | 2021-10-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-28 | Working | [6 empty] | 2021-04-30 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2022-03-15 | Finished | [6 empty] | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20017593 | 2021-07-06
TBL0703-TH | HET | 61001175 | HO | เลยสัญญา HO | - | TH219132 | Phuket Boat Lagoon | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154040 | -153857 | -153796 |  | OUG-1050-CO60,60S/4F | OUG-ON1 | 1050 | 60 | 4 | 4 |  | 1658500 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-01 | [36 empty] | 2021-10-01 | 2021-08-24 | 2021-08-24 | Finished | [14 empty] | 2021-10-01 | 2021-12-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2021-08-25 | Finished | [18 empty] | 2021-08-24 | Finished |  |  | 2021-08-24 | Finished |  |  | 2021-08-25 | Finished | [22 empty] | 437 | 85 | 16 | 16 | 554 | 437 | 85 | 16 | 16 | 554 | 0 | Red |  |  | 20017783 | 2021-10-01 |  |  |  | HDME001298 | -153895
TAJ1171-TH | HET | 61001175 | HO | เลยสัญญา HO | - | TH219132 | Phuket Boat Lagoon | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154040 | -153857 | -153796 |  | P-1050-CO60W2,60S/4F | UAG-SN1 | 1050 | 60 | 4 | 4 |  | 1123500 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-01 | [36 empty] | 2021-10-01 | 2021-08-24 | 2021-08-24 | Finished | [14 empty] | 2021-10-01 | 2021-12-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-01 | Working | [6 empty] | 2021-08-25 | Finished | [18 empty] | 2021-08-24 | Finished |  |  | 2021-08-24 | Finished |  |  | 2021-08-25 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20017783 | 2021-10-01 |  |  |  | HDME001298 | -153895
TAJ1173-TH | HET | 61001176 | HO | ยังอยู่ในสัญญา HO | - | TH219107 | Big Progress Residence | L-01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | SIRIRAT YUANGNGAM | 2021-03-19 | 2021-09-17 | 2021-11-19 |  | P-1000-CO60W1,60S/9F | UAG-SN1 | 1000 | 60 | 9 | 9 |  | 1280000 | Nonthaburi | อำเภอบางใหญ่ | 2021-09-17 | [36 empty] | 2021-09-17 | 1900-01-01 | [16 empty] | 2021-09-21 | 2021-10-29 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-10 | Working | [6 empty] | 2021-05-10 | Finished |  |  | 2021-09-28 | Finished | [6 empty] | 2021-12-19 | Finished | [38 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Green |  |  | 20017649 | 2021-09-17
TAK1172-TH | HET | 61001177 | HO | เลยสัญญา HO | - | TH219139 | Jetanin Hospital (PH2) | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Siraprapa Sihamart | 2021-04-10 | 2021-07-23 | 2021-09-25 |  | B-750-2S60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1650000 | Bangkok | แขวงลุมพินี | 2021-10-23 | [36 empty] | 2021-07-23 | 1900-01-01 |  |  | OTHERS | [13 empty] | 2021-10-23 | 2021-11-23 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-10 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-05-10 | Finished |  |  | 2021-08-03 | Finished | [6 empty] | 2021-09-25 | Finished | [38 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20017648 | 2021-07-23
TAJ1174-TH | HET | 61001178 | HO | ยังอยู่ในสัญญา HO | - | TH219053 | NACC Khonkaen | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Somsak Sutthosri | 2021-04-09 | 2021-07-26 | 2021-10-09 |  | P-1000-CO60D,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1060000 | Khon Kaen | อำเภอเมืองขอนแก่น | 2021-08-03 | 2021-08-03 | Finished | [34 empty] | 2021-07-26 | 2021-08-03 | 2021-08-03 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-08-30 | 2021-09-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-28 | Working | [6 empty] | 2021-05-16 | Finished |  |  | 2021-09-12 | Finished | [14 empty] | 2021-08-03 | Finished |  |  | 2021-08-03 | Finished |  |  | 2021-08-03 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Orange |  |  | 20017662 | 2021-07-26
TAJ1175-TH | HET | 61001178 |  | ยังอยู่ในสัญญา HO | - | TH219053 | NACC Khonkaen | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Somsak Sutthosri | 2021-04-09 | 2021-07-26 | 2021-10-09 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1030000 | Khon Kaen | อำเภอเมืองขอนแก่น | 2021-08-30 | 2021-09-03 | Finished | [34 empty] | 2021-07-26 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-28 | Working | [6 empty] | 2021-05-16 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Orange |  |  | 20017662 | 2021-07-26
TAJ1176-TH | HET | 61001178 |  | ยังอยู่ในสัญญา HO | - | TH219053 | NACC Khonkaen | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Somsak Sutthosri | 2021-04-09 | 2021-07-26 | 2021-10-09 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1030000 | Khon Kaen | อำเภอเมืองขอนแก่น | 2021-08-30 | 2021-09-03 | Finished | [34 empty] | 2021-07-26 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-15 | 2021-10-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-28 | Working | [6 empty] | 2021-05-16 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Orange |  |  | 20017662 | 2021-07-26
TAJ1177-TH | HET | 61001178 |  | ยังอยู่ในสัญญา HO | - | TH219053 | NACC Khonkaen | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Somsak Sutthosri | 2021-04-09 | 2021-07-26 | 2021-10-09 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1030000 | Khon Kaen | อำเภอเมืองขอนแก่น | 2021-09-12 | [36 empty] | 2021-07-26 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-30 | 2021-10-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-28 | Working | [6 empty] | 2021-05-16 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Orange |  |  | 20017662 | 2021-07-26
TAC1963-TH | HET | 61001179 | HO | ยังอยู่ในสัญญา HO | - | TH219013 | Multipurpose Building Woranari Chaloem Songkhla School | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 | Somsak Denpraphat | Janyaruk Choobuakhaw | 2021-04-21 | 2021-08-23 | 2021-10-21 |  | VFI-1000-CO60,60S/3F | VFI-II | 1000 | 60 | 3 | 3 |  | 1080000 | Songkhla | ตำบลบ่อยาง | 2021-09-21 | 2021-08-20 | Finished | [34 empty] | 2021-08-23 | 2021-08-18 | 2021-08-20 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-22 | 2021-10-22 | 2021-08-27 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-29 | Finished |  |  | 2021-09-03 | Finished | [22 empty] | 45 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-22 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-21 | Working | [6 empty] | 2021-05-25 | Finished |  |  | 2021-09-03 | Finished | [6 empty] | 2021-10-21 | Finished | [6 empty] | 2021-08-18 | Finished |  |  | 2021-08-20 | Finished |  |  | 2021-08-20 | Finished | [22 empty] | 417 | 89 | 16 | 16 | 538 | 229 | 89 | 16 | 16 | 350 | 34.94 | Green |  |  | 20017782 | 2021-08-23
TAC1964-TH | HET | 61001180 | Install | เลยสัญญา HO | - | TH219125 | Vajira Hospital (Medical Supply Center) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | -154071 | -153970 | -153829 |  | VFI-1000-CO60,60S/6F | VFI-II | 1000 | 60 | 6 | 6 |  | 1198400 | Bangkok | แขวงวชิรพยาบาล | 2021-10-11 | [36 empty] | 2021-09-15 | 1900-01-01 |  |  | PAYMENT DELAY | [13 empty] | 2021-10-11 | 2021-11-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-11-29 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-06-08 | Finished |  |  | 2021-12-04 | Finished | [6 empty] | 2021-12-30 | Finished | [38 empty] | 583 | 91 | 24 | 16 | 714 | 583 | 91 | 24 | 16 | 714 | 0 | Red |  |  | 20017846 | 2021-11-23
TAJ1178-TH | HET | 61001180 | Install | เลยสัญญา HO | - | TH219125 | Vajira Hospital (Medical Supply Center) | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | -154071 | -153970 | -153829 |  | P-1000-2S60,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 995100 | Bangkok | แขวงวชิรพยาบาล | 2021-09-03 | 2021-09-03 | Finished | [34 empty] | 2021-08-15 | 2021-08-14 | 2021-08-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-09-05 | 2021-09-28 | 2021-09-04 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-30 | Working | [6 empty] | 2021-06-08 | Finished |  |  | 2021-08-06 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-08-14 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-18 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 304 | 80 | 16 | 16 | 416 | 3.7 | Red |  |  | 20017846 | 2021-07-26 |  |  |  | HDME001284 | -153905
TAJ1179-TH | HET | 61001180 | Install | เลยสัญญา HO | - | TH219125 | Vajira Hospital (Medical Supply Center) | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Thannapat Srisamdang | 4 |  | 2 | Weerapoj Paijitvijarn | Phumiphat Siprajan | -154071 | -153970 | -153829 |  | P-1000-2S60,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 963000 | Bangkok | แขวงวชิรพยาบาล | 2021-09-03 | 2021-09-03 | Finished | [34 empty] | 2021-08-15 | 2021-08-14 | 2021-08-16 | Finished | PAYMENT DELAY | [13 empty] | 2021-09-05 | 2021-09-28 | 2021-09-04 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-12-30 | Working | [6 empty] | 2021-06-08 | Finished |  |  | 2021-08-06 | Finished | [6 empty] | 2021-12-30 | Finished | [6 empty] | 2021-08-14 | Finished |  |  | 2021-08-16 | Finished |  |  | 2021-08-18 | Finished | [22 empty] | 276 | 79 | 16 | 16 | 387 | 262 | 79 | 16 | 16 | 373 | 3.62 | Red |  |  | 20017846 | 2021-07-26 |  |  |  | HDME001284 | -153905
TAJ1181-TH | HET | 61001184 | Install | ยังอยู่ในสัญญา HO | - | TH219112 | Home Khun Chanit | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Somsak Denpraphat | Siraprapa Sihamart | 2021-04-19 | 2021-08-03 | 2021-10-04 |  | P-1000-CO60W1,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1050000 | Bangkok | อำเภอนครชัยศรี | 2021-09-01 | [36 empty] | 2021-08-03 | 1900-01-01 |  |  | OTHERS | [13 empty] | 2021-09-01 | 2021-09-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-08-13 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-09 | Working | [6 empty] | 2021-05-25 | Finished |  |  | 2021-08-14 | Finished | [6 empty] | 2022-03-04 | Finished | [38 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Orange |  |  | 20017884 | 2021-08-03
TAJ1183-TH | HET | 61001186 | HO | เลยสัญญา HO | - | TH219179 | Baan Toi Ting | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Yosvaris Limmethaphant | -153986 | -153894 | -153833 |  | P-1000-CO60W2,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1326800 | Udon Thani | ถนนทหาร | 2021-10-11 | [36 empty] | 2021-08-25 | 2021-08-26 | 2021-08-26 | Finished | [14 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-05 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-10 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-05 | Finished | [6 empty] | 2021-10-25 | Finished | [6 empty] | 2021-08-26 | Finished |  |  | 2021-08-26 | Finished |  |  | 2021-08-27 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20018302 | 2021-08-25
TAJ1182-TH | HET | 61001187 | HO | ยังอยู่ในสัญญา HO | - | TH219075 | PSL Home | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | Orawan Kwanpheng | 2021-04-23 | 2021-08-20 | 2021-10-20 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 970000 | Nonthaburi | ตำบลตลาดขวัญ | 2021-09-01 | 2021-09-05 | Finished | [34 empty] | 2021-08-20 | 2021-08-23 | 2021-08-24 | Finished | [14 empty] | 2021-09-24 | 2021-10-27 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-28 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-11 | Working | [6 empty] | 2021-05-25 | Finished |  |  | 2021-08-31 | Finished | [6 empty] | 2021-11-15 | Finished | [6 empty] | 2021-08-23 | Finished |  |  | 2021-08-24 | Finished |  |  | 2021-08-25 | Finished | [22 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Orange |  |  | 20017924 | 2021-08-20
TAJ1184-TH | HET | 61001188 |  | เลยสัญญา HO | - | TH219184 | Ocean Media | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Yosvaris Limmethaphant | -153973 | -153819 | -153790 |  | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1100000 | Pathum Thani |  | 2021-11-08 | [36 empty] | 2021-11-08 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2021-11-10 | 2021-12-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-21 | Finished |  |  | 2021-11-19 | Finished | [6 empty] | 2022-02-16 | Finished | [38 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20018486 | 2021-11-08
TAJ1185-TH | HET | 61001189 | Test | เลยสัญญา HO | - | TH219182 | JTK Apartment | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 | Somsak Denpraphat | Yosvaris Limmethaphant | -154010 | -153920 | -153857 |  | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1230500 | Chiang Rai | อำเภอแม่สาย | 2021-08-01 | 2021-08-06 | Finished | [34 empty] | 2021-08-02 | 2021-08-12 | 2021-08-12 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-10-11 | 2021-12-28 | 2021-08-07 | Finished |  |  | 2021-08-08 | Finished |  |  | 2021-08-14 | Finished |  |  | 2021-08-15 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-19 | Finished |  |  | 2021-08-23 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-09-01 | Finished | [6 empty] | 90 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2022-02-10 | Working | [6 empty] | 2021-06-10 | Finished |  |  | 2021-08-13 | Finished | [6 empty] | 2022-02-15 | Finished | [6 empty] | 2021-08-12 | Finished |  |  | 2021-08-12 | Finished |  |  | 2021-08-13 | Finished | [22 empty] | 497 | 83 | 24 | 16 | 620 | 49 | 83 | 24 | 16 | 172 | 72.26 | Red |  |  | 20017996 | 2021-08-02 |  |  |  | HDME001283 | -153907
TAJ1191-TH | HET | 61001201 | Install | เลยสัญญา HO | - | TH209178 | Phuket Provincial NACC Office Building | EL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Janyaruk Choobuakhaw | -154015 | -153898 | -153832 |  | P-1000-CO60D,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1177000 | Phuket | ตำบลตลาดเหนือ | 2021-10-11 | [36 empty] | 2021-08-20 | 2021-09-14 | 2021-09-14 | Finished | PAYMENT DELAY | [13 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-26 | Working | [6 empty] | 2021-06-07 | Finished |  |  | 2021-08-31 | Finished | [6 empty] | 2021-10-26 | Finished | [6 empty] | 2021-09-14 | Finished |  |  | 2021-09-14 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20017859 | 2021-08-20 |  |  |  | HDME001313 | -153874
TAJ1192-TH | HET | 61001201 | Install | เลยสัญญา HO | - | TH209178 | Phuket Provincial NACC Office Building | PL-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Janyaruk Choobuakhaw | -154015 | -153898 | -153832 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1123500 | Phuket | ตำบลตลาดเหนือ | 2021-10-11 | [36 empty] | 2021-08-20 | 2021-09-14 | 2021-09-14 | Finished | PAYMENT DELAY | [13 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-26 | Working | [6 empty] | 2021-06-07 | Finished |  |  | 2021-08-31 | Finished | [6 empty] | 2021-10-26 | Finished | [6 empty] | 2021-09-14 | Finished |  |  | 2021-09-14 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20017859 | 2021-08-20 |  |  |  | HDME001313 | -153874
TEB0238-TH | HET | 61001202 | HO | เลยสัญญา HO | - | TH219167 | Home Khun Suwat Uaweerawat | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 | Weerapoj Paijitvijarn | Prapaipim Netnonthai | 2021-04-23 | 2021-07-23 | 2021-08-23 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 4 | 4 |  | 800000 | Bangkok | เขตบางคอแหลม | 2021-08-30 | [36 empty] | 2021-07-09 | 2021-08-19 | 2021-08-19 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-01 | 2021-12-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-30 | [12 empty] | 0 | 2021-08-20 | 2000-01-01 | 2021-08-20 | Finished | [14 empty] | 25 | 2021-12-01 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-05-25 | Finished |  |  | 2021-08-12 | Finished | [6 empty] | 2021-11-15 | Finished | [6 empty] | 2021-08-19 | Finished |  |  | 2021-08-26 | Finished |  |  | 2021-08-31 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 4 | 16 | 245 | 4.67 | Red |  |  | 20017882 | 2021-07-09
TAC1981-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-BL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | VFI-1600-2S105,105S/13F | VFI-II | 1600 | 105 | 13 | 13 |  | 2161400 | Bangkok | แขวงพระโขนงใต้ | 2021-12-03 | [36 empty] | 2021-12-03 | 1900-01-01 | [16 empty] | 2021-12-03 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-06 | Finished | [46 empty] | 969 | 107 | 32 | 20 | 1128 | 969 | 107 | 32 | 20 | 1128 | 0 | Red |  |  | 20018043 | 2021-12-03
TAC1982-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-BL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | VFI-1600-2S105,105S/13F | VFI-II | 1600 | 105 | 13 | 13 |  | 2161400 | Bangkok | แขวงพระโขนงใต้ | 2021-12-03 | [36 empty] | 2021-12-03 | 1900-01-01 | [16 empty] | 2021-12-03 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-06 | Finished | [46 empty] | 969 | 107 | 32 | 20 | 1128 | 969 | 107 | 32 | 20 | 1128 | 0 | Red |  |  | 20018043 | 2021-12-03
TEC0206-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-DW-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | DT-100S-B30,30S/13F | DT | 100 | 30 | 13 | 13 |  | 288900 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 476 | 0 | 32 | 0 | 508 | 476 | 0 | 32 | 0 | 508 | 0 | Red |  |  | 20018042 | 2021-08-25
TEC0207-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-DW-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | DT-100S-B30,30S/6F | DT | 100 | 30 | 6 | 6 |  | 203300 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 283 | 0 | 24 | 0 | 307 | 283 | 0 | 24 | 0 | 307 | 0 | Red |  |  | 20018042 | 2021-08-25
TEC0208-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-DW-3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | DT-100S-B30,30S/7F | DT | 100 | 30 | 7 | 7 |  | 214000 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 310 | 0 | 24 | 0 | 334 | 310 | 0 | 24 | 0 | 334 | 0 | Red |  |  | 20018042 | 2021-08-25
TEC0209-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-DW-4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | DT-100S-B30,30S/2F | DT | 100 | 30 | 2 | 2 |  | 160500 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20018042 | 2021-08-25
TEC0210-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-DW-5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | DT-100S-B30,30S/2F | DT | 100 | 30 | 2 | 2 |  | 160500 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20018042 | 2021-08-25
TAC1977-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-PL1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | VFI-1350-CO105,105S/13F | VFI-II | 1350 | 105 | 13 | 13 |  | 2246465 | Bangkok | แขวงพระโขนงใต้ | 2021-12-03 | [36 empty] | 2021-12-03 | 1900-01-01 | [16 empty] | 2021-12-03 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-06 | Finished | [46 empty] | 969 | 107 | 32 | 20 | 1128 | 969 | 107 | 32 | 20 | 1128 | 0 | Red |  |  | 20018043 | 2021-12-03
TAC1978-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-PL2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | VFI-1350-CO105,105S/13F | VFI-II | 1350 | 105 | 13 | 13 |  | 2246465 | Bangkok | แขวงพระโขนงใต้ | 2021-12-03 | [36 empty] | 2021-12-03 | 1900-01-01 | [16 empty] | 2021-12-03 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-06 | Finished | [46 empty] | 969 | 107 | 32 | 20 | 1128 | 969 | 107 | 32 | 20 | 1128 | 0 | Red |  |  | 20018043 | 2021-12-03
TAC1979-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-PL3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | VFI-1350-CO105,105S/13F | VFI-II | 1350 | 105 | 13 | 13 |  | 2246465 | Bangkok | แขวงพระโขนงใต้ | 2021-12-03 | [36 empty] | 2021-12-03 | 1900-01-01 | [16 empty] | 2021-12-03 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-06 | Finished | [46 empty] | 969 | 107 | 32 | 20 | 1128 | 969 | 107 | 32 | 20 | 1128 | 0 | Red |  |  | 20018043 | 2021-12-03
TAC1980-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-PL4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | VFI-1350-CO105,105S/13F | VFI-II | 1350 | 105 | 13 | 13 |  | 2246465 | Bangkok | แขวงพระโขนงใต้ | 2021-12-03 | [36 empty] | 2021-12-03 | 1900-01-01 | [16 empty] | 2021-12-03 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-06 | Finished | [46 empty] | 969 | 107 | 32 | 20 | 1128 | 969 | 107 | 32 | 20 | 1128 | 0 | Red |  |  | 20018043 | 2021-12-03
TAJ1195-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-SL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | P-1600-2S90,90S/15F | UAG-SN1 | 1600 | 90 | 14 | 15 |  | 2033000 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-05 | Finished | [46 empty] | 850 | 97 | 32 | 20 | 999 | 850 | 97 | 32 | 20 | 999 | 0 | Red |  |  | 20018043 | 2021-08-25
TAJ1196-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | H-SL-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | P-1600-2S90,90S/15F | UAG-SN1 | 1600 | 90 | 15 | 15 |  | 2033000 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-05 | Finished | [46 empty] | 850 | 97 | 32 | 20 | 999 | 850 | 97 | 32 | 20 | 999 | 0 | Red |  |  | 20018043 | 2021-08-25
TAJ1193-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | P-PL-1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | P-1000-CO60W1,60S/9F | UAG-SN1 | 1000 | 60 | 9 | 9 |  | 1230500 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-05 | Finished | [46 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Red |  |  | 20018043 | 2021-08-25
TAJ1194-TH | HET | 61001203 | Install | เลยสัญญา HO | - | TH219010 | Ruamjairak Hospital | P-PL-2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Nattapol Muaynoo | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -154225 | -153894 | -153721 |  | P-1000-CO60W1,60S/9F | UAG-SN1 | 1000 | 60 | 9 | 9 |  | 1230500 | Bangkok | แขวงพระโขนงใต้ | 2021-09-10 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-10 | 2022-01-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-11 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-14 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-05 | Finished | [46 empty] | 585 | 84 | 24 | 16 | 709 | 585 | 84 | 24 | 16 | 709 | 0 | Red |  |  | 20018043 | 2021-08-25
TAJ1201-TH | HET | 61001204 | HO | เลยสัญญา HO | - | TH219168 | Temsuk Mansion | L-01 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 | Weerapoj Paijitvijarn | SIRIRAT YUANGNGAM | -154014 | -153908 | -153877 |  | P-750-CO60,60S/6F | UAG-SN1 | 750 | 60 | 6 | 6 |  | 1070000 | Bangkok | แขวงดินแดง | 2021-08-11 | [36 empty] | 2021-08-11 | 2021-08-18 | 2021-08-18 | Finished | STORE AREA | [13 empty] | 2021-08-23 | 2021-09-23 | 2021-08-25 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-05 | Finished | [6 empty] | 2021-09-04 | Finished |  |  | 2021-09-05 | Finished | [18 empty] | 60 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-24 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-02 | Finished |  |  | 2021-08-22 | Finished | [6 empty] | 2022-01-15 | Finished | [6 empty] | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished |  |  | 2021-08-18 | Finished | [22 empty] | 452 | 82 | 24 | 16 | 574 | 180 | 82 | 24 | 16 | 302 | 47.39 | Red |  |  | 20017992 | 2021-08-11 |  |  |  | HDME001288 | -153901
TEB0239-TH | HET | 61001205 | HO | เลยสัญญา HO | - | TH219183 | Home Siri Residence Sathupradit 49 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -154021 | -153920 | -153903 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-10-15 | 2021-10-15 | Finished | [34 empty] | 2021-07-15 | 2021-09-10 | 2021-09-10 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2021-10-15 | 2021-10-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-16 | Working | DELIVERY DELAY | [5 empty] | 2021-06-07 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-09-09 | Finished |  |  | 2021-09-10 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20017990 | 2021-07-15 |  |  |  | HDME001309 | -153879
TEB0240-TH | HET | 61001205 | HO | เลยสัญญา HO | - | TH219183 | Home Siri Residence Sathupradit 49 | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -154021 | -153920 | -153903 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-10-15 | 2021-10-15 | Finished | [34 empty] | 2021-07-15 | 2021-09-10 | 2021-09-10 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2021-10-15 | 2021-10-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-16 | Working | DELIVERY DELAY | [5 empty] | 2021-06-07 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-12-15 | Finished | [6 empty] | 2021-09-09 | Finished |  |  | 2021-09-10 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20017990 | 2021-07-15 |  |  |  | HDME001309 | -153879
TAK1202-TH | HET | 61001206 |  | เลยสัญญา HO | - | TH219110 | Ekachai Nursing | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SIRIRAT YUANGNGAM | -154012 | -153910 | -153849 |  | B-1000-2S60,60S/5F | UAG-SN1 | 1000 | 60 | 5 | 5 |  | 1219800 | Bangkok | แขวงบางมด | 2021-08-20 | [36 empty] | 2021-08-20 | 1900-01-01 |  |  | OTHERS | [13 empty] | 2021-09-09 | 2021-11-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-09 | Working | [6 empty] | 2021-06-07 | Finished |  |  | 2021-08-31 | Finished | [6 empty] | 2021-12-15 | Finished | [38 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20018105 | 2021-08-20
TAK1203-TH | HET | 61001206 |  | เลยสัญญา HO | - | TH219110 | Ekachai Nursing | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | SIRIRAT YUANGNGAM | -154012 | -153910 | -153849 |  | B-1000-2S60,60S/4F | UAG-SN1 | 1000 | 60 | 4 | 4 |  | 1187700 | Bangkok | แขวงบางมด | 2021-08-20 | [36 empty] | 2021-08-20 | 1900-01-01 |  |  | OTHERS | [13 empty] | 2021-09-09 | 2021-11-09 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-09 | Working | [6 empty] | 2021-06-07 | Finished |  |  | 2021-08-31 | Finished | [6 empty] | 2021-12-15 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20018105 | 2021-08-20
TEB0241-TH | HET | 61001207 | Test | เลยสัญญา HO | - | TH219180 | Home Khun Keng @Pathum Thani | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Siraprapa Sihamart | -153999 | -153923 | -153892 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 900000 | Bangkok | อำเภอคลองหลวง | 2021-08-28 | 2021-08-28 | Finished | [34 empty] | 2021-07-28 | 2021-08-23 | 2021-08-23 | Finished | CONSTRUCTION DELAY | [13 empty] | 2021-09-06 | 2021-09-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-09-30 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-07 | Finished |  |  | 2021-07-12 | Finished | [6 empty] | 2021-09-15 | Finished | [6 empty] | 2021-08-23 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-08-25 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20017973 | 2021-07-13 |  |  |  | HDME001297 | -153896
TAJ1204-TH | HET | 61001208 |  | เลยสัญญา HO | - | TH219166 | Home Office Khun Thanawat | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Siraprapa Sihamart | -154040 | -153826 | -153765 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1000000 | Bangkok | แขวงทวีวัฒนา | 2021-11-01 | [36 empty] | 2021-11-01 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-03 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20019037 | 2021-11-01
TAJ1205-TH | HET | 61001209 |  | เลยสัญญา HO | - | TH219193 | The Cube Boutique Ramintra 109 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Orawan Kwanpheng | -153997 | -153896 | -153842 |  | P-750-CO60,60S/8F | UAG-SN1 | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงมีนบุรี | 2021-09-20 | [36 empty] | 2021-08-23 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2021-09-30 | 2021-10-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-29 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-10 | Finished |  |  | 2021-09-03 | Finished | [6 empty] | 2022-02-16 | Finished | [38 empty] | 541 | 84 | 24 | 16 | 665 | 541 | 84 | 24 | 16 | 665 | 0 | Red |  |  | 20018250 | 2021-09-23
TBL0709-TH | HET | 61001210 |  | เลยสัญญา HO | - | TH219030 | NKH | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Chanyuth Soithong | -154299 | -153873 | -153720 |  | OUG-1000-CO150,150S/19F | OUG-ON1 | 1000 | 150 | 19 | 19 |  | 1808300 | Nakhon Ratchasima | ตำบลในเมือง | 2021-10-11 | [36 empty] | 2021-10-11 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-10 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-10-22 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 1232 | 103 | 40 | 20 | 1395 | 1232 | 103 | 40 | 20 | 1395 | 0 | Red |  |  | 20018198 | 2021-10-14
TBL0710-TH | HET | 61001210 |  | เลยสัญญา HO | - | TH219030 | NKH | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Chanyuth Soithong | -154299 | -153873 | -153720 |  | OUG-1000-CO150,150S/19F | OUG-ON1 | 1000 | 150 | 19 | 19 |  | 1808300 | Nakhon Ratchasima | ตำบลในเมือง | 2021-10-11 | [36 empty] | 2021-10-11 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-10 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-10-22 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 1232 | 103 | 40 | 20 | 1395 | 1232 | 103 | 40 | 20 | 1395 | 0 | Red |  |  | 20018198 | 2021-10-14
TBL0711-TH | HET | 61001210 |  | เลยสัญญา HO | - | TH219030 | NKH | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Chanyuth Soithong | -154299 | -153873 | -153720 |  | OUG-1000-CO150,150S/19F | OUG-ON1 | 1000 | 150 | 19 | 19 |  | 1808300 | Nakhon Ratchasima | ตำบลในเมือง | 2021-10-11 | [36 empty] | 2021-10-11 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-10 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-10-22 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 1232 | 103 | 40 | 20 | 1395 | 1232 | 103 | 40 | 20 | 1395 | 0 | Red |  |  | 20018198 | 2021-10-14
TAJ1206-TH | HET | 61001210 |  | เลยสัญญา HO | - | TH219030 | NKH | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Chanyuth Soithong | -154299 | -153873 | -153720 |  | P-1350-CO90D,90S/20F | UAG-SN1 | 1350 | 90 | 20 | 20 |  | 1926000 | Nakhon Ratchasima | ตำบลในเมือง | 2021-10-11 | [36 empty] | 2021-09-15 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-10 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-26 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 1071 | 100 | 40 | 24 | 1235 | 1071 | 100 | 40 | 24 | 1235 | 0 | Red |  |  | 20018198 | 2021-09-15
TAJ1207-TH | HET | 61001210 |  | เลยสัญญา HO | - | TH219030 | NKH | S1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Chanyuth Soithong | -154299 | -153873 | -153720 |  | P-1350-CO90D,90S/3F | UAG-SN1 | 1350 | 90 | 3 | 3 |  | 1016500 | Nakhon Ratchasima | ตำบลในเมือง | 2021-10-11 | [36 empty] | 2021-09-15 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-10 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-26 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20018198 | 2021-09-15
TAJ1208-TH | HET | 61001211 | HO | เลยสัญญา HO | - | TH219195 | Apartment 8 Floor Khun Niyom | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 | Weerapoj Paijitvijarn | Orawan Kwanpheng | -153991 | -153899 | -153838 |  | P-630-CO60D,60S/8F | UAG-SN1 | 630 | 60 | 8 | 8 |  | 832460 | Bangkok | ตำบลบางเขน | 2021-08-30 | 2021-08-30 | Finished | [34 empty] | 2021-08-20 | 1900-01-01 | [16 empty] | 2021-08-20 | 2021-09-24 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-26 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-10-08 | Working | [6 empty] | 2021-06-10 | Finished |  |  | 2021-08-31 | Finished | [6 empty] | 2021-10-20 | Finished | [38 empty] | 541 | 84 | 24 | 16 | 665 | 513 | 84 | 24 | 16 | 637 | 4.21 | Red |  |  | 20018246 | 2021-08-20 |  |  |  | HDME001324 | -153867
TFA2662-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | 1200TX-EN,R3.55M,D30 | TX-EN |  |  |  |  | 3550 | 1000000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 2021-10-10 | Finished | [46 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20018284 | 2021-09-29
TFA2663-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | ES2 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 6 |  | 1 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | 1200TX-EN,R3.55M,D30 | TX-EN |  |  |  |  | 3550 | 1000000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 2021-10-10 | Finished | [46 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20018284 | 2021-09-29
TAK1211-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | BED1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | B-1000-2S60,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1350000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 2021-09-14 | Finished | [46 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20018285 | 2021-09-03
TAK1212-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | BED2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | B-1000-2S60,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1350000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 2021-09-14 | Finished | [46 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20018285 | 2021-09-03
TAK1213-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | BED3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | B-1000-2S60,60S/7F | UAG-SN1 | 1000 | 60 | 7 | 7 |  | 1350000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 2021-09-14 | Finished | [46 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20018285 | 2021-09-03
TEC0219-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | DWF1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | DF-200S-B20,20S/3F | DF | 200 | 20 | 3 | 3 |  | 350000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20018287 | 2021-09-03
TEC0217-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | DWT1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | DT-100S-B20,20S/7F | DT | 100 | 20 | 7 | 7 |  | 350000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 310 | 0 | 24 | 0 | 334 | 310 | 0 | 24 | 0 | 334 | 0 | Red |  |  | 20018287 | 2021-09-03
TEC0218-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | DWT2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153793 |  | DT-100S-B20,20S/7F | DT | 100 | 20 | 7 | 7 |  | 350000 | Phuket | อำเภอเมืองภูเก็ต | 2021-10-11 | [36 empty] | 2021-09-04 | 1900-01-01 | [16 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished |  |  | 1900-01-01 | Finished | [46 empty] | 310 | 0 | 24 | 0 | 334 | 310 | 0 | 24 | 0 | 334 | 0 | Red |  |  | 20018287 | 2021-09-03
TAJ1214-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | P1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153731 |  | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1105000 | Phuket | อำเภอเมืองภูเก็ต | 2021-11-04 | [36 empty] | 2021-11-04 | 1900-01-01 | [16 empty] | 2021-11-04 | 2021-12-04 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished | [50 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20018285 | 2021-11-04
TAJ1215-TH | HET | 61001213 |  | เลยสัญญา HO | - | TH219040 | Mission Phuket Hospital | P2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | MONTARADSAMEE HEMTANON | -154007 | -153885 | -153731 |  | P-750-CO60,60S/7F | UAG-SN1 | 750 | 60 | 7 | 7 |  | 1105000 | Phuket | อำเภอเมืองภูเก็ต | 2021-11-04 | [36 empty] | 2021-11-04 | 1900-01-01 | [16 empty] | 2021-11-04 | 2021-12-04 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-04 | Working | [6 empty] | 2021-06-24 | Finished | [50 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20018285 | 2021-11-04
TAJ1216-TH | HET | 61001214 |  | เลยสัญญา HO | - | TH209160 | Kith Thepharak-Bangbo | A1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | -153979 | -153887 | -153766 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Samut Prakan | ตำบลบางเสาธง | 2021-09-01 | [36 empty] | 2021-09-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-02 | 2021-10-02 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20018310 | 2021-09-01
TAJ1217-TH | HET | 61001214 |  | เลยสัญญา HO | - | TH209160 | Kith Thepharak-Bangbo | B1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | -153979 | -153887 | -153766 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Samut Prakan | ตำบลบางเสาธง | 2021-09-01 | [36 empty] | 2021-09-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-02 | 2021-10-02 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20018310 | 2021-09-01
TAJ1218-TH | HET | 61001214 |  | เลยสัญญา HO | - | TH209160 | Kith Thepharak-Bangbo | C1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | -153979 | -153887 | -153766 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Samut Prakan | ตำบลบางเสาธง | 2021-09-01 | [36 empty] | 2021-09-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-02 | 2021-10-02 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20018310 | 2021-09-01
TAJ1219-TH | HET | 61001214 |  | เลยสัญญา HO | - | TH209160 | Kith Thepharak-Bangbo | D1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | -153979 | -153887 | -153766 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Samut Prakan | ตำบลบางเสาธง | 2021-09-01 | [36 empty] | 2021-09-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-09-02 | 2021-10-02 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20018310 | 2021-09-01
TAJ1220-TH | HET | 61001214 |  | เลยสัญญา HO | - | TH209160 | Kith Thepharak-Bangbo | E1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | -153979 | -153887 | -153766 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Samut Prakan | ตำบลบางเสาธง | 2021-11-01 | [36 empty] | 2021-09-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-11-02 | 2021-12-02 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-03 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20018310 | 2021-09-01
TAJ1221-TH | HET | 61001214 |  | เลยสัญญา HO | - | TH209160 | Kith Thepharak-Bangbo | F1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Orawan Kwanpheng | -153979 | -153887 | -153766 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 789660 | Samut Prakan | ตำบลบางเสาธง | 2021-11-01 | [36 empty] | 2021-09-01 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-11-02 | 2021-12-02 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-03 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-20 | Working | [6 empty] | 2021-06-14 | Finished |  |  | 2021-09-12 | Finished | [46 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20018310 | 2021-09-01
TAJ1224-TH | HET | 61001220 |  | เลยสัญญา HO | - | TH219202 | Wat Noi | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Orawan Kwanpheng | -153980 | -153887 | -153857 |  | P-630-CO60D,60S/2F | UAG-SN1 | 630 | 60 | 2 | 2 |  | 845000 | Nonthaburi | แขวงวงศ์สว่าง | 2021-10-11 | 2021-09-15 | Finished | [34 empty] | 2021-09-01 | 2021-09-15 | 2021-09-15 | Finished | [14 empty] | 2021-10-11 | 2021-12-28 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-10 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-12 | Finished | [6 empty] | 2022-03-15 | Finished | [38 empty] | 276 | 79 | 16 | 16 | 387 | 276 | 79 | 16 | 16 | 387 | 0 | Red |  |  | 20018408 | 2021-09-01 |  |  |  | HDME001321 | -153867
TEB0244-TH | HET | 61001230 |  | เลยสัญญา HO | - | TH219212 | Mr.Boonchai (Q House) | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Siraprapa Sihamart | -153937 | -153860 | -153830 |  | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 2 | 2 |  | 950000 | Bangkok | ตำบลคูเวียง | 2021-10-01 | [36 empty] | 2021-09-16 | 1900-01-01 | [16 empty] | 2021-10-01 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20018975 | 2021-09-16
TEB0248-TH | HET | 61001231 |  | เลยสัญญา HO | - | TH219209 | Bu Gaan Yothinpattana (No.4) | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | -153972 | -153889 | -153858 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 690000 | Bangkok | เขตบางกะปิ | 2021-09-15 | [36 empty] | 2021-09-02 | 1900-01-01 | [16 empty] | 2021-09-17 | 2021-10-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-22 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-30 | Working | [6 empty] | 2021-06-23 | Finished |  |  | 2021-09-13 | Finished | [6 empty] | 2021-11-15 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20018522 | 2021-09-02
TAJ1239-TH | HET | 61001244 | Install | เลยสัญญา HO | - | TH209180 | Home Atsawa Hem (Pattanakan 20) | 1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | SIRIRAT YUANGNGAM | -153986 | -153873 | -153812 |  | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1150000 | Bangkok | แขวงสวนหลวง | 2021-09-15 | [36 empty] | 2021-09-15 | 1900-01-01 | [16 empty] | 2021-09-17 | 2021-10-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-21 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-25 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-26 | Finished | [6 empty] | 2021-11-25 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20018362 | 2021-09-15
TEC0221-TH | HET | 61001246 | HO | เลยสัญญา HO | - | TH219196 | Court of Labor Samut-Songkhram | D1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | -154011 | -153896 | -153865 |  | DT-100S-B30,30S/3F | DT | 100 | 30 | 3 | 3 |  | 400000 | Samut Songkhram | จังหวัดสมุทรสงคราม | 2021-08-27 | 2021-08-27 | Finished | [34 empty] | 2021-08-23 | 2021-08-12 | 2021-08-12 | Finished | [14 empty] | 2021-08-27 | 2021-09-27 | 2021-08-27 | Finished | [14 empty] | 2021-08-30 | Finished |  |  | 2021-08-31 | Finished | [18 empty] | 45 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-27 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2021-10-15 | Finished | [6 empty] | 2021-08-16 | Finished |  |  | 2021-08-25 | Finished |  |  | 2021-08-27 | Finished | [22 empty] | 255 | 0 | 16 | 0 | 271 | 140 | 0 | 16 | 0 | 156 | 42.44 | Red |  |  | 20018384 | 2021-08-23 |  |  |  | HDME001287 | -153903
TAJ1242-TH | HET | 61001246 | HO | เลยสัญญา HO | - | TH219196 | Court of Labor Samut-Songkhram | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | -154011 | -153896 | -153865 |  | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 915000 | Samut Songkhram | จังหวัดสมุทรสงคราม | 2021-08-23 | 2021-08-24 | Finished | [34 empty] | 2021-08-23 | 2021-08-17 | 2021-08-17 | Finished | [14 empty] | 2021-08-24 | 2021-09-10 | 2021-08-24 | Finished |  |  | 2021-09-03 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-31 | Finished | [14 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-27 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-03 | Finished | [6 empty] | 2021-10-15 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 91 | 81 | 16 | 16 | 204 | 57.23 | Red |  |  | 20018383 | 2021-09-06
TAJ1243-TH | HET | 61001246 | HO | เลยสัญญา HO | - | TH219196 | Court of Labor Samut-Songkhram | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 | Somsak Denpraphat | Phumiphat Siprajan | -154011 | -153896 | -153865 |  | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 915000 | Samut Songkhram | จังหวัดสมุทรสงคราม | 2021-08-23 | 2021-08-24 | Finished | [34 empty] | 2021-08-23 | 2021-08-17 | 2021-08-17 | Finished | [14 empty] | 2021-08-24 | 2021-09-10 | 2021-08-24 | Finished |  |  | 2021-09-03 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-09-04 | Finished |  |  | 2021-08-27 | Finished |  |  | 2021-08-28 | Finished |  |  | 2021-08-31 | Finished | [14 empty] | 75 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-27 | [12 empty] | 0 | 2000-01-01 | 2000-01-01 | [16 empty] | 0 | 2021-11-15 | Working | [6 empty] | 2021-06-16 | Finished |  |  | 2021-09-03 | Finished | [6 empty] | 2021-10-15 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 91 | 81 | 16 | 16 | 204 | 57.23 | Red |  |  | 20018383 | 2021-09-06
TAC1990-TH | HET | 61001247 |  | เลยสัญญา HO | - | TH219177 | Scope Promsri | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Chanyuth Soithong | -154099 | -153857 | -153782 |  | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 1425000 | Bangkok | แขวงคลองตันเหนือ | 2021-12-08 | [36 empty] | 2021-12-08 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-01-01 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-24 | Finished |  |  | 2021-12-19 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20018438 | 2021-12-08
TAC1991-TH | HET | 61001247 |  | เลยสัญญา HO | - | TH219177 | Scope Promsri | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Chanyuth Soithong | -154099 | -153857 | -153782 |  | VFI-1000-CO105,105S/11F | VFI-II | 1000 | 105 | 11 | 11 |  | 1425000 | Bangkok | แขวงคลองตันเหนือ | 2021-12-08 | [36 empty] | 2021-12-08 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-01-01 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-24 | Finished |  |  | 2021-12-19 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20018438 | 2021-12-08
TAD0546-TH | HET | 61001247 |  | เลยสัญญา HO | - | TH219177 | Scope Promsri | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Chanyuth Soithong | -154099 | -153857 | -153782 |  | B-1000-2S105,105S/11F | B-II(VFI-II) | 1000 | 105 | 11 | 11 |  | 1450000 | Bangkok | แขวงคลองตันเหนือ | 2021-12-08 | [36 empty] | 2021-12-08 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2022-01-01 | 2022-02-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-24 | Finished |  |  | 2021-12-19 | Finished | [6 empty] | 2022-02-15 | Finished | [38 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20018438 | 2021-12-08
TAJ1244-TH | HET | 61001248 | HO | เลยสัญญา HO | - | TH219080 | Food and Drug Administation | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | APHIRADA BUNKUEA | -153973 | -153866 | -153820 |  | P-1050-CO60W2,60S/6F | UAG-SN1 | 1050 | 60 | 6 | 6 |  | 1337500 | Nonthaburi | ตำบลตลาดขวัญ | 2021-09-22 | [36 empty] | 2021-09-22 | 1900-01-01 | [16 empty] | 2021-09-20 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-17 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-07 | Working | [6 empty] | 2021-06-21 | Finished |  |  | 2021-10-03 | Finished | [6 empty] | 2021-11-07 | Finished | [38 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Red |  |  | 20018455 | 2021-09-22
TAJ1245-TH | HET | 61001248 | HO | เลยสัญญา HO | - | TH219080 | Food and Drug Administation | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 4 |  | 2 |  | APHIRADA BUNKUEA | -153973 | -153866 | -153820 |  | P-1050-CO60W2,60S/6F | UAG-SN1 | 1050 | 60 | 6 | 6 |  | 1337500 | Nonthaburi | ตำบลตลาดขวัญ | 2021-09-22 | [36 empty] | 2021-09-22 | 1900-01-01 | [16 empty] | 2021-09-22 | 2021-10-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-17 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-07 | Working | [6 empty] | 2021-06-21 | Finished |  |  | 2021-10-03 | Finished | [6 empty] | 2021-11-07 | Finished | [38 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Red |  |  | 20018455 | 2021-09-22
TEB0250-TH | HET | 61001250 | HO | เลยสัญญา HO | - | TH219120 | The Welton Rama 3 | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153991 | -153899 | -153868 |  | P3-200-CO2030 (SVC200),RM,D | P3 |  |  | 4 | 4 |  | 780000 | Bangkok | เขตยานนาวา | 2021-09-04 | 2021-09-11 | Finished | [34 empty] | 2021-09-04 | 2021-09-11 | 2021-09-11 | Finished | OVERSEA SHIPMENT DELAY | [13 empty] | 2021-09-11 | 2021-09-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-03-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-30 | Working | DELIVERY DELAY | [5 empty] | 2021-06-23 | Finished |  |  | 2021-08-31 | Finished | [14 empty] | 2021-09-11 | Finished |  |  | 2021-09-11 | Finished |  |  | 2021-09-15 | Finished | [22 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20018491 | 2021-08-20 |  |  |  | HDME001312 | -153877
TFB0118-TH | HET | 61001251 |  | เลยสัญญา HO | - | TH219171 | Taxi Drop Lane Don Mueang Airport | MS1 |  |  | 1 | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 6 |  | 1 |  | Somsak Sutthosri | -153990 | -153806 | -153776 |  | 1200EXS-N,R1.9M,D12 | EXS-N |  |  |  |  | 1900 | 2500000 | Bangkok | แขวงสนามบิน | 2021-11-05 | [36 empty] | 2021-11-05 | 1900-01-01 | [16 empty] | 2021-11-22 | 2021-12-10 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-21 | Working | [6 empty] | 2021-06-23 | Finished |  |  | 2021-11-16 | Finished | [6 empty] | 2022-01-21 | Finished | [38 empty] | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | Red |  |  | 20018485 | 2021-11-05
TFB0119-TH | HET | 61001251 |  | เลยสัญญา HO | - | TH219171 | Taxi Drop Lane Don Mueang Airport | MS2 |  |  | 1 | 1 | Worayuth Srisakda | Sittichoke Boonpa | Nattaphon Wongwiboonsin | 6 |  | 1 |  | Somsak Sutthosri | -153990 | -153806 | -153776 |  | 1200EXS-N,R1.9M,D12 | EXS-N |  |  |  |  | 1900 | 2500000 | Bangkok | แขวงสนามบิน | 2021-11-05 | [36 empty] | 2021-11-05 | 1900-01-01 | [16 empty] | 2021-11-22 | 2021-12-10 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-11 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-21 | Working | [6 empty] | 2021-06-23 | Finished |  |  | 2021-11-16 | Finished | [6 empty] | 2022-01-21 | Finished | [38 empty] | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | Red |  |  | 20018485 | 2021-11-05
TEC0222-TH | HET | 61001252 |  | เลยสัญญา HO | - | TH219221 | Court of Province Krabi | D1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Phumiphat Siprajan | -153979 | -153887 | -153857 |  | DT-100S-B20,20S/4F | DT | 100 | 20 | 4 | 4 |  | 320000 | Krabi | อำเภอเมืองกระบี่ | 2021-09-10 | [36 empty] | 2021-09-02 | 1900-01-01 |  |  | STORE AREA | [13 empty] | 2021-09-10 | 2021-10-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-21 | Working | [6 empty] | 2021-06-23 | Finished |  |  | 1900-01-01 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20018529 | 2021-09-02
TAJ1246-TH | HET | 61001252 |  | เลยสัญญา HO | - | TH219221 | Court of Province Krabi | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Phumiphat Siprajan | -153979 | -153887 | -153857 |  | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1070000 | Krabi | อำเภอเมืองกระบี่ | 2021-09-10 | [36 empty] | 2021-09-02 | 1900-01-01 |  |  | STORE AREA | [13 empty] | 2021-09-10 | 2021-10-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-21 | Working | [6 empty] | 2021-06-23 | Finished |  |  | 2021-09-13 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20018526 | 2021-09-02
TAJ1247-TH | HET | 61001252 |  | เลยสัญญา HO | - | TH219221 | Court of Province Krabi | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Phumiphat Siprajan | -153979 | -153887 | -153857 |  | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1080000 | Krabi | อำเภอเมืองกระบี่ | 2021-09-10 | [36 empty] | 2021-09-02 | 1900-01-01 |  |  | STORE AREA | [13 empty] | 2021-09-10 | 2021-10-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-21 | Working | [6 empty] | 2021-06-23 | Finished |  |  | 2021-09-13 | Finished | [6 empty] | 2022-01-15 | Finished | [38 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20018526 | 2021-09-02
TEB0251-TH | HET | 61001253 |  | เลยสัญญา HO | - | TH219200 | Home Khun Pornpilai | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Prapaipim Netnonthai | -153966 | -153874 | -153844 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 4 | 4 |  | 850000 | Bangkok | แขวงท่าแร้ง | 2021-09-14 | [36 empty] | 2021-08-30 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2021-09-16 | 2021-10-16 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-23 | Finished |  |  | 2021-09-10 | Finished | [6 empty] | 2022-02-16 | Finished | [38 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20018547 | 2021-08-30
TAJ1248-TH | HET | 61001254 | HO | เลยสัญญา HO | - | TH219222 | Resident Khun Kuncharee Rama 9 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Korkiti Chapongpop | 4 |  | 2 |  | Orawan Kwanpheng | -153980 | -153888 | -153827 |  | P-630-CO60D,60S/7F | UAG-SN1 | 630 | 60 | 7 | 7 |  | 1150000 | Bangkok | เขตบางกะปิ | 2022-09-15 | [36 empty] | 2021-09-10 | 1900-01-01 |  |  | CONSTRUCTION DELAY | [13 empty] | 2021-10-01 | 2021-10-30 | 2021-08-30 | Finished | [38 empty] | 5 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-06-24 | Finished | [10 empty] | 2021-12-15 | Finished | [38 empty] | 497 | 83 | 24 | 16 | 620 | 472 | 83 | 24 | 16 | 595 | 4.03 | Red |  |  | 20018616 | 2021-09-10
TAJ1249-TH | HET | 61001255 |  | เลยสัญญา HO | - | TH219199 | Kissada Hotel Surin | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Sirawit Pakdeesung | -153963 | -153871 | -153810 |  | P-630-CO60W,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1016500 | Surin | ตำบลในเมือง | 2021-09-17 | [36 empty] | 2021-09-17 | 1900-01-01 | [16 empty] | 2021-09-17 | 2021-10-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-08 | Finished |  |  | 2021-11-08 | Finished | [46 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20018663 | 2021-09-17 |  |  |  | HDME001323 | -153867
TBL0718-TH | HET | 61001256 |  | เลยสัญญา HO | - | TH219031 | CTW (Isetan) | L22 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Chanyuth Soithong | -153976 | -153826 | -153615 |  | OUG-1600-2S120,120S/9F | OUG-ON1 | 1600 | 120 | 9 | 9 |  | 2114600 | Bangkok | แขวงปทุมวัน | 2021-11-01 | [36 empty] | 2021-06-11 | 1900-01-01 | [16 empty] | 2021-11-01 | 2022-05-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-31 | Working | [6 empty] | 2021-07-19 | Finished | [50 empty] | 702 | 88 | 24 | 16 | 830 | 702 | 88 | 24 | 16 | 830 | 0 | Red |  |  | 20018730 | 2021-11-11
TBL0719-TH | HET | 61001256 |  | เลยสัญญา HO | - | TH219031 | CTW (Isetan) | L23 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Chanyuth Soithong | -153976 | -153826 | -153615 |  | OUG-1600-2S120,120S/9F | OUG-ON1 | 1600 | 120 | 9 | 9 |  | 2114600 | Bangkok | แขวงปทุมวัน | 2021-11-01 | [36 empty] | 2021-06-11 | 1900-01-01 | [16 empty] | 2021-11-01 | 2022-05-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-31 | Working | [6 empty] | 2021-07-19 | Finished | [50 empty] | 702 | 88 | 24 | 16 | 830 | 702 | 88 | 24 | 16 | 830 | 0 | Red |  |  | 20018730 | 2021-11-11
TBL0720-TH | HET | 61001256 |  | เลยสัญญา HO | - | TH219031 | CTW (Isetan) | L24 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Chanyuth Soithong | -153976 | -153826 | -153615 |  | OUG-1600-2S120,120S/9F | OUG-ON1 | 1600 | 120 | 9 | 9 |  | 2114600 | Bangkok | แขวงปทุมวัน | 2021-11-01 | [36 empty] | 2021-06-11 | 1900-01-01 | [16 empty] | 2021-11-01 | 2022-05-31 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-20 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-31 | Working | [6 empty] | 2021-07-19 | Finished | [50 empty] | 702 | 88 | 24 | 16 | 830 | 702 | 88 | 24 | 16 | 830 | 0 | Red |  |  | 20018730 | 2021-11-11
TAC2011-TH | HET | 61001256 |  | เลยสัญญา HO | - | TH219031 | CTW (Isetan) | L5 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Chanyuth Soithong | -153976 | -153826 | -153615 |  | VFI-1350-CO120,120S/10F | VFI-II | 1350 | 120 | 10 | 10 |  | 2061100 | Bangkok | แขวงปทุมวัน | 2022-02-14 | [36 empty] | 2022-02-14 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-25 | Finished | [50 empty] | 804 | 95 | 24 | 16 | 939 | 804 | 95 | 24 | 16 | 939 | 0 | Red |  |  | 20019175 | 2022-02-14
TAC2012-TH | HET | 61001256 |  | เลยสัญญา HO | - | TH219031 | CTW (Isetan) | L6 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Chanyuth Soithong | -153976 | -153826 | -153615 |  | VFI-1350-CO120,120S/10F | VFI-II | 1350 | 120 | 10 | 10 |  | 2061100 | Bangkok | แขวงปทุมวัน | 2022-02-14 | [36 empty] | 2022-02-14 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-25 | Finished | [50 empty] | 804 | 95 | 24 | 16 | 939 | 804 | 95 | 24 | 16 | 939 | 0 | Red |  |  | 20019175 | 2022-02-14
TAC2013-TH | HET | 61001256 |  | เลยสัญญา HO | - | TH219031 | CTW (Isetan) | L7 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Chanyuth Soithong | -153976 | -153826 | -153615 |  | VFI-1350-CO120,120S/10F | VFI-II | 1350 | 120 | 10 | 10 |  | 2061100 | Bangkok | แขวงปทุมวัน | 2022-02-14 | [36 empty] | 2022-02-14 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-25 | Finished | [50 empty] | 804 | 95 | 24 | 16 | 939 | 804 | 95 | 24 | 16 | 939 | 0 | Red |  |  | 20019175 | 2022-02-14
TEB0252-TH | HET | 61001257 |  | เลยสัญญา HO | - | TH219122 | Home Khun Panpornkamon | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Siraprapa Sihamart | -153965 | -153873 | -153843 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 950000 | Bangkok | แขวงลาดพร้าว | 2021-09-15 | [36 empty] | 2021-08-31 | 1900-01-01 | [16 empty] | 2021-09-17 | 2021-10-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-21 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-15 | Finished |  |  | 2021-09-11 | Finished | [46 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20018679 | 2021-08-31
TEB0253-TH | HET | 61001258 |  | เลยสัญญา HO | - | TH219223 | Home Demi Sathupradit 49 | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153960 | -153888 | -153858 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-09-15 | [36 empty] | 2021-09-15 | 1900-01-01 |  |  | OVERSEA SHIPMENT DELAY | [13 empty] | 2021-10-14 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | DELIVERY DELAY | [5 empty] | 2021-07-15 | Finished | [50 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20018727 | 2021-08-30
TEB0254-TH | HET | 61001258 |  | เลยสัญญา HO | - | TH219223 | Home Demi Sathupradit 49 | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153960 | -153888 | -153827 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-09-15 | [36 empty] | 2021-09-15 | 1900-01-01 | [16 empty] | 2021-10-14 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-15 | Finished | [50 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20018727 | 2021-09-15
TEB0255-TH | HET | 61001258 |  | เลยสัญญา HO | - | TH219223 | Home Demi Sathupradit 49 | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153960 | -153888 | -153827 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-09-15 | [36 empty] | 2021-09-15 | 1900-01-01 | [16 empty] | 2021-10-14 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-15 | Finished | [50 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20018727 | 2021-09-15
TEB0256-TH | HET | 61001258 |  | เลยสัญญา HO | - | TH219223 | Home Demi Sathupradit 49 | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153960 | -153888 | -153827 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-09-15 | [36 empty] | 2021-09-15 | 1900-01-01 | [16 empty] | 2021-10-14 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-15 | Finished | [50 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20018727 | 2021-09-15
TEB0257-TH | HET | 61001258 |  | เลยสัญญา HO | - | TH219223 | Home Demi Sathupradit 49 | 7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153960 | -153888 | -153797 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-10-14 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-14 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-15 | Finished | [50 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20018727 | 2021-10-14
TEB0258-TH | HET | 61001258 |  | เลยสัญญา HO | - | TH219223 | Home Demi Sathupradit 49 | 8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153960 | -153888 | -153797 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-10-14 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-14 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-15 | Finished | [50 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20018727 | 2021-10-14
TEB0259-TH | HET | 61001258 |  | เลยสัญญา HO | - | TH219223 | Home Demi Sathupradit 49 | 9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Wanthanee Phoonphatthanachai | 4 |  | 2 |  | Prapaipim Netnonthai | -153960 | -153888 | -153797 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 5 | 5 |  | 710000 | Bangkok | เขตยานนาวา | 2021-10-14 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-14 | 2021-11-14 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-04 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-24 | Working | [6 empty] | 2021-07-15 | Finished | [50 empty] | 170 | 27 | 16 | 16 | 229 | 170 | 27 | 16 | 16 | 229 | 0 | Red |  |  | 20018727 | 2021-10-14
TFA2688-TH | HET | 61001259 |  | เลยสัญญา HO | - | TH219142 | Surat Thani International Airport | ES1 |  | 1 |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 6 |  | 1 |  | Orawan Kwanpheng | -153948 | -153825 | -153733 |  | 1200TX-EN,R5M,D35 | TX-EN |  |  |  |  | 5000 | 909500 | Surat Thani | อำเภอพุนพิน | 2021-11-04 | [36 empty] | 2021-11-04 | 1900-01-01 | [16 empty] | 2021-11-02 | 2021-12-05 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-20 | Working | [6 empty] | 2021-07-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20018853 | 2021-11-04
TBL0721-TH | HET | 61001259 |  | เลยสัญญา HO | - | TH219142 | Surat Thani International Airport | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Orawan Kwanpheng | -153948 | -153825 | -153733 |  | OUG-1050-CO60,60S/2F | OUG-ON1 | 1050 | 60 | 2 | 2 |  | 1498000 | Surat Thani | อำเภอพุนพิน | 2021-11-19 | [36 empty] | 2021-11-19 | 1900-01-01 | [16 empty] | 2021-11-02 | 2021-12-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-20 | Working | [6 empty] | 2021-07-16 | Finished | [50 empty] | 331 | 83 | 16 | 16 | 446 | 331 | 83 | 16 | 16 | 446 | 0 | Red |  |  | 20018854 | 2021-11-19
TBL0723-TH | HET | 61001259 |  | เลยสัญญา HO | - | TH219142 | Surat Thani International Airport | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Orawan Kwanpheng | -153948 | -153825 | -153733 |  | OUG-1050-CO60,60S/2F | OUG-ON1 | 1050 | 60 | 2 | 2 |  | 936250 | Surat Thani | อำเภอพุนพิน | 2021-11-19 | [36 empty] | 2021-11-19 | 1900-01-01 | [16 empty] | 2021-11-02 | 2021-12-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-20 | Working | [6 empty] | 2021-07-16 | Finished | [50 empty] | 331 | 83 | 16 | 16 | 446 | 331 | 83 | 16 | 16 | 446 | 0 | Red |  |  | 20018854 | 2021-11-19
TBL0722-TH | HET | 61001259 |  | เลยสัญญา HO | - | TH219142 | Surat Thani International Airport | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Orawan Kwanpheng | -153948 | -153825 | -153733 |  | OUG-1050-CO60,60S/2F | OUG-ON1 | 1050 | 60 | 2 | 2 |  | 1498000 | Surat Thani | อำเภอพุนพิน | 2021-11-19 | [36 empty] | 2021-11-19 | 1900-01-01 | [16 empty] | 2021-11-02 | 2021-12-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-20 | Working | [6 empty] | 2021-07-16 | Finished | [50 empty] | 331 | 83 | 16 | 16 | 446 | 331 | 83 | 16 | 16 | 446 | 0 | Red |  |  | 20018854 | 2021-11-19
TAJ1253-TH | HET | 61001262 |  | เลยสัญญา HO | - | TH219228 | Office of Phuket Public Prosecution | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Unchaleeporn Wongrak | -153949 | -153857 | -153826 |  | P-1000-CO60W1,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 1102100 | Phuket | อำเภอเมือง | 2021-10-01 | [36 empty] | 2021-10-01 | 1900-01-01 | [16 empty] | 2021-10-01 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-01 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 276 | 79 | 16 | 16 | 387 | 276 | 79 | 16 | 16 | 387 | 0 | Red |  |  | 20018966 | 2021-10-01
TAJ1254-TH | HET | 61001262 |  | เลยสัญญา HO | - | TH219228 | Office of Phuket Public Prosecution | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Unchaleeporn Wongrak | -153949 | -153857 | -153826 |  | P-1000-CO60W1,60S/2F | UAG-SN1 | 1000 | 60 | 2 | 2 |  | 1102100 | Phuket | อำเภอเมือง | 2021-10-01 | [36 empty] | 2021-10-01 | 1900-01-01 | [16 empty] | 2021-10-01 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-20 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-01 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 276 | 79 | 16 | 16 | 387 | 276 | 79 | 16 | 16 | 387 | 0 | Red |  |  | 20018966 | 2021-10-01
TAJ1266-TH | HET | 61001268 |  | เลยสัญญา HO | - | TH219231 | NACC Prachinburi | PL-01 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Somsak Sutthosri | -153950 | -153858 | -153828 |  | P-1000-CO60D,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1348200 | Phrachin Buri | อำเภอเมืองปราจีนบุรี | 2021-09-30 | [36 empty] | 2021-09-30 | 1900-01-01 | [16 empty] | 2021-09-30 | 2021-10-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-12 | Working | [6 empty] | 2021-07-19 | Finished | [50 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20018855 | 2021-09-30
TAJ1267-TH | HET | 61001268 |  | เลยสัญญา HO | - | TH219231 | NACC Prachinburi | PL-02 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Somsak Sutthosri | -153950 | -153858 | -153828 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1305400 | Phrachin Buri | อำเภอเมืองปราจีนบุรี | 2021-09-30 | [36 empty] | 2021-09-30 | 1900-01-01 | [16 empty] | 2021-09-30 | 2021-10-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-25 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-12 | Working | [6 empty] | 2021-07-19 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20018855 | 2021-09-30
TAC1995-TH | HET | 61001271 |  | เลยสัญญา HO | - | TH219237 | Dormitory 32 Unit Phahol Hospital | 1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Siraprapa Sihamart | -153950 | -153796 | -153750 |  | VFI-600-CO60,60S/5F | VFI-II | 600 | 60 | 5 | 5 |  | 1391000 | Kanchanaburi | ตำบลปากแพรก | 2022-01-13 | [36 empty] | 2022-01-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-03 | Finished | [50 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Red |  |  | 20018976 | 2022-01-05
TAJ1275-TH | HET | 61001284 |  | เลยสัญญา HO | - | TH219178 | Factory Suwinthawong KhunVinij | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Thamnul Kongsar | -153950 | -153797 | -153736 |  | P-750-CO60,60S/3F | UAG-SN1 | 750 | 60 | 3 | 3 |  | 1027200 | Chachoengsao | อำเภอเมืองฉะเชิงเทรา | 2021-11-30 | [36 empty] | 2021-11-30 | 1900-01-01 | [16 empty] | 2021-11-30 | 2021-12-30 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-05 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-30 | Working | [6 empty] | 2021-07-19 | Finished | [50 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20018896 | 2021-11-30
TAJ1276-TH | HET | 61001285 |  | เลยสัญญา HO | - | TH219153 | Apartment 4 Floor Khun Pranomjit Chaiyaphum | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Somsak Sutthosri | -153955 | -153802 | -153741 |  | P-750-CO60,60S/4F | UAG-SN1 | 750 | 60 | 4 | 4 |  | 1000000 | Chaiyaphum | อำเภอเมืองชัยภูมิ | 2021-11-25 | [36 empty] | 2021-11-25 | 1900-01-01 | [16 empty] | 2021-11-25 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20018965 | 2021-11-25
TAJ1277-TH | HET | 61001286 |  | เลยสัญญา HO | - | TH219123 | NACC Chaiyaphum | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Somsak Sutthosri | -153954 | -153864 | -153817 |  | P-1000-CO60D,60S/3F | UAG-SN1 | 1000 | 60 | 3 | 3 |  | 1177000 | Chaiyaphum | จังหวัดชัยภูมิ 36000 | 2021-10-04 | [36 empty] | 2021-10-04 | 1900-01-01 | [16 empty] | 2021-10-04 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20019003 | 2021-10-04
TAJ1278-TH | HET | 61001286 |  | เลยสัญญา HO | - | TH219123 | NACC Chaiyaphum | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Sarawut Buttara | 4 |  | 2 |  | Somsak Sutthosri | -153954 | -153864 | -153817 |  | P-630-CO60D,60S/4F | UAG-SN1 | 630 | 60 | 4 | 4 |  | 1102100 | Chaiyaphum | จังหวัดชัยภูมิ 36000 | 2021-10-04 | [36 empty] | 2021-10-04 | 1900-01-01 | [16 empty] | 2021-10-04 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20019003 | 2021-10-04
TEB0267-TH | HET | 61001287 |  | เลยสัญญา HO | - | TH219245 | Bu Gaan Yothinpattana (No.12) | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | -153964 | -153872 | -153872 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตบึงกุ่ม | 2021-09-28 | [36 empty] | 2021-09-13 | 1900-01-01 | [16 empty] | 2021-09-17 | 2021-10-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-09-21 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-05 | Working | [6 empty] | 2021-07-19 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20018932 | 2021-09-13
TAC1998-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153782 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2021-12-07 | [36 empty] | 2021-12-07 | 1900-01-01 | [16 empty] | 2021-12-07 | 2021-12-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-26 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-11 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20018908 | 2021-12-07
TAC2037-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L10 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TAC1999-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153782 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2021-12-07 | [36 empty] | 2021-12-07 | 1900-01-01 | [16 empty] | 2021-12-07 | 2021-12-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-26 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-11 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20018908 | 2021-12-07
TAC2030-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TAC2031-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TAC2032-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TAC2033-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TAC2034-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L7 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TAC2035-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L8 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TAC2036-TH | HET | 61001288 |  | เลยสัญญา HO | - | TH219246 | Supalai City Resort Charan 91 | L9 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Ukrit Rungruang | 4 |  | 2 |  | Chonticha Angsuwichitkun | -153970 | -153812 | -153707 |  | VFI-750-CO60,60S/8F | MCA | 750 | 60 | 8 | 8 |  | 900000 | Bangkok | แขวงบางอ้อ | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-28 | Working | [6 empty] | 2021-09-10 | Finished | [50 empty] | 693 | 93 | 24 | 16 | 826 | 693 | 93 | 24 | 16 | 826 | 0 | Red |  |  | 20019597 | 2022-01-22
TBL0730-TH | HET | 61001289 |  | เลยสัญญา HO | - | TH219020 | Broadcasting Center Building at PRD | EL-01 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153791 | -153701 |  | OUG-1350-CO105,105S/8F | OUG-ON1 | 1350 | 105 | 8 | 8 |  | 1444500 | Bangkok | แขวงดินแดง | 2021-12-06 | [36 empty] | 2021-12-06 | 1900-01-01 | [16 empty] | 2021-12-06 | 2022-01-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 649 | 88 | 24 | 16 | 777 | 649 | 88 | 24 | 16 | 777 | 0 | Red |  |  | 20019005 | 2021-12-06
TBL0731-TH | HET | 61001289 |  | เลยสัญญา HO | - | TH219020 | Broadcasting Center Building at PRD | EL-02 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153791 | -153701 |  | OUG-1350-CO105,105S/8F | OUG-ON1 | 1350 | 105 | 8 | 8 |  | 1444500 | Bangkok | แขวงดินแดง | 2021-12-06 | [36 empty] | 2021-12-06 | 1900-01-01 | [16 empty] | 2021-12-06 | 2022-01-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 649 | 88 | 24 | 16 | 777 | 649 | 88 | 24 | 16 | 777 | 0 | Red |  |  | 20019005 | 2021-12-06
TBL0732-TH | HET | 61001289 |  | เลยสัญญา HO | - | TH219020 | Broadcasting Center Building at PRD | EL-03 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153791 | -153701 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 7 | 7 |  | 1637100 | Bangkok | แขวงดินแดง | 2021-12-06 | [36 empty] | 2021-12-06 | 1900-01-01 | [16 empty] | 2021-12-06 | 2022-01-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019005 | 2021-12-06
TBL0733-TH | HET | 61001289 |  | เลยสัญญา HO | - | TH219020 | Broadcasting Center Building at PRD | EL-04 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153791 | -153701 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 7 | 7 |  | 1637100 | Bangkok | แขวงดินแดง | 2021-12-06 | [36 empty] | 2021-12-06 | 1900-01-01 | [16 empty] | 2021-12-06 | 2022-01-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019005 | 2021-12-06
TAJ1279-TH | HET | 61001289 |  | เลยสัญญา HO | - | TH219020 | Broadcasting Center Building at PRD | EL-05 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Warut Chang | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153791 | -153701 |  | P-1600-CO60,60S/7F | UAG-SN1 | 1600 | 60 | 7 | 7 |  | 1540800 | Bangkok | แขวงดินแดง | 2021-12-06 | [36 empty] | 2021-12-06 | 1900-01-01 | [16 empty] | 2021-12-06 | 2022-01-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-10 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-10 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20019005 | 2021-12-06
TAC2000-TH | HET | 61001290 |  | เลยสัญญา HO | - | TH219187 | Dormnitory bldg. 7 fl, Photharam Hospital | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153937 | -153753 | -153694 |  | VFI-1000-CO90,90S/7F | VFI-II | 1000 | 90 | 7 | 7 |  | 1241200 | Ratchaburi | จังหวัดราชบุรี 70120 | 2022-01-13 | [36 empty] | 2022-01-13 | 1900-01-01 | [16 empty] | 2022-01-13 | 2022-02-13 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-13 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019006 | 2022-01-13
TEB0268-TH | HET | 61001291 |  | เลยสัญญา HO | - | TH219224 | De Promise Plus Consult at Day Ramintra | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Oran Wuthicharn | 4 |  | 2 |  | Orawan Kwanpheng | -153937 | -153845 | -153814 |  | P4-300-2S20 (SED300S),RM,D | P4 |  |  | 4 | 4 |  | 802500 | Bangkok | แขวงท่าแร้ง | 2021-10-13 | [36 empty] | 2021-09-28 | 1900-01-01 |  |  | CONSTRUCTION STOP | [13 empty] | 2021-10-20 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-02-15 | [12 empty] | 0 | [18 empty] | 0 | 2022-03-15 | Working | CONSTRUCTION DELAY | [5 empty] | 2021-08-03 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20019004 | 2021-09-28
TAK1280-TH | HET | 61001292 |  | เลยสัญญา HO | - | TH219189 | Aikchon Hospital | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | -153935 | -153858 | -153828 |  | B-1000-2S60,60S/10F | UAG-SN1 | 1000 | 60 | 10 | 10 |  | 1845750 | Chon Buri | อำเภอเมืองชลบุรี | 2021-10-15 | [36 empty] | 2021-10-14 | 1900-01-01 | [16 empty] | 2021-10-15 | 2021-10-22 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-10-23 | [12 empty] | 0 | [18 empty] | 0 | 2021-10-30 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 629 | 85 | 24 | 16 | 754 | 629 | 85 | 24 | 16 | 754 | 0 | Red |  |  | 20019009 | 2021-10-18
TAJ1282-TH | HET | 61001293 |  | เลยสัญญา HO | - | TH219128 | Court of Justice (Phuket) | L1/1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153948 | -153854 | -153810 |  | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 4 | 5 |  | 1284000 | Phuket | จังหวัดภูเก็ต 83000 | 2021-10-04 | [36 empty] | 2021-10-04 | 1900-01-01 | [16 empty] | 2021-10-04 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-17 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20019007 | 2021-10-04
TAJ1283-TH | HET | 61001293 |  | เลยสัญญา HO | - | TH219128 | Court of Justice (Phuket) | L1/2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153948 | -153854 | -153810 |  | P-1000-CO60W2,60S/5F | UAG-SN1 | 1000 | 60 | 4 | 5 |  | 1284000 | Phuket | จังหวัดภูเก็ต 83000 | 2021-10-04 | [36 empty] | 2021-10-04 | 1900-01-01 | [16 empty] | 2021-10-04 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-17 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20019007 | 2021-10-04
TAJ1281-TH | HET | 61001293 |  | เลยสัญญา HO | - | TH219128 | Court of Justice (Phuket) | L1/3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153948 | -153854 | -153810 |  | P-1000-CO60W2,60S/4F | UAG-SN1 | 1000 | 60 | 2 | 4 |  | 1230500 | Phuket | จังหวัดภูเก็ต 83000 | 2021-10-04 | [36 empty] | 2021-10-04 | 1900-01-01 | [16 empty] | 2021-10-04 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-17 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20019007 | 2021-10-04
TAC2001-TH | HET | 61001293 |  | เลยสัญญา HO | - | TH219128 | Court of Justice (Phuket) | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153948 | -153854 | -153718 |  | VFI-900-CO60,60S/5F | VFI-II | 900 | 60 | 4 | 5 |  | 1391000 | Phuket | จังหวัดภูเก็ต 83000 | 2021-10-04 | [36 empty] | 2021-10-04 | 1900-01-01 | [16 empty] | 2021-10-04 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-17 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Red |  |  | 20019007 | 2022-01-17
TEC0224-TH | HET | 61001293 |  | เลยสัญญา HO | - | TH219128 | Court of Justice (Phuket) | L3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Jakkapan Koteera | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153948 | -153854 | -153810 |  | DT-100S-B30,30S/3F | DT | 100 | 30 | 3 | 3 |  | 267500 | Phuket | จังหวัดภูเก็ต 83000 | 2021-10-04 | [36 empty] | 2021-10-04 | 1900-01-01 | [16 empty] | 2021-10-04 | 2021-12-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-04 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-17 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20019008 | 2021-10-04
TAC2002-TH | HET | 61001294 |  | เลยสัญญา HO | - | TH219092 | Laemchabang Hospital, Support Building | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | -153949 | -153766 | -153734 |  | VFI-750-CO90,90S/7F | VFI-II | 750 | 90 | 7 | 7 |  | 1123500 | Chon Buri | ตำบลทุ่งสงขลา | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 2022-01-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-21 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-01 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019044 | 2022-01-05
TAD0557-TH | HET | 61001294 |  | เลยสัญญา HO | - | TH219092 | Laemchabang Hospital, Support Building | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | -153949 | -153766 | -153734 |  | B-1000-2S90,90S/5F | B-II(VFI-II) | 1000 | 90 | 5 | 5 |  | 1337500 | Chon Buri | ตำบลทุ่งสงขลา | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 2022-01-05 | 2022-01-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-21 | [12 empty] | 0 | [18 empty] | 0 | 2022-02-01 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Red |  |  | 20019044 | 2022-01-05
TAJ1284-TH | HET | 61001295 |  | เลยสัญญา HO | - | TH219225 | Suan Dusit University | EL1(Bld.7) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153822 | -153760 |  | P-630-CO60D,60S/5F | UAG-SN1 | 630 | 60 | 5 | 5 |  | 1391000 | Bangkok | แขวงดุสิต | 2021-11-05 | [36 empty] | 2021-11-05 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-03 | Finished | [50 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20019043 | 2021-11-05
TAC2003-TH | HET | 61001295 |  | เลยสัญญา HO | - | TH219225 | Suan Dusit University | EL1(Building 12) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153822 | -153760 |  | VFI-750-2S60,60S/7F | VFI-II | 750 | 60 | 7 | 7 |  | 1498000 | Bangkok | แขวงดุสิต | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019043 | 2022-01-05
TAC2005-TH | HET | 61001295 |  | เลยสัญญา HO | - | TH219225 | Suan Dusit University | EL1(Hotel) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153822 | -153760 |  | VFI-900-CO60,60S/5F | VFI-II | 900 | 60 | 5 | 5 |  | 1391000 | Bangkok | แขวงดุสิต | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-03 | Finished | [50 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Red |  |  | 20019043 | 2022-01-05
TAC2004-TH | HET | 61001295 |  | เลยสัญญา HO | - | TH219225 | Suan Dusit University | EL2(Building 12) | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Nattasit Kanma | 4 |  | 2 |  | Orawan Kwanpheng | -153944 | -153822 | -153760 |  | VFI-750-2S60,60S/7F | VFI-II | 750 | 60 | 7 | 7 |  | 1498000 | Bangkok | แขวงดุสิต | 2022-01-05 | [36 empty] | 2022-01-05 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019043 | 2022-01-05
TAC2006-TH | HET | 61001296 |  | เลยสัญญา HO | - | TH219247 | Resident Military at Chonburi | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Orawan Kwanpheng | -153924 | -153838 | -153803 |  | VFI-550-CO60,60S/7F | VFI-II | 550 | 60 | 7 | 7 |  | 1000000 | Chon Buri | จังหวัดชลบุรี 20240 | 2021-10-20 | [36 empty] | 2021-10-20 | 1900-01-01 | [16 empty] | 2021-10-20 | 2021-11-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-06 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-24 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019173 | 2022-01-17
TAC2007-TH | HET | 61001296 |  | เลยสัญญา HO | - | TH219247 | Resident Military at Chonburi | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Orawan Kwanpheng | -153924 | -153838 | -153803 |  | VFI-550-CO60,60S/7F | VFI-II | 550 | 60 | 7 | 7 |  | 1000000 | Chon Buri | จังหวัดชลบุรี 20240 | 2021-10-20 | [36 empty] | 2021-10-20 | 1900-01-01 | [16 empty] | 2021-10-20 | 2021-11-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-06 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-24 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019173 | 2022-01-17
TAC2008-TH | HET | 61001296 |  | เลยสัญญา HO | - | TH219247 | Resident Military at Chonburi | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Orawan Kwanpheng | -153924 | -153838 | -153803 |  | VFI-550-CO60,60S/7F | VFI-II | 550 | 60 | 7 | 7 |  | 1000000 | Chon Buri | จังหวัดชลบุรี 20240 | 2021-10-20 | [36 empty] | 2021-10-20 | 1900-01-01 | [16 empty] | 2021-10-20 | 2021-11-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-06 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-24 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019173 | 2022-01-17
TAC2009-TH | HET | 61001296 |  | เลยสัญญา HO | - | TH219247 | Resident Military at Chonburi | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Orawan Kwanpheng | -153924 | -153838 | -153803 |  | VFI-550-CO60,60S/7F | VFI-II | 550 | 60 | 7 | 7 |  | 1000000 | Chon Buri | จังหวัดชลบุรี 20240 | 2021-10-20 | [36 empty] | 2021-10-20 | 1900-01-01 | [16 empty] | 2021-10-20 | 2021-11-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-06 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-24 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019173 | 2022-01-17
TAC2010-TH | HET | 61001296 |  | เลยสัญญา HO | - | TH219247 | Resident Military at Chonburi | L5 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Orawan Kwanpheng | -153924 | -153838 | -153803 |  | VFI-550-CO60,60S/7F | VFI-II | 550 | 60 | 7 | 7 |  | 1000000 | Chon Buri | จังหวัดชลบุรี 20240 | 2021-10-20 | [36 empty] | 2021-10-20 | 1900-01-01 | [16 empty] | 2021-10-20 | 2021-11-05 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-06 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-24 | Working | [6 empty] | 2021-08-03 | Finished | [50 empty] | 638 | 92 | 24 | 16 | 770 | 638 | 92 | 24 | 16 | 770 | 0 | Red |  |  | 20019173 | 2022-01-17
TAJ1298-TH | HET | 61001308 |  | เลยสัญญา HO | - | TH219198 | Home 3 Floor Nakhon Pathom @Khun Inchan | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Yosvaris Limmethaphant | -153923 | -153805 | -153770 |  | P-630-CO60W,60S/3F | UAG-SN1 | 630 | 60 | 3 | 3 |  | 1048600 | Nakhon Pathom | อำเภอนครชัยศรี | 2021-11-22 | [36 empty] | 2021-11-22 | 1900-01-01 | [16 empty] | 2021-11-22 | 2021-12-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-12-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-12-27 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20019365 | 2021-11-22
TFA2693-TH | HET | 61001309 |  | เลยสัญญา HO | - | TH209253 | MU Ramathibodi Hospital (Food Court Building) | ESC1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Phumiphat Siprajan | -153928 | -153775 | -153713 |  | 1200TX-EN,R5.5M,D35 | TX-EN |  |  |  |  | 5500 | 1310750 | Bangkok | อำเภอบางพลี | 1900-01-01 | [36 empty] | 2021-12-18 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019316 | 2021-12-18
TFA2694-TH | HET | 61001309 |  | เลยสัญญา HO | - | TH209253 | MU Ramathibodi Hospital (Food Court Building) | ESC2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 6 |  | 1 |  | Phumiphat Siprajan | -153928 | -153775 | -153713 |  | 1200TX-EN,R5.5M,D35 | TX-EN |  |  |  |  | 5500 | 1310750 | Bangkok | อำเภอบางพลี | 1900-01-01 | [36 empty] | 2021-12-18 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019316 | 2021-12-18
TEC0225-TH | HET | 61001309 |  | เลยสัญญา HO | - | TH209253 | MU Ramathibodi Hospital (Food Court Building) | DW-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Phumiphat Siprajan | -153928 | -153775 | -153713 |  | DT-100S-B30,30S/2F | DT | 100 | 30 | 2 | 2 |  | 374500 | Bangkok | อำเภอบางพลี | 1900-01-01 | [36 empty] | 2021-12-22 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20019397 | 2021-12-22
TAJ1300-TH | HET | 61001309 |  | เลยสัญญา HO | - | TH209253 | MU Ramathibodi Hospital (Food Court Building) | FL-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Phumiphat Siprajan | -153928 | -153775 | -153713 |  | P-1600-CO60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1669200 | Bangkok | อำเภอบางพลี | 1900-01-01 | [36 empty] | 2021-12-22 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20019396 | 2021-12-22
TAJ1299-TH | HET | 61001309 |  | เลยสัญญา HO | - | TH209253 | MU Ramathibodi Hospital (Food Court Building) | PL-1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Patipran Sukjit | 4 |  | 2 |  | Phumiphat Siprajan | -153928 | -153775 | -153713 |  | P-1600-CO60,60S/5F | UAG-SN1 | 1600 | 60 | 5 | 5 |  | 1647800 | Bangkok | อำเภอบางพลี | 1900-01-01 | [36 empty] | 2021-12-22 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 408 | 82 | 16 | 16 | 522 | 408 | 82 | 16 | 16 | 522 | 0 | Red |  |  | 20019396 | 2021-12-22
TAJ1301-TH | HET | 61001310 |  | เลยสัญญา HO | - | TH219188 | Ban Sang Chan | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | -153923 | -153837 | -153806 |  | P-630-CO60D,60S/2F | UAG-SN1 | 630 | 60 | 2 | 2 |  | 1100000 | Chanthaburi | ตำบลวัดใหม่ | 2021-10-27 | [36 empty] | 2021-10-27 | 1900-01-01 | [16 empty] | 2021-10-27 | 2021-11-10 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-16 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-26 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 276 | 79 | 16 | 16 | 387 | 276 | 79 | 16 | 16 | 387 | 0 | Red |  |  | 20019344 | 2021-10-27
TAJ1302-TH | HET | 61001311 |  | เลยสัญญา HO | - | TH219253 | Orasa Factory | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Vongsakon Domrongrat | 4 |  | 2 |  | Somsak Sutthosri | -153919 | -153797 | -153735 |  | P-630-CO60D,60S/3F | UAG-SN1 | 630 | 60 | 3 | 3 |  | 1030000 | Chanthaburi | อำเภอเมืองจันทบุรี | 2021-11-30 | [36 empty] | 2021-11-30 | 1900-01-01 | [16 empty] | 2021-11-30 | 2021-12-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2022-01-21 | [12 empty] | 0 | [18 empty] | 0 | 2022-01-31 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 320 | 80 | 16 | 16 | 432 | 320 | 80 | 16 | 16 | 432 | 0 | Red |  |  | 20019437 | 2021-11-30
TAC2028-TH | HET | 61001312 |  | เลยสัญญา HO | - | TH209274 | Innovation Hubs 4.0 Building | L1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153920 | -153735 | -153677 |  | VFI-900-CO60,60S/4F | VFI-II | 900 | 60 | 4 | 4 |  | 1070000 | Bangkok | อำเภอเมืองนนทบุรี | 2022-01-31 | [36 empty] | 2022-01-31 | 1900-01-01 | [16 empty] | 2021-02-02 | 2021-02-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-02-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-03-29 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Red |  |  | 20019487 | 2022-02-04
TAC2029-TH | HET | 61001312 |  | เลยสัญญา HO | - | TH209274 | Innovation Hubs 4.0 Building | L2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153920 | -153735 | -153677 |  | VFI-900-CO60,60S/4F | VFI-II | 900 | 60 | 4 | 4 |  | 1070000 | Bangkok | อำเภอเมืองนนทบุรี | 2022-01-31 | [36 empty] | 2022-01-31 | 1900-01-01 | [16 empty] | 2021-02-02 | 2021-02-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-02-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-03-29 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Red |  |  | 20019487 | 2022-02-04
TAJ1303-TH | HET | 61001312 |  | เลยสัญญา HO | - | TH209274 | Innovation Hubs 4.0 Building | L3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Denchai Jankachan | 4 |  | 2 |  | Jitphisut Piamsuktana-anan | -153920 | -153735 | -153677 |  | P-1600-2S60,60S/4F | UAG-SN1 | 1600 | 60 | 4 | 4 |  | 1391000 | Bangkok | อำเภอเมืองนนทบุรี | 2022-01-31 | [36 empty] | 2022-01-31 | 1900-01-01 | [16 empty] | 2021-02-04 | 2021-02-25 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-02-26 | [12 empty] | 0 | [18 empty] | 0 | 2021-03-29 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 364 | 81 | 16 | 16 | 477 | 364 | 81 | 16 | 16 | 477 | 0 | Red |  |  | 20019487 | 2022-01-31
TAD0564-TH | HET | 61001313 |  | เลยสัญญา HO | - | TH229009 | Phrae Hospital (Service support building) | 1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | -153920 | -153705 | -153585 |  | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1200000 | Phrae | ตำบลในเวียง | 1900-01-01 | [36 empty] | 2022-03-02 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Red |  |  | 20019486 | 2022-03-02
TAD0565-TH | HET | 61001313 |  | เลยสัญญา HO | - | TH229009 | Phrae Hospital (Service support building) | 2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | -153920 | -153705 | -153585 |  | B-1000-2S60,60S/5F | B-II(VFI-II) | 1000 | 60 | 5 | 5 |  | 1200000 | Phrae | ตำบลในเวียง | 1900-01-01 | [36 empty] | 2022-03-02 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 527 | 91 | 16 | 16 | 650 | 527 | 91 | 16 | 16 | 650 | 0 | Red |  |  | 20019486 | 2022-03-02
TAD0562-TH | HET | 61001313 |  | เลยสัญญา HO | - | TH229009 | Phrae Hospital (Service support building) | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | -153920 | -153705 | -153585 |  | B-1000-2S60,60S/6F | B-II(VFI-II) | 1000 | 60 | 6 | 6 |  | 1300000 | Phrae | ตำบลในเวียง | 1900-01-01 | [36 empty] | 2022-03-02 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 583 | 91 | 24 | 16 | 714 | 583 | 91 | 24 | 16 | 714 | 0 | Red |  |  | 20019486 | 2022-03-02
TAD0563-TH | HET | 61001313 |  | เลยสัญญา HO | - | TH229009 | Phrae Hospital (Service support building) | 4 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Yosvaris Limmethaphant | -153920 | -153705 | -153585 |  | B-1000-2S60,60S/6F | B-II(VFI-II) | 1000 | 60 | 6 | 6 |  | 1300000 | Phrae | ตำบลในเวียง | 1900-01-01 | [36 empty] | 2022-03-02 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 583 | 91 | 24 | 16 | 714 | 583 | 91 | 24 | 16 | 714 | 0 | Red |  |  | 20019486 | 2022-03-02
TAJ1304-TH | HET | 61001314 |  | เลยสัญญา HO | - | TH219256 | Phichaiyatikaram | EL1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Yosvaris Limmethaphant | -153909 | -153817 | -153756 |  | P-1050-CO60W2,60S/7F | UAG-SN1 | 1050 | 60 | 7 | 7 |  | 1177000 | Bangkok | แขวงสมเด็จเจ้าพระยา | 2021-11-15 | [36 empty] | 2021-11-15 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-27 | Finished | [50 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20019488 | 2021-11-15
TAJ1305-TH | HET | 61001314 |  | เลยสัญญา HO | - | TH219256 | Phichaiyatikaram | EL2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Yosvaris Limmethaphant | -153909 | -153817 | -153756 |  | P-1050-CO60W2,60S/7F | UAG-SN1 | 1050 | 60 | 7 | 7 |  | 1177000 | Bangkok | แขวงสมเด็จเจ้าพระยา | 2021-11-15 | [36 empty] | 2021-11-15 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-08-27 | Finished | [50 empty] | 497 | 83 | 24 | 16 | 620 | 497 | 83 | 24 | 16 | 620 | 0 | Red |  |  | 20019488 | 2021-11-15
TEB0274-TH | HET | 61001315 |  | เลยสัญญา HO | - | TH219230 | Home Khun Praphat | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Patsadayu Whangjaroensub | Nitipong Urairat | 4 |  | 2 |  | Unchaleeporn Wongrak | -153913 | -153821 | -153791 |  | P3-250-CO2030 (SVC250L),RM,D | P3 |  |  | 2 | 2 |  | 650000 | Bangkok | แขวงบางระมาด | 2021-10-22 | [36 empty] | 2021-10-22 | 1900-01-01 | [16 empty] | 2021-10-22 | 2021-11-15 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-15 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-22 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20019516 | 2021-10-22
TFA2703-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES1.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2704-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES1.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2705-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES2.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2706-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES2.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2707-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES3.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2708-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES3.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2709-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES4.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-28 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-02-28
TFA2710-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B1ES4.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R4M,D30 | TX-P |  |  |  |  | 4000 | 1232267.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-28 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019528 | 2022-02-28
TFA2695-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES1.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2696-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES1.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2697-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES2.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2698-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES2.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2699-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES3.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2700-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES3.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2701-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES4.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2702-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | B2ES4.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R3.5M,D30 | TX-P |  |  |  |  | 3500 | 1203377.88 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 32 | 16 | 14 | 544 | 482 | 32 | 16 | 14 | 544 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2711-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES1.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R11M,D30 | TX-P |  |  |  |  | 11000 | 3803478 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 857 | 53 | 32 | 28 | 970 | 857 | 53 | 32 | 28 | 970 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2712-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES1.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R11M,D30 | TX-P |  |  |  |  | 11000 | 3803478 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 857 | 53 | 32 | 28 | 970 | 857 | 53 | 32 | 28 | 970 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2713-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES2.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R11M,D30 | TX-P |  |  |  |  | 11000 | 3803478 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 857 | 53 | 32 | 28 | 970 | 857 | 53 | 32 | 28 | 970 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2714-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES2.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R11M,D30 | TX-P |  |  |  |  | 11000 | 3803478 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 857 | 53 | 32 | 28 | 970 | 857 | 53 | 32 | 28 | 970 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2721-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES3.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492812.83 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2722-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES3.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492812.83 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2717-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES4.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492812.83 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2718-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES4.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492812.83 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2719-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES5.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492812.83 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2720-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES5.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492812.83 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2715-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES6.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R11M,D30 | TX-P |  |  |  |  | 11000 | 3803478 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 857 | 53 | 32 | 28 | 970 | 857 | 53 | 32 | 28 | 970 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2716-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES6.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R11M,D30 | TX-P |  |  |  |  | 11000 | 3803478 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 857 | 53 | 32 | 28 | 970 | 857 | 53 | 32 | 28 | 970 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2723-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GES7 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1319473 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2724-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GMES1.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492813 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2725-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GMES1.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492813 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-01-16
TFA2726-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GMES2.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492813 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2727-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GMES2.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492813 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2728-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GMES3.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492813 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2729-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | GMES3.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R5.5M,D30 | TX-P |  |  |  |  | 5500 | 1492813 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 536 | 42 | 16 | 21 | 615 | 536 | 42 | 16 | 21 | 615 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2730-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L1ES1.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R7.5M,D30 | TX-P |  |  |  |  | 7500 | 1929727.57 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2731-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L1ES1.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R7.5M,D30 | TX-P |  |  |  |  | 7500 | 1929727.57 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2732-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L1ES1.3 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R7.5M,D30 | TX-P |  |  |  |  | 7500 | 1929727.57 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2733-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L1ES2.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R7.5M,D30 | TX-P |  |  |  |  | 7500 | 1929727.57 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2734-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L1ES2.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R7.5M,D30 | TX-P |  |  |  |  | 7500 | 1929727.57 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2735-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L1ES3.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R7.5M,D30 | TX-P |  |  |  |  | 7500 | 1929727.57 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2736-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L1ES3.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R7.5M,D30 | TX-P |  |  |  |  | 7500 | 1929727.57 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 643 | 42 | 24 | 21 | 730 | 643 | 42 | 24 | 21 | 730 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2737-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L2ES1.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R6M,D30 | TX-P |  |  |  |  | 6000 | 1486661.24 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2738-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L2ES1.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R6M,D30 | TX-P |  |  |  |  | 6000 | 1486661.24 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-02-13 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20019528 | 2022-02-13
TFA2739-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L2ES2.1 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R6M,D30 | TX-P |  |  |  |  | 6000 | 1486661.24 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20019528 | 2022-03-16
TFA2740-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | L2ES2.2 |  | 1 |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 6 |  | 1 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | 1200TX-P,R6M,D30 | TX-P |  |  |  |  | 6000 | 1486661.24 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-16 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 590 | 42 | 24 | 21 | 677 | 590 | 42 | 24 | 21 | 677 | 0 | Red |  |  | 20019528 | 2022-03-16
TEC0226-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | FRL1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | DT-50T-B15,15S/9F | DT | 50 | 15 | 7 | 9 |  | 5147294.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 366 | 0 | 24 | 0 | 390 | 366 | 0 | 24 | 0 | 390 | 0 | Red |  |  | 20019535 | 2022-03-31
TEC0227-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | FRL2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153661 |  | DT-50T-B15,15S/9F | DT | 50 | 15 | 7 | 9 |  | 5147294.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 366 | 0 | 24 | 0 | 390 | 366 | 0 | 24 | 0 | 390 | 0 | Red |  |  | 20019535 | 2022-01-31
TBL0734-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | PL1.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-1600-CO105,105S/6F | OUG-ON1 | 1600 | 105 | 6 | 6 |  | 2113844.33 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 543 | 86 | 24 | 16 | 669 | 543 | 86 | 24 | 16 | 669 | 0 | Red |  |  | 20019530 | 2022-03-31
TBL0735-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | PL1.2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-1600-CO105,105S/6F | OUG-ON1 | 1600 | 105 | 6 | 6 |  | 2113844.33 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 543 | 86 | 24 | 16 | 669 | 543 | 86 | 24 | 16 | 669 | 0 | Red |  |  | 20019530 | 2022-03-31
TBL0736-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | PL1.3 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-1600-CO105,105S/6F | OUG-ON1 | 1600 | 105 | 6 | 6 |  | 2113844.33 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 543 | 86 | 24 | 16 | 669 | 543 | 86 | 24 | 16 | 669 | 0 | Red |  |  | 20019530 | 2022-03-31
TBL0738-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | PL2.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153706 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 7 | 7 |  | 2167344.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-04
TBL0739-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | PL2.2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153706 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 7 | 7 |  | 2167344.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-04
TBL0740-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | PL3.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153706 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 7 | 7 |  | 2167344.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-04
TBL0741-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | PL3.2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153706 |  | OUG-1600-CO105,105S/7F | OUG-ON1 | 1600 | 105 | 7 | 7 |  | 2167344.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-04
TBL0742-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL1.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-2000-CO105,105S/8F | OUG-ON1 | 2000 | 105 | 8 | 8 |  | 2547194.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 649 | 88 | 24 | 16 | 777 | 649 | 88 | 24 | 16 | 777 | 0 | Red |  |  | 20019530 | 2022-03-31
TBL0743-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL1.2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-2000-CO105,105S/8F | OUG-ON1 | 2000 | 105 | 8 | 8 |  | 2547194.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 649 | 88 | 24 | 16 | 777 | 649 | 88 | 24 | 16 | 777 | 0 | Red |  |  | 20019530 | 2022-03-31
TBL0744-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL2.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153706 |  | OUG-2000-CO105,105S/7F | OUG-ON1 | 2000 | 105 | 7 | 7 |  | 2547194.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-04
TBL0745-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL2.2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153706 |  | OUG-2000-CO105,105S/7F | OUG-ON1 | 2000 | 105 | 7 | 7 |  | 2547194.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-04
TBL0746-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL3.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-2000-CO105,105S/7F | OUG-ON1 | 2000 | 105 | 11 | 7 |  | 2729094.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-03-31
TBL0747-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL3.2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-2000-CO105,105S/7F | OUG-ON1 | 2000 | 105 | 11 | 7 |  | 2729094.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-03-31
TBL0748-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL4.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153661 |  | OUG-2000-CO105,105S/7F | OUG-ON1 | 2000 | 105 | 11 | 7 |  | 2729094.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-31
TBL0749-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | SL4.2 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153661 |  | OUG-2000-CO105,105S/7F | OUG-ON1 | 2000 | 105 | 11 | 7 |  | 2729094.5 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-01-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 596 | 87 | 24 | 16 | 723 | 596 | 87 | 24 | 16 | 723 | 0 | Red |  |  | 20019530 | 2022-01-31
TBL0737-TH | HET | 61001316 |  | เลยสัญญา HO | - | TH219255 | Queen Sirikit National Convention Center Renovation | VPL1.1 | 1 |  |  | 1 | Worayuth Srisakda | Naris Janjaroenkit | Panupong Pathumborisuth | 4 |  | 2 |  | Orawan Kwanpheng | -153994 | -153782 | -153585 |  | OUG-1350-CO105,105S/8F | OUG-ON1 | 1350 | 105 | 8 | 8 |  | 2595344 | Bangkok | แขวงคลองเตย | 1900-01-01 | [36 empty] | 2022-03-31 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 649 | 88 | 24 | 16 | 777 | 649 | 88 | 24 | 16 | 777 | 0 | Red |  |  | 20019530 | 2022-03-31
TEB0278-TH | HET | 61001317 |  | เลยสัญญา HO | - | TH219252 | Bu Gaan Yothinpattana (No.3,5,6,14,15) | 14 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | -153927 | -153835 | -153804 |  | P4-300-2S20 (SED300S),RM,D | P3 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตบึงกุ่ม | 2021-10-19 | [36 empty] | 2021-10-19 | 1900-01-01 | [16 empty] | 2021-10-23 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-20 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20019521 | 2021-10-19
TEB0279-TH | HET | 61001317 |  | เลยสัญญา HO | - | TH219252 | Bu Gaan Yothinpattana (No.3,5,6,14,15) | 15 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | -153927 | -153835 | -153804 |  | P4-300-2S20 (SED300S),RM,D | P3 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตบึงกุ่ม | 2021-10-19 | [36 empty] | 2021-10-19 | 1900-01-01 | [16 empty] | 2021-10-23 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-20 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20019521 | 2021-10-19
TEB0275-TH | HET | 61001317 |  | เลยสัญญา HO | - | TH219252 | Bu Gaan Yothinpattana (No.3,5,6,14,15) | 3 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | -153927 | -153835 | -153804 |  | P4-300-2S20 (SED300S),RM,D | P3 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตบึงกุ่ม | 2021-10-19 | [36 empty] | 2021-10-19 | 1900-01-01 | [16 empty] | 2021-10-23 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-20 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20019521 | 2021-10-19
TEB0276-TH | HET | 61001317 |  | เลยสัญญา HO | - | TH219252 | Bu Gaan Yothinpattana (No.3,5,6,14,15) | 5 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | -153927 | -153835 | -153804 |  | P4-300-2S20 (SED300S),RM,D | P3 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตบึงกุ่ม | 2021-10-19 | [36 empty] | 2021-10-19 | 1900-01-01 | [16 empty] | 2021-10-23 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-20 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20019521 | 2021-10-19
TEB0277-TH | HET | 61001317 |  | เลยสัญญา HO | - | TH219252 | Bu Gaan Yothinpattana (No.3,5,6,14,15) | 6 | 1 |  |  | 1 | Thanundorn Nuamkaew | Atcha Wongrak | Kanin Suttipong | 4 |  | 2 |  | Prapaipim Netnonthai | -153927 | -153835 | -153804 |  | P4-300-2S20 (SED300S),RM,D | P3 |  |  | 3 | 3 |  | 640000 | Bangkok | เขตบึงกุ่ม | 2021-10-19 | [36 empty] | 2021-10-19 | 1900-01-01 | [16 empty] | 2021-10-23 | 2021-11-20 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 2021-11-01 | [12 empty] | 0 | [18 empty] | 0 | 2021-11-20 | Working | [6 empty] | 2021-08-27 | Finished | [50 empty] | 170 | 55 | 16 | 16 | 257 | 170 | 55 | 16 | 16 | 257 | 0 | Red |  |  | 20019521 | 2021-10-19
TED0101-TH | HET | 61001318 |  | เลยสัญญา HO | - | TH219251 | Baan Chum Phaban Surat Thani | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Unchaleeporn Wongrak | -153914 | -153730 | -153671 |  | MCA-1050-CO60,60S/4F | MCA | 1050 | 60 | 4 | 4 |  | 1337500 | Surat Thani | อำเภอเมือง | 1900-01-01 | [36 empty] | 2021-02-05 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Red |  |  | 20019701 | 2022-01-21
TED0102-TH | HET | 61001318 |  | เลยสัญญา HO | - | TH219251 | Baan Chum Phaban Surat Thani | L2 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Krich Chauychom | 4 |  | 2 |  | Unchaleeporn Wongrak | -153914 | -153730 | -153671 |  | MCA-1050-CO60,60S/4F | MCA | 1050 | 60 | 4 | 4 |  | 1337500 | Surat Thani | อำเภอเมือง | 1900-01-01 | [36 empty] | 2021-02-05 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 472 | 90 | 16 | 16 | 594 | 472 | 90 | 16 | 16 | 594 | 0 | Red |  |  | 20019701 | 2022-01-21
TFA2741-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | ES1 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | 1200TX-EN,R4.2M,D35 | TX-EN |  |  |  |  | 4200 | 909500 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019665 | 2022-01-04
TFA2742-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | ES2 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | 1200TX-EN,R4.2M,D35 | TX-EN |  |  |  |  | 4200 | 909500 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019665 | 2022-01-04
TFA2743-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | ES3 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | 1200TX-EN,R4.2M,D35 | TX-EN |  |  |  |  | 4200 | 909500 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019665 | 2022-01-04
TFA2744-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | ES4 |  | 1 |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 6 |  | 1 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | 1200TX-EN,R4.2M,D35 | TX-EN |  |  |  |  | 4200 | 909500 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-01-04 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [81 empty] | 0 | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 482 | 42 | 16 | 21 | 561 | 482 | 42 | 16 | 21 | 561 | 0 | Red |  |  | 20019665 | 2022-01-04
TAC2038-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | VFI-1600-2S105,105S/12F | VFI-II | 1600 | 105 | 12 | 12 |  | 1915300 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-28 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 914 | 106 | 32 | 20 | 1072 | 914 | 106 | 32 | 20 | 1072 | 0 | Red |  |  | 20019666 | 2022-02-28
TAD0566-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L2 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | B-1000-2S105,105S/11F | B-II(VFI-II) | 1000 | 105 | 11 | 11 |  | 1669200 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-17 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20019666 | 2022-02-17
TAD0567-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L3 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | B-1000-2S105,105S/11F | B-II(VFI-II) | 1000 | 105 | 11 | 11 |  | 1669200 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-17 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20019666 | 2022-02-17
TAD0568-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L4 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | B-1000-2S105,105S/11F | B-II(VFI-II) | 1000 | 105 | 11 | 11 |  | 1669200 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-17 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20019666 | 2022-02-17
TAD0569-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L5 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | B-1000-2S105,105S/11F | B-II(VFI-II) | 1000 | 105 | 11 | 11 |  | 1669200 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-17 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20019666 | 2022-02-17
TAD0570-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L6 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | B-1000-2S105,105S/11F | B-II(VFI-II) | 1000 | 105 | 11 | 11 |  | 1669200 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-17 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20019666 | 2022-02-17
TAD0571-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L7 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | B-1000-2S105,105S/11F | B-II(VFI-II) | 1000 | 105 | 11 | 11 |  | 1669200 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-17 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 859 | 105 | 32 | 20 | 1016 | 859 | 105 | 32 | 20 | 1016 | 0 | Red |  |  | 20019666 | 2022-02-17
TAC2039-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L8 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | VFI-1600-2S105,105S/12F | VFI-II | 1600 | 105 | 12 | 12 |  | 1915300 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2022-02-28 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 914 | 106 | 32 | 20 | 1072 | 914 | 106 | 32 | 20 | 1072 | 0 | Red |  |  | 20019666 | 2022-02-28
TEC0228-TH | HET | 61001319 |  | เลยสัญญา HO | - | TH219038 | Thammasat Hospital (Medical Center Building) | L-DM | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Kittitat Tiamkul | 4 |  | 2 |  | Orawan Kwanpheng | -154011 | -153782 | -153554 |  | DT-100S-B30,30S/2F | DT | 100 | 30 | 2 | 2 |  | 278200 | Pathum Thani | อำเภอคลองหลวง | 1900-01-01 | [36 empty] | 2021-12-15 | 1900-01-01 | [16 empty] | 1900-01-01 | 1900-01-01 | [40 empty] | 0 | [41 empty] | 1900-01-01 | 1900-01-01 |  |  |  |  | 1900-01-01 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 2021-09-16 | Finished | [50 empty] | 255 | 0 | 16 | 0 | 271 | 255 | 0 | 16 | 0 | 271 | 0 | Red |  |  | 20019667 | 2022-02-28
TBL0750-TH | HET | 61001323 |  | เลยสัญญา HO | - | TH219258 | Hotel 5 Floor Sukhumvit 45 | L1 | 1 |  |  | 1 | Worayuth Srisakda | Sittichoke Boonpa | Tanakorn Piluk | 4 |  | 2 |  | Unchaleeporn Wongrak | -153903 | -153686 | -153616 |  | OUG-1000-CO60,60S/5F | OUG-ON1 | 1000 | 60 | 5 | 5 |  | 1177000 | Bangkok | แขวงคลองตันเหนือ | 2 | [36 empty] | 44641 | 2 | [16 empty] | 2 | 2 | [40 empty] | 0 | [41 empty] | 2 | 2 |  |  |  |  | 2 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 44455 | Finished | [50 empty] | 490 | 86 | 16 | 16 | 608 | 490 | 86 | 16 | 16 | 608 | 0 | Red |  |  | 20019682 | 44641
TAK1319-TH | HET | 61001335 |  | เลยสัญญา HO | - | TH219262 | Mae Sot Ram Hospital | L1 | 1 |  |  | 1 | Thanundorn Nuamkaew | Nipol Lerknork | Eknarin Seamsayan | 4 |  | 2 |  | Thamnul Kongsar | -153888 | -153797 | -153735 |  | UAG-SN1-1000-2S2P60;6S/6F; | UAG-SN1 | 1000 | 60 | 6 | 6 |  | 1410260 | Tak | ตำบลพบพระ | 2 | [36 empty] | 44543 | 2 | [16 empty] | 2 | 2 | [40 empty] | 0 | [41 empty] | 2 | 2 |  |  |  |  | 2 | [12 empty] | 0 | [18 empty] | 0 | [8 empty] | 44455 | Finished | [50 empty] | 452 | 82 | 24 | 16 | 574 | 452 | 82 | 24 | 16 | 574 | 0 | Red |  |  | 20019805 | 44543